## One Pager
[7 empty] | Todays Date | 2024-04-08
[7 empty] | TA Start Date | 2024-05-01 |  | Finish Date | 2024-05-30 |  | Staging Date | 2024-04-03
Total WO's | Total WO Lines | [5 empty] | Days Remaining | 23
142 | 686
Created | CRTD WO Lines | PR Never | [11 empty] | 2024-04-17
2 | 5 | 3
REL WO's | REL WO Lines | PR Never
138 | 680 | 102
STATUS | [5 empty] | OUTLOOK (excl PR NEVER)
# WO's: TOTAL | # WO Lines: TOTAL (excl PR NEVER) | # WO's @ CRTD: TOTAL | # WO Lines @ CRTD: TOTAL (excl PR NEVER) | # WO's @ RELEASED TOTAL | # WO Lines @ RELEASED TOTAL (excl PR NEVER) | # WO Lines @ PR, PO Ariving Late or After TA | # WO Lines @ PR, PO - Arriving On Time pre TA Start date | At STO raised (through orchestration) | Pre S4 Del - EXW, In TRANSIT or DELIVERY CRTD, STAGED | SOH - In Transit to PDC; Material SOH @ PDC / KSF | Workpack / staged @ PDC / BASE W/H | Material is rec'd & work packed / staged @ SITE | REFURB Material to be rtnd ex SITE | # WO Lines: INT'L FREIGHT REMAINING
142 | 581 | 2 | 5 | 138 | 578 | 15 | 78 |  | 47 | 53 | 289 | 23 | 7 | 13

## KGP Win 1
Release id (" "=rel., X=not yet,1=never) | WO Revision | WO Status | WO Actual Release date | Requirement date (WO component) | Material Staging date (STO) | WO basic Start date | WO basic Finish date | WO Main work centre | WO number | Oper/Act number of Reservation | BOM item number | WO Description | Description | Functional location | Description | Procurement plant | Req Priority for Material/Component | Alert / Exception | Material / Component | Material Description | Requirement quantity | Requirement UOM | Stock on-hand @ Base | Stock In-Transit into Remote | Stock on-hand @ Remote | HU Quantity | UoM of HU | Expediting Note / User Comment | Message log(Orchestration / Derivation) | Supply status | Supply Process | Supply Process (Desc.) | Planned Deliver Time (in days) (PR) | Supplying Plant (STO) | Current STO | Current STO Item | Incoterms | Planned Delivery Time (in days) (STO) | Purchase Requisition | Purchase Requisition Item | Vendor | Name of Supplier | Vendor PO | Vendor PO item | PO qty | Requirement UOM | Delivery date (PO) | Batch/Valudation type(from WO component) | Inbound Delivery (PO) | Latest Inbound Delivery (STO) | Latest Outbound Delivery STO | Process Phase | Short Description | Reservation | Reservation Item | Reservation item deletion indicator | UoM of HU | Nested HU Lvl 2 | Nested HU Lvl 3 | Top HU | Shipping Type | Voyage-id | Voyage type | Voyage status | Container-ID | Linked Work-pack/HU | Workpack bin | Unloading Point | Incompletion indic. (Y/N) | Return STO | Return STO Item | Return STO Qty | Return STO UOM | Withdrawn quantity | Remaining quanity | Arrival (actual) | Arrival (plan) | Campaign (Y/N) | Company Code (STO) | Creation Date (STO) | Current document | Delay @ Demand plant | Delay @ Procument plant | Delay @ Supply plant | Delivery date (PR) | Delivery date (STO) | Demand Plant | Early start date (WO) | Equipment | Description | ETA @ Demand plant | ETA @ Procument plant | ETA @ Supply plant | EWM task for GI (STO) | EWM Warehouse for GI (STO) | Final Due Date | GI qty (OBD for STO) | Good Issue (STO) | Good Receipt (PO) | Goods Issue date (STO) | Goods Receipt End date (STO) | Goods Recipient | GR OBD Document (STO) | GR processing time | GR Processing time Demand plant (STO) | GR Processing time Supply plant (PR) | GR qty (IBD for STO) | GR qty (PO) | Inbound Delivery (STO) | Internal alert code | Item category (BOM) | Latest GI (STO) | Latest GI STO Year | Latest GR (PO) | Latest GR IBD (STO) | Latest GR IBD Year(STO) | Latest GR PO Year | Latest IBD (PO) | Loading Date (STO) | Maint. Operation Exec. Stage Code | Maintenance Planning Plant | Plant Name | Maintenance Plant | Plant Name | Maintenance Storage Location | Material / Component description | Material Description | Oper. Phase Status | Operation / Activity | Operation description | Operation Control key | Operation description | Operation System Condition | Order Phase Status | Outbound Delivery (STO) | Person responsible | Picking bin | PO item deletion indic | Position | PR Processing State | Short Description | PR Release Indicator | Process Subphase | Subphase Description | Profile Status | Project stock | Purchasing Group | Purchasing Grp. Name | Purchasing group (STO) | Purchasing Grp. Name | Purchasing Organisation (STO) | Purchasing Processing time(PR) | Receiving Plant (STO) | Ref Latest Outbound Delivery (STO) | Release date (PR) | Req Urgency for Material/Component | Requirements date (PR) | Reservation Item (reverse link) | Reservation Special Stock Ind. | Responsible Buyer (for PO) | Return doc (MvT 262) | Revision | Revision Type | Route (STO) | Routing number (of WO Operation) | Shipping Point (STO) | Status of Material (Demand Plant) | Status of Material (Supplying Plant) | STO (Supplying) - 1st STO | STO (Supplying) - 1st STO Item | STO Committed date (STO) | STO for SP97 (2nd STO) | STO for SP97 2ndS STO Item | STO quantity (STO) | STO quantity UoM (STO) | Storage Location (STO) based on WO | Supplying Plant | Transportation Planning date (STO) | User Responsible | User-status | Vehicle departure date | Vendor PO Pur Org | Warehouse | WO Actual Finish date | WO Actual Start date | WO Company Code | Company Name | WO Controlling Area | WO created by | WO creation date | WO from PR (reverse link) | WO item number | WO Overall Status | WO overall status code | WO Planner Group | WO Priority | WO Responsible Cost Center | WO Scheduled Finish date | WO Scheduled Release date | WO Scheduled Start date | WO System Status | WO type | Order Type Name | WO WBS element | Material Analysis | Expected Delivery into PDC | Purchasing Delivery Category | INCOTERMS | Name of Supplier | Vendor PO | Delivery date (PO) | CALC CHECK | LOGIC | Any order which is ahead date | Any order which is ahead qty | Count
| 24SDGT10 | Released | 2024-02-16 | 2024-03-02 | 2024-02-28 | 2024-05-03 | 2024-05-04 | ROTAT | 100037746 | 0010 | 0030 | 100037746 | Replace filters on AU01.GT4010A3 | AA53.GT4010A3 | PKG EQ,GT4010A3 HYDRAULIC STARTING SKID | AA01 | 255 | No issue identified | 10412550 | FILTER,PIGNONE ISM990645338,RTN | 4 | EA | 0 | 0 | 0 | 0 |  | 26.03 - RFQ 6000001439 / RFQ 6000001054 - ex BH NP; all del dates at SEPT 2024 | Supply for Order 100037746, Item 2 cannot be changed 90001123 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006672 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90001123 | 05 | Preparation | 0000136198 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-02-16 | ODST-0090001123_0020 | 0 | 0 | 0 |  | 2024-02-29 | AA53 | 2024-05-03 |  |  | 2024-03-02 |  |  |  |  | 2024-05-15 | 0 |  |  | 2024-02-28 | 2024-03-02 | GT4010S7 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10412550 | FILTER,PIGNONE ISM990645338,RTN |  | 0010 | Isolate Hyd Starter Motor | INT | Isolate Hyd Starter Motor | 5 |  | 90001123_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90001123 |  | 99 |  | 2 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000135628 | S002 | 30 | 30 | 5300006672 | 20 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 136198 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Material shortage/Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved | AM01 | Reactive Maintenance | [8 empty] | 0 | 00001361984535310412550100037746
| 24SDGT9 | Released | 2024-02-06 | 2024-05-19 | 2024-04-29 | 2024-05-19 | 2024-05-19 | ROTAT | 100033767 | 0020 | 0040 | 100033767 | Replace Servo Filter and Compensator | AA53.GT4009A3 | PKG EQ,GT4009A3 HYDRAULIC STARTING SKID | AA01 | 20 | No Issue identified | 10412550 | FILTER,PIGNONE ISM990645338,RTN | 1 | EA | 0 | 0 | 0 | 0 |  | 26.03 - RFQ 6000001439 / RFQ 6000001054 - ex BH NP; all del dates at SEPT 20324 | Supply for Order 100033767, Item 4 cannot be changed 90000784 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006126 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000784 | 05 | Preparation | 0000132281 | 4 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-06 | ODST-0090000784_0020 | 0 | 0 | 0 |  | 2024-04-30 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-03-13 | 0 |  |  | 2024-04-29 | 2024-05-02 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10412550 | FILTER,PIGNONE ISM990645338,RTN |  | 0020 | Replace Servo Filters | INT | Replace Servo Filters |  |  | 90000784_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000784 |  | 20 |  | 4 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000131663 | S002 | 30 | 30 | 5300006126 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-29 | W35069 |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132281 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | [8 empty] | 0 | 00001322814543110412550100033767
| 24SDGT9 | Released | 2024-02-06 | 2024-05-19 | 2024-04-29 | 2024-05-19 | 2024-05-19 | ROTAT | 100033767 | 0020 | 0030 | 100033767 | Replace Servo Filter and Compensator | AA53.GT4009A3 | PKG EQ,GT4009A3 HYDRAULIC STARTING SKID | AA01 | 20 | No Issue identified | 10613434 | FILTER,HYD STARTER;NP ISM990645306 | 1 | EA | 0 | 0 | 0 | 0 |  | 01.04 - PR 2000020252 | Supply for Order 100033767, Item 3 cannot be changed 90000784 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006126 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000784 | 05 | Preparation | 0000132281 | 3 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-06 | ODST-0090000784_0010 | 0 | 0 | 0 |  | 2024-04-30 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-03-13 | 0 |  |  | 2024-04-29 | 2024-05-02 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10613434 | FILTER,HYD STARTER;NP ISM990645306 |  | 0020 | Replace Servo Filters | INT | Replace Servo Filters |  |  | 90000784_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000784 |  | 20 |  | 3 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000131663 | S002 | 30 | 30 | 5300006126 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-29 | W35069 |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132281 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance | [8 empty] | 0 | 00001322814543110613434100033767
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-22 | 2024-05-03 | 2024-05-03 | INLEC | 100040070 | 0020 | 0030 | 100040070 | MOC-119547 Replace meters S24H7 GT7 | AA53.S24H7 | SWBD,DIST 110VDC/240VAC UPS G4007 | AA01 | 20 | PR due for release | 11401662 | METER,V;115-230VAC,FRER D72EV | 1 | EA | 0 | 0 | 0 | 0 |  | 05.04 - PR 1000007714 |  | PR approved; PO not issued | SP97 | Direct Multi-base | 42 | AA01 | 5300008693 | 10 |  | 7 | 1000007714 | 3 |  |  |  | 0 | 0 | EA |  |  |  |  | 90007149 | 05 | Preparation | 0000138591 | 3 | 0 | [9 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-04-04 | PRPO-1000007714_00003 | 0 | 33 | 0 | 2024-05-23 | 2024-04-28 | AA53 | 2024-05-03 |  |  | 2024-06-05 | 2024-05-25 | 2024-06-02 |  |  | 2022-08-19 | 0 |  |  | 2024-04-22 | 2024-04-30 | AA53.S24H7 |  | 0 | 2 | 2 | 0 | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  | 2024-04-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11401662 | METER,V;115-230VAC,FRER D72EV |  | 0020 | Replace panel meters S24H7 & TAUX/1 | INT | Replace panel meters S24H7 & TAUX/1 |  |  | 90007149_0010 |  |  |  |  | 05 | Release Completed | X | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 90007149 | 2024-04-04 | 20 | 2024-05-25 | 0 |  | 0 |  | 24SDGT7 | MJ | AU1009 | 1000137960 | S001 | 30 | 30 | 5300006133 | 20 |  | 5300008693 | 10 | 1 | EA | 1001 | AA02 | 2024-04-22 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 1 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance | [8 empty] | 0 | 00001385914541511401662100040070
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-22 | 2024-05-03 | 2024-05-03 | INLEC | 100040070 | 0020 | 0040 | 100040070 | MOC-119547 Replace meters S24H7 GT7 | AA53.S24H7 | SWBD,DIST 110VDC/240VAC UPS G4007 | AA01 | 20 | PR due for release | 11401663 | AMMETER;5A,115-230VAC,FRER D72EA4PROG05S | 1 | EA | 0 | 0 | 0 | 0 |  | 05.04 - PR 1000007714 |  | PR approved; PO not issued | SP97 | Direct Multi-base | 42 | AA01 | 5300008693 | 20 |  | 7 | 1000007714 | 4 |  |  |  | 0 | 0 | EA |  |  |  |  | 90007149 | 05 | Preparation | 0000138591 | 4 | 0 | [9 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-04-04 | PRPO-1000007714_00004 | 0 | 33 | 0 | 2024-05-23 | 2024-04-28 | AA53 | 2024-05-03 |  |  | 2024-06-05 | 2024-05-25 | 2024-06-02 |  |  | 2022-08-19 | 0 |  |  | 2024-04-22 | 2024-04-30 | AA53.S24H7 |  | 0 | 2 | 2 | 0 | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  | 2024-04-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11401663 | AMMETER;5A,115-230VAC,FRER D72EA4PROG05S |  | 0020 | Replace panel meters S24H7 & TAUX/1 | INT | Replace panel meters S24H7 & TAUX/1 |  |  | 90007149_0020 |  |  |  |  | 05 | Release Completed | X | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 90007149 | 2024-04-04 | 20 | 2024-05-25 | 0 |  | 0 |  | 24SDGT7 | MJ | AU1009 | 1000137960 | S001 | 30 | 30 | 5300006133 | 30 |  | 5300008693 | 20 | 1 | EA | 1001 | AA02 | 2024-04-22 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 1 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance | [8 empty] | 0 | 00001385914541511401663100040070
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-22 | 2024-05-03 | 2024-05-03 | INLEC | 100040070 | 0020 | 0050 | 100040070 | MOC-119547 Replace meters S24H7 GT7 | AA53.S24H7 | SWBD,DIST 110VDC/240VAC UPS G4007 | AA01 | 20 | PR due for release | 11401664 | AMMETER;60MV,FRER D72MA5YYYX60L | 1 | EA | 0 | 0 | 0 | 0 |  | 05.04 - PR 1000007714 |  | PR approved; PO not issued | SP97 | Direct Multi-base | 42 | AA01 | 5300008693 | 30 |  | 7 | 1000007714 | 5 |  |  |  | 0 | 0 | EA |  |  |  |  | 90007149 | 05 | Preparation | 0000138591 | 5 | 0 | [9 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-04-04 | PRPO-1000007714_00005 | 0 | 33 | 0 | 2024-05-23 | 2024-04-28 | AA53 | 2024-05-03 |  |  | 2024-06-05 | 2024-05-25 | 2024-06-02 |  |  | 2022-08-19 | 0 |  |  | 2024-04-22 | 2024-04-30 | AA53.S24H7 |  | 0 | 2 | 2 | 0 | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  | 2024-04-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11401664 | AMMETER;60MV,FRER D72MA5YYYX60L |  | 0020 | Replace panel meters S24H7 & TAUX/1 | INT | Replace panel meters S24H7 & TAUX/1 |  |  | 90007149_0030 |  |  |  |  | 05 | Release Completed | X | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 | 0 | AA02 | 90007149 | 2024-04-04 | 20 | 2024-05-25 | 0 |  | 0 |  | 24SDGT7 | MJ | AU1009 | 1000137960 | S001 | 30 | 30 | 5300006133 | 40 |  | 5300008693 | 30 | 1 | EA | 1001 | AA02 | 2024-04-22 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 1 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance | [8 empty] | 0 | 00001385914541511401664100040070
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | ROTAT | 100046883 | 0030 | 0062 | 100046883 | 409LG504 Clean Oil Sampling Valve | AA53.409LG504 | GAUGE,LEVEL GT4009V3 STARTING OIL TANK | AA01 | 255 | No Issue identified | 10530791 | OIL,LUB;SHELL TURBO S4 X 32,209L | 3 | DR | 0 | 2 | 2 | 0 |  | 27.03 - Need Purchasing, ETA 05.04.24 PO 4500008292 x 1 Viva Energy, 1 @ AA01 | Supply for Order 100046883, Item 3 cannot be changed 90000427 item 30 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300002928 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180004337 | 9000028 | 05 | Preparation | 0000145404 | 3 | 0 | [9 empty] | WorkPackLink |  | PK_STAGING | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-01-02 | IDST-0180004337 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2018-09-14 | 2 | 4900030573_2024_0005 |  | 2024-02-12 | 2024-05-03 | GT4009 |  | 0 | 2 | 0 | 0 | 0 | 180004337/180004337 | 3 | L | 4900030573 | 2024 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10530791 | OIL,LUB;SHELL TURBO S4 X 32,209L |  | 0030 | REPLACE WITH NEW OIL | INT | REPLACE WITH NEW OIL | 5 |  | 90000427_0030/9000028_0090_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000427 |  | 99 |  | 3 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000144753 | S002 | 30 | 30 | 5300002928 | 30 |  |  | 0 | 3 | DR | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 145404 | 0 |  | 2 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance |  | 2Wks Before Start | 2024-04-05 | 2Wks Before Start | CPT | VIVA ENERGY' | 4500008292 | 2024-04-05 | 1
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-03 | INLEC | 100040070 | 0020 | 0060 | 100040070 | MOC-119547 Replace meters S24H7 GT7 | AA53.S24H7 | SWBD,DIST 110VDC/240VAC UPS G4007 |  | 20 | No Issue identified | 11401665 | METER,V;200V,FRER D72MV5200XSDL | 1 | EA | 0 | 0 | 0 | 0 |  | 05.04 - Need Purchasing |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000138591 | 6 | 0 | [9 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2022-08-19 | 0 |  |  |  |  | AA53.S24H7 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11401665 | METER,V;200V,FRER D72MV5200XSDL |  | 0020 | Replace panel meters S24H7 & TAUX/1 | INT | Replace panel meters S24H7 & TAUX/1 | [10 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000137960 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 1 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance | [8 empty] | 0 | 00001385914541511401665100040070
| 24SDGT7 | Released | 2024-01-02 | 2024-05-06 | 2024-05-08 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0130 | 0160 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10537210 | BOLT;FORWARD MOUNT,GE MS955728 | 6 | EA | 0 | 0 | 0 | 0 |  | 01.03 - PO 4510756070/4510756028 on hold for correct pressure equipment doc | Supply for Order 200064906, Item 16 cannot be changed 90000127 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000127 | 05 | Preparation | 0000099208 | 16 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000127_0020 | 5 | 0 | 0 |  | 2024-05-09 | AA53 | 2024-05-06 |  |  | 2024-05-11 |  |  |  |  | 2024-07-20 | 0 |  |  | 2024-05-08 | 2024-05-11 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-08 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10537210 | BOLT;FORWARD MOUNT,GE MS955728 |  | 0130 | PCC FORWARD MOUNT BOLT WEAR INSPECTION | INT | PCC FORWARD MOUNT BOLT WEAR INSPECTION | 5 |  | 90000127_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000127 |  | 5 |  | 16 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 | 30 | 30 | 5300003442 | 140 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-05-08 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | [8 empty] | 0 | 00000992084541810537210200064906
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-08 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0130 | 0160 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10537210 | BOLT;FORWARD MOUNT,GE MS955728 | 6 | EA | 0 | 0 | 0 | 0 |  | 01.03 - PO 4510756070/4510756028 on hold for correct pressure equipment doc | Supply for Order 200071136, Item 16 cannot be changed 90000086 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000086 | 05 | Preparation | 0000105457 | 16 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000086_0020 | 0 | 0 | 0 |  | 2024-05-09 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-06-30 | 0 |  |  | 2024-05-08 | 2024-05-11 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-08 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10537210 | BOLT;FORWARD MOUNT,GE MS955728 |  | 0130 | PCC FORWARD MOUNT BOLT WEAR INSPECTION | INT | PCC FORWARD MOUNT BOLT WEAR INSPECTION | 5 |  | 90000086_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000086 |  | 5 |  | 16 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 | 30 | 30 | 5300004106 | 140 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-05-08 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | [8 empty] | 0 | 00001054574543110537210200071136
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-08 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0100 | 0210 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10537210 | BOLT;FORWARD MOUNT,GE MS955728 | 6 | EA | 0 | 0 | 0 | 0 |  | 01.03 - PO 4510756070/4510756028 on hold for correct pressure equipment doc | Supply for Order 200083506, Item 21 cannot be changed 90000284 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000284 | 05 | Preparation | 0000121037 | 21 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000284_0010 | 0 | 0 | 0 |  | 2024-05-09 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-06-30 | 0 |  |  | 2024-05-08 | 2024-05-11 | 2200670051 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-08 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10537210 | BOLT;FORWARD MOUNT,GE MS955728 |  | 0100 | PCC FORWARD MOUNT BOLT WEAR | INT | PCC FORWARD MOUNT BOLT WEAR | 5 |  | 90000284_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000284 |  | 5 |  | 21 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 | 30 | 30 | 5300003974 | 180 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-05-08 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance | [8 empty] | 0 | 00001210374542710537210200083506
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-12 | 2024-05-15 | 2024-05-15 | ROTAT | 200057958 | 0010 | 0010 | 200057958 | 2Y GT4008 TURB PRE FILTER REPLACE | AA53.GT4008S2 | FILT,AIR INLET GT4008 | AA01 | 20 | No Issue identified | 10565960 | SLEEVE;PRE FLT,DONALDSON P039859 | 200 | EA | 0 | 0 | 0 | 0 |  | 05.04 - PO W451780337 is ready for collection, |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006424 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000092306 | 2 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 200 |  |  | Y | 1001 | 2024-02-12 | STST-5300006424_00010 | 0 | 0 | 0 |  | 2024-05-13 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-05-30 | 0 |  |  | 2024-05-12 | 2024-05-15 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10565960 | SLEEVE;PRE FLT,DONALDSON P039859 |  | 0010 | Mobilise Filters and Equipment | INT | Mobilise Filters and Equipment | 0 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 20 |  | 2 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000091660 | S002 | 30 | 30 | 5300006424 | 10 |  |  | 0 | 200 | EA | 2001 | AA02 | 2024-05-12 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 92306 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | [8 empty] | 0 | 00000923064542710565960200057958
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-16 | 2024-05-19 | 2024-05-19 | ROTAT | 200057959 | 0010 | 0010 | 200057959 | 2Y GT4009 TURB PRE FILTER REPLACE | AA53.GT4009S2 | FILT,AIR INLET,GT4009 | AA01 | 20 | No Issue identified | 10565960 | SLEEVE;PRE FLT,DONALDSON P039859 | 200 | EA | 0 | 0 | 0 | 0 |  | 05.04 - PO W451780337 is ready for collection, |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006425 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000092307 | 2 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 200 |  |  | Y | 1001 | 2024-02-12 | STST-5300006425_00010 | 0 | 0 | 0 |  | 2024-05-17 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-05-30 | 0 |  |  | 2024-05-16 | 2024-05-19 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10565960 | SLEEVE;PRE FLT,DONALDSON P039859 |  | 0010 | Mobilise Filters and Equipment | INT | Mobilise Filters and Equipment | 0 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 20 |  | 2 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000091721 | S002 | 30 | 30 | 5300006425 | 10 |  |  | 0 | 200 | EA | 2001 | AA02 | 2024-05-16 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 92307 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance | [8 empty] | 0 | 00000923074543110565960200057959
| 24SDGT7 | Released | 2024-02-08 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-04 | ROTAT | 200079172 | 0040 | 0030 | 200079172 | 12Y P01 INT INSP PRESS VESSEL GT4007S5B | AA53.GT4007S5B | FILT,GT FUEL GAS GT4007 FILTERS | AA01 | 10 | No Issue identified | 10008156 | FILTER,CART;GF,5.5X36",NP ISM4113520 | 1 | EA | 0 | 0 | 2 | 0 |  | 27.03 - ETA 14.05.24 PO W451774754 x 12 NP | Supply for Order 200079172, Item 3 cannot be changed 90006337 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006250 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006337 | 05 | Preparation | 0000113528 | 3 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-08 | ODST-0090006337_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-07-15 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008156 | FILTER,CART;GF,5.5X36",NP ISM4113520 |  | 0040 | Open Top Lid / N-11, Remove Filters | INT | Open Top Lid / N-11, Remove Filters | 5 |  | 90006337_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006337 |  | 5 |  | 3 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000112891 | S002 | 30 | 30 | 5300006250 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 113528 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Material committed/Printed/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | During Turnaround | 2024-05-29 | During Turnaround | FCA | NUOVO PIGNONE | W451774754 | 2024-05-14 | 2
| 24SDGT7 | Released | 2024-02-08 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-06 | ROTAT | 200079174 | 0040 | 0030 | 200079174 | 12Y P01 INT INSP PRESS VESSEL GT4007S5A | AA53.GT4007S5A | FILT,GT FUEL GAS GT4007 FILTERS | AA01 | 10 | No Issue identified | 10008156 | FILTER,CART;GF,5.5X36",NP ISM4113520 | 1 | EA | 0 | 0 | 2 | 0 |  | 27.03 - ETA 14.05.24 PO W451774754 x 12 NP | Supply for Order 200079174, Item 3 cannot be changed 90006338 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006251 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006338 | 05 | Preparation | 0000113530 | 3 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-08 | ODST-0090006338_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-07-15 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008156 | FILTER,CART;GF,5.5X36",NP ISM4113520 |  | 0040 | Open Top Lid / N-11 For Insp | INT | Open Top Lid / N-11 For Insp | 5 |  | 90006338_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006338 |  | 5 |  | 3 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000112893 | S002 | 30 | 30 | 5300006251 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 113530 | 0 |  | 2 |  |  | RC00025003 | 2024-05-06 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | During Turnaround | 2024-05-29 | During Turnaround | FCA | NUOVO PIGNONE | W451774754 | 2024-05-14 | 2
| 24SDGT8 | Released | 2024-02-07 | 2024-05-15 | 2024-04-30 | 2024-02-04 | 2024-06-07 | INLEC | 100037026 | 0030 | 0040 | 100037026 | MOC-118435 CO2 Discharge Switch Replacem | AA53.860PZ653 | SW,PRESS DISCH EXT CO2 T/ENCL GT4008 | AA01 | 20 | No Issue identified | 10038826 | VALVE,BALL;0.25",6000PSIG,GYROLOCK,SS316 | 10 | EA | 5 | 0 | 0 | 2 | EA | IN GRAY TUB/ETA 22.04.24 PO 4500006433 x 5 Prochem | Supply for Order 100037026, Item 4 cannot be changed 90000782 item 40 already exists | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006181 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000782 | 07 | Execution | 0000135527 | 4 | 0 | EA | 102000000003504 |  | 102000000003513 | [5 empty] | WorkPackLink | PACKING | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-02-07 | ODST-0090000782_0040 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2023-12-31 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10038826 | VALVE,BALL;0.25",6000PSIG,GYROLOCK,SS316 |  | 0030 | Complete Replacement | INT | Complete Replacement |  |  | 90000782_0040 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000782 |  | 20 |  | 4 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000134916 | S002 | 30 | 30 | 5300006181 | 40 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  | 2024-02-04 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 135527 | 0 |  | 3 |  |  | RC00025003 | 2024-06-07 | 2024-02-04 | 2024-02-04 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Printed/Goods movement posted | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-22 | After Staging Date | CPT | PROCHEM | 4500006433 | 2024-04-22 | FALSE
| 24SDGT9 | Released | 2024-02-13 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | INLEC | 100039826 | 0010 | 0020 | 100039826 | Combustion drain rubbing | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 255 | No Issue identified | 10047842 | ADAPTOR;COMP/PIPE,M,1"ODX 1"NPT,SS | 10 | EA | 1 | 0 | 0 | 1 | EA | IN GRAY TUB/ETA 19.04.24 PO 4500006433 x 10 Prochem | Supply for Order 100039826, Item 2 cannot be changed 90006342 item 20 already exists | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006511 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006342 | 05 | Preparation | 0000138318 | 2 | 0 | EA | 102000000003506 |  | 102000000003512 | [5 empty] | WorkPackLink | PACKING | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-02-13 | ODST-0090006342_0020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-06-18 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10047842 | ADAPTOR;COMP/PIPE,M,1"ODX 1"NPT,SS |  | 0010 | Isolate & Disconnect Tubing | INT | Isolate & Disconnect Tubing |  |  | 90006342_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006342 |  | 99 |  | 2 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000137748 | S002 | 30 | 30 | 5300006511 | 20 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138318 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-19 | After Staging Date | CPT | PROCHEM | 4500006433 | 2024-04-19 | FALSE
| 24SD4401 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-02 | 2024-05-03 | VALVE | 100043677 | 0010 | 0040 | 100043677 | MV-RE 12" 300# 44GAV0277 | AA53.K4401C | COMPR,FUEL GAS BOOSTER | AA01 | 30 | No Issue identified | 10054896 | VALVE,GATE,300MM,CL300,RF,CS,C3G | 1 | EA | 0 | 0 | 0 | 0 |  | 22.03 - ETA 02.05.24 PO W451779024 ex Score (Revised now ETA Score Pth 18.04) |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006338 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142209 | 5 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-09 | STST-5300006338_00020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2020-11-02 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10054896 | VALVE,GATE,300MM,CL300,RF,CS,C3G |  | 0010 | Remove Valve | INT | Remove Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 30 |  | 5 |  | 0 |  | 24SD4401 | MJ | AU1072 | 1000141579 | S002 | 30 | 30 | 5300006338 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142209 | 0 |  | 2 |  |  | RC00025003 | 2024-05-03 | 2024-05-02 | 2024-05-02 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | 2Wks After Start | 2024-05-02 | 2Wks After Start | CPT | SCORE | W451779024 | 2024-05-02 | 0
| 24SDFR2 | Released | 2024-01-02 | 2024-04-05 | 2024-04-02 | 2024-04-16 | 2024-04-23 | MECH | 600001793 | 0011 | 0010 | 600001793 | MOC-89056 Fab/Weld Install 218UCV112 | AA53.2E1801 | EXCH,HEAT DE-ETH REBOIL FRACT2 | AA01 | 10 | No Issue identified | 10202346 | FLANGE,WN;150MM,CL300,RF,A105N,SCH 40 | 2 | EA | 0 | 0 | 0 | 0 |  | 28.03 - ETA 18.04.24 PO 4500009023 x 2 Australian Fittings | Supply for Order 600001793, Item 18 cannot be changed 90006652 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004605 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006652 | 06 | Scheduling | 0000084711 | 18 | 0 | [9 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006652_0010 | 0 | 0 | 0 |  | 2024-04-03 | AA53 | 2024-04-16 |  |  | 2024-04-05 |  |  |  |  | 2024-12-15 | 0 |  |  | 2024-04-02 | 2024-04-05 | 218UCV112 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-02 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202346 | FLANGE,WN;150MM,CL300,RF,A105N,SCH 40 |  | 0011 | Fabricate Pup Piece Spool | INT | Fabricate Pup Piece Spool |  |  | 90006652_0010 | [7 empty] | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 | 90006652 |  | 5 |  | 18 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000084095 | S002 |  |  | 5300004605 | 120 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-02 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84711 | 0 |  | 2 |  |  | RC00018003 | 2024-04-23 | 2024-04-16 | 2024-04-16 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Material shortage/Printed | AM06 | Capital |  | After Staging Date | 2024-04-18 | After Staging Date | CPT | AUSTRALIAN FITTINGS | 4500009023 | 2024-04-18 | 0
| 24SDFR2 | Released | 2024-01-02 | 2024-04-22 | 2024-04-19 | 2024-04-16 | 2024-04-23 | MECH | 600001793 | 0070 | 0010 | 600001793 | MOC-89056 Fab/Weld Install 218UCV112 | AA53.2E1801 | EXCH,HEAT DE-ETH REBOIL FRACT2 | AA01 | 10 | No Issue identified | 10202346 | FLANGE,WN;150MM,CL300,RF,A105N,SCH 40 | 2 | EA | 0 | 0 | 0 | 0 |  | 28.03 - ETA 14.04.24 PO 4500008801 x 2 Australian Fittings | Supply for Order 600001793, Item 12 cannot be changed 90006857 item 60 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004605 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006857 | 06 | Scheduling | 0000084711 | 12 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006857_0060 | 0 | 0 | 0 |  | 2024-04-20 | AA53 | 2024-04-22 |  |  | 2024-04-22 |  |  |  |  | 2024-12-15 | 0 |  |  | 2024-04-19 | 2024-04-22 | 218UCV112 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10202346 | FLANGE,WN;150MM,CL300,RF,A105N,SCH 40 |  | 0070 | Cut Spool In-Situ | INT | Cut Spool In-Situ | 5 |  | 90006857_0060 | [7 empty] | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 | 90006857 |  | 5 |  | 12 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000084095 | S002 |  |  | 5300004605 | 130 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-19 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84711 | 0 |  | 2 |  |  | RC00018003 | 2024-04-23 | 2024-04-16 | 2024-04-16 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Material shortage/Printed | AM06 | Capital |  | 2Wks Before Start | 2024-04-14 | 2Wks Before Start | CPT | AUSTRALIAN FITTINGS | 4500008801 | 2024-04-14 | 0
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0160 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10242467 | FOAM;LIQ ISOCYANATE;250KG,ARIEL B9001 | 750 | KG | 0 | 0 | 0 | 0 |  | 26.02 - ETA 18.04.24: qty 3 x Drum (750kg) PO 4500003015 ex ERA Polymers | Supply for Order 100033847, Item 16 cannot be changed 90004487 item 140 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | KG |  |  |  |  | 90004487 | 07 | Execution | 0000132381 | 16 | 0 | [9 empty] | WorkPackLink |  | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 750 |  |  | Y | 1001 | 2024-01-15 | ODST-0090004487_0140 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  |  |  | 2025-10-01 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10242467 | FOAM;LIQ ISOCYANATE;250KG,ARIEL B9001 |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 90004487_0140 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 16 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 160 |  |  | 0 | 750 | KG | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | After Staging Date | 2024-04-18 | After Staging Date | CPT | POLYMERS | 4500003015 | 2024-04-18 | 0
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0150 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10242468 | FOAM,POLYOL;230KG DRM,ARIEL DP9505POLYOL | 690 | KG | 0 | 0 | 0 | 0 |  | 26.02 - ETA 18.04.24: qty 3 x Drum (690kg) PO 4500003015 ex ERA Polymers | Supply for Order 100033847, Item 15 cannot be changed 90004487 item 130 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | KG |  |  |  |  | 90004487 | 07 | Execution | 0000132381 | 15 | 0 | [9 empty] | WorkPackLink |  | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 690 |  |  | Y | 1001 | 2024-01-15 | ODST-0090004487_0130 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  |  |  | 2025-10-01 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10242468 | FOAM,POLYOL;230KG DRM,ARIEL DP9505POLYOL |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 90004487_0130 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 15 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 150 |  |  | 0 | 690 | KG | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | After Staging Date | 2024-04-18 | After Staging Date | CPT | POLYMERS | 4500003015 | 2024-04-18 | 0
| 24SDFR2 | Released | 2024-03-20 | 2024-04-23 | 2024-04-20 | 2024-04-23 | 2024-04-23 | INLEC | 100036100 | 0040 | 0010 | 100036100 | T20CD3 & T20CD4 LV cables clamping | AA53.T20CD3 | XFMR,6.6/0.433KV FDR FOR MCC S20D2 A | AA01 | 20 | No Issue identified | 10245837 | CLAMP,CDUIT,38MM,HDG | 100 | EA | 36 | 0 | 0 | 0 |  | 21.03 - ETA 08.04.24 PO 4500007825 Blackwoods |  | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300008135 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006881 | 05 | Preparation | 0000134624 | 1 | 0 | [9 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 100 |  |  | Y | 1001 | 2024-03-20 | ODST-0090006881_0010 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-20 | 2024-04-23 | T20CD3 & 4 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10245837 | CLAMP,CDUIT,38MM,HDG |  | 0040 | T20CD3 & T20CD4 LV Cable Clamping | INT | T20CD3 & T20CD4 LV Cable Clamping | 2 |  | 90006881_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006881 |  | 20 |  | 1 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000133975 | S002 |  | 30 | 5300008135 | 10 |  |  | 0 | 100 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 134624 | 0 |  | 3 |  |  | RC00025003 | 2024-04-23 | 2024-04-23 | 2024-04-23 | Printed/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage | AM01 | Reactive Maintenance |  | 2Wks Before Start | 2024-04-08 | 2Wks Before Start | CPT | Blackwoods | 4500007825 | 2024-04-08 | FALSE
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0220 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | Shipped qty below requirement qty | 10248914 | TAPE,FIL;CROSS WEAVE,170UM,19MM | 30 | ROL | 0 | 0 | 10 | 10 | ROL | 21.03 - ETA 18.04.2024 PO 4500007655 PYROTEK | Supply for Order 100033847, Item 21 cannot be changed 90004487 item 190 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180013609 | 9000596 | 07 | Execution | 0000132381 | 21 | 0 | ROL | 102000000003648 |  | 102000000003683 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | P07-BENCH | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y | 1001 | 2024-01-15 | GRST-5000045904 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  | 100000005106 | 1020 | 2025-10-01 | 10 | 4900040481_2024_0027 |  | 2024-03-26 | 2024-05-03 |  | 5000045904_2024_0014 | 0 | 2 | 0 | 10 | 0 | 180013609 | 1 | L | 4900040481 | 2024 |  | 5000045904 | 2024 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10248914 | TAPE,FIL;CROSS WEAVE,170UM,19MM |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 90004487_0190/9000596_0190 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 21 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 |  | 30 | 5300004834 | 210 |  |  | 0 | 30 | ROL | 2001 | AA02 | 2024-04-30 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | After Staging Date | 2024-04-18 | After Staging Date | CPT | PYROTEK | 4500007655 | 2024-04-18 | 30
| 24SDGT7 | Released | 2024-01-02 | 2024-05-04 | 2024-05-01 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0050 | 0100 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10255241 | WASHER,TFR/ACCESS;GE 9009M32P01 | 3 | EA | 0 | 0 | 0 | 0 |  | 05.04 - ETA 03.05.24 PO W451780583 x 200 NP, BH advise readiness in April |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 320 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000099208 | 34 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-01-02 | STST-5300003442_00320 | 0 | 0 | 0 |  | 2024-05-02 | AA53 | 2024-05-04 |  |  | 2024-05-04 |  |  |  |  | 2024-07-20 | 0 |  |  | 2024-05-01 | 2024-05-04 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-01 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255241 | WASHER,TFR/ACCESS;GE 9009M32P01 |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 5 |  | 34 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 |  | 30 | 5300003442 | 320 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-05-01 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | During Turnaround | 2024-05-18 | During Turnaround | FCA | NUOVO PIGNONE | W451780583 | 2024-05-03 | 0
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-16 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0050 | 0100 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10255241 | WASHER,TFR/ACCESS;GE 9009M32P01 | 100 | EA | 0 | 0 | 0 | 0 |  | 05.04 - ETA 03.05.24 PO W451780583 x 200 NP, BH advise readiness in April |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 320 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000105457 | 34 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 100 |  |  | Y | 1001 | 2024-01-02 | STST-5300004106_00320 | 0 | 0 | 0 |  | 2024-05-17 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-06-30 | 0 |  |  | 2024-05-16 | 2024-05-19 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255241 | WASHER,TFR/ACCESS;GE 9009M32P01 |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 5 |  | 34 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 |  | 30 | 5300004106 | 320 |  |  | 0 | 100 | EA | 2001 | AA02 | 2024-05-16 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | During Turnaround | 2024-05-18 | During Turnaround | FCA | NUOVO PIGNONE | W451780583 | 2024-05-03 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0080 | 0160 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10255241 | WASHER,TFR/ACCESS;GE 9009M32P01 | 100 | EA | 0 | 0 | 0 | 0 |  | 27.03 - ETA 10.05.24 PO W451765139 x 200 NP |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000117945 | 33 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 100 |  |  | Y | 1001 | 2024-01-02 | STST-5300003490_00290 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-06-30 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255241 | WASHER,TFR/ACCESS;GE 9009M32P01 |  | 0080 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 5 |  | 33 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 |  | 30 | 5300003490 | 290 |  |  | 0 | 100 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | During Turnaround | 2024-05-25 | During Turnaround | FCA | NUOVO PIGNONE | W451765139 | 2024-05-10 | 0
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-12 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0080 | 0340 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10255241 | WASHER,TFR/ACCESS;GE 9009M32P01 | 100 | EA | 0 | 0 | 0 | 0 |  | 27.03 - ETA 10.05.24 PO W451765139 x 200 NP |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000121037 | 33 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 100 |  |  | Y | 1001 | 2024-01-02 | STST-5300003974_00290 | 0 | 0 | 0 |  | 2024-05-13 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-06-30 | 0 |  |  | 2024-05-12 | 2024-05-15 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255241 | WASHER,TFR/ACCESS;GE 9009M32P01 |  | 0080 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 5 |  | 33 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 |  | 30 | 5300003974 | 290 |  |  | 0 | 100 | EA | 2001 | AA02 | 2024-05-12 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | During Turnaround | 2024-05-25 | During Turnaround | FCA | NUOVO PIGNONE | W451765139 | 2024-05-10 | 0
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0010 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | Shipped qty below requirement qty | 10290467 | PLUG,TUBE;8.6X7.8X76.2MM LG,TAP,O/S,AL | 40 | EA | 0 | 0 | 10 | 10 | EA | 21.03 - ETA 18.04.2024 PO 4500007653 | Supply for Order 100033847, Item 1 cannot be changed 90004487 item 10 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180013609 | 9000596 | 07 | Execution | 0000132381 | 1 | 0 | EA | 102000000003648 |  | 102000000003683 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | P07-BENCH | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 40 |  |  | Y | 1001 | 2024-01-15 | GRST-5000045904 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  | 100000005106 | 1020 | 2025-10-01 | 10 | 4900040481_2024_0001 |  | 2024-03-26 | 2024-05-03 |  | 5000045904_2024_0001 | 0 | 2 | 0 | 10 | 0 | 180013609 | 1 | L | 4900040481 | 2024 |  | 5000045904 | 2024 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10290467 | PLUG,TUBE;8.6X7.8X76.2MM LG,TAP,O/S,AL |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 90004487_0010/9000596_0010 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 1 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 10 |  |  | 0 | 40 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | After Staging Date | 2024-04-18 | After Staging Date | CPT | PROCHEM | 4500007653 | 2024-04-18 | 0
| 24SDLN1 | Released | 2024-03-05 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-13 | VALVE | 100073710 | 0010 | 0030 | 100073710 | CV-OH 10" 600# 141FCV02 | AA53.141FCV02 | VALVE,H/W FLOW TO 1E4102 CV | AA01 | 255 | No Issue identified | 10294388 | GASKET;FISHER RGASKETX232 | 2 | KIT | 0 | 0 | 0 | 0 |  | 06.03 - ETA 10.04.24 PO 4500005289 x 2 SCORE |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300007483 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT | [5 empty] | 05 | Preparation | 0000224102 | 3 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-03-05 | STST-5300007483_00030 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2026-02-15 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10294388 | GASKET;FISHER RGASKETX232 |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | [10 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 99 |  | 3 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000221710 | S002 |  | 30 | 5300007483 | 30 |  |  | 0 | 2 | KIT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-02-26 | 224102 | 0 |  | 2 |  |  | RC00025003 | 2024-05-13 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | 2Wks Before Start | 2024-04-10 | 2Wks Before Start | CPT | SCORE | 4500005289 | 2024-04-10 | 0
| 24SDLN1 | Released | 2024-03-14 | 2024-05-03 | 2024-04-22 | 2024-05-03 | 2024-05-08 | VALVE | 100033493 | 0010 | 0030 | 100033493 | CV-OH 3" 600# 114URC37 | AA53.114URC37 | LOOP,1E1405 BLOWDOWN PRESS RATIO CONTROL | AA01 | 10 | No Issue identified | 10294794 | GASKET KIT;FISHER RGASKETX192 | 1 | KIT | 0 | 0 | 0 | 0 |  | 25.03 - ETA 26.04.24 PO 4500008188 Western Process | Supply for Order 100033493, Item 3 cannot be changed 90005621 item 50 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300007886 | 10 | CPT | 7 | 1000005511 | 3 | 30000278 | WESTERN PROCESS CONTROLS PTY LTD | 4500008188 | 10 | 1 | KIT | 2024-04-15 |  |  |  | 90005621 | 05 | Preparation | 0000131994 | 3 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-03-14 | ODST-0090005621_0050 | 0 | 18 | 0 | 2024-05-08 | 2024-04-28 | AA53 | 2024-05-03 |  |  | 2024-05-21 | 2024-05-10 | 2024-05-18 |  |  | 2023-11-11 | 0 |  |  | 2024-04-22 | 2024-04-30 |  |  | 0 | 2 | 2 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10294794 | GASKET KIT;FISHER RGASKETX192 |  | 0010 | Transport Valve to Workshop | INT | Transport Valve to Workshop |  |  | 90005621_0050 |  |  |  |  | 05 | Release Completed | X | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 90005621 | 2024-03-14 | 10 | 2024-05-10 | 0 |  | 0 |  | 24SDLN1 | MJ | AU1009 | 1000131423 | S001 | 30 | 30 | 5300007885 | 20 |  | 5300007886 | 10 | 1 | KIT | 1001 | AA02 | 2024-04-22 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Released/Order Approved/Settlement rule created/Object created/Pre-costed | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | Western Process | 4500008188 | 2024-04-26 | 0
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-01 | 2024-05-15 | 2024-05-15 | ROTAT | 200083165 | 0030 | 0100 | 200083165 | 1Y GT4008 TURB VSV REPLACEMENT | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | Shipped qty below requirement qty | 10297383 | NUT,HEX;0.250"X28UN,GE AN316C4R | 60 | EA | 0 | 0 | 100 | 40 | EA | 24SDGT8-SW3R02A01B/ETA 03.05.24 PO W451780474 x 60 Nuovo Pignone | Supply for Order 200083165, Item 10 cannot be changed 90000278 item 70 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003892 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004309 | 9000024 | 05 | Preparation | 0000120014 | 10 | 0 | EA | 102000000000283 | 102000000000300 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 60 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017867_2024 | 0 | 0 | 0 |  | 2024-05-02 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-05-20 | 40 | 4900030498_2024_0011 |  | 2024-02-12 | 2024-05-04 | GT4008 | 5000017867_2024_0006 | 0 | 2 | 0 | 40 | 0 | 180004309 | 1 | L | 4900030498 | 2024 |  | 5000017867 | 2024 |  |  | 2024-05-01 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297383 | NUT,HEX;0.250"X28UN,GE AN316C4R |  | 0030 | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | INT | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | 5 |  | 90000278_0070/9000024_0070 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000278 |  | 20 |  | 10 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000119504 | S002 |  | 30 | 5300003892 | 100 |  |  | 0 | 60 | EA | 2001 | AA02 | 2024-05-01 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120014 | 0 |  | 1 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | During Turnaround | 2024-05-18 | During Turnaround | FCA | NUOVO PIGNONE | W451780474 | 2024-05-03 | 0
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-23 | 2024-09-14 | VALVE | 100040577 | 0010 | 0050 | 100040577 | CV-OH 1" 300# 218PDCV506 | AA53.218PDCV506 | VALVE,2K1820E1 S/OIL PRESS CTRL | AA01 | 20 | No Issue identified | 10306122 | RING;BOX,PACKING,SS,FISHER 1J873235072 | 1 | EA | 0 | 0 | 0 | 0 |  | 20.03 - ETA 19.08.24 PO 4500006431 Score Expediting Exhausted on Critical Report | Supply for Order 100040577, Item 5 cannot be changed 90006874 item 30 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300002250 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006874 | 05 | Preparation | 0000139149 | 5 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006874_0030 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-31 | 0 |  |  | 2024-04-20 | 2024-04-23 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10306122 | RING;BOX,PACKING,SS,FISHER 1J873235072 |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90006874_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006874 |  | 20 |  | 5 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000138479 | S002 |  | 30 | 5300002250 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139149 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Order Approved/Printed/Object created/Date set by external system/Pre-costed/Released/Settlement rule created/Material shortage | AM01 | Reactive Maintenance |  | After Turnaround | 2024-08-19 | After Turnaround | CPT | SCORE | 4500006431 | 2024-08-19 | 1
| 24SD4403 | Released | 2024-01-30 | 2024-05-07 | 2024-05-04 | 2024-05-07 | 2024-05-07 | INLEC | 100042451 | 0090 | 0010 | 100042451 | Replace Flow Tx - 44FIT520 | AA53.44FIT520 | METER,FLOW K4403 SEALGAS PRIM VENT | AA01 | 20 | No Issue identified | 10313669 | FMTR;NP RJO01742 | 1 | EA | 0 | 0 | 0 | 0 |  | 27.03 - ETA 02.07.24 PO 4500002946 x 1 NP |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300005745 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000140972 | 3 | 0 | [9 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-30 | STST-5300005745_00020 | 0 | 0 | 0 |  | 2024-05-05 | AA53 | 2024-05-07 |  |  | 2024-05-07 |  |  |  |  | 2021-12-26 | 0 |  |  | 2024-05-04 | 2024-05-07 | 44FIT520 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-04 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10313669 | FMTR;NP RJO01742 |  | 0090 | Replace Flow Meter | INT | Replace Flow Meter | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 20 |  | 3 |  | 0 |  | 24SD4403 | MJ | AU1072 | 1000140401 | S002 |  | 30 | 5300005745 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-04 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140972 | 0 |  | 3 |  |  | RC00025003 | 2024-05-07 | 2024-05-07 | 2024-05-07 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | After Turnaround | 2024-07-17 | After Turnaround | FCA | NUOVO PIGNONE | 4500002946 | 2024-07-02 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-12 | 2024-05-03 | 2024-05-06 | ROTAT | 200072093 | 0170 | 0020 | 200072093 | 1Y GT4010 PACKAGE INSPECTION | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 20 | No Issue identified | 10349278 | GASKET;C4430,KLINGER 864432121 | 2 | KIT | 0 | 0 | 0 | 0 |  | 21.03 - ETA 17.04.24 PO 4500007644 KLINGER | Supply for Order 200072093, Item 2 cannot be changed 90000106 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004286 | 20 |  | 14 |  | 0 |  | 2 |  | 0 | 0 | KIT |  |  |  |  | 90000106 | 05 | Preparation | 0000106395 | 2 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000106_0020 | 12 | 0 | 0 |  | 2024-05-13 | AA53 | 2024-05-03 |  |  | 2024-05-15 |  |  |  |  | 2024-06-08 | 0 |  |  | 2024-05-12 | 2024-05-15 | GT10-MLO |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10349278 | GASKET;C4430,KLINGER 864432121 |  | 0170 | REPLACE MINERAL LUBE OIL FILTERS | INT | REPLACE MINERAL LUBE OIL FILTERS | 5 |  | 90000106_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000106 |  | 20 |  | 2 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000105812 | S002 | 30 | 30 | 5300004286 | 20 |  |  | 0 | 2 | KIT | 2001 | AA02 | 2024-05-12 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 106395 | 0 |  | 3 |  |  | RC00025003 | 2024-05-06 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | After Staging Date | 2024-04-17 | After Staging Date | CPT | KLINGER | 4500007644 | 2024-04-17 | 2
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-16 | 2024-05-19 | 2024-05-19 | ROTAT | 200083838 | 0280 | 0050 | 200083838 | 1Y GT4009 TURB OFF-ENGINE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | No Issue identified | 10349278 | GASKET;C4430,KLINGER 864432121 | 2 | KIT | 0 | 0 | 0 | 0 |  | 21.03 - ETA 29.04.2024 PO 4500007644 KLINGER | Supply for Order 200083838, Item 3 cannot be changed 90006607 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004043 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90006607 | 05 | Preparation | 0000121806 | 3 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006607_0010 | 0 | 0 | 0 |  | 2024-05-17 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-04-22 | 0 |  |  | 2024-05-16 | 2024-05-19 | GT9 S1A/B |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10349278 | GASKET;C4430,KLINGER 864432121 |  | 0280 | REPLACE MINERAL LUBE OIL FILTERS | INT | REPLACE MINERAL LUBE OIL FILTERS | 5 |  | 90006607_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006607 |  | 20 |  | 3 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000121198 | S002 | 30 | 30 | 5300004043 | 30 |  |  | 0 | 2 | KIT | 2001 | AA02 | 2024-05-16 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121806 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | After Staging Date | 2024-04-29 | After Staging Date | CPT | KLINGER | 4500007644 | 2024-04-29 | 2
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-03-25 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0370 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10353457 | TARPAULIN;2500MMX30M,PVC,WHT | 5 | ROL | 0 | 0 | 0 | 0 |  | 05.04 - ETA 26.04.24 PO 4500009755 x 8 / 4500005511 x 1 05.08.24 Blackwoods | Supply for Order 100033847, Item 45 cannot be changed 90006896 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 450 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90006896 | 07 | Execution | 0000132381 | 45 | 0 | [9 empty] | WorkPackLink |  | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-01-15 | ODST-0090006896_0010 | 22 | 0 | 0 |  | 2024-03-04 | AA53 | 2024-03-06 |  |  | 2024-03-28 |  |  |  |  | 2025-10-01 | 0 |  |  | 2024-03-25 | 2024-03-28 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-03-25 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10353457 | TARPAULIN;2500MMX30M,PVC,WHT |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 90006896_0010 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006896 |  | 99 |  | 45 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 450 |  |  | 0 | 5 | ROL | 2001 | AA02 | 2024-03-25 |  |  |  |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | After Staging Date | 2024-04-26 | After Staging Date | CPT | Blackwoods | 4500009755 | 2024-04-26 | 0
| 24SDLN1 | Released | 2024-03-14 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-08 | VALVE | 100033493 | 0010 | 0020 | 100033493 | CV-OH 3" 600# 114URC37 | AA53.114URC37 | LOOP,1E1405 BLOWDOWN PRESS RATIO CONTROL | AA01 | 10 | No Issue identified | 10428762 | GASKET;FISHER 1R3098X0052 | 1 | EA | 0 | 0 | 0 | 0 |  | 05.04 - ETA 26.04.24 PO 4500009655 x 1 Western Process |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300007885 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131994 | 2 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-03-14 | STST-5300007885_00010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2023-11-11 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10428762 | GASKET;FISHER 1R3098X0052 |  | 0010 | Transport Valve to Workshop | INT | Transport Valve to Workshop | [10 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 10 |  | 2 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131423 | S002 | 30 | 30 | 5300007885 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 131994 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Released/Order Approved/Settlement rule created/Object created/Pre-costed | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | Western Process | 4500009655 | 2024-04-26 | 0
| 24SDGT9 | Released | 2024-02-13 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | INLEC | 100039826 | 0010 | 0010 | 100039826 | Combustion drain rubbing | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 255 | No Issue identified | 10431311 | TUBE;SML,1.0"OD,2.76MM WT,SS316L,RB80 | 2 | EA | 0 | 0 | 0 | 0 |  | 16.02 - ETA 19.04.24 PO 4500002803 x qty 2 Prochem | Supply for Order 100039826, Item 1 cannot be changed 90006342 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006511 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006342 | 05 | Preparation | 0000138318 | 1 | 0 | [9 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-02-13 | ODST-0090006342_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-06-18 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10431311 | TUBE;SML,1.0"OD,2.76MM WT,SS316L,RB80 |  | 0010 | Isolate & Disconnect Tubing | INT | Isolate & Disconnect Tubing |  |  | 90006342_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006342 |  | 99 |  | 1 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000137748 | S002 |  | 30 | 5300006511 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138318 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-19 | After Staging Date | CPT | PROCHEM | 4500002803 | 2024-04-19 | 0
| 24SDLN1 | Released | 2024-01-15 | 2024-03-30 | 2024-03-27 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0270 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10431950 | INSULATION,BLANKET;2X50M,BIDIM A12 | 5 | ROL | 2 | 0 | 0 | 0 |  | 14.03 - qty 2 SOH at AA02; qty 5 SOH at AA01; ETA 22.0424 PO 4500006113 x qty 2 | Supply for Order 100033847, Item 27 cannot be changed 90004536 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 270 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90004536 | 07 | Execution | 0000132381 | 27 | 0 | [9 empty] | WorkPackLink |  | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-01-15 | ODST-0090004536_0010 | 0 | 0 | 0 |  | 2024-03-28 | AA53 | 2024-03-06 |  |  | 2024-03-30 |  |  |  |  | 2025-10-01 | 0 |  |  | 2024-03-27 | 2024-03-30 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-03-27 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10431950 | INSULATION,BLANKET;2X50M,BIDIM A12 |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 90004536_0010 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004536 |  | 99 |  | 27 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 270 |  |  | 0 | 5 | ROL | 2001 | AA02 | 2024-03-27 |  |  |  |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | After Staging Date | 2024-04-22 | After Staging Date | CPT | PYROTEK | 4500006113 | 2024-04-22 | FALSE
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0170 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | Shipped qty below requirement qty | 10441222 | TAPE,FOIL,REINF,TESA 51495,RL/50M | 30 | ROL | 2 | 0 | 24 | 24 | ROL | 19.03 - ETA 22.04.2024 PO 4500006918 BLACKWOODS | Supply for Order 100033847, Item 17 cannot be changed 90004487 item 150 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180013609 | 9000596 | 07 | Execution | 0000132381 | 17 | 0 | ROL | 102000000003648 |  | 102000000003683 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | P07-BENCH | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 30 |  |  | Y | 1001 | 2024-01-15 | GRST-5000045904 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  | 100000005106 | 1020 | 2025-10-01 | 24 | 4900040481_2024_0023 |  | 2024-03-26 | 2024-05-03 |  | 5000045904_2024_0012 | 0 | 2 | 0 | 24 | 0 | 180013609 | 1 | L | 4900040481 | 2024 |  | 5000045904 | 2024 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10441222 | TAPE,FOIL,REINF,TESA 51495,RL/50M |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 90004487_0150/9000596_0150 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 17 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 170 |  |  | 0 | 30 | ROL | 2001 | AA02 | 2024-04-30 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | After Staging Date | 2024-04-22 | After Staging Date | CPT | Blackwoods | 4500006918 | 2024-04-22 | FALSE
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-23 | 2024-09-11 | INLEC | 100041682 | 0010 | 0010 | 100041682 | Damaged Isolator Handles Replace(3)S20D2 | AA53.S20D2 | SWBD,415V MOTOR CONTROL CENTRE | AA01 | 30 | No Issue identified | 10443375 | HANDLE KIT,ISOL;K-LINE 1818064 | 3 | KIT | 1 | 0 | 0 | 0 |  | ETA 01.05.2024 PO 4500008331 ABB /no issues with the timing of delivery Gargs |  | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300000539 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90006872 | 05 | Preparation | 0000140203 | 1 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006872_0010 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2022-05-30 | 0 |  |  | 2024-04-20 | 2024-04-23 | S20D2 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10443375 | HANDLE KIT,ISOL;K-LINE 1818064 |  | 0010 | Complete Replacement Handles | INT | Complete Replacement Handles | 5 |  | 90006872_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006872 |  | 30 |  | 1 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000139572 | S002 | 30 | 30 | 5300000539 | 10 |  |  | 0 | 3 | KIT | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140203 | 0 |  | 3 |  |  | RC00025003 | 2024-09-11 | 2024-04-23 | 2024-04-23 | Released/Settlement rule created/Object created/Date set by external system/Order Approved/Printed/Pre-costed/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-05-01 | After Staging Date | CPT | ABB | 4500008331 | 2024-05-01 | FALSE
| 24SDLN1 | Released | 2024-01-01 | 2024-03-31 | 2024-03-17 | 2024-05-03 | 2024-05-03 | INLEC | 100034626 | 0080 | 0040 | 100034626 | OPSD 1K1410 Turb Heat Det Fault 160TZ511 | AA53.160TZ511A | LOOP,HEAT DETECT 1KT1410 TURBINE COMPART | AA01 | 10 | No issue identified | 10453861 | RESISTOR;WIRE WOUND,2.0K OHM,2.5W,12.7MM | 10 | EA | 0 | 0 | 0 | 0 |  | 13.03 - ETA 05.04.24 PO 4500006501 x 10 Macleans | Supply for Order 100034626, Item 6 cannot be changed 90003651 item 50 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006043 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90003651 | 07 | Execution | 0000133118 | 6 | 0 | [9 empty] | WorkPackLink |  | P19 FLInlecs | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-02-04 | ODST-0090003651_0050 | 0 | 0 | 0 |  | 2024-03-18 | AA53 | 2024-05-03 |  |  | 2024-03-31 |  |  |  |  | 2023-09-24 | 0 |  |  | 2024-03-17 | 2024-03-20 | Buffer Stock |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-03-17 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10453861 | RESISTOR;WIRE WOUND,2.0K OHM,2.5W,12.7MM |  | 0080 | Operation for Buffer Stock - wierd FL | INT | Operation for Buffer Stock - wierd FL |  | Opportune Shutdown | 90003651_0050 | [7 empty] | 0070 | Main Work Started (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90003651 |  | 10 |  | 6 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000132528 | S002 | 30 | 30 | 5300006043 | 50 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-03-17 |  | Opportune Shutdown |  |  | 1070 |  | 2024-02-03 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 133118 | 0 |  | 2 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Ready For Scheduling Canceled/Part printed/Job In Process/Partially confirmed/Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | 2Wks Before Start | 2024-04-05 | 2Wks Before Start | CPT | MACLEANS | 4500006501 | 2024-04-05 | 0
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 100043679 | 0010 | 0040 | 100043679 | Hose Replace Starter Package - GT4007A3 | AA53.GT4007A3 | PKG EQ,GT ELECTRO-HYD START SYS,GT4007 | AA01 | 255 | No Issue identified | 10458031 | GUARD,SPR;SPIRAL GUARD SGX40 | 1 | ROL | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006816 | 40 |  | 48 |  | 0 |  |  |  | 0 | 0 | ROL | [5 empty] | 05 | Preparation | 0000142211 | 4 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006816_00040 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2022-04-16 | 0 |  |  | 2024-04-30 | 2024-05-03 | 100043679 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10458031 | GUARD,SPR;SPIRAL GUARD SGX40 |  | 0010 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 99 |  | 4 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000141621 | S002 | 30 | 30 | 5300006816 | 40 |  |  | 0 | 1 | ROL | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142211 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed/Goods movement posted | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDLN1 | Released | 2024-01-15 | 2024-04-03 | 2024-03-31 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0020 | 0060 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10499155 | ELEMENT,FLT;GRACO 180199 | 20 | EA | 0 | 0 | 0 | 0 |  | 19.03 - ETA 08.04.24 PO 4500007212 x 20 Pumpline. | Supply for Order 100033847, Item 42 cannot be changed 90004627 item 60 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 420 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90004627 | 07 | Execution | 0000132381 | 42 | 0 | [9 empty] | WorkPackLink |  | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-01-15 | ODST-0090004627_0060 | 0 | 0 | 0 |  | 2024-04-01 | AA53 | 2024-05-03 |  |  | 2024-04-03 |  |  |  |  | 2025-10-01 | 0 |  |  | 2024-03-31 | 2024-04-03 | B.Vorn TA |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-03-31 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10499155 | ELEMENT,FLT;GRACO 180199 |  | 0020 | Pre Shut Insulation | INT | Pre Shut Insulation | 5 |  | 90004627_0060 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004627 |  | 99 |  | 42 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 420 |  |  | 0 | 20 | EA | 2001 | AA02 | 2024-03-31 |  |  |  |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | 2Wks Before Start | 2024-04-08 | 2Wks Before Start | CPT | Pump Line | 4500007212 | 2024-04-08 | 20
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | ROTAT | 100040078 | 0010 | 0010 | 100040078 | GT4009 debris in trash screens | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | Shipped qty below requirement qty | 10507164 | COVERALL,PROT;HOODED,DISP,WHT,XXL | 50 | EA | 0 | 0 | 10 | 10 | EA | 04.03 - ETA 22.04.24 PO 4500002382 x 50 Blackwoods | Supply for Order 100040078, Item 1 cannot be changed 90000785 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006189 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004331 | 9000033 | 05 | Preparation | 0000138599 | 1 | 0 | EA | 102000000001210 |  | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL | AU53 P07 | 0 |  | 0 | 0 |  | 0 | 50 | 2024-02-13 |  | Y | 1001 | 2024-02-07 | GRST-5000017936_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2023-01-08 | 10 | 4900030561_2024_0001 |  | 2024-02-12 | 2024-05-03 | TA LAGGERS | 5000017936_2024_0001 | 0 | 2 | 0 | 10 | 0 | 180004331 | 1 | L | 4900030561 | 2024 |  | 5000017936 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10507164 | COVERALL,PROT;HOODED,DISP,WHT,XXL |  | 0010 | Clear Debris From Trash Screens | INT | Clear Debris From Trash Screens | 5 |  | 90000785_0010/9000033_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000785 |  | 20 |  | 1 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000138028 | S002 | 30 | 30 | 5300006189 | 10 |  |  | 0 | 50 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138599 | 0 |  | 1 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-22 | After Staging Date | CPT | Blackwoods | 4500002382 | 2024-04-22 | 50
| 24SDLN1 | Released | 2024-01-15 | 2024-04-03 | 2024-03-31 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0020 | 0050 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10507597 | VALVE,S/OFF;GRACO 246349 | 5 | EA | 0 | 0 | 0 | 0 |  | 19.03 - ETA 08.04.24 PO 4500007212 x 5 Pumpline. | Supply for Order 100033847, Item 41 cannot be changed 90004627 item 50 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 410 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90004627 | 07 | Execution | 0000132381 | 41 | 0 | [9 empty] | WorkPackLink |  | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-01-15 | ODST-0090004627_0050 | 0 | 0 | 0 |  | 2024-04-01 | AA53 | 2024-05-03 |  |  | 2024-04-03 |  |  |  |  | 2025-10-01 | 0 |  |  | 2024-03-31 | 2024-04-03 | B.Vorn TA |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-03-31 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10507597 | VALVE,S/OFF;GRACO 246349 |  | 0020 | Pre Shut Insulation | INT | Pre Shut Insulation | 5 |  | 90004627_0050 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004627 |  | 99 |  | 41 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 410 |  |  | 0 | 5 | EA | 2001 | AA02 | 2024-03-31 |  |  |  |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | 2Wks Before Start | 2024-04-08 | 2Wks Before Start | CPT | Pump Line | 4500007212 | 2024-04-08 | 5
| 24SDLN1 | Released | 2024-01-15 | 2024-05-03 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0020 | 0070 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No Issue identified | 10517811 | DRUM,STORAGE,M,20L,HD SCR TOP,WHT | 10 | EA | 0 | 0 | 0 | 0 |  | 14.03 - ETA 02.04.2024 PO 4500006609 |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 430 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000132381 | 43 | 0 | [9 empty] | WorkPackLink |  | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-01-15 | STST-5300004834_00430 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2025-10-01 | 0 |  |  | 2024-04-30 | 2024-05-03 | B.Vorn TA |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10517811 | DRUM,STORAGE,M,20L,HD SCR TOP,WHT |  | 0020 | Pre Shut Insulation | INT | Pre Shut Insulation | 5 | [9 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 99 |  | 43 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 430 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | 2Wks Before Start | 2024-04-02 | 2Wks Before Start | CPT | Blackwoods | 4500006609 | 2024-04-02 | 10
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100042088 | 0020 | 0040 | 100042088 | MOC-119 EEHA Replace JB 314QT20-1J | AA53.314QT20-1J | JB,HEAT TRACE 314QT20-1 | AA01 | 10 | No Issue identified | 10536673 | BOX,JUNCTION;IP66,KLIPPON XFB648075704A | 1 | EA | 0 | 0 | 0 | 0 |  | 13.02 - Inv PO 4500002679 x 1 ETA 02.04.24 Macleans |  | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300000711 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006330 | 05 | Preparation | 0000140572 | 4 | 0 | [9 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006330_0040 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-09-28 | 0 |  |  | 2024-04-30 | 2024-05-03 | AA53.314QT20 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10536673 | BOX,JUNCTION;IP66,KLIPPON XFB648075704A |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90006330_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006330 |  | 5 |  | 4 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000140003 | S002 | 30 | 30 | 5300000711 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140572 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance |  | 2Wks Before Start | 2024-04-02 | 2Wks Before Start | CPT | MACLEANS | 4500008292 | 2024-04-02 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0220 | 0330 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10539834 | NUT,SWIVEL;GE J1317P10B | 1 | EA | 0 | 0 | 0 | 0 |  | 27.03 - ETA 28.03.24 PO W451765739 x 1 NP, 3 available @ AA53 |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 300 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000117945 | 34 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | STST-5300003490_00300 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-06-30 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10539834 | NUT,SWIVEL;GE J1317P10B |  | 0220 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 5 |  | 34 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 | 30 | 30 | 5300003490 | 300 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | 2Wks Before Start | 2024-04-12 | 2Wks Before Start | FCA | NUOVO PIGNONE | W451765739 | 2024-03-28 | 0
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-12 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0220 | 0340 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10539834 | NUT,SWIVEL;GE J1317P10B | 1 | EA | 0 | 0 | 0 | 0 |  | 27.03 - ETA 23.09.24 PO W451780583 x 2 NP, 3 available @ AA53 |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 310 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000121037 | 35 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | STST-5300003974_00310 | 0 | 0 | 0 |  | 2024-05-13 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-06-30 | 0 |  |  | 2024-05-12 | 2024-05-15 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10539834 | NUT,SWIVEL;GE J1317P10B |  | 0220 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 5 |  | 35 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 | 30 | 30 | 5300003974 | 310 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-12 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | After Turnaround | 2024-10-08 | After Turnaround | FCA | NUOVO PIGNONE | W451780583 | 2024-09-23 | 0
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-12 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0220 | 0330 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10539834 | NUT,SWIVEL;GE J1317P10B | 1 | EA | 0 | 0 | 0 | 0 |  | 27.03 - ETA 23.09.24 PO W451780583 x 2 NP, 3 available @ AA53 |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 300 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000121037 | 34 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | STST-5300003974_00300 | 0 | 0 | 0 |  | 2024-05-13 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-06-30 | 0 |  |  | 2024-05-12 | 2024-05-15 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10539834 | NUT,SWIVEL;GE J1317P10B |  | 0220 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 5 |  | 34 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 | 30 | 30 | 5300003974 | 300 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-12 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | After Turnaround | 2024-10-08 | After Turnaround | FCA | NUOVO PIGNONE | W451780583 | 2024-09-23 | 0
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100037734 | 0020 | 0010 | 100037734 | EEHA Replace JB seals 3KT1440V4L1 | AA53.3KT1440V4L1 | JB,L/O TANK VENT MIST SEPARATOR BLWR JB2 | AA01 | 10 | No Issue identified | 10543991 | BOX,JCT;EX,XFB6639088759KTB453815 | 1 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 22.04.24 PO 4500004023 x 1 Macleans |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006680 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000136258 | 1 | 0 | [9 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-16 | STST-5300006680_00010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-12-31 | 0 |  |  | 2024-04-30 | 2024-05-03 | 3KT1440V4L1 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10543991 | BOX,JCT;EX,XFB6639088759KTB453815 |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 5 |  | 1 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000135649 | S002 | 30 | 30 | 5300006680 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 136258 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-22 | After Staging Date | CPT | MACLEANS | 4500004023 | 2024-04-22 | 0
| 24SDLN1 | Released | 2024-01-01 | 2024-03-31 | 2024-03-17 | 2024-05-03 | 2024-05-03 | INLEC | 100034626 | 0080 | 0010 | 100034626 | OPSD 1K1410 Turb Heat Det Fault 160TZ511 | AA53.160TZ511A | LOOP,HEAT DETECT 1KT1410 TURBINE COMPART | AA01 | 10 | No issue identified | 10547852 | INS,HEAT SHRINK;TUBE,6.4MM,TE TFER14X | 6 | EA | 5 | 0 | 0 | 0 |  | 13.03 - ETA 19.04.24 PO 4500006002 x 6 MM Electricals | Supply for Order 100034626, Item 3 cannot be changed 90003651 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006043 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90003651 | 07 | Execution | 0000133118 | 3 | 0 | [9 empty] | WorkPackLink |  | P19 FLInlecs | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-02-04 | ODST-0090003651_0020 | 0 | 0 | 0 |  | 2024-03-18 | AA53 | 2024-05-03 |  |  | 2024-03-31 |  |  |  |  | 2023-09-24 | 0 |  |  | 2024-03-17 | 2024-03-20 | Buffer Stock |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-03-17 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10547852 | INS,HEAT SHRINK;TUBE,6.4MM,TE TFER14X |  | 0080 | Operation for Buffer Stock - wierd FL | INT | Operation for Buffer Stock - wierd FL |  | Opportune Shutdown | 90003651_0020 | [7 empty] | 0070 | Main Work Started (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90003651 |  | 10 |  | 3 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000132528 | S002 | 30 | 30 | 5300006043 | 20 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-03-17 |  | Opportune Shutdown |  |  | 1070 |  | 2024-02-03 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 133118 | 0 |  | 2 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Ready For Scheduling Canceled/Part printed/Job In Process/Partially confirmed/Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-19 | After Staging Date | CPT | MM ELECTRICALS | 4500006002 | 2024-04-19 | FALSE
| 24SDGT8 | Released | 2024-02-07 | 2024-05-15 | 2024-04-30 | 2024-02-04 | 2024-06-07 | INLEC | 100037026 | 0030 | 0020 | 100037026 | MOC-118435 CO2 Discharge Switch Replacem | AA53.860PZ653 | SW,PRESS DISCH EXT CO2 T/ENCL GT4008 | AA01 | 20 | No Issue identified | 10562513 | SWITCH,PRESS;EX,UEC CO 12SHSN8BM277QC1 | 3 | EA | 0 | 0 | 0 | 0 |  | 16.02 - ETA 26.04.24 PO 4500003031 x qty 3 DG Instruments | Supply for Order 100037026, Item 2 cannot be changed 90000782 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006181 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000782 | 07 | Execution | 0000135527 | 2 | 0 | [9 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-02-07 | ODST-0090000782_0020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2023-12-31 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10562513 | SWITCH,PRESS;EX,UEC CO 12SHSN8BM277QC1 |  | 0030 | Complete Replacement | INT | Complete Replacement |  |  | 90000782_0020 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000782 |  | 20 |  | 2 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000134916 | S002 | 30 | 30 | 5300006181 | 20 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  | 2024-02-04 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 135527 | 0 |  | 3 |  |  | RC00025003 | 2024-06-07 | 2024-02-04 | 2024-02-04 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Printed/Goods movement posted | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | DG INSTRUMENTS | 4500003031 | 2024-04-26 | 0
| 24SDLN1 | Released | 2024-03-05 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-13 | VALVE | 100073710 | 0010 | 0010 | 100073710 | CV-OH 10" 600# 141FCV02 | AA53.141FCV02 | VALVE,H/W FLOW TO 1E4102 CV | AA01 | 255 | No Issue identified | 10564940 | SEAL KIT;CV,AES SEAL 20715 | 2 | EA | 0 | 0 | 0 | 0 |  | 06.03 - ETA 10.04.24 PO 4500005289 x 2 SCORE |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300007483 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000224102 | 1 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-03-05 | STST-5300007483_00010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2026-02-15 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10564940 | SEAL KIT;CV,AES SEAL 20715 |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | [10 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 99 |  | 1 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000221710 | S002 | 30 | 30 | 5300007483 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-02-26 | 224102 | 0 |  | 2 |  |  | RC00025003 | 2024-05-13 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | 2Wks Before Start | 2024-04-10 | 2Wks Before Start | CPT | SCORE | 4500005289 | 2024-04-10 | 0
| 24SD4401 | Released | 2024-02-09 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 100040481 | 0040 | 0010 | 100040481 | SO Filter Repair XOver Vlv - K4401CS1A/B | AA53.K4401CS1A | FILT,SEAL OIL FOR K4401C | AA01 | 30 | No Issue identified | 10565746 | O-RING;HILLIARD 39100012 | 6 | EA | 0 | 0 | 0 | 0 |  | 07.03 - ETA 17.04.24 PO 4500005344 TRINKOR |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006337 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139005 | 1 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-02-09 | STST-5300006337_00010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-11 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10565746 | O-RING;HILLIARD 39100012 |  | 0040 | Clean up Valve Stem | INT | Clean up Valve Stem | [10 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 30 |  | 1 |  | 0 |  | 24SD4401 | MJ | AU1072 | 1000138356 | S002 | 30 | 30 | 5300006337 | 10 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139005 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Settlement rule created/Released/Date set by external system/Object created/Pre-costed/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-17 | After Staging Date | CPT | TRINKOR | 4500005344 | 2024-04-17 | 3
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-04 | ROTAT | 200057503 | 0010 | 0010 | 200057503 | 2Y GT4007 TURB PRE FILTER REPLACE | AA53.GT4007S2 | FILT,AIR INLET GT4007 | AA01 | 20 | No Issue identified | 10565960 | SLEEVE;PRE FLT,DONALDSON P039859 | 200 | EA | 0 | 0 | 0 | 0 |  | 05.04 - ETA 05.04.24 PO W451779667 x 200 DONALDSON |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006134 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000091791 | 3 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 200 |  |  | Y | 1001 | 2024-02-06 | STST-5300006134_00020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-04-22 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10565960 | SLEEVE;PRE FLT,DONALDSON P039859 |  | 0010 | Mobilise Filters and Equipment | INT | Mobilise Filters and Equipment | 0 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 20 |  | 3 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000091225 | S002 | 30 | 30 | 5300006134 | 20 |  |  | 0 | 200 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 91791 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | 2Wks Before Start | 2024-04-05 | 2Wks Before Start | CPT | DONALDSON | W451779667 | 2024-04-05 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-04 | ROTAT | 200065121 | 0020 | 0010 | 200065121 | 2Y GT4010 TURB PRE FILTER REPLACE | AA53.GT4010S2 | FILT,AIR INLET,GT4010 | AA01 | 20 | No Issue identified | 10565960 | SLEEVE;PRE FLT,DONALDSON P039859 | 200 | EA | 0 | 0 | 0 | 0 |  | 01.04 - ETA 05.04.24 PO W451780424 x 200 DONALDSON |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006428 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000099410 | 2 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 200 |  |  | Y | 1001 | 2024-02-12 | STST-5300006428_00010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-07-15 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10565960 | SLEEVE;PRE FLT,DONALDSON P039859 |  | 0020 | Mobilise Filters and Equipment | INT | Mobilise Filters and Equipment | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 20 |  | 2 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000098780 | S002 | 30 | 30 | 5300006428 | 10 |  |  | 0 | 200 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99410 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material shortage | AM02 | Proactive Maintenance |  | 2Wks Before Start | 2024-04-05 | 2Wks Before Start | CPT | DONALDSON | W451780424 | 2024-04-05 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 100033722 | 0030 | 0060 | 100033722 | G4010P1A LO leak from fitting | AA53.G4010P1A | PUMP,G4010 MAIN/AUX AC MINERAL LUBE OIL | AA01 | 20 | No Issue identified | 10573194 | WASHER;JNT,ALLWEILER 17251 | 1 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 29.04.24 PO 4500004029 x 2 Pump Power Australia |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300004662 | 30 |  | 21 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000132194 | 7 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-09 | STST-5300004662_00030 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-04-20 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10573194 | WASHER;JNT,ALLWEILER 17251 |  | 0030 | Contingency Repair Works | INT | Contingency Repair Works | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 20 |  | 7 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000131624 | S002 | 30 | 30 | 5300004662 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132194 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-29 | After Staging Date | CPT | Pump Power | 4500004029 | 2024-04-29 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 100037490 | 0030 | 0090 | 100037490 | G4010P1B LO leak from fitting | AA53.G4010P1B | PUMP,G4010 MAIN/AUX AC MINERAL LUBE OIL | AA01 | 20 | No Issue identified | 10573194 | WASHER;JNT,ALLWEILER 17251 | 1 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 29.04.24 PO 4500004029 x 2 Pump Power Australia |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300001581 | 50 |  | 21 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000136004 | 14 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | STST-5300001581_00050 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2023-11-17 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10573194 | WASHER;JNT,ALLWEILER 17251 |  | 0030 | Contingency Repair Works | INT | Contingency Repair Works | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 20 |  | 14 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000135386 | S002 | 30 | 30 | 5300001581 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 136004 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-29 | After Staging Date | CPT | Pump Power | 4500004029 | 2024-04-29 | 0
| 24SDLN1 | Released | 2024-01-15 | 2024-04-03 | 2024-03-31 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0020 | 0040 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10577117 | CHAMBER;MIX,SPRAY GUN,GRACO AR4242 | 10 | EA | 0 | 0 | 0 | 0 |  | 05.04 - ETA 26.04.24 PO 4500009386 x 10 Pump Line | Supply for Order 100033847, Item 40 cannot be changed 90004627 item 40 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 400 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90004627 | 07 | Execution | 0000132381 | 40 | 0 | [9 empty] | WorkPackLink |  | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-01-15 | ODST-0090004627_0040 | 0 | 0 | 0 |  | 2024-04-01 | AA53 | 2024-05-03 |  |  | 2024-04-03 |  |  |  |  | 2025-10-01 | 0 |  |  | 2024-03-31 | 2024-04-03 | B.Vorn TA |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-03-31 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10577117 | CHAMBER;MIX,SPRAY GUN,GRACO AR4242 |  | 0020 | Pre Shut Insulation | INT | Pre Shut Insulation | 5 |  | 90004627_0040 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004627 |  | 99 |  | 40 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 400 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-03-31 |  |  |  |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | After Staging Date | 2024-04-26 | After Staging Date | CPT | Pump Line | 4500009386 | 2024-04-26 | 0
| 24SDLN1 | Released | 2024-01-15 | 2024-03-04 | 2024-03-01 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0260 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC |  | 255 | No issue identified | 10577778 | BAR,MET;FLAT,160X10MM,4M,6060 T5 AL,MILL | 3 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 18.04.24 PO 4500001713 Infra Build | Supply for Order 100033847, Item 25 cannot be changed 90006895 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006895 | 07 | Execution | 0000132381 | 25 | 0 | [9 empty] | WorkPackLink |  | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-01-15 | ODST-0090006895_0010 | 0 | 0 | 0 |  | 2024-03-02 | AA53 | 2024-03-06 |  |  | 2024-03-04 |  |  |  |  | 2025-10-01 | 0 |  |  | 2024-03-01 | 2024-03-04 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-03-01 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10577778 | BAR,MET;FLAT,160X10MM,4M,6060 T5 AL,MILL |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 90006895_0010 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006895 |  | 99 |  | 25 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 250 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-03-01 |  |  |  |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | After Staging Date | 2024-04-18 | After Staging Date | CPT | INFRA BUILD | 4500001713 | 2024-04-18 | 0
| 24SDLN1 | Released | 2024-03-05 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-13 | VALVE | 100073710 | 0010 | 0040 | 100073710 | CV-OH 10" 600# 141FCV02 | AA53.141FCV02 | VALVE,H/W FLOW TO 1E4102 CV | AA01 | 255 | No Issue identified | 10591716 | STEM,VV;INCON 718,10"CL600 CV,WITH PINS | 2 | EA | 0 | 0 | 0 | 0 |  | 06.03 - ETA 10.04.24 PO 4500005289 x 2 SCORE |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300007483 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000224102 | 4 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-03-05 | STST-5300007483_00040 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2026-02-15 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10591716 | STEM,VV;INCON 718,10"CL600 CV,WITH PINS |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | [10 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 99 |  | 4 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000221710 | S002 | 30 | 30 | 5300007483 | 40 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-02-26 | 224102 | 0 |  | 2 |  |  | RC00025003 | 2024-05-13 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | 2Wks Before Start | 2024-04-10 | 2Wks Before Start | CPT | SCORE | 4500005289 | 2024-04-10 | 0
| 24SDLN1 | Released | 2024-03-05 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-13 | VALVE | 100073710 | 0010 | 0020 | 100073710 | CV-OH 10" 600# 141FCV02 | AA53.141FCV02 | VALVE,H/W FLOW TO 1E4102 CV | AA01 | 255 | No Issue identified | 10591966 | RING,PST;8",C-GR,FISHER 17A3991X012 | 4 | EA | 0 | 0 | 0 | 0 |  | 06.03 - ETA 10.04.24 PO 4500005289 x 4 SCORE |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300007483 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000224102 | 2 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-03-05 | STST-5300007483_00020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2026-02-15 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10591966 | RING,PST;8",C-GR,FISHER 17A3991X012 |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | [10 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 99 |  | 2 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000221710 | S002 | 30 | 30 | 5300007483 | 20 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-02-26 | 224102 | 0 |  | 2 |  |  | RC00025003 | 2024-05-13 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | 2Wks Before Start | 2024-04-10 | 2Wks Before Start | CPT | SCORE | 4500005289 | 2024-04-10 | 0
| 24SDLN1 | Released | 2024-01-15 | 2024-05-03 | 2024-04-22 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0070 | 0020 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No Issue identified | 10599947 | VACUUM,COMPACT;MILWAUKEE M18FCVL0 | 2 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 30.04.24 PO 4500009394 | Supply for Order 100033847, Item 44 cannot be changed 90006913 item 10 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300007337 | 20 | CPT | 7 | 1000006631 | 44 | 30002095 | ALLTOOLS WA PTY LTD | 4500009394 | 10 | 2 | EA | 2024-04-30 |  |  |  | 90006913 | 07 | Execution | 0000132381 | 44 | 0 | [9 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-02-29 | ODST-0090006913_0010 | 0 | 30 | 0 | 2024-05-20 | 2024-04-28 | AA53 | 2024-05-03 |  |  | 2024-06-02 | 2024-05-22 | 2024-05-30 |  |  | 2025-10-01 | 0 |  |  | 2024-04-22 | 2024-04-30 | JB / Brandon |  | 0 | 2 | 2 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10599947 | VACUUM,COMPACT;MILWAUKEE M18FCVL0 |  | 0070 | Insulation | INT | Insulation | 7 |  | 90006913_0010 |  |  |  |  | 05 | Release Completed | X | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 90006913 | 2024-03-22 | 99 | 2024-05-22 | 0 |  | 0 |  | 24SDLN1 | MJ | AU1009 | 1000131783 | S001 | 30 | 30 | 5300004834 | 440 |  | 5300007337 | 20 | 2 | EA | 1001 | AA02 | 2024-04-22 |  |  |  | AU00 | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | After Staging Date | 2024-04-30 | After Staging Date | CPT | ALLTOOLS WA PTY LTD | 4500009394 | 2024-04-30 | 0
| 24SDLN1 | Released | 2024-01-15 | 2024-04-03 | 2024-03-31 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0020 | 0020 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10600397 | HOLESAW,BIMETAL;HSSCO,25MM,BORDO 701025 | 10 | EA | 0 | 0 | 0 | 0 |  | 26.03 - ETA 08.04.24 PO 4500008380 BELLIS AUSTRALIA | Supply for Order 100033847, Item 38 cannot be changed 90004627 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 380 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90004627 | 07 | Execution | 0000132381 | 38 | 0 | [9 empty] | WorkPackLink |  | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-01-15 | ODST-0090004627_0020 | 0 | 0 | 0 |  | 2024-04-01 | AA53 | 2024-05-03 |  |  | 2024-04-03 |  |  |  |  | 2025-10-01 | 0 |  |  | 2024-03-31 | 2024-04-03 | B.Vorn TA |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-03-31 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10600397 | HOLESAW,BIMETAL;HSSCO,25MM,BORDO 701025 |  | 0020 | Pre Shut Insulation | INT | Pre Shut Insulation | 5 |  | 90004627_0020 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004627 |  | 99 |  | 38 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 380 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-03-31 |  |  |  |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | 2Wks Before Start | 2024-04-08 | 2Wks Before Start | CPT | BELLIS AUST | 4500008380 | 2024-04-08 | 0
| 24SDLN1 | Released | 2024-01-15 | 2024-04-03 | 2024-03-31 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0020 | 0030 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10600399 | MANDREL,HOLESAW;0.250",BORDO 70505514 | 2 | EA | 0 | 0 | 0 | 0 |  | 26.03 - ETA 08.04.2024 PO 4500008380 BELLIS AUSTRALIA | Supply for Order 100033847, Item 39 cannot be changed 90004627 item 30 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 390 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90004627 | 07 | Execution | 0000132381 | 39 | 0 | [9 empty] | WorkPackLink |  | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-15 | ODST-0090004627_0030 | 0 | 0 | 0 |  | 2024-04-01 | AA53 | 2024-05-03 |  |  | 2024-04-03 |  |  |  |  | 2025-10-01 | 0 |  |  | 2024-03-31 | 2024-04-03 | B.Vorn TA |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-03-31 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10600399 | MANDREL,HOLESAW;0.250",BORDO 70505514 |  | 0020 | Pre Shut Insulation | INT | Pre Shut Insulation | 5 |  | 90004627_0030 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004627 |  | 99 |  | 39 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 390 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-03-31 |  |  |  |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | 2Wks Before Start | 2024-04-08 | 2Wks Before Start | CPT | BELLIS AUST | 4500008380 | 2024-04-08 | 0
| 24SDLN1 | Released | 2024-01-15 | 2024-03-04 | 2024-03-01 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0130 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC |  | 255 | No issue identified | 10600755 | GAS,COMP;AR,SHIELDING,CYL,069F3VIPR | 5 | EA | 0 | 2 | 5 | 3 | EA | 26.02 - ETA 28.04.24 PO 4500000957 BOC | Supply for Order 100033847, Item 13 cannot be changed 9001339 item 900030 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180013327 | 9001339 | 07 | Execution | 0000132381 | 13 | 0 | EA |  |  | 102000000003610 | [5 empty] | WorkPackLink |  | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-01-15 | GRST-5000044910 | 0 | 0 | 0 |  | 2024-03-02 | AA53 | 2024-03-06 |  |  | 2024-03-04 |  |  | 100000004704 | 1020 | 2025-10-01 | 5 | 4900040880_2024_0001/4900040074_2024_0001 |  | 2024-03-25 | 2024-03-04 |  | 5000046885_2024_0001/5000044910_2024_0001 | 0 | 2 | 0 | 5 | 0 | 180013982/180013982/180013982/180013327/180013327 | 3 | L | 4900040074 | 2024 |  | 5000044910 | 2024 |  |  | 2024-03-01 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10600755 | GAS,COMP;AR,SHIELDING,CYL,069F3VIPR |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 9001339_0090_0030/9001198_0090_0040 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90001524 |  | 99 |  | 13 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 130 |  |  | 0 | 5 | EA | 2001 | AA02 | 2024-03-01 |  |  |  |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | After Staging Date | 2024-04-28 | After Staging Date | CPT | BOC | 4500000957 | 2024-04-28 | 0
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-03-16 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0350 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10601288 | INSULATION,BLKT;DUCTWRAP,CSR 170594871 | 6 | ROL | 0 | 0 | 1 | 0 |  | 19.03 - ETA 29.03.2024 PO 4500006682 PYROTEK | Supply for Order 100033847, Item 35 cannot be changed 90005862 item 60 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 350 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90005862 | 07 | Execution | 0000132381 | 35 | 0 | [9 empty] | WorkPackLink |  | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-01-15 | ODST-0090005862_0060 | 13 | 0 | 0 |  | 2024-03-04 | AA53 | 2024-03-06 |  |  | 2024-03-19 |  |  |  |  | 2025-10-01 | 0 |  |  | 2024-03-16 | 2024-03-19 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-03-16 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10601288 | INSULATION,BLKT;DUCTWRAP,CSR 170594871 |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 90005862_0060 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90005862 |  | 99 |  | 35 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 350 |  |  | 0 | 6 | ROL | 2001 | AA02 | 2024-03-16 |  |  |  |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | 2Wks Before Start | 2024-03-29 | 2Wks Before Start | CPT | PYROTEK | 4500006682 | 2024-03-29 | 1
| 24SDGT10 | Released | 2024-02-16 | 2024-03-02 | 2024-02-28 | 2024-05-03 | 2024-05-04 | ROTAT | 100037746 | 0010 | 0040 | 100037746 | Replace filters on AU01.GT4010A3 | AA53.GT4010A3 | PKG EQ,GT4010A3 HYDRAULIC STARTING SKID | AA01 | 255 | No issue identified | 10613434 | FILTER,HYD STARTER;NP ISM990645306 | 4 | EA | 0 | 0 | 0 | 0 |  | 27.03 - ETA 20.06.24 PO W451781820 x 4 NP | Supply for Order 100037746, Item 3 cannot be changed 90001123 item 30 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006672 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90001123 | 05 | Preparation | 0000136198 | 3 | 0 | [9 empty] | WorkPackLink |  | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-02-16 | ODST-0090001123_0030 | 0 | 0 | 0 |  | 2024-02-29 | AA53 | 2024-05-03 |  |  | 2024-03-02 |  |  |  |  | 2024-05-15 | 0 |  |  | 2024-02-28 | 2024-03-02 | GT4010S7 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10613434 | FILTER,HYD STARTER;NP ISM990645306 |  | 0010 | Isolate Hyd Starter Motor | INT | Isolate Hyd Starter Motor | 5 |  | 90001123_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90001123 |  | 99 |  | 3 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000135628 | S002 | 30 | 30 | 5300006672 | 30 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 136198 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Material shortage/Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved | AM01 | Reactive Maintenance |  | After Turnaround | 2024-07-05 | After Turnaround | FCA | NUOVO PIGNONE | W451781820 | 2024-06-20 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 100033722 | 0030 | 0050 | 100033722 | G4010P1A LO leak from fitting | AA53.G4010P1A | PUMP,G4010 MAIN/AUX AC MINERAL LUBE OIL | AA01 | 20 | No Issue identified | 11400261 | COUPLING,HD;ALLWEILER 34820 | 1 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 29.04.24 PO 4500004029 x 2 Pump Power Australia |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300004662 | 20 |  | 63 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000132194 | 6 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-09 | STST-5300004662_00020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-04-20 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400261 | COUPLING,HD;ALLWEILER 34820 |  | 0030 | Contingency Repair Works | INT | Contingency Repair Works | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 20 |  | 6 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000131624 | S002 | 30 | 30 | 5300004662 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132194 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-29 | After Staging Date | CPT | Pump Power | 4500004029 | 2024-04-29 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 100037490 | 0030 | 0060 | 100037490 | G4010P1B LO leak from fitting | AA53.G4010P1B | PUMP,G4010 MAIN/AUX AC MINERAL LUBE OIL | AA01 | 20 | No Issue identified | 11400261 | COUPLING,HD;ALLWEILER 34820 | 1 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 29.04.24 PO 4500004029 x 2 Pump Power Australia |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300001581 | 20 |  | 63 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000136004 | 11 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | STST-5300001581_00020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2023-11-17 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400261 | COUPLING,HD;ALLWEILER 34820 |  | 0030 | Contingency Repair Works | INT | Contingency Repair Works | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 20 |  | 11 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000135386 | S002 | 30 | 30 | 5300001581 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 136004 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-29 | After Staging Date | CPT | Pump Power | 4500004029 | 2024-04-29 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 100033722 | 0030 | 0070 | 100033722 | G4010P1A LO leak from fitting | AA53.G4010P1A | PUMP,G4010 MAIN/AUX AC MINERAL LUBE OIL | AA01 | 20 | No Issue identified | 11400262 | UNION,PIPE;ST,ALLWEILER 59220 | 1 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 29.04.24 PO 4500004029 x 2 Pump Power Australia |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300004662 | 40 |  | 63 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000132194 | 8 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-09 | STST-5300004662_00040 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-04-20 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400262 | UNION,PIPE;ST,ALLWEILER 59220 |  | 0030 | Contingency Repair Works | INT | Contingency Repair Works | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 20 |  | 8 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000131624 | S002 | 30 | 30 | 5300004662 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132194 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-29 | After Staging Date | CPT | Pump Power | 4500004029 | 2024-04-29 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 100037490 | 0030 | 0070 | 100037490 | G4010P1B LO leak from fitting | AA53.G4010P1B | PUMP,G4010 MAIN/AUX AC MINERAL LUBE OIL | AA01 | 20 | No Issue identified | 11400262 | UNION,PIPE;ST,ALLWEILER 59220 | 1 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 29.04.24 PO 4500004029 x 2 Pump Power Australia |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300001581 | 30 |  | 63 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000136004 | 12 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | STST-5300001581_00030 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2023-11-17 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400262 | UNION,PIPE;ST,ALLWEILER 59220 |  | 0030 | Contingency Repair Works | INT | Contingency Repair Works | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 20 |  | 12 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000135386 | S002 | 30 | 30 | 5300001581 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 136004 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-29 | After Staging Date | CPT | Pump Power | 4500004029 | 2024-04-29 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 100033722 | 0030 | 0080 | 100033722 | G4010P1A LO leak from fitting | AA53.G4010P1A | PUMP,G4010 MAIN/AUX AC MINERAL LUBE OIL | AA01 | 20 | No Issue identified | 11400263 | PIPE;18X1MM,ST37,BLK,ALLWEILER 13327 | 1 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 29.04.24 PO 4500004029 x 2 Pump Power Australia |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300004662 | 50 |  | 63 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000132194 | 9 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-09 | STST-5300004662_00050 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-04-20 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400263 | PIPE;18X1MM,ST37,BLK,ALLWEILER 13327 |  | 0030 | Contingency Repair Works | INT | Contingency Repair Works | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 20 |  | 9 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000131624 | S002 | 30 | 30 | 5300004662 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132194 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-29 | After Staging Date | CPT | Pump Power | 4500004029 | 2024-04-29 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 100037490 | 0030 | 0080 | 100037490 | G4010P1B LO leak from fitting | AA53.G4010P1B | PUMP,G4010 MAIN/AUX AC MINERAL LUBE OIL | AA01 | 20 | No Issue identified | 11400263 | PIPE;18X1MM,ST37,BLK,ALLWEILER 13327 | 1 | EA | 0 | 0 | 0 | 0 |  | 26.02 - ETA 29.04.24 PO 4500004029 x 2 Pump Power Australia |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300001581 | 40 |  | 63 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000136004 | 13 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | STST-5300001581_00040 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2023-11-17 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400263 | PIPE;18X1MM,ST37,BLK,ALLWEILER 13327 |  | 0030 | Contingency Repair Works | INT | Contingency Repair Works | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 20 |  | 13 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000135386 | S002 | 30 | 30 | 5300001581 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 136004 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-29 | After Staging Date | CPT | Pump Power | 4500004029 | 2024-04-29 | 0
| 24SDGT10 | Released | 2024-02-21 | 2024-05-03 | 2024-04-22 | 2024-05-03 | 2024-05-04 | INLEC | 100039092 | 0020 | 0010 | 100039092 | Replace Door Latching Mech - G4010CP1 | AA53.G4010CP1 | PANEL,TURBINE CONTROL GT4010 | AA01 | 20 | No Issue identified | 11400383 | LATCH,DOOR;NP IRQ502078702 | 1 | EA | 0 | 0 | 0 | 0 |  | 27.03 - ETA 04.06.24 PO 4500003602 x 1 NP | Supply for Order 100039092, Item 1 cannot be changed 90005621 item 30 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300006928 | 10 | FCA | 14 | 1000003136 | 1 | 30001942 | NUOVO PIGNONE INTERNATIONAL SRL | 4500003602 | 50 | 1 | EA | 2024-06-05 |  |  |  | 90005621 | 05 | Preparation | 0000137624 | 1 | 0 | [9 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-21 | ODST-0090005621_0030 | 0 | 0 | 0 | 2024-04-18 | 2024-04-28 | AA53 | 2024-05-03 |  |  | 2024-05-03 | 2024-04-20 | 2024-04-30 |  |  | 2023-04-22 | 0 |  |  | 2024-04-22 | 2024-04-30 | G4010CP1 |  | 0 | 2 | 2 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400383 | LATCH,DOOR;NP IRQ502078702 |  | 0020 | Punchlist & Closeout WP100039092IET001 | ENON | Punchlist & Closeout WP100039092IET001 | 5 |  | 90005621_0030 |  |  |  |  | 05 | Release Completed | X | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 90005621 | 2024-02-23 | 20 | 2024-04-20 | 0 |  | 59789 |  | 24SDGT10 | MJ | AU1009 | 1000137014 | S001 | 30 | 30 | 5300006927 | 10 |  | 5300006928 | 10 | 1 | EA | 1001 | AA02 | 2024-04-22 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | After Turnaround | 2024-06-19 | After Turnaround | FCA | NUOVO PIGNONE | 4500003602 | 2024-06-04 | 0
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 100043679 | 0010 | 0030 | 100043679 | Hose Replace Starter Package - GT4007A3 | AA53.GT4007A3 | PKG EQ,GT ELECTRO-HYD START SYS,GT4007 | AA01 | 255 | No Issue identified | 11400526 | HOSE,HYD;25X2320MM,2SN,1",SS316 | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006816 | 30 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142211 | 3 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006816_00030 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2022-04-16 | 0 |  |  | 2024-04-30 | 2024-05-03 | 100043679 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400526 | HOSE,HYD;25X2320MM,2SN,1",SS316 |  | 0010 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 99 |  | 3 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000141621 | S002 | 30 | 30 | 5300006816 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142211 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed/Goods movement posted | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-12 | 2024-05-15 | 2024-05-15 | ROTAT | 200083886 | 0312 | 0020 | 200083886 | 1Y GT4008 TURB OFF-ENGINE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | No Issue identified | 11400530 | HOSE,HYD;31X2800MM,R15,1.5",SS316 | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300004051 | 50 |  | 98 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000121836 | 5 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | STST-5300004051_00050 | 0 | 0 | 0 |  | 2024-05-13 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-05-16 | 0 |  |  | 2024-05-12 | 2024-05-15 | 200083886 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400530 | HOSE,HYD;31X2800MM,R15,1.5",SS316 |  | 0312 | REMOVE & REPLACE STARTER SKID HYD HOSES | ENON | REMOVE & REPLACE STARTER SKID HYD HOSES | [10 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 20 |  | 5 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000121239 | S002 | 30 | 30 | 5300004051 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-12 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121836 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT8 | Released | 2024-02-21 | 2024-05-15 | 2024-04-22 | 2024-05-15 | 2024-05-15 | INLEC | 100043183 | 0020 | 0010 | 100043183 | MOC-119177 Replace G4008 Space Heaters | AA53.G4008E2 | HTR,ELEC GENERATOR SPACE G4008 | AA01 | 20 | No Issue identified | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ | 12 | EA | 0 | 0 | 0 | 0 |  | 05.03 - ETA 18.04.24 PO 4500004945 x 12 Bartec | Supply for Order 100043183, Item 1 cannot be changed 90005621 item 20 already exists | Vendor PO raised | SP97 | Direct Multi-base | 48 | AA01 | 5300006925 | 10 | CPT | 14 | 1000003119 | 1 | 30002959 | BARTEC AUSTRALIA PTY LTD | 4500004945 | 10 | 12 | EA | 2024-04-18 |  |  |  | 90005621 | 05 | Preparation | 0000141707 | 1 | 0 | [9 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-02-21 | ODST-0090005621_0020 | 0 | 0 | 0 | 2024-04-18 | 2024-04-28 | AA53 | 2024-05-15 |  |  | 2024-05-03 | 2024-04-20 | 2024-04-30 |  |  | 2022-06-15 | 0 |  |  | 2024-04-22 | 2024-04-30 | G4008E2 |  | 0 | 2 | 2 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400538 | RADIATOR;EX,HSF,BARTEC 272B537204150Z50+ |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90005621_0020 |  |  |  |  | 05 | Release Completed | X | 0055 | In Preparation (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 90005621 | 2024-02-23 | 20 | 2024-04-20 | 0 |  | 0 |  | 24SDGT8 | MJ | AU1009 | 1000141038 | S001 | 30 | 30 | 5300006924 | 10 |  | 5300006925 | 10 | 12 | EA | 1001 | AA02 | 2024-04-22 |  |  |  | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Settlement rule created/Released/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-18 | After Staging Date | CPT | BARTEC | 4500004945 | 2024-04-18 | 0
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 100043679 | 0010 | 0010 | 100043679 | Hose Replace Starter Package - GT4007A3 | AA53.GT4007A3 | PKG EQ,GT ELECTRO-HYD START SYS,GT4007 | AA01 | 255 | No Issue identified | 11400557 | HOSE,HYD;38X2760MM,2SN,1.5",SS316 | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006816 | 10 |  | 98 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142211 | 1 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006816_00010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2022-04-16 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400557 | HOSE,HYD;38X2760MM,2SN,1.5",SS316 |  | 0010 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 99 |  | 1 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000141621 | S002 | 30 | 30 | 5300006816 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142211 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed/Goods movement posted | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 100043679 | 0010 | 0020 | 100043679 | Hose Replace Starter Package - GT4007A3 | AA53.GT4007A3 | PKG EQ,GT ELECTRO-HYD START SYS,GT4007 | AA01 | 255 | No Issue identified | 11400560 | HOSE,HYD;31X2840MM,R15,1.5",SS316 | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006816 | 20 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142211 | 2 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006816_00020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2022-04-16 | 0 |  |  | 2024-04-30 | 2024-05-03 | 100043679 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400560 | HOSE,HYD;31X2840MM,R15,1.5",SS316 |  | 0010 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 99 |  | 2 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000141621 | S002 | 30 | 30 | 5300006816 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142211 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed/Goods movement posted | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-12 | 2024-05-15 | 2024-05-15 | ROTAT | 200083886 | 0312 | 0030 | 200083886 | 1Y GT4008 TURB OFF-ENGINE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | No Issue identified | 11400583 | HOSE,HYD;25X2350MM,2SN,1",SS316 | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300004051 | 60 |  | 98 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000121836 | 6 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | STST-5300004051_00060 | 0 | 0 | 0 |  | 2024-05-13 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-05-16 | 0 |  |  | 2024-05-12 | 2024-05-15 | 200083886 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400583 | HOSE,HYD;25X2350MM,2SN,1",SS316 |  | 0312 | REMOVE & REPLACE STARTER SKID HYD HOSES | ENON | REMOVE & REPLACE STARTER SKID HYD HOSES | [10 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 20 |  | 6 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000121239 | S002 | 30 | 30 | 5300004051 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-12 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121836 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-12 | 2024-05-15 | 2024-05-15 | ROTAT | 200083886 | 0312 | 0010 | 200083886 | 1Y GT4008 TURB OFF-ENGINE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | No Issue identified | 11400631 | HOSE,HYD;38X2800MM,2SN,1.5",SS316 | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 08.05.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300004051 | 40 |  | 98 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000121836 | 4 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | STST-5300004051_00040 | 0 | 0 | 0 |  | 2024-05-13 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-05-16 | 0 |  |  | 2024-05-12 | 2024-05-15 | 200083886 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400631 | HOSE,HYD;38X2800MM,2SN,1.5",SS316 |  | 0312 | REMOVE & REPLACE STARTER SKID HYD HOSES | ENON | REMOVE & REPLACE STARTER SKID HYD HOSES | [10 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 20 |  | 4 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000121239 | S002 | 30 | 30 | 5300004051 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-12 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121836 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | 2Wks After Start | 2024-05-08 | 2Wks After Start | CPT | HDS Hoses | 4500003656 | 2024-05-08 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-05 | ROTAT | 100043858 | 0040 | 0010 | 100043858 | GT4010A3 Starter Package Hose Replacemen | AA53.GT4010A3 | PKG EQ,GT4010A3 HYDRAULIC STARTING SKID | AA01 | 30 | No Issue identified | 11400704 | HOSE,HYD;31X1250MM,ISO/28,1.25",PLTD ST | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006818 | 10 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142379 | 8 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006818_00010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2020-12-31 | 0 |  |  | 2024-04-30 | 2024-05-03 | 100043858 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400704 | HOSE,HYD;31X1250MM,ISO/28,1.25",PLTD ST |  | 0040 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | [10 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 30 |  | 8 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000141788 | S002 | 30 | 30 | 5300006818 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142379 | 0 |  | 2 |  |  | RC00025003 | 2024-05-05 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-16 | 2024-05-19 | 2024-05-19 | ROTAT | 100046727 | 0150 | 0010 | 100046727 | GT4009A3 Hyd Starter Package Hoses | AA53.GT4009A3 | PKG EQ,GT4009A3 HYDRAULIC STARTING SKID | AA01 | 10 | No Issue identified | 11400704 | HOSE,HYD;31X1250MM,ISO/28,1.25",PLTD ST | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006817 | 10 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000145248 | 19 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006817_00010 | 0 | 0 | 0 |  | 2024-05-17 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2018-05-25 | 0 |  |  | 2024-05-16 | 2024-05-19 | 100046727 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400704 | HOSE,HYD;31X1250MM,ISO/28,1.25",PLTD ST |  | 0150 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | 5 | Order Requires Replanning | [8 empty] | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 10 |  | 19 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000144617 | S002 | 30 | 30 | 5300006817 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-16 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 145248 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-05 | ROTAT | 100043858 | 0040 | 0020 | 100043858 | GT4010A3 Starter Package Hose Replacemen | AA53.GT4010A3 | PKG EQ,GT4010A3 HYDRAULIC STARTING SKID | AA01 | 30 | No Issue identified | 11400705 | HOSE,HYD;31X1900MM,R15,1.25",PLTD ST | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006818 | 20 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142379 | 9 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006818_00020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2020-12-31 | 0 |  |  | 2024-04-30 | 2024-05-03 | 100043858 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400705 | HOSE,HYD;31X1900MM,R15,1.25",PLTD ST |  | 0040 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | [10 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 30 |  | 9 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000141788 | S002 | 30 | 30 | 5300006818 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142379 | 0 |  | 2 |  |  | RC00025003 | 2024-05-05 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-16 | 2024-05-19 | 2024-05-19 | ROTAT | 100046727 | 0150 | 0020 | 100046727 | GT4009A3 Hyd Starter Package Hoses | AA53.GT4009A3 | PKG EQ,GT4009A3 HYDRAULIC STARTING SKID | AA01 | 10 | No Issue identified | 11400705 | HOSE,HYD;31X1900MM,R15,1.25",PLTD ST | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006817 | 20 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000145248 | 20 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006817_00020 | 0 | 0 | 0 |  | 2024-05-17 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2018-05-25 | 0 |  |  | 2024-05-16 | 2024-05-19 | 100046727 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400705 | HOSE,HYD;31X1900MM,R15,1.25",PLTD ST |  | 0150 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | 5 | Order Requires Replanning | [8 empty] | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 10 |  | 20 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000144617 | S002 | 30 | 30 | 5300006817 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-16 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 145248 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-05 | ROTAT | 100043858 | 0040 | 0030 | 100043858 | GT4010A3 Starter Package Hose Replacemen | AA53.GT4010A3 | PKG EQ,GT4010A3 HYDRAULIC STARTING SKID | AA01 | 30 | No Issue identified | 11400706 | HOSE,HYD;25X750MM,2SN,1",PLTD ST | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006818 | 30 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142379 | 10 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006818_00030 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2020-12-31 | 0 |  |  | 2024-04-30 | 2024-05-03 | 100043858 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400706 | HOSE,HYD;25X750MM,2SN,1",PLTD ST |  | 0040 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | [10 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 30 |  | 10 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000141788 | S002 | 30 | 30 | 5300006818 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142379 | 0 |  | 2 |  |  | RC00025003 | 2024-05-05 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-16 | 2024-05-19 | 2024-05-19 | ROTAT | 100046727 | 0150 | 0030 | 100046727 | GT4009A3 Hyd Starter Package Hoses | AA53.GT4009A3 | PKG EQ,GT4009A3 HYDRAULIC STARTING SKID | AA01 | 10 | No Issue identified | 11400706 | HOSE,HYD;25X750MM,2SN,1",PLTD ST | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006817 | 30 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000145248 | 21 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006817_00030 | 0 | 0 | 0 |  | 2024-05-17 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2018-05-25 | 0 |  |  | 2024-05-16 | 2024-05-19 | 100046727 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400706 | HOSE,HYD;25X750MM,2SN,1",PLTD ST |  | 0150 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | 5 | Order Requires Replanning | [8 empty] | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 10 |  | 21 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000144617 | S002 | 30 | 30 | 5300006817 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-16 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 145248 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-05 | ROTAT | 100043858 | 0040 | 0040 | 100043858 | GT4010A3 Starter Package Hose Replacemen | AA53.GT4010A3 | PKG EQ,GT4010A3 HYDRAULIC STARTING SKID | AA01 | 30 | No Issue identified | 11400707 | HOSE,HYD;25X1380MM,2SN,1",PLTD ST | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006818 | 40 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142379 | 11 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006818_00040 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2020-12-31 | 0 |  |  | 2024-04-30 | 2024-05-03 | 100043858 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400707 | HOSE,HYD;25X1380MM,2SN,1",PLTD ST |  | 0040 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | [10 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 30 |  | 11 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000141788 | S002 | 30 | 30 | 5300006818 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142379 | 0 |  | 2 |  |  | RC00025003 | 2024-05-05 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-16 | 2024-05-19 | 2024-05-19 | ROTAT | 100046727 | 0150 | 0040 | 100046727 | GT4009A3 Hyd Starter Package Hoses | AA53.GT4009A3 | PKG EQ,GT4009A3 HYDRAULIC STARTING SKID | AA01 | 10 | No Issue identified | 11400707 | HOSE,HYD;25X1380MM,2SN,1",PLTD ST | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006817 | 40 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000145248 | 22 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006817_00040 | 0 | 0 | 0 |  | 2024-05-17 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2018-05-25 | 0 |  |  | 2024-05-16 | 2024-05-19 | 100046727 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400707 | HOSE,HYD;25X1380MM,2SN,1",PLTD ST |  | 0150 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | 5 | Order Requires Replanning | [8 empty] | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 10 |  | 22 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000144617 | S002 | 30 | 30 | 5300006817 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-16 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 145248 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-05 | ROTAT | 100043858 | 0040 | 0050 | 100043858 | GT4010A3 Starter Package Hose Replacemen | AA53.GT4010A3 | PKG EQ,GT4010A3 HYDRAULIC STARTING SKID | AA01 | 30 | No Issue identified | 11400708 | HOSE,HYD;25X1300MM,2SN,1",PLTD ST | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006818 | 50 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142379 | 12 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006818_00050 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2020-12-31 | 0 |  |  | 2024-04-30 | 2024-05-03 | 100043858 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400708 | HOSE,HYD;25X1300MM,2SN,1",PLTD ST |  | 0040 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | [10 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 30 |  | 12 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000141788 | S002 | 30 | 30 | 5300006818 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142379 | 0 |  | 2 |  |  | RC00025003 | 2024-05-05 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-16 | 2024-05-19 | 2024-05-19 | ROTAT | 100046727 | 0150 | 0050 | 100046727 | GT4009A3 Hyd Starter Package Hoses | AA53.GT4009A3 | PKG EQ,GT4009A3 HYDRAULIC STARTING SKID | AA01 | 10 | No Issue identified | 11400708 | HOSE,HYD;25X1300MM,2SN,1",PLTD ST | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006817 | 50 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000145248 | 23 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006817_00050 | 0 | 0 | 0 |  | 2024-05-17 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2018-05-25 | 0 |  |  | 2024-05-16 | 2024-05-19 | 100046727 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400708 | HOSE,HYD;25X1300MM,2SN,1",PLTD ST |  | 0150 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | 5 | Order Requires Replanning | [8 empty] | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 10 |  | 23 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000144617 | S002 | 30 | 30 | 5300006817 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-16 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 145248 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-05 | ROTAT | 100043858 | 0040 | 0060 | 100043858 | GT4010A3 Starter Package Hose Replacemen | AA53.GT4010A3 | PKG EQ,GT4010A3 HYDRAULIC STARTING SKID | AA01 | 30 | No Issue identified | 11400709 | HOSE,HYD;25X1700MM,2SN,1",PLTD ST | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006818 | 60 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142379 | 13 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006818_00060 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2020-12-31 | 0 |  |  | 2024-04-30 | 2024-05-03 | 100043858 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400709 | HOSE,HYD;25X1700MM,2SN,1",PLTD ST |  | 0040 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | [10 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 30 |  | 13 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000141788 | S002 | 30 | 30 | 5300006818 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142379 | 0 |  | 2 |  |  | RC00025003 | 2024-05-05 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-16 | 2024-05-19 | 2024-05-19 | ROTAT | 100046727 | 0150 | 0060 | 100046727 | GT4009A3 Hyd Starter Package Hoses | AA53.GT4009A3 | PKG EQ,GT4009A3 HYDRAULIC STARTING SKID | AA01 | 10 | No Issue identified | 11400709 | HOSE,HYD;25X1700MM,2SN,1",PLTD ST | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006817 | 60 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000145248 | 24 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006817_00060 | 0 | 0 | 0 |  | 2024-05-17 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2018-05-25 | 0 |  |  | 2024-05-16 | 2024-05-19 | 100046727 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400709 | HOSE,HYD;25X1700MM,2SN,1",PLTD ST |  | 0150 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | 5 | Order Requires Replanning | [8 empty] | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 10 |  | 24 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000144617 | S002 | 30 | 30 | 5300006817 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-16 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 145248 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-05 | ROTAT | 100043858 | 0040 | 0070 | 100043858 | GT4010A3 Starter Package Hose Replacemen | AA53.GT4010A3 | PKG EQ,GT4010A3 HYDRAULIC STARTING SKID | AA01 | 30 | No Issue identified | 11400710 | HOSE,HYD;25X1400MM,2SN,1",PLTD ST | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006818 | 70 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142379 | 14 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006818_00070 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2020-12-31 | 0 |  |  | 2024-04-30 | 2024-05-03 | 100043858 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400710 | HOSE,HYD;25X1400MM,2SN,1",PLTD ST |  | 0040 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | [10 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 30 |  | 14 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000141788 | S002 | 30 | 30 | 5300006818 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142379 | 0 |  | 2 |  |  | RC00025003 | 2024-05-05 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-16 | 2024-05-19 | 2024-05-19 | ROTAT | 100046727 | 0150 | 0070 | 100046727 | GT4009A3 Hyd Starter Package Hoses | AA53.GT4009A3 | PKG EQ,GT4009A3 HYDRAULIC STARTING SKID | AA01 | 10 | No Issue identified | 11400710 | HOSE,HYD;25X1400MM,2SN,1",PLTD ST | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006817 | 70 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000145248 | 25 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006817_00070 | 0 | 0 | 0 |  | 2024-05-17 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2018-05-25 | 0 |  |  | 2024-05-16 | 2024-05-19 | 100046727 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400710 | HOSE,HYD;25X1400MM,2SN,1",PLTD ST |  | 0150 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | 5 | Order Requires Replanning | [8 empty] | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 10 |  | 25 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000144617 | S002 | 30 | 30 | 5300006817 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-16 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 145248 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-05 | ROTAT | 100043858 | 0040 | 0080 | 100043858 | GT4010A3 Starter Package Hose Replacemen | AA53.GT4010A3 | PKG EQ,GT4010A3 HYDRAULIC STARTING SKID | AA01 | 30 | No Issue identified | 11400722 | HOSE,HYD;19X270MM,2SN,21500KPAG,0.25" | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006818 | 80 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142379 | 15 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006818_00080 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2020-12-31 | 0 |  |  | 2024-04-30 | 2024-05-03 | 100043858 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400722 | HOSE,HYD;19X270MM,2SN,21500KPAG,0.25" |  | 0040 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | [10 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 30 |  | 15 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000141788 | S002 | 30 | 30 | 5300006818 | 80 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142379 | 0 |  | 2 |  |  | RC00025003 | 2024-05-05 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-16 | 2024-05-19 | 2024-05-19 | ROTAT | 100046727 | 0150 | 0080 | 100046727 | GT4009A3 Hyd Starter Package Hoses | AA53.GT4009A3 | PKG EQ,GT4009A3 HYDRAULIC STARTING SKID | AA01 | 10 | No Issue identified | 11400722 | HOSE,HYD;19X270MM,2SN,21500KPAG,0.25" | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006817 | 80 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000145248 | 26 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006817_00080 | 0 | 0 | 0 |  | 2024-05-17 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2018-05-25 | 0 |  |  | 2024-05-16 | 2024-05-19 | 100046727 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400722 | HOSE,HYD;19X270MM,2SN,21500KPAG,0.25" |  | 0150 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | 5 | Order Requires Replanning | [8 empty] | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 10 |  | 26 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000144617 | S002 | 30 | 30 | 5300006817 | 80 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-16 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 145248 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-05 | ROTAT | 100043858 | 0040 | 0090 | 100043858 | GT4010A3 Starter Package Hose Replacemen | AA53.GT4010A3 | PKG EQ,GT4010A3 HYDRAULIC STARTING SKID | AA01 | 30 | No Issue identified | 11400723 | HOSE,HYD;19X750MM,2SN,0.75",PLTD ST | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006818 | 90 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142379 | 16 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006818_00090 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2020-12-31 | 0 |  |  | 2024-04-30 | 2024-05-03 | 100043858 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400723 | HOSE,HYD;19X750MM,2SN,0.75",PLTD ST |  | 0040 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | [10 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 30 |  | 16 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000141788 | S002 | 30 | 30 | 5300006818 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142379 | 0 |  | 2 |  |  | RC00025003 | 2024-05-05 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-16 | 2024-05-19 | 2024-05-19 | ROTAT | 100046727 | 0150 | 0090 | 100046727 | GT4009A3 Hyd Starter Package Hoses | AA53.GT4009A3 | PKG EQ,GT4009A3 HYDRAULIC STARTING SKID | AA01 | 10 | No Issue identified | 11400723 | HOSE,HYD;19X750MM,2SN,0.75",PLTD ST | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006817 | 90 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000145248 | 27 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006817_00090 | 0 | 0 | 0 |  | 2024-05-17 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2018-05-25 | 0 |  |  | 2024-05-16 | 2024-05-19 | 100046727 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400723 | HOSE,HYD;19X750MM,2SN,0.75",PLTD ST |  | 0150 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | 5 | Order Requires Replanning | [8 empty] | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 10 |  | 27 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000144617 | S002 | 30 | 30 | 5300006817 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-16 |  | Order Requires Replanning |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 145248 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-05 | ROTAT | 100043858 | 0040 | 0100 | 100043858 | GT4010A3 Starter Package Hose Replacemen | AA53.GT4010A3 | PKG EQ,GT4010A3 HYDRAULIC STARTING SKID | AA01 | 30 | No Issue identified | 11400724 | FLANGE,SPLIT;CLP,ST,MANULI O8330820 | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - ETA 26.04.24 PO 4500003656 HDS Hoses |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006818 | 100 |  | 48 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142379 | 17 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-19 | STST-5300006818_00100 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2020-12-31 | 0 |  |  | 2024-04-30 | 2024-05-03 | 100043858 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400724 | FLANGE,SPLIT;CLP,ST,MANULI O8330820 |  | 0040 | Replace All Starter Package Skid Hoses | INT | Replace All Starter Package Skid Hoses | [10 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 30 |  | 17 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000141788 | S002 | 30 | 30 | 5300006818 | 100 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142379 | 0 |  | 2 |  |  | RC00025003 | 2024-05-05 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material shortage | AM01 | Reactive Maintenance |  | After Staging Date | 2024-04-26 | After Staging Date | CPT | HDS Hoses | 4500003656 | 2024-04-26 | 0
| 24SDFR2 | Released | 2024-01-02 | 2024-04-22 | 2024-04-19 | 2024-04-16 | 2024-04-23 | MECH | 600001793 | 0130 |  | 600001793 | MOC-89056 Fab/Weld Install 218UCV112 | AA53.2E1801 | EXCH,HEAT DE-ETH REBOIL FRACT2 | AA01 | 10 | No Issue identified | 30003261 | VALVE,GLOBE;6",CL300,FLOWSV,MARK100,CV5+ | 1 | EA | 0 | 0 | 0 | 0 |  | 28.03 - ETA 01.05.24 PO W451769116 x 2 SCORE ETA 1/05/24 or slightly Before | Supply for Order 600001793, Item 11 cannot be changed 90006857 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004605 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006857 | 06 | Scheduling | 0000084711 | 11 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006857_0010 | 0 | 0 | 0 |  | 2024-04-20 | AA53 | 2024-04-22 |  |  | 2024-04-22 |  |  |  |  | 2024-12-15 | 0 |  |  | 2024-04-19 | 2024-04-22 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-19 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 30003261 | VALVE,GLOBE;6",CL300,FLOWSV,MARK100,CV5+ |  | 0130 | Install 218UCV112 | INT | Install 218UCV112 | 5 |  | 90006857_0010 | [7 empty] | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 | 90006857 |  | 5 |  | 11 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000084095 | S002 | 30 | 30 | 5300004605 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-19 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84711 | 0 |  | 2 |  |  | RC00018003 | 2024-04-23 | 2024-04-16 | 2024-04-16 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Material shortage/Printed | AM06 | Capital |  | After Staging Date | 2024-05-01 | After Staging Date | CPT | SCORE | W451769116 | 2024-05-01 | 0
| 24SDGT8 | Released | 2024-02-12 | 2024-05-15 | 2024-04-29 | 2024-05-15 | 2024-05-15 | ROTAT | 200079115 | 0080 | 0030 | 200079115 | 12Y P01 INT INSP PRESS VESSEL GT4008S5A | AA53.GT4008S5A | FILT,GT FUEL GAS GT4008 FILTERS | AA01 | 10 | No Issue identified | 10008156 | FILTER,CART;GF,5.5X36",NP ISM4113520 | 1 | EA | 2 | 0 | 2 | 0 |  | 01.04 - 2 SOH @ AA02 | Supply for Order 200079115, Item 3 cannot be changed 90006340 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006472 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006340 | 05 | Preparation | 0000113450 | 3 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-12 | ODST-0090006340_0010 | 0 | 0 | 0 |  | 2024-04-30 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-06-30 | 0 |  |  | 2024-04-29 | 2024-05-02 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008156 | FILTER,CART;GF,5.5X36",NP ISM4113520 |  | 0080 | Install Filters, Top Lid / N-11 | INT | Install Filters, Top Lid / N-11 |  |  | 90006340_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006340 |  | 5 |  | 3 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000112814 | S002 | 30 | 30 | 5300006472 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-29 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 113450 | 0 |  | 2 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Released | AM02 | Proactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001134504542710008156200079115
| 24SDGT8 | Released | 2024-02-12 | 2024-05-15 | 2024-04-29 | 2024-05-15 | 2024-05-15 | ROTAT | 200079118 | 0080 | 0030 | 200079118 | 12Y P01 INT INSP PRESS VESSEL GT4008S5B | AA53.GT4008S5B | FILT,GT FUEL GAS GT4008 FILTERS | AA01 | 10 | No Issue identified | 10008156 | FILTER,CART;GF,5.5X36",NP ISM4113520 | 1 | EA | 2 | 0 | 2 | 0 |  | 01.04 - 2 SOH @ AA02 | Supply for Order 200079118, Item 3 cannot be changed 90006341 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006473 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006341 | 05 | Preparation | 0000113453 | 3 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-12 | ODST-0090006341_0010 | 0 | 0 | 0 |  | 2024-04-30 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-06-30 | 0 |  |  | 2024-04-29 | 2024-05-02 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008156 | FILTER,CART;GF,5.5X36",NP ISM4113520 |  | 0080 | Install Filters, Top Lid / N-11 | INT | Install Filters, Top Lid / N-11 |  |  | 90006341_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006341 |  | 5 |  | 3 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000112817 | S002 | 30 | 30 | 5300006473 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-29 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 113453 | 0 |  | 2 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Released | AM02 | Proactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001134534542710008156200079118
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-23 | 2024-09-14 | VALVE | 100040576 | 0010 | 0012 | 100040576 | CV-OH 2" 300# 218PCV507 | AA53.218PCV507 | VALVE,2K1820E1 L/O PRESS CTRL | AA01 | 20 | No Issue identified | 10021107 | GASKET;GR,FISHER 1R3296X0042 | 1 | EA | 1 | 0 | 0 | 0 |  | 21.02 - qty 1 SOH at AA02 | Supply for Order 100040576, Item 7 cannot be changed 90006873 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300002248 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006873 | 05 | Preparation | 0000139148 | 7 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006873_0020 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-31 | 0 |  |  | 2024-04-20 | 2024-04-23 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021107 | GASKET;GR,FISHER 1R3296X0042 |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90006873_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006873 |  | 20 |  | 7 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000138478 | S002 |  | 30 | 5300002248 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139148 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Released/Pre-costed/Order Approved/Date set by external system/Settlement rule created/Object created/Printed/Material shortage | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001391484540510021107100040576
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-23 | 2024-09-14 | VALVE | 100040577 | 0010 | 0010 | 100040577 | CV-OH 1" 300# 218PDCV506 | AA53.218PDCV506 | VALVE,2K1820E1 S/OIL PRESS CTRL | AA01 | 20 | No Issue identified | 10021149 | GASKET;CNAF,FISHER 1R2859X0042 | 1 | EA | 1 | 0 | 0 | 0 |  | 21.02 - qty 1 SOH at AA02 | Supply for Order 100040577, Item 1 cannot be changed 90006874 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300002250 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006874 | 05 | Preparation | 0000139149 | 1 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006874_0010 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-31 | 0 |  |  | 2024-04-20 | 2024-04-23 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021149 | GASKET;CNAF,FISHER 1R2859X0042 |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90006874_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006874 |  | 20 |  | 1 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000138479 | S002 |  | 30 | 5300002250 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139149 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Order Approved/Printed/Object created/Date set by external system/Pre-costed/Released/Settlement rule created/Material shortage | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001391494540510021149100040577
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-23 | 2024-09-14 | VALVE | 100040576 | 0010 | 0042 | 100040576 | CV-OH 2" 300# 218PCV507 | AA53.218PCV507 | VALVE,2K1820E1 L/O PRESS CTRL | AA01 | 20 | No Issue identified | 10021156 | GASKET,SW;CL300,76X89X4.5MM,GR | 1 | EA | 1 | 0 | 0 | 0 |  | 21.02 - qty 1 SOH at AA02 | Supply for Order 100040576, Item 9 cannot be changed 90006873 item 40 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300002248 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006873 | 05 | Preparation | 0000139148 | 9 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006873_0040 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-31 | 0 |  |  | 2024-04-20 | 2024-04-23 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021156 | GASKET,SW;CL300,76X89X4.5MM,GR |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90006873_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006873 |  | 20 |  | 9 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000138478 | S002 |  | 30 | 5300002248 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139148 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Released/Pre-costed/Order Approved/Date set by external system/Settlement rule created/Object created/Printed/Material shortage | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001391484540510021156100040576
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-23 | 2024-09-14 | VALVE | 100040577 | 0010 | 0062 | 100040577 | CV-OH 1" 300# 218PDCV506 | AA53.218PDCV506 | VALVE,2K1820E1 S/OIL PRESS CTRL | AA01 | 20 | No Issue identified | 10021292 | GASKET;FISHER 1R2862X0062 | 1 | EA | 1 | 0 | 0 | 0 |  | 21.02 - qty 1 SOH at AA02 | Supply for Order 100040577, Item 10 cannot be changed 90006874 item 40 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300002250 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006874 | 05 | Preparation | 0000139149 | 10 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006874_0040 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-31 | 0 |  |  | 2024-04-20 | 2024-04-23 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021292 | GASKET;FISHER 1R2862X0062 |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90006874_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006874 |  | 20 |  | 10 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000138479 | S002 | 30 | 30 | 5300002250 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139149 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Order Approved/Printed/Object created/Date set by external system/Pre-costed/Released/Settlement rule created/Material shortage | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001391494540510021292100040577
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-23 | 2024-09-14 | VALVE | 100040577 | 0010 | 0020 | 100040577 | CV-OH 1" 300# 218PDCV506 | AA53.218PDCV506 | VALVE,2K1820E1 S/OIL PRESS CTRL | AA01 | 20 | No Issue identified | 10021426 | GASKET SET,VV,CONTR;FISHER RGASKETX162 | 1 | KIT | 1 | 0 | 0 | 0 |  | 21.02 - qty 1 SOH at AA02; qty 4 SOH at AA01 | Supply for Order 100040577, Item 2 cannot be changed 90006874 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300002250 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90006874 | 05 | Preparation | 0000139149 | 2 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006874_0020 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-31 | 0 |  |  | 2024-04-20 | 2024-04-23 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021426 | GASKET SET,VV,CONTR;FISHER RGASKETX162 |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90006874_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006874 |  | 20 |  | 2 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000138479 | S002 |  | 30 | 5300002250 | 20 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139149 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Order Approved/Printed/Object created/Date set by external system/Pre-costed/Released/Settlement rule created/Material shortage | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001391494540510021426100040577
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-23 | 2024-09-14 | VALVE | 100040576 | 0010 | 0022 | 100040576 | CV-OH 2" 300# 218PCV507 | AA53.218PCV507 | VALVE,2K1820E1 L/O PRESS CTRL | AA01 | 20 | No Issue identified | 10021547 | GASKET;FISHER 1R3299X0042 | 1 | EA | 1 | 0 | 0 | 0 |  | 21.02 - qty 1 SOH at AA02 | Supply for Order 100040576, Item 8 cannot be changed 90006873 item 30 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300002248 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006873 | 05 | Preparation | 0000139148 | 8 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006873_0030 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-31 | 0 |  |  | 2024-04-20 | 2024-04-23 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021547 | GASKET;FISHER 1R3299X0042 |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90006873_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006873 |  | 20 |  | 8 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000138478 | S002 | 30 | 30 | 5300002248 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139148 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Released/Pre-costed/Order Approved/Date set by external system/Settlement rule created/Object created/Printed/Material shortage | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001391484540510021547100040576
| 24SDLN1 | Released | 2024-03-14 | 2024-05-03 |  | 2024-05-03 | 2024-05-08 | VALVE | 100033493 | 0010 | 0010 | 100033493 | CV-OH 3" 600# 114URC37 | AA53.114URC37 | LOOP,1E1405 BLOWDOWN PRESS RATIO CONTROL |  | 10 | No Issue identified | 10021722 | PACKING KIT,VV,CONTR;FISHER RPACKX00032 | 1 | KIT | 0 | 0 | 0 | 0 |  | 19.03 - 1 SOH @ AA02 | Supply Process could not be determined for item 1, material 10021722 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | KIT | [5 empty] | 05 | Preparation | 0000131994 | 1 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2023-11-11 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021722 | PACKING KIT,VV,CONTR;FISHER RPACKX00032 |  | 0010 | Transport Valve to Workshop | INT | Transport Valve to Workshop | [10 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 10 |  | 0 |  | 0 |  | 24SDLN1 | MJ |  | 1000131423 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Released/Order Approved/Settlement rule created/Object created/Pre-costed | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | 1 | 00001319944541510021722100033493
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-23 | 2024-09-14 | VALVE | 100040577 | 0010 | 0072 | 100040577 | CV-OH 1" 300# 218PDCV506 | AA53.218PDCV506 | VALVE,2K1820E1 S/OIL PRESS CTRL | AA01 | 20 | No Issue identified | 10021813 | DIAPHRAGM,ACT;FARRIS 0F092802162 | 1 | EA | 1 | 0 | 0 | 0 |  | 21.02 - qty 1 SOH at AA02 | Supply for Order 100040577, Item 11 cannot be changed 90006874 item 50 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300002250 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006874 | 05 | Preparation | 0000139149 | 11 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006874_0050 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-31 | 0 |  |  | 2024-04-20 | 2024-04-23 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021813 | DIAPHRAGM,ACT;FARRIS 0F092802162 |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90006874_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006874 |  | 20 |  | 11 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000138479 | S002 |  | 30 | 5300002250 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139149 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Order Approved/Printed/Object created/Date set by external system/Pre-costed/Released/Settlement rule created/Material shortage | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001391494540510021813100040577
| 24SD4403 | Released | 2024-01-02 | 2024-05-07 | 2024-05-04 | 2024-05-07 | 2024-05-07 | VALVE | 100041467 | 0010 | 0030 | 100041467 | CV-OH 2" 300# 44PCV523 | AA53.44PCV523 | VALVE,PRESS K4403 LUBEOIL TNK RECYC | AA01 | 30 | No Issue identified | 10022983 | PACKING,VV STEM;MASON 011488495999 | 1 | EA | 1 | 0 | 0 | 0 |  | 22.02 - 1 SOH @ AA02 |  | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300000440 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006601 | 05 | Preparation | 0000139988 | 1 | 0 | [9 empty] | WorkPackLink |  | SCORE | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006601_0010 | 0 | 0 | 0 |  | 2024-05-05 | AA53 | 2024-05-07 |  |  | 2024-05-07 |  |  |  |  | 2019-09-13 | 0 |  |  | 2024-05-04 | 2024-05-07 | 2100338885 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-04 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10022983 | PACKING,VV STEM;MASON 011488495999 |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90006601_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006601 |  | 30 |  | 1 |  | 0 |  | 24SD4403 | MJ | AU1072 | 1000139337 | S002 | 30 | 30 | 5300000440 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-04 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139988 | 0 |  | 2 |  |  | RC00025003 | 2024-05-07 | 2024-05-07 | 2024-05-07 | Printed/Material shortage/Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001399884541910022983100041467
| 24SD4403 | Released | 2024-01-02 | 2024-05-07 | 2024-05-04 | 2024-05-07 | 2024-05-07 | VALVE | 100041467 | 0010 | 0042 | 100041467 | CV-OH 2" 300# 44PCV523 | AA53.44PCV523 | VALVE,PRESS K4403 LUBEOIL TNK RECYC | AA01 | 30 | No Issue identified | 10022984 | GASKET;BODY,304SS,GRAFOIL,536H REG | 1 | EA | 1 | 0 | 0 | 0 |  | 22.02 - 1 SOH @ AA02 |  | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300000440 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006601 | 05 | Preparation | 0000139988 | 7 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006601_0040 | 0 | 0 | 0 |  | 2024-05-05 | AA53 | 2024-05-07 |  |  | 2024-05-07 |  |  |  |  | 2019-09-13 | 0 |  |  | 2024-05-04 | 2024-05-07 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-04 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10022984 | GASKET;BODY,304SS,GRAFOIL,536H REG |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90006601_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006601 |  | 30 |  | 7 |  | 0 |  | 24SD4403 | MJ | AU1072 | 1000139337 | S002 | 30 | 30 | 5300000440 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-04 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139988 | 0 |  | 2 |  |  | RC00025003 | 2024-05-07 | 2024-05-07 | 2024-05-07 | Printed/Material shortage/Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001399884541910022984100041467
| 24SD4403 | Released | 2024-01-02 | 2024-05-07 | 2024-05-04 | 2024-05-07 | 2024-05-07 | VALVE | 100041467 | 0010 | 0052 | 100041467 | CV-OH 2" 300# 44PCV523 | AA53.44PCV523 | VALVE,PRESS K4403 LUBEOIL TNK RECYC | AA01 | 30 | No Issue identified | 10022985 | GASKET;SEAT RING,314SS,GRAFOIL,536H REG | 1 | EA | 1 | 0 | 0 | 0 |  | 22.02 - 1 SOH @ AA02 |  | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300000440 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006601 | 05 | Preparation | 0000139988 | 8 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006601_0050 | 0 | 0 | 0 |  | 2024-05-05 | AA53 | 2024-05-07 |  |  | 2024-05-07 |  |  |  |  | 2019-09-13 | 0 |  |  | 2024-05-04 | 2024-05-07 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-04 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10022985 | GASKET;SEAT RING,314SS,GRAFOIL,536H REG |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90006601_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006601 |  | 30 |  | 8 |  | 0 |  | 24SD4403 | MJ | AU1072 | 1000139337 | S002 | 30 | 30 | 5300000440 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-04 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139988 | 0 |  | 2 |  |  | RC00025003 | 2024-05-07 | 2024-05-07 | 2024-05-07 | Printed/Material shortage/Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001399884541910022985100041467
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-05-01 | 2024-05-03 | 2024-05-03 | INLEC | 100035583 | 0010 | 0030 | 100035583 | MOC-72065 Modify GT7 Hard-Wired Trip S2A | AA53.S2A1A4 | FEEDER,GENERATOR G4007 INCOMER | AA01 | 30 | No Issue identified | 10034254 | TERMINAL;1.5MM2,INS,BLK,CABAC BLP150 | 5 | PAC | 0 | 0 | 0 | 0 |  | 28.02 - 900 SOH @ AA01 | Supply for Order 100035583, Item 2 cannot be changed 90000120 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300000667 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | PAC |  |  |  |  | 90000120 | 05 | Preparation | 0000134055 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000120_0020 | 1 | 0 | 0 |  | 2024-05-02 | AA53 | 2024-05-03 |  |  | 2024-05-04 |  |  |  |  | 2024-08-02 | 0 |  |  | 2024-05-01 | 2024-05-04 | AU01.S2A1A4 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-01 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034254 | TERMINAL;1.5MM2,INS,BLK,CABAC BLP150 |  | 0010 | MOC-72065 Modify GT7 Hard-wired trip | ENON | MOC-72065 Modify GT7 Hard-wired trip | 5 | Management of Change | 90000120_0020 | [7 empty] | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000120 |  | 30 |  | 2 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000133465 | S002 | 30 | 30 | 5300000667 | 20 |  |  | 0 | 5 | PAC | 2001 | AA02 | 2024-05-01 |  | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 134055 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance | [8 empty] | 3 | 00001340554541510034254100035583
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0090 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | Shipped qty below requirement qty | 10034649 | TIE,CABLE;UV,6.9X343MM,PA,BLK | 20 | PKT | 0 | 0 | 6 | 6 | PKT | 14.03 - Qty 6 SOH at AA02; Qty 21 SOH at AA01 | Supply for Order 100033847, Item 9 cannot be changed 90004487 item 80 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | PKT |  |  |  | 180013609 | 9000596 | 07 | Execution | 0000132381 | 9 | 0 | PKT | 102000000003649 |  | 102000000003683 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | P07-BENCH | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-01-15 | GRST-5000045904 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  | 100000005106 | 1020 | 2025-10-01 | 6 | 4900040481_2024_0015 |  | 2024-03-26 | 2024-05-03 |  | 5000045904_2024_0008 | 0 | 2 | 0 | 6 | 0 | 180013609 | 1 | L | 4900040481 | 2024 |  | 5000045904 | 2024 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034649 | TIE,CABLE;UV,6.9X343MM,PA,BLK |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 90004487_0080/9000596_0080 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 9 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 90 |  |  | 0 | 20 | PKT | 2001 | AA02 | 2024-04-30 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | [7 empty] | 40 | 00001323814535710034649100033847
| 24SDLN1 | Released | 2024-01-15 | 2024-03-30 | 2024-03-27 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0340 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | Shipped qty below requirement qty | 10034650 | TIE,CABLE;UV,370X4.8X1.4MM,PA,100PK | 10 | PKT | 10 | 6 | 5 | 1 | PKT | 14.03 - Qty 21 SOH at AA02; Qty 29 In Transit ex AA01 to AA02. | Supply for Order 100033847, Item 34 cannot be changed 90004536 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 340 |  | 14 |  | 0 |  |  |  | 0 | 0 | PKT |  |  |  | 180014022 | 9000597 | 07 | Execution | 0000132381 | 34 | 0 | PKT | 102000000003753 |  | 102000000003599 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | KSF-KGP P07P08 SML | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-01-15 | GRST-5000047035_2024 | 0 | 0 | 0 |  | 2024-03-28 | AA53 | 2024-03-06 |  |  | 2024-03-30 |  |  | 100000005124 | 1020 | 2025-10-01 | 1 | 4900040874_2024_0001 |  | 2024-03-27 | 2024-03-30 |  | 5000047035_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180014022 | 1 | L | 4900040874 | 2024 |  | 5000047035 | 2024 |  |  | 2024-03-27 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034650 | TIE,CABLE;UV,370X4.8X1.4MM,PA,100PK |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 90004536_0030/9000597_0030 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004536 |  | 99 |  | 34 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 340 |  |  | 0 | 10 | PKT | 2001 | AA02 | 2024-03-27 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | SOH @ AA02 | [6 empty] | FALSE | 00001323814538110034650100033847
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-16 | 2024-04-23 | MECH | 600001793 | 0170 |  | 600001793 | MOC-89056 Fab/Weld Install 218UCV112 | AA53.2E1801 | EXCH,HEAT DE-ETH REBOIL FRACT2 | AA01 | 10 | No Issue identified | 10038178 | TUBE,SML,0.375"OD,A269-TP316L,1.65MM WT | 5 | EA | 30 | 0 | 11 | 0 |  | 14.03 - 30 SOH 2 AA02 | Supply for Order 600001793, Item 5 cannot be changed 90006878 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004605 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006878 | 06 | Scheduling | 0000084711 | 5 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006878_0010 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-15 | 0 |  |  | 2024-04-20 | 2024-04-23 | 218UCV112 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10038178 | TUBE,SML,0.375"OD,A269-TP316L,1.65MM WT |  | 0170 | Complete Final Hook-Up | INT | Complete Final Hook-Up | 5 |  | 90006878_0010 | [7 empty] | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 | 90006878 |  | 5 |  | 5 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000084095 | S002 | 30 | 30 | 5300004605 | 10 |  |  | 0 | 5 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84711 | 0 |  | 2 |  |  | RC00018003 | 2024-04-23 | 2024-04-16 | 2024-04-16 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Material shortage/Printed | AM06 | Capital |  | SOH @ AA02 | [6 empty] | FALSE | 00000847114540510038178600001793
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-16 | 2024-04-23 | MECH | 600001793 | 0170 |  | 600001793 | MOC-89056 Fab/Weld Install 218UCV112 | AA53.2E1801 | EXCH,HEAT DE-ETH REBOIL FRACT2 | AA01 | 10 | No Issue identified | 10047898 | CONNECTOR,COMP/M,0.375" X 0.25" NPT,SS | 5 | EA | 118 | 0 | 79 | 0 |  | 25.01 - 197 SOH @ AA02 | Supply for Order 600001793, Item 7 cannot be changed 90006878 item 30 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004605 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006878 | 06 | Scheduling | 0000084711 | 7 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006878_0030 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-15 | 0 |  |  | 2024-04-20 | 2024-04-23 | 218UCV112 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10047898 | CONNECTOR,COMP/M,0.375" X 0.25" NPT,SS |  | 0170 | Complete Final Hook-Up | INT | Complete Final Hook-Up | 5 |  | 90006878_0030 | [7 empty] | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 | 90006878 |  | 5 |  | 7 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000084095 | S002 | 30 | 30 | 5300004605 | 30 |  |  | 0 | 5 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84711 | 0 |  | 2 |  |  | RC00018003 | 2024-04-23 | 2024-04-16 | 2024-04-16 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Material shortage/Printed | AM06 | Capital |  | SOH @ AA02 | [6 empty] | FALSE | 00000847114540510047898600001793
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-16 | 2024-04-23 | MECH | 600001793 | 0170 |  | 600001793 | MOC-89056 Fab/Weld Install 218UCV112 | AA53.2E1801 | EXCH,HEAT DE-ETH REBOIL FRACT2 | AA01 | 10 | No Issue identified | 10048155 | UNION,COMP,STR;GYRO 6U316 | 5 | EA | 31 | 0 | 12 | 0 |  | 25.01 - 43 SOH @ AA02 | Supply for Order 600001793, Item 6 cannot be changed 90006878 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004605 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006878 | 06 | Scheduling | 0000084711 | 6 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006878_0020 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-15 | 0 |  |  | 2024-04-20 | 2024-04-23 | 218UCV112 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048155 | UNION,COMP,STR;GYRO 6U316 |  | 0170 | Complete Final Hook-Up | INT | Complete Final Hook-Up | 5 |  | 90006878_0020 | [7 empty] | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 | 90006878 |  | 5 |  | 6 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000084095 | S002 | 30 | 30 | 5300004605 | 20 |  |  | 0 | 5 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84711 | 0 |  | 2 |  |  | RC00018003 | 2024-04-23 | 2024-04-16 | 2024-04-16 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Material shortage/Printed | AM06 | Capital |  | SOH @ AA02 | [6 empty] | FALSE | 00000847114540510048155600001793
| 24SDGT9 | Released | 2024-02-13 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | INLEC | 100039826 | 0010 | 0030 | 100039826 | Combustion drain rubbing | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 255 | No Issue identified | 10048158 | UNION,STR;COMP,F&F,1"OD,SS,HOKE 16U316 | 10 | EA | 0 | 0 | 0 | 0 |  | 05.04 - 22 SOH @ AA01 | Supply for Order 100039826, Item 3 cannot be changed 90006342 item 30 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006511 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006342 | 05 | Preparation | 0000138318 | 3 | 0 | [9 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-02-13 | ODST-0090006342_0030 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-06-18 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048158 | UNION,STR;COMP,F&F,1"OD,SS,HOKE 16U316 |  | 0010 | Isolate & Disconnect Tubing | INT | Isolate & Disconnect Tubing |  |  | 90006342_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006342 |  | 99 |  | 3 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000137748 | S002 | 30 | 30 | 5300006511 | 30 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138318 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance | [8 empty] | 22 | 00001383184543110048158100039826
| 24SDFR2 | Released | 2024-03-20 | 2024-04-23 | 2024-04-20 | 2024-04-23 | 2024-04-23 | INLEC | 100036100 | 0040 | 0020 | 100036100 | T20CD3 & T20CD4 LV cables clamping | AA53.T20CD3 | XFMR,6.6/0.433KV FDR FOR MCC S20D2 A | AA01 | 20 | No Issue identified | 10057799 | RUBBER,NATURAL,1200 X 1000MM,3.00MM THK | 2 | SHT | 2 | 0 | 0 | 0 |  | 01.04 - 2 SOH @ AA02 |  | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300008135 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | SHT |  |  |  |  | 90006881 | 05 | Preparation | 0000134624 | 2 | 0 | [9 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-03-20 | ODST-0090006881_0020 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-20 | 2024-04-23 | T20CD3 & 4 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10057799 | RUBBER,NATURAL,1200 X 1000MM,3.00MM THK |  | 0040 | T20CD3 & T20CD4 LV Cable Clamping | INT | T20CD3 & T20CD4 LV Cable Clamping | 2 |  | 90006881_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006881 |  | 20 |  | 2 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000133975 | S002 |  | 30 | 5300008135 | 20 |  |  | 0 | 2 | SHT | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 134624 | 0 |  | 3 |  |  | RC00025003 | 2024-04-23 | 2024-04-23 | 2024-04-23 | Printed/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001346244540510057799100036100
| 24SD4403 | Released | 2024-02-13 | 2024-05-07 | 2024-05-04 | 2024-05-07 | 2024-05-07 | MECH | 100044208 | 0030 |  | 100044208 | Fin Fan Plugs Leaking - K4403 E1 | AA53.K4403E1 | EXCH,K4403 LUBE OIL AIR COOLER | AA01 | 20 | No Issue identified | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK | 8 | EA | 0 | 0 | 0 | 0 |  | 22.02 - 168 SOH @ AA01 |  | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006489 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006605 | 06 | Scheduling | 0000142722 | 2 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-02-13 | ODST-0090006605_0020 | 0 | 0 | 0 |  | 2024-05-05 | AA53 | 2024-05-07 |  |  | 2024-05-07 |  |  |  |  | 2018-12-13 | 0 |  |  | 2024-05-04 | 2024-05-07 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-04 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK |  | 0030 | REFIT DRAIN AND VENT FLANGES | INT | REFIT DRAIN AND VENT FLANGES |  |  | 90006605_0020 | [7 empty] | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006605 |  | 20 |  | 2 |  | 0 |  | 24SD4403 | MJ | AU1072 | 1000142104 | S002 | 30 | 30 | 5300006489 | 20 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-05-04 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142722 | 0 |  | 2 |  |  | RC00025003 | 2024-05-07 | 2024-05-07 | 2024-05-07 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Ready For Scheduling | AM01 | Reactive Maintenance | [8 empty] | 168 | 00001427224541910058984100044208
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-04 | ROTAT | 200057503 | 0010 | 0020 | 200057503 | 2Y GT4007 TURB PRE FILTER REPLACE | AA53.GT4007S2 | FILT,AIR INLET GT4007 | AA01 | 20 | No Issue identified | 10059514 | HANDLE,BROOM;GP,25MM DIA X 1500MM | 6 | EA | 0 | 0 | 0 | 0 |  | 08.03 - 6 SOH @ AA02 |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006134 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000091791 | 4 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-02-06 | STST-5300006134_00030 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-04-22 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059514 | HANDLE,BROOM;GP,25MM DIA X 1500MM |  | 0010 | Mobilise Filters and Equipment | INT | Mobilise Filters and Equipment | 0 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 20 |  | 4 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000091225 | S002 | 30 | 30 | 5300006134 | 30 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 91791 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance | [8 empty] | 7 | 00000917914541510059514200057503
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-16 | 2024-04-23 | MECH | 600001793 | 0170 |  | 600001793 | MOC-89056 Fab/Weld Install 218UCV112 | AA53.2E1801 | EXCH,HEAT DE-ETH REBOIL FRACT2 | AA01 | 10 | No Issue identified | 10059550 | CLAMP,TUBE;SNGL,9.5MM,PA,SS316 | 6 | EA | 88 | 0 | 0 | 0 |  | 25.01 - 88 SOH @ AA02 | Supply for Order 600001793, Item 8 cannot be changed 90006878 item 40 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004605 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006878 | 06 | Scheduling | 0000084711 | 8 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006878_0040 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-15 | 0 |  |  | 2024-04-20 | 2024-04-23 | 218UCV112 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059550 | CLAMP,TUBE;SNGL,9.5MM,PA,SS316 |  | 0170 | Complete Final Hook-Up | INT | Complete Final Hook-Up | 5 |  | 90006878_0040 | [7 empty] | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 | 90006878 |  | 5 |  | 8 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000084095 | S002 |  | 30 | 5300004605 | 40 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84711 | 0 |  | 2 |  |  | RC00018003 | 2024-04-23 | 2024-04-16 | 2024-04-16 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Material shortage/Printed | AM06 | Capital |  | SOH @ AA02 | [6 empty] | FALSE | 00000847114540510059550600001793
| 24SDLN1 | Released | 2024-01-15 | 2024-04-03 | 2024-03-31 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0020 | 0010 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10059589 | SAW,HOLE;25MM,32MM,COBALT HSS | 10 | EA | 0 | 0 | 0 | 0 |  | 22.03 - qty 10 SOH at AA01 | Supply for Order 100033847, Item 37 cannot be changed 90004627 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 370 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90004627 | 07 | Execution | 0000132381 | 37 | 0 | [9 empty] | WorkPackLink |  | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-01-15 | ODST-0090004627_0010 | 0 | 0 | 0 |  | 2024-04-01 | AA53 | 2024-05-03 |  |  | 2024-04-03 |  |  |  |  | 2025-10-01 | 0 |  |  | 2024-03-31 | 2024-04-03 | B.Vorn TA |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-03-31 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059589 | SAW,HOLE;25MM,32MM,COBALT HSS |  | 0020 | Pre Shut Insulation | INT | Pre Shut Insulation | 5 |  | 90004627_0010 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004627 |  | 99 |  | 37 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 370 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-03-31 |  |  |  |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | [7 empty] | 10 | 00001323814538510059589100033847
| 24SDGT9 | Released | 2024-02-16 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | ROTAT | 100039179 | 0010 | 0020 | 100039179 | Repair leakis lubeoil demister RO& motor | AA53.409RO522 | ORIF,G4009V2 MINERAL OIL VAP SEP OUTLET | AA01 | 30 | No Issue identified | 10059951 | JOINTING,1.5M X 2M X 1.50MM,C4500,CNAF | 1 | SHT | 0 | 0 | 0 | 0 |  |  | Supply for Order 100039179, Item 2 cannot be changed 90006344 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006669 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | SHT |  |  |  |  | 90006344 | 05 | Preparation | 0000137691 | 2 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-16 | ODST-0090006344_0020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2023-11-03 | 0 |  |  | 2024-04-30 | 2024-05-03 | 100039179 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059951 | JOINTING,1.5M X 2M X 1.50MM,C4500,CNAF |  | 0010 | Erect Scaffold Access | INT | Erect Scaffold Access |  |  | 90006344_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006344 |  | 30 |  | 2 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000137101 | S002 |  | 30 | 5300006669 | 20 |  |  | 0 | 1 | SHT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 137691 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance | [8 empty] | 0 | 00001376914543110059951100039179
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-07 | ROTAT | 200083164 | 0010 | 0020 | 200083164 | 1Y GT4007 TURB VSV REPLACEMENT | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | No Issue identified | 10060883 | GASKET,SW;25MM,CL150,4.5MM,SS316L,GR | 20 | EA | 5 | 0 | 2 | 0 |  | 17.01 - 119 SOH @ AA01 | Supply for Order 200083164, Item 2 cannot be changed 90000252 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003891 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000252 | 05 | Preparation | 0000120013 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000252_0020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-05-20 | 0 |  |  | 2024-04-30 | 2024-05-03 | Spades |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET,SW;25MM,CL150,4.5MM,SS316L,GR |  | 0010 | SPADE (Materials ordered can't DEL) | INT | SPADE (Materials ordered can't DEL) | 5 | Ready for Release | 90000252_0020 | [7 empty] | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000252 |  | 20 |  | 2 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000119503 | S002 | 30 | 30 | 5300003891 | 20 |  |  | 0 | 20 | EA | 2001 | AA02 | 2024-04-30 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120013 | 0 |  | 1 |  |  | RC00025003 | 2024-05-07 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance | [8 empty] | Need Purchasing | 00001200134541510060883200083164
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 200083165 | 0010 | 0020 | 200083165 | 1Y GT4008 TURB VSV REPLACEMENT | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | No Issue identified | 10060883 | GASKET,SW;25MM,CL150,4.5MM,SS316L,GR | 20 | EA | 5 | 0 | 2 | 0 |  | 18.01 - enough SOH @ AA01 for our demand | Supply for Order 200083165, Item 2 cannot be changed 90000277 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003892 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000277 | 05 | Preparation | 0000120014 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000277_0020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-05-20 | 0 |  |  | 2024-04-30 | 2024-05-03 | GT4008 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET,SW;25MM,CL150,4.5MM,SS316L,GR |  | 0010 | PERFORM SPADE | INT | PERFORM SPADE | 5 |  | 90000277_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000277 |  | 20 |  | 2 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000119504 | S002 | 30 | 30 | 5300003892 | 20 |  |  | 0 | 20 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120014 | 0 |  | 1 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance | [8 empty] | Need Purchasing | 00001200144542710060883200083165
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 200085913 | 0040 | 0090 | 200085913 | 1Y Waterwash Maintenance GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | No Issue identified | 10060883 | GASKET,SW;25MM,CL150,4.5MM,SS316L,GR | 12 | EA | 5 | 0 | 2 | 0 |  | 17.01 - 119 SOH @ AA01 | Supply for Order 200085913, Item 6 cannot be changed 90000132 item 60 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003547 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000132 | 05 | Preparation | 0000124191 | 6 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000132_0060 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-03-17 | 0 |  |  | 2024-04-30 | 2024-05-03 | GT4007 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET,SW;25MM,CL150,4.5MM,SS316L,GR |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 90000132_0060 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000132 |  | 20 |  | 6 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000123582 | S002 | 30 | 30 | 5300003547 | 60 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124191 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance | [8 empty] | Need Purchasing | 00001241914541510060883200085913
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 200085915 | 0040 | 0090 | 200085915 | 1Y GT4008 WATERWASH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | No Issue identified | 10060883 | GASKET,SW;25MM,CL150,4.5MM,SS316L,GR | 12 | EA | 5 | 0 | 2 | 0 |  | 17.01 - 119 SOH @ AA01 | Supply for Order 200085915, Item 6 cannot be changed 90000289 item 60 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003548 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000289 | 05 | Preparation | 0000124193 | 6 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000289_0060 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-03-17 | 0 |  |  | 2024-04-30 | 2024-05-03 | GT4008 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET,SW;25MM,CL150,4.5MM,SS316L,GR |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 90000289_0060 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000289 |  | 20 |  | 6 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000123584 | S002 | 30 | 30 | 5300003548 | 60 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124193 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | [8 empty] | Need Purchasing | 00001241934542710060883200085915
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | ROTAT | 200085917 | 0040 | 0090 | 200085917 | 1Y GT4009 WATERWASH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | No Issue identified | 10060883 | GASKET,SW;25MM,CL150,4.5MM,SS316L,GR | 12 | EA | 5 | 0 | 2 | 0 |  | 17.01 - 119 SOH @ AA01 | Supply for Order 200085917, Item 6 cannot be changed 90000426 item 60 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003549 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000426 | 05 | Preparation | 0000124195 | 6 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000426_0060 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-03-17 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET,SW;25MM,CL150,4.5MM,SS316L,GR |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 90000426_0060 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000426 |  | 20 |  | 6 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000123586 | S002 | 30 | 30 | 5300003549 | 60 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124195 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance | [8 empty] | Need Purchasing | 00001241954543110060883200085917
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-04 | ROTAT | 200085919 | 0040 | 0090 | 200085919 | 1Y GT4010 WATERWASH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 20 | No Issue identified | 10060883 | GASKET,SW;25MM,CL150,4.5MM,SS316L,GR | 12 | EA | 5 | 0 | 2 | 0 |  | 17.01 - 119 SOH @ AA01 | Supply for Order 200085919, Item 6 cannot be changed 90000110 item 60 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003552 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000110 | 05 | Preparation | 0000124197 | 6 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000110_0060 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-03-17 | 0 |  |  | 2024-04-30 | 2024-05-03 | GT4010 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET,SW;25MM,CL150,4.5MM,SS316L,GR |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 90000110_0060 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000110 |  | 20 |  | 6 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000123588 | S002 | 30 | 30 | 5300003552 | 60 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124197 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | [8 empty] | Need Purchasing | 00001241974541510060883200085919
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | WORK | 200089392 | 0020 | 0010 | 200089392 | 10Y RECERTIFY PSV ROTABLE | AA53.407RV521 | PSV,CO2 DISCH LINE GT4007A CO2 | AA01 | 10 | No Issue identified | 10060883 | GASKET,SW;25MM,CL150,4.5MM,SS316L,GR | 1 | EA | 5 | 0 | 2 | 0 |  | 22.03 - qty 121 SOH @ AA01 | Supply for Order 200089392, Item 2 cannot be changed 90000133 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003819 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000133 | 05 | Preparation | 0000127702 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000133_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-07-18 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200628652 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET,SW;25MM,CL150,4.5MM,SS316L,GR |  | 0020 | Remove / Install PSV | INT | Remove / Install PSV | 5 |  | 90000133_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000133 |  | 5 |  | 2 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000127064 | S002 | 30 | 30 | 5300003819 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127702 | 0 |  | 2 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001277024541510060883200089392
| 24SD4403 | Released | 2024-02-13 | 2024-05-07 | 2024-05-04 | 2024-05-07 | 2024-05-07 | MECH | 100044208 | 0030 |  | 100044208 | Fin Fan Plugs Leaking - K4403 E1 | AA53.K4403E1 | EXCH,K4403 LUBE OIL AIR COOLER | AA01 | 20 | No Issue identified | 10060884 | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR | 2 | EA | 40 | 0 | 0 | 0 |  | 27.03 - 40 SOH @ AA02 |  | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006489 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006605 | 06 | Scheduling | 0000142722 | 1 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-02-13 | ODST-0090006605_0010 | 0 | 0 | 0 |  | 2024-05-05 | AA53 | 2024-05-07 |  |  | 2024-05-07 |  |  |  |  | 2018-12-13 | 0 |  |  | 2024-05-04 | 2024-05-07 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-04 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060884 | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR |  | 0030 | REFIT DRAIN AND VENT FLANGES | INT | REFIT DRAIN AND VENT FLANGES |  |  | 90006605_0010 | [7 empty] | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006605 |  | 20 |  | 1 |  | 0 |  | 24SD4403 | MJ | AU1072 | 1000142104 | S002 | 30 | 30 | 5300006489 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-05-04 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142722 | 0 |  | 2 |  |  | RC00025003 | 2024-05-07 | 2024-05-07 | 2024-05-07 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Ready For Scheduling | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001427224541910060884100044208
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-23 | 2024-09-10 | WORK | 200064070 | 0020 | 0030 | 200064070 | 9Y F21 RECERTIFY SC PSV ROTABLE | AA53.218RV13 | PSV,2V1805 ON 2" LINE 2W41534 | AA01 | 10 | No Issue identified | 10060885 | GASKET;SWCI,50MM,CL150,316L/GR/316 | 1 | EA | 2 | 0 | 27 | 0 |  | 22.03 - qty 312 SOH at AA01 | Supply for Order 200064070, Item 3 cannot be changed 90006875 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300002997 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006875 | 05 | Preparation | 0000098352 | 3 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006875_0020 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-07-03 | 0 |  |  | 2024-04-20 | 2024-04-23 | 218RV13 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060885 | GASKET;SWCI,50MM,CL150,316L/GR/316 |  | 0020 | REMOVE / INSTALL PSV | INT | REMOVE / INSTALL PSV | 5 |  | 90006875_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006875 |  | 5 |  | 3 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000097789 | S002 | 30 | 30 | 5300002997 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98352 | 0 |  | 2 |  |  | RC00025003 | 2024-09-10 | 2024-04-23 | 2024-04-23 | Material shortage/Date set by external system/Object created/Pre-costed/Released/Settlement rule created | AM02 | Proactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00000983524540510060885200064070
| 24SDGT9 | Released | 2024-02-16 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | ROTAT | 100039179 | 0010 | 0010 | 100039179 | Repair leakis lubeoil demister RO& motor | AA53.409RO522 | ORIF,G4009V2 MINERAL OIL VAP SEP OUTLET | AA01 | 30 | No Issue identified | 10060887 | GASKET;SWCI,100MM,CL150,316L/GR/316 | 2 | EA | 21 | 0 | 11 | 0 |  | 31.01 - 234 SOH @ AA01 | Supply for Order 100039179, Item 1 cannot be changed 90006344 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006669 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006344 | 05 | Preparation | 0000137691 | 1 | 0 | [9 empty] | WorkPackLink |  | NEVER | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-02-16 | ODST-0090006344_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2023-11-03 | 0 |  |  | 2024-04-30 | 2024-05-03 | NEVER |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET;SWCI,100MM,CL150,316L/GR/316 |  | 0010 | Erect Scaffold Access | INT | Erect Scaffold Access |  |  | 90006344_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006344 |  | 30 |  | 1 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000137101 | S002 | 30 | 30 | 5300006669 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 137691 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001376914543110060887100039179
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-23 | 2024-09-09 | WORK | 200089031 | 0004 | 0020 | 200089031 | 6Y F21 RECERTIFY SC MAIN PSV TURNAROUND | AA53.218RV97A | PSV,PROPANE TRANSFER SURGE DRUM | AA01 | 10 | No Issue identified | 10060887 | GASKET;SWCI,100MM,CL150,316L/GR/316 | 1 | EA | 21 | 0 | 11 | 0 |  | 21.03 - qty 202 SOH @ AA01 |  | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004094 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006876 | 05 | Preparation | 0000127309 | 5 | 0 | [9 empty] | WorkPackLink |  | 200089031 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006876_0020 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-10-30 | 0 |  |  | 2024-04-20 | 2024-04-23 | T24-SD-P07 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET;SWCI,100MM,CL150,316L/GR/316 |  | 0004 | Remove & Replace PSV | INT | Remove & Replace PSV |  |  | 90006876_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006876 |  | 5 |  | 5 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000126680 | S002 | 30 | 30 | 5300004094 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127309 | 0 |  | 3 |  |  | RC00025003 | 2024-09-09 | 2024-04-23 | 2024-04-23 | Material committed/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001273094540510060887200089031
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-23 | 2024-09-12 | WORK | 200089033 | 0110 | 0020 | 200089033 | 6Y F21 RECERTIFY SC MAIN PSV TURNAROUND | AA53.218RV97B | PSV,PROPANE TRANSFER SURGE DRUM | AA01 | 10 | No Issue identified | 10060887 | GASKET;SWCI,100MM,CL150,316L/GR/316 | 1 | EA | 21 | 0 | 11 | 0 |  | 21.03 - qty 202 SOH @ AA01 |  | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004098 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006877 | 05 | Preparation | 0000127311 | 5 | 0 | [9 empty] | WorkPackLink |  | 200089033 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006877_0020 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-10-30 | 0 |  |  | 2024-04-20 | 2024-04-23 | T24-SD-P07 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET;SWCI,100MM,CL150,316L/GR/316 |  | 0110 | Remove & Replace PSV | INT | Remove & Replace PSV |  |  | 90006877_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006877 |  | 5 |  | 5 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000126742 | S002 | 30 | 30 | 5300004098 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127311 | 0 |  | 3 |  |  | RC00025003 | 2024-09-12 | 2024-04-23 | 2024-04-23 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001273114540510060887200089033
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-23 | 2024-09-10 | WORK | 200064070 | 0020 | 0020 | 200064070 | 9Y F21 RECERTIFY SC PSV ROTABLE | AA53.218RV13 | PSV,2V1805 ON 2" LINE 2W41534 | AA01 | 10 | No Issue identified | 10060917 | GASKET;SWCI,25MM,CL300/600,316L/GR/316 | 1 | EA | 388 | 1 | 43 | 0 |  | 22.03 - qty 390 SOH at AA02 | Supply for Order 200064070, Item 2 cannot be changed 90006875 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300002997 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006875 | 05 | Preparation | 0000098352 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006875_0010 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-07-03 | 0 |  |  | 2024-04-20 | 2024-04-23 | 218RV13 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET;SWCI,25MM,CL300/600,316L/GR/316 |  | 0020 | REMOVE / INSTALL PSV | INT | REMOVE / INSTALL PSV | 5 |  | 90006875_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006875 |  | 5 |  | 2 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000097789 | S002 | 30 | 30 | 5300002997 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98352 | 0 |  | 2 |  |  | RC00025003 | 2024-09-10 | 2024-04-23 | 2024-04-23 | Material shortage/Date set by external system/Object created/Pre-costed/Released/Settlement rule created | AM02 | Proactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00000983524540510060917200064070
| 24SDLN1 | Released | 2024-01-15 | 2024-03-04 | 2024-03-01 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0040 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC |  | 255 | No issue identified | 10062555 | GAS,LIQ;,IND,LPG,SNG9,P CYL,9KG | 4 | CYL | 4 | 0 | 4 | 2 | CYL | 22.03 - qty 6 SOH at AA02 | Supply for Order 100033847, Item 4 cannot be changed 9000261 item 900010 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | CYL |  |  |  | 180008157 | 9000261 | 07 | Execution | 0000132381 | 4 | 0 | CYL |  |  | 102000000002591 | 01-Road | 1000000904 |  | 3-In Transit |  | WorkPackLink | P07YRDBAY8 | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-01-15 | GRST-5000034672_2024 | 0 | 0 | 0 |  | 2024-03-02 | AA53 | 2024-03-06 |  |  | 2024-03-04 |  |  | 100000002877 | 1020 | 2025-10-01 | 4 | 4900034480_2024_0001/4900034480_2024_0003 |  | 2024-03-04 | 2024-03-04 |  | 5000034672_2024_0002/5000034672_2024_0001 | 0 | 2 | 0 | 4 | 0 | 180008157/180008157/180008157 | 3 | L | 4900034480 | 2024 |  | 5000034672 | 2024 |  |  | 2024-03-01 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062555 | GAS,LIQ;,IND,LPG,SNG9,P CYL,9KG |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 9000261_0090_0020/9000261_0090_0010 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90001524 |  | 99 |  | 4 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 40 |  |  | 0 | 4 | CYL | 2001 | AA02 | 2024-03-01 |  |  |  |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | SOH @ AA02 | [6 empty] | FALSE | 00001323814535510062555100033847
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-03-16 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0360 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | Shipped qty below requirement qty | 10062910 | SEALANT,SILASTIC,RTV732,CLEAR,CART | 60 | CQ | 18 | 64 | 70 | 0 |  | 05.04 - SOH @ AA01 | Supply for Order 100033847, Item 36 cannot be changed 90005862 item 70 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 360 |  | 14 |  | 0 |  |  |  | 0 | 0 | CQ |  |  |  | 180014018 | 9000598 | 07 | Execution | 0000132381 | 36 | 0 | [9 empty] | WorkPackLink |  | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 60 |  |  | Y | 1001 | 2024-01-15 | GRST-5000047022 | 13 | 0 | 0 |  | 2024-03-04 | AA53 | 2024-03-06 |  |  | 2024-03-19 |  |  | 100000005124 | 1020 | 2025-10-01 | 48 | 4900040867_2024_0011 |  | 2024-03-27 | 2024-03-19 |  | 5000047022_2024_0006 | 0 | 2 | 0 | 48 | 0 | 180014018/180014018 | 1 | L | 4900040867 | 2024 |  | 5000047022 | 2024 |  |  | 2024-03-16 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10062910 | SEALANT,SILASTIC,RTV732,CLEAR,CART |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 90005862_0070/9000598_0090_0010 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90005862 |  | 99 |  | 36 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 360 |  |  | 0 | 60 | CQ | 2001 | AA02 | 2024-03-16 |  |  |  |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | [7 empty] | Need Purchasing | 00001323814535710062910100033847
| 24SDLN1 | Released | 2024-01-15 | 2024-04-05 | 2024-04-03 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0380 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | Issue detected, please check message in derivation | 10204140 | BAG,PL;1200X900MM,200UM | 250 | EA | 815 | 170 | 60 | 0 |  | UserCommentLink | Supply for Order 100033847, Item 46 cannot be changed 90007104 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 460 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90007104 | 07 | Execution | 0000132381 | 46 | 0 | [9 empty] | WorkPackLink |  | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 250 |  |  | Y | 1001 | 2024-01-15 | ODST-0090007104_0010 | 1 | 0 | 0 |  | 2024-04-03 | AA53 | 2024-03-06 |  |  | 2024-04-06 |  |  |  |  | 2025-10-01 | 0 |  |  | 2024-04-03 | 2024-04-06 | B.Vorn TA |  | 0 | 2 | 0 | 0 | 0 |  | 1 | L |  | 0 |  |  | 0 |  |  | 2024-04-03 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204140 | BAG,PL;1200X900MM,200UM |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 90007104_0010 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90007104 |  | 99 |  | 46 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 460 |  |  | 0 | 250 | EA | 2001 | AA02 | 2024-04-03 |  |  |  |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | SOH @ AA02 | [6 empty] | FALSE | 00001323814538710204140100033847
| 24SDFR2 | Released | 2024-01-02 | 2024-04-22 | 2024-04-19 | 2024-04-16 | 2024-04-23 | MECH | 600001793 | 0010 | 0040 | 600001793 | MOC-89056 Fab/Weld Install 218UCV112 | AA53.2E1801 | EXCH,HEAT DE-ETH REBOIL FRACT2 | AA01 | 10 | No Issue identified | 10210152 | THINNER,PAINT;AKZO NOBEL,GTA007,20L | 1 | DR | 1 | 0 | 0 | 0 |  | 27.03 - 1 SOH @ AA02 | Supply for Order 600001793, Item 17 cannot be changed 90006857 item 50 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004605 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  |  | 90006857 | 06 | Scheduling | 0000084711 | 17 | 0 | [9 empty] | WorkPackLink |  | STONEHENGE S/D | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006857_0050 | 0 | 0 | 0 |  | 2024-04-20 | AA53 | 2024-04-22 |  |  | 2024-04-22 |  |  |  |  | 2024-12-15 | 0 |  |  | 2024-04-19 | 2024-04-22 | BLAST/PAINT |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-19 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10210152 | THINNER,PAINT;AKZO NOBEL,GTA007,20L |  | 0010 | Erect Scaffold Access | INT | Erect Scaffold Access | 0 |  | 90006857_0050 | [7 empty] | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 | 90006857 |  | 5 |  | 17 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000084095 | S002 | 30 | 30 | 5300004605 | 110 |  |  | 0 | 1 | DR | 2001 | AA02 | 2024-04-19 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84711 | 0 |  | 2 |  |  | RC00018003 | 2024-04-23 | 2024-04-16 | 2024-04-16 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Material shortage/Printed | AM06 | Capital |  | SOH @ AA02 | [6 empty] | FALSE | 00000847114540410210152600001793
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0180 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10242497 | TAPE,ADHESIVE;INS,50X3X9.14MM,ARMACELL | 5 | ROL | 74 | 0 | 0 | 0 |  | 26.02 - qty 74 SOH at AA02 | Supply for Order 100033847, Item 18 cannot be changed 90004487 item 160 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90004487 | 07 | Execution | 0000132381 | 18 | 0 | [9 empty] | WorkPackLink |  | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-01-15 | ODST-0090004487_0160 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  |  |  | 2025-10-01 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10242497 | TAPE,ADHESIVE;INS,50X3X9.14MM,ARMACELL |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 90004487_0160 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 18 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 |  | 30 | 5300004834 | 180 |  |  | 0 | 5 | ROL | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | SOH @ AA02 | [6 empty] | FALSE | 00001323814535710242497100033847
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-18 | 2024-04-23 | 2024-09-10 | WORK | 200064070 | 0010 | 0010 | 200064070 | 9Y F21 RECERTIFY SC PSV ROTABLE | AA53.218RV13 | PSV,2V1805 ON 2" LINE 2W41534 |  | 10 | No Issue identified | 10245543 | VALVE,REL,FUKUI,REC371-(A)1D2,4000-5000 | 1 | EA | 3 | 0 | 0 | 0 |  | 29.01 - 3 SOH @ AA03 | Supply for Order 200064070, Item 5 cannot be changed 90006750 item 10 already exists | Material avail; awaiting work-packing @AA03 | SP12 | Stock at Base | 0 | AA03 | 5300005080 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006750 | 05 | Preparation | 0000098352 | 5 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-17 | ODST-0090006750_0010 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-07-03 | 0 |  |  | 2024-04-18 | 2024-04-23 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-18 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10245543 | VALVE,REL,FUKUI,REC371-(A)1D2,4000-5000 |  | 0010 | CERTIFY PSV | INT | CERTIFY PSV | 5 |  | 90006750_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006750 |  | 5 |  | 5 |  | 0 |  | 24SDFR2 | MJ | AU1098 | 1000097789 | S003 | 30 | 30 | 5300005080 | 10 |  |  | 0 | 1 | EA | 2001 | AA03 | 2024-04-18 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 98352 | 0 |  | 2 |  |  | RC00025003 | 2024-09-10 | 2024-04-23 | 2024-04-23 | Material shortage/Date set by external system/Object created/Pre-costed/Released/Settlement rule created | AM02 | Proactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00000983524540510245543200064070
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | WORK | 200090588 | 0010 | 0010 | 200090588 | 6Y RECERTIFY PSV ROTABLE | AA53.407RV501 | PSV,GAS TURBINE GT4007 |  | 10 | No Issue identified | 10255659 | VALVE,REL,AGCO 81PSF88-8,OIL,SET 1200KPA | 1 | EA | 0 | 2 | 0 | 0 |  | 26.02 - To be changed out INSITU per Stan Vaccaro | Supply for Order 200090588, Item 4 cannot be changed 90000261 item 10 already exists | Material avail; awaiting work-packing @AA03 | SP12 | Stock at Base | 0 | AA03 | 5300005163 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000261 | 05 | Preparation | 0000128817 | 4 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-17 | ODST-0090000261_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-06-30 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255659 | VALVE,REL,AGCO 81PSF88-8,OIL,SET 1200KPA |  | 0010 | Certify PSV | INT | Certify PSV | 5 |  | 90000261_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000261 |  | 5 |  | 4 |  | 0 |  | 24SDGT7 | MJ | AU1098 | 1000128267 | S003 | 30 | 30 | 5300005163 | 10 |  |  | 0 | 1 | EA | 2001 | AA03 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128817 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance | [8 empty] | 0 | 00001288174541510255659200090588
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-16 | 2024-04-23 | MECH | 600001793 | 0170 |  | 600001793 | MOC-89056 Fab/Weld Install 218UCV112 | AA53.2E1801 | EXCH,HEAT DE-ETH REBOIL FRACT2 | AA01 | 10 | No Issue identified | 10257642 | GLAND,CABLE,E1EX-00,EX(DE),SIZE 00-20SS | 2 | EA | 33 | 0 | 0 | 0 |  | 25.01 - 33 SOH @ AA02 | Supply for Order 600001793, Item 9 cannot be changed 90006878 item 50 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004605 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006878 | 06 | Scheduling | 0000084711 | 9 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006878_0050 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-15 | 0 |  |  | 2024-04-20 | 2024-04-23 | 218UCV112 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10257642 | GLAND,CABLE,E1EX-00,EX(DE),SIZE 00-20SS |  | 0170 | Complete Final Hook-Up | INT | Complete Final Hook-Up | 5 |  | 90006878_0050 | [7 empty] | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 | 90006878 |  | 5 |  | 9 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000084095 | S002 | 30 | 30 | 5300004605 | 50 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84711 | 0 |  | 2 |  |  | RC00018003 | 2024-04-23 | 2024-04-16 | 2024-04-16 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Material shortage/Printed | AM06 | Capital |  | SOH @ AA02 | [6 empty] | FALSE | 00000847114540510257642600001793
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | WORK | 200089855 | 0020 | 0020 | 200089855 | 6Y RECERTIFY PSV ROTABLE | AA53.408RV501 | PSV,GAS TURB GT4008 | AA01 | 10 | No Issue identified | 10257883 | SGK,VV,SAF REL;AGCO 044805032 | 1 | KIT | 0 | 0 | 0 | 0 |  | 22.03 - qty 8 SOH at AA01 | Supply for Order 200089855, Item 2 cannot be changed 90000290 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003916 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90000290 | 05 | Preparation | 0000128133 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000290_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-06-30 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200618972 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10257883 | SGK,VV,SAF REL;AGCO 044805032 |  | 0020 | Remove / Install PSV | INT | Remove / Install PSV | 5 |  | 90000290_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000290 |  | 5 |  | 2 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000127524 | S002 | 30 | 10 | 5300003916 | 20 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128133 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | [8 empty] | 8 | 00001281334542710257883200089855
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | WORK | 200090101 | 0020 | 0020 | 200090101 | 6Y RECERTIFY PSV ROTABLE | AA53.410RV501 | PSV,GT4010 LUBEOIL TANK | AA01 | 10 | No Issue identified | 10257883 | SGK,VV,SAF REL;AGCO 044805032 | 1 | KIT | 0 | 0 | 0 | 0 |  | 22.03 - qty 8 SOH at AA01 | Supply for Order 200090101, Item 2 cannot be changed 90000107 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003981 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90000107 | 05 | Preparation | 0000128339 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000107_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-06-30 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200620642 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10257883 | SGK,VV,SAF REL;AGCO 044805032 |  | 0020 | Remove / Install PSV | INT | Remove / Install PSV | 5 |  | 90000107_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000107 |  | 5 |  | 2 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000127750 | S002 | 30 | 10 | 5300003981 | 20 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128339 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance | [8 empty] | 8 | 00001283394541510257883200090101
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | WORK | 200090588 | 0020 | 0020 | 200090588 | 6Y RECERTIFY PSV ROTABLE | AA53.407RV501 | PSV,GAS TURBINE GT4007 | AA01 | 10 | No Issue identified | 10257883 | SGK,VV,SAF REL;AGCO 044805032 | 1 | KIT | 0 | 0 | 0 | 0 |  | 22.03 - qty 8 SOH at AA01 | Supply for Order 200090588, Item 2 cannot be changed 90000259 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004073 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90000259 | 05 | Preparation | 0000128817 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000259_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-06-30 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200616814 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10257883 | SGK,VV,SAF REL;AGCO 044805032 |  | 0020 | Remove / Install PSV | INT | Remove / Install PSV | 5 |  | 90000259_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000259 |  | 5 |  | 2 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000128267 | S002 | 30 | 10 | 5300004073 | 20 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128817 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance | [8 empty] | 8 | 00001288174541510257883200090588
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-03-16 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0280 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10258211 | WASHER,NEOPRENE,10GGE,TEK SCREW TYPE | 100 | EA | 8230 | 0 | 100 | 48 | CQ | 11.03 - SOH @ AA02 | Supply for Order 100033847, Item 28 cannot be changed 9000598 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 280 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180014018 | 9000598 | 07 | Execution | 0000132381 | 28 | 0 | CQ | 102000000003759 |  | 102000000003599 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | KSF-KGP P07P08 SML | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 100 |  |  | Y | 1001 | 2024-01-15 | GRST-5000047022_2024 | 13 | 0 | 0 |  | 2024-03-04 | AA53 | 2024-03-06 |  |  | 2024-03-19 |  |  | 100000005124 | 1020 | 2025-10-01 | 100 | 4900040867_2024_0001 |  | 2024-03-27 | 2024-03-19 |  | 5000047022_2024_0001 | 0 | 2 | 0 | 100 | 0 | 180014018 | 3 | L | 4900040867 | 2024 |  | 5000047022 | 2024 |  |  | 2024-03-16 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258211 | WASHER,NEOPRENE,10GGE,TEK SCREW TYPE |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 9000598_0010 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90005862 |  | 99 |  | 28 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 280 |  |  | 0 | 100 | EA | 2001 | AA02 | 2024-03-16 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | SOH @ AA02 | [6 empty] | FALSE | 00001323814535710258211100033847
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100044897 | 0010 | 0012 | 100044897 | UPS Battery Cell replace GT4010 | AA53.B35H8BAT1 | BATT,BANKS G4010 110VDC B8342 | AA01 | 30 | No Issue identified | 10260114 | BATTERY,NICAD;SAFT SBM740 | 1 | EA | 1 | 0 | 0 | 0 |  | 09.02 - 1 SOH @ AA02 | Supply for Order 100044897, Item 1 cannot be changed 90000097 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300002444 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000097 | 05 | Preparation | 0000143429 | 1 | 0 | [9 empty] | WorkPackLink |  | AU01-P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000097_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2020-05-22 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10260114 | BATTERY,NICAD;SAFT SBM740 |  | 0010 | Replace UPS Battery Cell GT4010 | INT | Replace UPS Battery Cell GT4010 | 5 |  | 90000097_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000097 |  | 30 |  | 1 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000142779 | S002 | 30 | 30 | 5300002444 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 143429 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material shortage/Printed | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001434294541510260114100044897
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-18 | 2024-04-23 | 2024-09-09 | WORK | 200089032 | 0010 | 0010 | 200089032 | 6Y F21 RECERTIFY SC PILOT PSV ROTABLE | AA53.218RV97AP | PSV,PILOT PROP TRANS SURGE DRUM |  | 10 | No Issue identified | 10264996 | VALVE,REL,PLT,AGCO 200,1896KPAG | 1 | EA | 16 | 0 | 0 | 0 |  | 12.03 - qty 16 SOH at AA03 |  | Material avail; awaiting work-packing @AA03 | SP12 | Stock at Base | 0 | AA03 | 5300005156 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006751 | 05 | Preparation | 0000127310 | 3 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-17 | ODST-0090006751_0010 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-10-30 | 0 |  |  | 2024-04-18 | 2024-04-23 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-18 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10264996 | VALVE,REL,PLT,AGCO 200,1896KPAG |  | 0010 | CERTIFY PSV | INT | CERTIFY PSV |  |  | 90006751_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006751 |  | 5 |  | 3 |  | 0 |  | 24SDFR2 | MJ | AU1098 | 1000126741 | S003 | 30 | 30 | 5300005156 | 10 |  |  | 0 | 1 | EA | 2001 | AA03 | 2024-04-18 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127310 | 0 |  | 3 |  |  | RC00025003 | 2024-09-09 | 2024-04-23 | 2024-04-23 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001273104540510264996200089032
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-18 | 2024-04-23 | 2024-09-09 | WORK | 200089034 | 0010 | 0010 | 200089034 | 6Y F21 RECERTIFY SC PILOT PSV ROTABLE | AA53.218RV97BP | PSV,PILOT PROP TRANS SURGE DRUM |  | 10 | No Issue identified | 10264996 | VALVE,REL,PLT,AGCO 200,1896KPAG | 1 | EA | 16 | 0 | 0 | 0 |  | 12.03 - qty 16 SOH at AA03 |  | Material avail; awaiting work-packing @AA03 | SP12 | Stock at Base | 0 | AA03 | 5300005157 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006752 | 05 | Preparation | 0000127312 | 3 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-17 | ODST-0090006752_0010 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-10-30 | 0 |  |  | 2024-04-18 | 2024-04-23 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-18 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10264996 | VALVE,REL,PLT,AGCO 200,1896KPAG |  | 0010 | CERTIFY PSV | INT | CERTIFY PSV |  |  | 90006752_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006752 |  | 5 |  | 3 |  | 0 |  | 24SDFR2 | MJ | AU1098 | 1000126743 | S003 | 30 | 30 | 5300005157 | 10 |  |  | 0 | 1 | EA | 2001 | AA03 | 2024-04-18 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127312 | 0 |  | 3 |  |  | RC00025003 | 2024-09-09 | 2024-04-23 | 2024-04-23 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released | AM02 | Proactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001273124540510264996200089034
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-07 | ROTAT | 200083164 | 0030 | 0090 | 200083164 | 1Y GT4007 TURB VSV REPLACEMENT | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | Shipped qty below requirement qty | 10297385 | BOLT;GE 1855M35P08 | 120 | EA | 0 | 0 | 50 | 50 | EA | 03.04 - In Transit MOT 20115 Air Freight ETA PDC 09.04.24 PO 4510780474 x 240 | Supply for Order 200083164, Item 9 cannot be changed 90000252 item 90 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003891 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004062 | 9000312 | 05 | Preparation | 0000120013 | 9 | 0 | EA | 102000000000357 | 102000000000416 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 120 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015639_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-05-20 | 50 | 4900030155_2024_0015 |  | 2024-02-09 | 2024-05-03 | GT7 VSV blt | 5000015639_2024_0008 | 0 | 2 | 0 | 50 | 0 | 180004062 | 1 | L | 4900030155 | 2024 |  | 5000015639 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297385 | BOLT;GE 1855M35P08 |  | 0030 | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | INT | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | 5 | Ready for Release | 90000252_0090/9000312_0090 | [7 empty] | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000252 |  | 20 |  | 9 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000119503 | S002 |  | 30 | 5300003891 | 90 |  |  | 0 | 120 | EA | 2001 | AA02 | 2024-04-30 |  | Ready for Release | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120013 | 0 |  | 1 |  |  | RC00025003 | 2024-05-07 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | In Transit to PDC from Vendor | [6 empty] | 0
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-01 | 2024-05-15 | 2024-05-15 | ROTAT | 200083165 | 0030 | 0090 | 200083165 | 1Y GT4008 TURB VSV REPLACEMENT | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | No Issue identified | 10297385 | BOLT;GE 1855M35P08 | 120 | EA | 0 | 0 | 50 | 0 |  | 03.04 - In Transit MOT 20115 Air Freight ETA PDC 09.04.24 PO 4510780474 x 240 | Supply for Order 200083165, Item 9 cannot be changed 90000278 item 60 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003892 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000278 | 05 | Preparation | 0000120014 | 9 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 120 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000278_0060 | 0 | 0 | 0 |  | 2024-05-02 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-05-20 | 0 |  |  | 2024-05-01 | 2024-05-04 | GT4008 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-01 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297385 | BOLT;GE 1855M35P08 |  | 0030 | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | INT | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | 5 |  | 90000278_0060 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000278 |  | 20 |  | 9 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000119504 | S002 |  | 30 | 5300003892 | 90 |  |  | 0 | 120 | EA | 2001 | AA02 | 2024-05-01 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120014 | 0 |  | 1 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | In Transit to PDC from Vendor | [6 empty] | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-04 | ROTAT | 100040480 | 0010 | 0050 | 100040480 | GT4010 - Replace bushes and bell cranks | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 255 | No Issue identified | 10297503 | BELLCRANK,COMP;GE L69684P01 | 12 | EA | 9 | 3 | 0 | 3 | EA | 28.02 - 9 SOH @ AA02 , 3 24SDGT10-SW3R02B01B | Supply for Order 100040480, Item 5 cannot be changed 90000080 item 20 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300002226 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006809 | 9000349 | 05 | Preparation | 0000139004 | 5 | 0 | EA | 102000000000133 | 102000000000162 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006809 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000003162 | 1020 | 2023-04-27 | 3 | 4900033163_2024_0003 |  | 2024-02-27 | 2024-05-03 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006809 | 3 | L | 4900033163 | 2024 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297503 | BELLCRANK,COMP;GE L69684P01 |  | 0010 | GT4010 - Replace Bushes & Bell Cranks | ENON | GT4010 - Replace Bushes & Bell Cranks | 5 |  | 90000080_0020/9000349_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000080 |  | 99 |  | 5 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000138355 | S002 |  | 30 | 5300002226 | 20 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139004 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance | [8 empty] | Need Purchasing | 00001390044541510297503100040480
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-23 | 2024-09-09 | WORK | 200089031 | 0004 | 0010 | 200089031 | 6Y F21 RECERTIFY SC MAIN PSV TURNAROUND | AA53.218RV97A | PSV,PROPANE TRANSFER SURGE DRUM | AA01 | 10 | No Issue identified | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 1 | EA | 26 | 1 | 28 | 0 |  | 01.04 - 27 SOH @ AA02, 26 SOH @ AA01 |  | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004094 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006876 | 05 | Preparation | 0000127309 | 4 | 0 | [9 empty] | WorkPackLink |  | 200089031 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006876_0010 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-10-30 | 0 |  |  | 2024-04-20 | 2024-04-23 | T24-SD-P07 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L |  | 0004 | Remove & Replace PSV | INT | Remove & Replace PSV |  |  | 90006876_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006876 |  | 5 |  | 4 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000126680 | S002 | 30 | 30 | 5300004094 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127309 | 0 |  | 3 |  |  | RC00025003 | 2024-09-09 | 2024-04-23 | 2024-04-23 | Material committed/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001273094540510305744200089031
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-23 | 2024-09-12 | WORK | 200089033 | 0110 | 0010 | 200089033 | 6Y F21 RECERTIFY SC MAIN PSV TURNAROUND | AA53.218RV97B | PSV,PROPANE TRANSFER SURGE DRUM | AA01 | 10 | No Issue identified | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L | 16 | EA | 26 | 1 | 28 | 0 |  | 01.04 - 27 SOH @ AA02, 26 SOH @ AA01 |  | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004098 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006877 | 05 | Preparation | 0000127311 | 4 | 0 | [9 empty] | WorkPackLink |  | 200089033 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006877_0010 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-10-30 | 0 |  |  | 2024-04-20 | 2024-04-23 | T24-SD-P07 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10305744 | GASKET,SW;CRIR,80MM,CL300/600,RF,316L |  | 0110 | Remove & Replace PSV | INT | Remove & Replace PSV |  |  | 90006877_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006877 |  | 5 |  | 4 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000126742 | S002 | 30 | 30 | 5300004098 | 40 |  |  | 0 | 16 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127311 | 0 |  | 3 |  |  | RC00025003 | 2024-09-12 | 2024-04-23 | 2024-04-23 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001273114540510305744200089033
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-23 | 2024-09-14 | VALVE | 100040576 | 0010 | 0030 | 100040576 | CV-OH 2" 300# 218PCV507 | AA53.218PCV507 | VALVE,2K1820E1 L/O PRESS CTRL | AA01 | 20 | No Issue identified | 10306122 | RING;BOX,PACKING,SS,FISHER 1J873235072 | 1 | EA | 1 | 0 | 0 | 0 |  | 13.03 - 1 SOH @ AA02 | Supply for Order 100040576, Item 1 cannot be changed 90006873 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300002248 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006873 | 05 | Preparation | 0000139148 | 1 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006873_0010 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-31 | 0 |  |  | 2024-04-20 | 2024-04-23 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10306122 | RING;BOX,PACKING,SS,FISHER 1J873235072 |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90006873_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006873 |  | 20 |  | 1 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000138478 | S002 |  | 30 | 5300002248 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139148 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Released/Pre-costed/Order Approved/Date set by external system/Settlement rule created/Object created/Printed/Material shortage | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001391484540510306122100040576
| 24SDLN1 | Released | 2024-03-25 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-04 | VALVE | 100074551 | 0010 | 0020 | 100074551 | replace valve on URCA skid Accumulator | AA53.114URCAHYD | PKG EQ,HYD PWR PACK 114URCA62/68/72/76 |  | 255 | No Issue identified | 10423729 | GAS,COMP;N2,IND GDE,EHP 99.5%,G2,MOP16 | 1 | SET | 1 | 0 | 0 | 0 |  | 26.03 - 1 SOH @ AA02 | Supply for Order 100074551, Item 2 cannot be changed 90006610 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300008323 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90006610 | 05 | Preparation | 0000226613 | 2 | 0 | [9 empty] | WorkPackLink |  | T24-W1-LN1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-03-25 | ODST-0090006610_0020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2026-03-03 | 0 |  |  | 2024-04-30 | 2024-05-03 | 100074551 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10423729 | GAS,COMP;N2,IND GDE,EHP 99.5%,G2,MOP16 |  | 0010 | Clean Oil & De-Pressure Accumulator | INT | Clean Oil & De-Pressure Accumulator |  |  | 90006610_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006610 |  | 99 |  | 2 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000223992 | S002 | 30 | 30 | 5300008323 | 20 |  |  | 0 | 1 | SET | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-03-13 | 226613 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00002266134541510423729100074551
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-23 | 2024-09-14 | VALVE | 100040576 | 0010 | 0082 | 100040576 | CV-OH 2" 300# 218PCV507 | AA53.218PCV507 | VALVE,2K1820E1 L/O PRESS CTRL | AA01 | 20 | No Issue identified | 10430134 | GASKET;FISHER 1R3298X0032 | 1 | EA | 1 | 0 | 0 | 0 |  | 10.03 - 1 SOH @ AA02 | Supply for Order 100040576, Item 10 cannot be changed 90006873 item 50 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300002248 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006873 | 05 | Preparation | 0000139148 | 10 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006873_0050 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-31 | 0 |  |  | 2024-04-20 | 2024-04-23 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10430134 | GASKET;FISHER 1R3298X0032 |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90006873_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006873 |  | 20 |  | 10 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000138478 | S002 | 30 | 30 | 5300002248 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139148 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Released/Pre-costed/Order Approved/Date set by external system/Settlement rule created/Object created/Printed/Material shortage | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001391484540510430134100040576
| 24SD3410 | Released | 2024-02-01 | 2024-02-29 | 2024-02-28 | 2024-05-06 | 2024-05-06 | INLEC | 100038540 | 0020 | 0020 | 100038540 | Inspect & Clean Parital Discharge S50C1A | AA53.S50C1A02 | START,KM3410A LNG BOIL OFF COMPRESSOR | AA01 | 255 | No issue identified | 10431318 | TAPE,SELF AMALGAMATING;3M 05400715025 | 5 | ROL | 1 | 0 | 0 | 0 |  | 13.03 - 5 SOH 2 AA01 | Supply for Order 100038540, Item 2 cannot be changed 90002726 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300007202 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  |  | 90002726 | 05 | Preparation | 0000137044 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-02-27 | ODST-0090002726_0020 | 2 | 0 | 0 |  | 2024-02-27 | AA53 | 2024-05-06 |  |  | 2024-03-02 |  |  |  |  | 2024-12-01 | 0 |  |  | 2024-02-28 | 2024-03-02 | AU01.S50C1A0 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10431318 | TAPE,SELF AMALGAMATING;3M 05400715025 |  | 0020 | Complete Inspection/Clean | INT | Complete Inspection/Clean | 5 |  | 90002726_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90002726 |  | 99 |  | 2 |  | 0 |  | 24SD3410 | MJ | AU1072 | 1000136415 | S002 | 30 | 30 | 5300007202 | 20 |  |  | 0 | 5 | ROL | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 137044 | 0 |  | 3 |  |  | RC00025003 | 2024-05-06 | 2024-05-06 | 2024-05-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance | [8 empty] | Need Purchasing | 00001370444535110431318100038540
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | ROTAT | 200070157 | 0020 | 0010 | 200070157 | 2Y G4009 AIR SYSTEM FILTERS CHANGE OUT | AA53.G4009S2 | FILT,GENERATOR INLET AIR GT4009 | AA01 | 20 | No Issue identified | 10434976 | FILTER ELEM,AIR,DONALDSON P902840 | 32 | EA | 230 | 0 | 0 | 0 |  | 15.01 - 230 SOH @ AA02 | Supply for Order 200070157, Item 1 cannot be changed 90000425 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003716 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000425 | 05 | Preparation | 0000104459 | 1 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000425_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-10-31 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10434976 | FILTER ELEM,AIR,DONALDSON P902840 |  | 0020 | REPLACE GENERATOR AIR FILTERS | INT | REPLACE GENERATOR AIR FILTERS | 5 |  | 90000425_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000425 |  | 20 |  | 1 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000103876 | S002 | 30 | 30 | 5300003716 | 10 |  |  | 0 | 32 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 104459 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001044594543110434976200070157
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 200070297 | 0020 | 0010 | 200070297 | 2Y G4008 AIR SYSTEM FILTERS CHANGE OUT | AA53.G4008S2 | FILT,GENERATOR INLET AIR G4008 | AA01 | 20 | No Issue identified | 10434976 | FILTER ELEM,AIR,DONALDSON P902840 | 32 | EA | 230 | 0 | 0 | 0 |  | 15.01 - 230 SOH @ AA02 | Supply for Order 200070297, Item 1 cannot be changed 90000276 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003745 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000276 | 05 | Preparation | 0000104646 | 1 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000276_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-06-08 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10434976 | FILTER ELEM,AIR,DONALDSON P902840 |  | 0020 | REPLACE GENERATOR AIR FILTERS | INT | REPLACE GENERATOR AIR FILTERS | 5 |  | 90000276_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000276 |  | 20 |  | 1 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000104016 | S002 | 30 | 30 | 5300003745 | 10 |  |  | 0 | 32 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 104646 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001046464542710434976200070297
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 200083436 | 0020 | 0010 | 200083436 | 2Y G4010 AIR SYSTEM FILTERS CHANGE OUT | AA53.G4010S2 | FILT,GENERATOR INLET AIR GT4010 | AA01 | 20 | No Issue identified | 10434976 | FILTER ELEM,AIR,DONALDSON P902840 | 32 | EA | 230 | 0 | 0 | 0 |  | 15.01 - 230 SOH @ AA02 | Supply for Order 200083436, Item 1 cannot be changed 90000109 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003951 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000109 | 05 | Preparation | 0000120885 | 1 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000109_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-05-14 | 0 |  |  | 2024-04-30 | 2024-05-03 | GT4010 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10434976 | FILTER ELEM,AIR,DONALDSON P902840 |  | 0020 | REPLACE GENERATOR AIR FILTERS | INT | REPLACE GENERATOR AIR FILTERS | 5 |  | 90000109_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000109 |  | 20 |  | 1 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000120238 | S002 | 30 | 30 | 5300003951 | 10 |  |  | 0 | 32 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120885 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001208854541510434976200083436
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | ROTAT | 200070157 | 0020 | 0020 | 200070157 | 2Y G4009 AIR SYSTEM FILTERS CHANGE OUT | AA53.G4009S2 | FILT,GENERATOR INLET AIR GT4009 | AA01 | 20 | No Issue identified | 10435942 | ELEMENT,FLT;AIR,26",DONALD P902842 | 32 | EA | 0 | 0 | 0 | 0 |  | 15.01 - 774 SOH @ AA01 | Supply for Order 200070157, Item 2 cannot be changed 90000425 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003716 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000425 | 05 | Preparation | 0000104459 | 2 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000425_0020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-10-31 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10435942 | ELEMENT,FLT;AIR,26",DONALD P902842 |  | 0020 | REPLACE GENERATOR AIR FILTERS | INT | REPLACE GENERATOR AIR FILTERS | 5 |  | 90000425_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000425 |  | 20 |  | 2 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000103876 | S002 | 30 | 30 | 5300003716 | 20 |  |  | 0 | 32 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 104459 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | [8 empty] | 742 | 00001044594543110435942200070157
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 200070297 | 0020 | 0020 | 200070297 | 2Y G4008 AIR SYSTEM FILTERS CHANGE OUT | AA53.G4008S2 | FILT,GENERATOR INLET AIR G4008 | AA01 | 20 | No Issue identified | 10435942 | ELEMENT,FLT;AIR,26",DONALD P902842 | 32 | EA | 0 | 0 | 0 | 0 |  | 15.01 - 774 SOH @ AA01 | Supply for Order 200070297, Item 2 cannot be changed 90000276 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003745 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000276 | 05 | Preparation | 0000104646 | 2 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000276_0020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-06-08 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10435942 | ELEMENT,FLT;AIR,26",DONALD P902842 |  | 0020 | REPLACE GENERATOR AIR FILTERS | INT | REPLACE GENERATOR AIR FILTERS | 5 |  | 90000276_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000276 |  | 20 |  | 2 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000104016 | S002 | 30 | 30 | 5300003745 | 20 |  |  | 0 | 32 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 104646 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance | [8 empty] | 742 | 00001046464542710435942200070297
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 200083436 | 0020 | 0020 | 200083436 | 2Y G4010 AIR SYSTEM FILTERS CHANGE OUT | AA53.G4010S2 | FILT,GENERATOR INLET AIR GT4010 | AA01 | 20 | No Issue identified | 10435942 | ELEMENT,FLT;AIR,26",DONALD P902842 | 32 | EA | 0 | 0 | 0 | 0 |  | 15.01 - 774 SOH @ AA01 | Supply for Order 200083436, Item 2 cannot be changed 90000109 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003951 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000109 | 05 | Preparation | 0000120885 | 2 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000109_0020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-05-14 | 0 |  |  | 2024-04-30 | 2024-05-03 | GT4010 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10435942 | ELEMENT,FLT;AIR,26",DONALD P902842 |  | 0020 | REPLACE GENERATOR AIR FILTERS | INT | REPLACE GENERATOR AIR FILTERS | 5 |  | 90000109_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000109 |  | 20 |  | 2 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000120238 | S002 | 30 | 30 | 5300003951 | 20 |  |  | 0 | 32 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120885 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance | [8 empty] | 742 | 00001208854541510435942200083436
| 24SD3410 | Released | 2024-02-27 | 2024-03-02 | 2024-02-28 | 2024-05-06 | 2024-05-06 | INLEC | 100072705 | 0020 | 0010 | 100072705 | MoC-49660 - K3410A Seal Vulnerability | AA53.134PDT503 | TX,DIFF PRESS S/O PUMP AUTO START | AA01 | 20 | Shipped qty below requirement qty | 10452627 | TX,DP;RG4,SMART,EXIA,EMERSON 3051S1 | 2 | EA | 0 | 0 | 1 | 1 | EA | 12.03 - INLEC to check squirrel store 1 item ETA 20.06.24 PO W451780404 | Supply for Order 100072705, Item 1 cannot be changed 90002681 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300007233 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180007934 | 9000381 | 05 | Preparation | 0000219271 | 1 | 0 | EA | 102000000002355 |  | 102000000002484 | 01-Road | 20000363 |  | 2-Loaded |  | WorkPackLink | P07YRDBAY8 | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-02-27 | GRST-5000029191_2024 | 0 | 0 | 0 |  | 2024-02-29 | AA53 | 2024-05-06 |  |  | 2024-03-02 |  |  | 100000003411 | 1020 | 2024-10-05 | 1 | 4900034037_2024_0001 |  | 2024-03-01 | 2024-03-02 | 134PT503,505 | 5000029191_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180007934 | 1 | L | 4900034037 | 2024 |  | 5000029191 | 2024 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10452627 | TX,DP;RG4,SMART,EXIA,EMERSON 3051S1 |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90002681_0010/9000381_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90002681 |  | 20 |  | 1 |  | 0 |  | 24SD3410 | MJ | AU1072 | 1000217166 | S002 | 30 | 30 | 5300007233 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-02-07 | 219271 | 0 |  | 1 |  |  | RC00025003 | 2024-05-06 | 2024-05-06 | 2024-05-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | Material Handed to Maintenance | [6 empty] | 0
| 24SDLN1 | Released | 2024-03-25 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-04 | VALVE | 100074551 | 0010 | 0010 | 100074551 | replace valve on URCA skid Accumulator | AA53.114URCAHYD | PKG EQ,HYD PWR PACK 114URCA62/68/72/76 | AA01 | 255 | No Issue identified | 10453021 | OIL,HYD;SHELL TELLUS S2 VX 46,20L | 2 | CON | 34 | 0 | 0 | 0 |  | 26.03 - 34 SOH @ AA02 | Supply for Order 100074551, Item 1 cannot be changed 90006610 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300008323 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | CON |  |  |  |  | 90006610 | 05 | Preparation | 0000226613 | 1 | 0 | [9 empty] | WorkPackLink |  | T24-W1-LN1-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-03-25 | ODST-0090006610_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2026-03-03 | 0 |  |  | 2024-04-30 | 2024-05-03 | 100074551 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10453021 | OIL,HYD;SHELL TELLUS S2 VX 46,20L |  | 0010 | Clean Oil & De-Pressure Accumulator | INT | Clean Oil & De-Pressure Accumulator |  |  | 90006610_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006610 |  | 99 |  | 1 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000223992 | S002 | 30 | 30 | 5300008323 | 10 |  |  | 0 | 2 | CON | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-03-13 | 226613 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Pre-costed/Object created/Date set by external system/Order Approved/Released/Material shortage/Settlement rule created | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00002266134541510453021100074551
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0190 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10461586 | PLUG,TUBE;BLANKING,PL,1.00",BLK | 600 | EA | 250 | 0 | 0 | 0 |  | 01.04 - 103/105 Complete for qty 350, 250 in stock @ AA02 | Supply for Order 100033847, Item 19 cannot be changed 90004487 item 170 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90004487 | 07 | Execution | 0000132381 | 19 | 0 | [9 empty] | WorkPackLink |  | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 600 |  |  | Y | 1001 | 2024-01-15 | ODST-0090004487_0170 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  |  |  | 2025-10-01 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10461586 | PLUG,TUBE;BLANKING,PL,1.00",BLK |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 90004487_0170 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 19 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 190 |  |  | 0 | 600 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | [7 empty] | Need Purchasing | 00001323814535710461586100033847
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-16 | 2024-05-19 | 2024-05-19 | ROTAT | 100040408 | 0030 | 0030 | 100040408 | MV-RE 40NB 300# 409BAV0034 GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 255 | No Issue identified | 10473763 | OIL,LUB;MOBIL JET OIL II,208L | 1 | DR | 0 | 0 | 3 | 0 |  | 01.04 - 101 COMPLETE IN SAP |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300002200 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR | [5 empty] | 05 | Preparation | 0000138900 | 5 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | STST-5300002200_00020 | 0 | 0 | 0 |  | 2024-05-17 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-06-08 | 0 |  |  | 2024-05-16 | 2024-05-19 | GT4009 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10473763 | OIL,LUB;MOBIL JET OIL II,208L |  | 0030 | Remove & Replace Valve | INT | Remove & Replace Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 99 |  | 5 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000138310 | S002 | 30 | 30 | 5300002200 | 20 |  |  | 0 | 1 | DR | 2001 | AA02 | 2024-05-16 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138900 | 0 |  | 2 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance | [8 empty] | 5 | 00001389004543110473763100040408
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-04 | ROTAT | 100040409 | 0031 | 0030 | 100040409 | MV-RE 40NB 300# 410BAV0034 GT4010 | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 255 | No Issue identified | 10473763 | OIL,LUB;MOBIL JET OIL II,208L | 1 | DR | 0 | 0 | 3 | 0 |  | 01.04 - 101 COMPLETE IN SAP |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006959 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR | [5 empty] | 05 | Preparation | 0000138961 | 5 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-21 | STST-5300006959_00010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-06-09 | 0 |  |  | 2024-04-30 | 2024-05-03 | 100040409 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10473763 | OIL,LUB;MOBIL JET OIL II,208L |  | 0031 | Remove & Replace Valve | INT | Remove & Replace Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 99 |  | 5 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000138311 | S002 | 30 | 30 | 5300006959 | 10 |  |  | 0 | 1 | DR | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138961 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance | [8 empty] | 5 | 00001389614541510473763100040409
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-04 | ROTAT | 100040411 | 0040 | 0010 | 100040411 | MV-RE 40NB 300# 407BAV0027 GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 255 | No Issue identified | 10473763 | OIL,LUB;MOBIL JET OIL II,208L | 1 | DR | 0 | 0 | 3 | 0 |  | 01.04 - 101 COMPLETE IN SAP |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006952 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR | [5 empty] | 05 | Preparation | 0000138963 | 5 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-21 | STST-5300006952_00010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-06-09 | 0 |  |  | 2024-04-30 | 2024-05-03 | 100040411 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10473763 | OIL,LUB;MOBIL JET OIL II,208L |  | 0040 | Punchlist & Closeout WP100040411MET001 | ENON | Punchlist & Closeout WP100040411MET001 | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 99 |  | 5 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000138313 | S002 | 30 | 30 | 5300006952 | 10 |  |  | 0 | 1 | DR | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138963 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance | [8 empty] | 5 | 00001389634541510473763100040411
| 24SDLN1 | Released | 2024-02-07 | 2024-05-02 | 2024-04-29 | 2024-04-26 | 2024-05-04 | VALVE | 100072016 | 0040 | 0050 | 100072016 | CV-OH 8" 600# 114PCV13 | AA53.114PCV13 | VALVE,PRESS CTRL 1E1405 | AA01 | 20 | No Issue identified | 10473950 | KIT,LIVE LOADING,VALTEK 094138.556.000 | 1 | KIT | 0 | 0 | 0 | 0 |  | IN GREY TUB |  | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006172 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90006608 | 05 | Preparation | 0000216559 | 5 | 0 | [9 empty] | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-07 | ODST-0090006608_0050 | 0 | 0 | 0 |  | 2024-04-30 | AA53 | 2024-05-02 |  |  | 2024-05-02 |  |  |  |  | 2024-07-22 | 0 |  |  | 2024-04-29 | 2024-05-02 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10473950 | KIT,LIVE LOADING,VALTEK 094138.556.000 |  | 0040 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind |  |  | 90006608_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006608 |  | 20 |  | 5 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000214974 | S002 | 30 | 30 | 5300006172 | 50 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-29 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPDGT | 2024-01-24 | 216559 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-04-26 | 2024-04-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance | M0-000001-99-01 | [7 empty] | 0 | 00002165594541410473950100072016
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-16 | 2024-04-23 | MECH | 600001793 | 0170 |  | 600001793 | MOC-89056 Fab/Weld Install 218UCV112 | AA53.2E1801 | EXCH,HEAT DE-ETH REBOIL FRACT2 | AA01 | 10 | No Issue identified | 10529603 | GLAND,CABLE;00-20SS,E1EXUQS,CCG 057200 | 2 | EA | 50 | 0 | 0 | 0 |  | 25.01 - 50 SOH @ AA02 | Supply for Order 600001793, Item 10 cannot be changed 90006878 item 60 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004605 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006878 | 06 | Scheduling | 0000084711 | 10 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006878_0060 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-15 | 0 |  |  | 2024-04-20 | 2024-04-23 | 218UCV112 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10529603 | GLAND,CABLE;00-20SS,E1EXUQS,CCG 057200 |  | 0170 | Complete Final Hook-Up | INT | Complete Final Hook-Up | 5 |  | 90006878_0060 | [7 empty] | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 | 90006878 |  | 5 |  | 10 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000084095 | S002 | 30 | 30 | 5300004605 | 60 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84711 | 0 |  | 2 |  |  | RC00018003 | 2024-04-23 | 2024-04-16 | 2024-04-16 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Material shortage/Printed | AM06 | Capital |  | SOH @ AA02 | [6 empty] | FALSE | 00000847114540510529603600001793
| 24SDFR2 | Released | 2024-01-02 | 2024-04-22 | 2024-04-19 | 2024-04-16 | 2024-04-23 | MECH | 600001793 | 0010 | 0030 | 600001793 | MOC-89056 Fab/Weld Install 218UCV112 | AA53.2E1801 | EXCH,HEAT DE-ETH REBOIL FRACT2 | AA01 | 10 | No Issue identified | 10536165 | ABRASIVE,BLAST;GARNET,25KG,PREMIUM | 6 | BAG | 43 | 0 | 2 | 0 |  | 21.03 - 200 SOH @ AA01, 45 SOH @ AA02 | Supply for Order 600001793, Item 15 cannot be changed 90006857 item 40 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004605 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | BAG |  |  |  |  | 90006857 | 06 | Scheduling | 0000084711 | 15 | 0 | [9 empty] | WorkPackLink |  | STONEHENGE S/D | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006857_0040 | 0 | 0 | 0 |  | 2024-04-20 | AA53 | 2024-04-22 |  |  | 2024-04-22 |  |  |  |  | 2024-12-15 | 0 |  |  | 2024-04-19 | 2024-04-22 | BLAST/PAINT |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-19 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10536165 | ABRASIVE,BLAST;GARNET,25KG,PREMIUM |  | 0010 | Erect Scaffold Access | INT | Erect Scaffold Access | 0 |  | 90006857_0040 | [7 empty] | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 | 90006857 |  | 5 |  | 15 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000084095 | S002 | 30 | 30 | 5300004605 | 100 |  |  | 0 | 6 | BAG | 2001 | AA02 | 2024-04-19 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84711 | 0 |  | 2 |  |  | RC00018003 | 2024-04-23 | 2024-04-16 | 2024-04-16 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Material shortage/Printed | AM06 | Capital |  | SOH @ AA02 | [6 empty] | FALSE | 00000847114540410536165600001793
| 24SDGT7 | Released | 2024-01-02 | 2024-05-06 | 2024-05-03 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0100 | 0140 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10539834 | NUT,SWIVEL;GE J1317P10B | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - In Transit MOT 20115 Air Freight, ETA 09.04.24 PO 4510765139 |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 310 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000099208 | 33 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | STST-5300003442_00310 | 0 | 0 | 0 |  | 2024-05-04 | AA53 | 2024-05-06 |  |  | 2024-05-06 |  |  |  |  | 2024-07-20 | 0 |  |  | 2024-05-03 | 2024-05-06 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-03 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10539834 | NUT,SWIVEL;GE J1317P10B |  | 0100 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 5 |  | 33 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 | 30 | 30 | 5300003442 | 310 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-03 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | In Transit to PDC from Vendor | [6 empty] | 0
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-16 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0100 | 0140 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10539834 | NUT,SWIVEL;GE J1317P10B | 1 | EA | 0 | 0 | 0 | 0 |  | 03.04 - In Transit MOT 20115 Air Freight, ETA 09.04.24 PO 4510765139 |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 310 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000105457 | 33 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | STST-5300004106_00310 | 0 | 0 | 0 |  | 2024-05-17 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-06-30 | 0 |  |  | 2024-05-16 | 2024-05-19 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-16 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10539834 | NUT,SWIVEL;GE J1317P10B |  | 0100 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 5 |  | 33 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 | 30 | 30 | 5300004106 | 310 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-16 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | In Transit to PDC from Vendor | [6 empty] | 0
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100040070 | 0020 | 0020 | 100040070 | MOC-119547 Replace meters S24H7 GT7 | AA53.S24H7 | SWBD,DIST 110VDC/240VAC UPS G4007 | AA01 | 20 | No Issue identified | 10542035 | TRANSFORMER;GE ICF100001371 | 1 | EA | 0 | 0 | 0 | 0 |  | 01.03 - In Transit MOT 20034 by AIR, ETA 10/03/24 |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006133 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000138591 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-06 | STST-5300006133_00010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2022-08-19 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10542035 | TRANSFORMER;GE ICF100001371 |  | 0020 | Replace panel meters S24H7 & TAUX/1 | INT | Replace panel meters S24H7 & TAUX/1 | [10 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 20 |  | 2 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000137960 | S002 | 30 | 30 | 5300006133 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138591 | 0 |  | 1 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance |  | In Transit to PDC from Vendor | [6 empty] | 0
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100043426 | 0010 | 0070 | 100043426 | MOC-119715 MCC Switch Replace S24D16A5RA | AA53.GT4007KM1B | MOTOR,TURB ACCOUST ENCL VENT FAN,GT4007 | AA01 | 30 | No Issue identified | 10545015 | SWITCH,FUSE;400A,3P,ABB 1SCA102413R1001 | 1 | EA | 0 | 0 | 0 | 0 |  | 28.02 - 2 SOH @ AA01 |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300001299 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000141927 | 7 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | STST-5300001299_00050 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2021-06-07 | 0 |  |  | 2024-04-30 | 2024-05-03 | S24D16A5RA |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10545015 | SWITCH,FUSE;400A,3P,ABB 1SCA102413R1001 |  | 0010 | Isolate & Disconnect S24D16A5RA | INT | Isolate & Disconnect S24D16A5RA | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 30 |  | 7 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000141296 | S002 | 30 | 30 | 5300001299 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141927 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance | [8 empty] | 1 | 00001419274541510545015100043426
| 24SD3410 | Released | 2024-02-01 | 2024-02-29 | 2024-02-28 | 2024-05-06 | 2024-05-06 | INLEC | 100038540 | 0020 | 0010 | 100038540 | Inspect & Clean Parital Discharge S50C1A | AA53.S50C1A02 | START,KM3410A LNG BOIL OFF COMPRESSOR | AA01 | 255 | No issue identified | 10547418 | INS,HEAT SHRINK;TUBE,RAYCHEM BPTM3012AU | 10 | M | 10 | 0 | 0 | 0 |  | 06.04 - 10 SOH @ AA02 | Supply for Order 100038540, Item 1 cannot be changed 90002726 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300007202 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 90002726 | 05 | Preparation | 0000137044 | 1 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-02-27 | ODST-0090002726_0010 | 2 | 0 | 0 |  | 2024-02-27 | AA53 | 2024-05-06 |  |  | 2024-03-02 |  |  |  |  | 2024-12-01 | 0 |  |  | 2024-02-28 | 2024-03-02 | AU01.S50C1A0 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10547418 | INS,HEAT SHRINK;TUBE,RAYCHEM BPTM3012AU |  | 0020 | Complete Inspection/Clean | INT | Complete Inspection/Clean | 5 |  | 90002726_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90002726 |  | 99 |  | 1 |  | 0 |  | 24SD3410 | MJ | AU1072 | 1000136415 | S002 | 30 | 30 | 5300007202 | 10 |  |  | 0 | 10 | M | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 137044 | 0 |  | 3 |  |  | RC00025003 | 2024-05-06 | 2024-05-06 | 2024-05-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001370444535110547418100038540
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0140 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC |  | 255 | No issue identified | 10569805 | MATERIAL,SHT;INS,1X15MX1.2MM | 5 | EA | 0 | 0 | 0 | 0 |  | 12.03 - 5 SOH @ AA01 | Supply for Order 100033847, Item 14 cannot be changed 90004487 item 120 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90004487 | 07 | Execution | 0000132381 | 14 | 0 | [9 empty] | WorkPackLink |  | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-01-15 | ODST-0090004487_0120 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  |  |  | 2025-10-01 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10569805 | MATERIAL,SHT;INS,1X15MX1.2MM |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 90004487_0120 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 14 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 140 |  |  | 0 | 5 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | [7 empty] | 0 | 00001323814535710569805100033847
| 24SDLN1 | Released | 2024-01-01 | 2024-03-31 | 2024-03-17 | 2024-05-03 | 2024-05-03 | INLEC | 100034626 | 0080 | 0020 | 100034626 | OPSD 1K1410 Turb Heat Det Fault 160TZ511 | AA53.160TZ511A | LOOP,HEAT DETECT 1KT1410 TURBINE COMPART | AA01 | 10 | No issue identified | 10572733 | TUBE;HEAT SHRINK,2.4MM,1.2M,TE RW175332X | 6 | EA | 6 | 0 | 0 | 0 |  | 01.04 - 103/105 COMPLETE, Scheduled for Delivery to AA02 | Supply for Order 100034626, Item 4 cannot be changed 90003651 item 30 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006043 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90003651 | 07 | Execution | 0000133118 | 4 | 0 | [9 empty] | WorkPackLink |  | P19 FLInlecs | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-02-04 | ODST-0090003651_0030 | 0 | 0 | 0 |  | 2024-03-18 | AA53 | 2024-05-03 |  |  | 2024-03-31 |  |  |  |  | 2023-09-24 | 0 |  |  | 2024-03-17 | 2024-03-20 | Buffer Stock |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-03-17 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10572733 | TUBE;HEAT SHRINK,2.4MM,1.2M,TE RW175332X |  | 0080 | Operation for Buffer Stock - wierd FL | INT | Operation for Buffer Stock - wierd FL |  | Opportune Shutdown | 90003651_0030 | [7 empty] | 0070 | Main Work Started (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90003651 |  | 10 |  | 4 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000132528 | S002 | 30 | 30 | 5300006043 | 30 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-03-17 |  | Opportune Shutdown |  |  | 1070 |  | 2024-02-03 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 133118 | 0 |  | 2 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Ready For Scheduling Canceled/Part printed/Job In Process/Partially confirmed/Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001331184538210572733100034626
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100037745 | 0020 | 0020 | 100037745 | Pressure Gauge Replace GT4007V5 | AA53.GT4007V5 | ACC,VESSEL HYD OIL GT4007 | AA01 | 20 | No Issue identified | 10581204 | GAUGE,PRESS;15000KPA,0.5",WIKA 68171340 | 1 | EA | 0 | 0 | 0 | 0 |  | 28.02 - 1 SOH @ AA01 |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006130 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000136197 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-06 | STST-5300006130_00010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-04-16 | 0 |  |  | 2024-04-30 | 2024-05-03 | GT40007V5 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10581204 | GAUGE,PRESS;15000KPA,0.5",WIKA 68171340 |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 20 |  | 2 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000135627 | S002 | 30 | 30 | 5300006130 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 136197 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance | [8 empty] | 1 | 00001361974541510581204100037745
| 24SDLN1 | Released | 2024-01-01 | 2024-03-31 | 2024-03-17 | 2024-05-03 | 2024-05-03 | INLEC | 100034626 | 0080 | 0030 | 100034626 | OPSD 1K1410 Turb Heat Det Fault 160TZ511 | AA53.160TZ511A | LOOP,HEAT DETECT 1KT1410 TURBINE COMPART | AA01 | 10 | No issue identified | 10586057 | RESISTOR;VISHAY RS02B5K000FE12 | 8 | EA | 8 | 0 | 0 | 0 |  | 01.04 - 103/105 COMPLETE, Scheduled for Delivery to AA02 | Supply for Order 100034626, Item 5 cannot be changed 90003651 item 40 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006043 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90003651 | 07 | Execution | 0000133118 | 5 | 0 | [9 empty] | WorkPackLink |  | P19 FLInlecs | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-02-04 | ODST-0090003651_0040 | 0 | 0 | 0 |  | 2024-03-18 | AA53 | 2024-05-03 |  |  | 2024-03-31 |  |  |  |  | 2023-09-24 | 0 |  |  | 2024-03-17 | 2024-03-20 | Buffer Stock |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-03-17 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10586057 | RESISTOR;VISHAY RS02B5K000FE12 |  | 0080 | Operation for Buffer Stock - wierd FL | INT | Operation for Buffer Stock - wierd FL |  | Opportune Shutdown | 90003651_0040 | [7 empty] | 0070 | Main Work Started (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90003651 |  | 10 |  | 5 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000132528 | S002 | 30 | 30 | 5300006043 | 40 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-03-17 |  | Opportune Shutdown |  |  | 1070 |  | 2024-02-03 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 133118 | 0 |  | 2 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Ready For Scheduling Canceled/Part printed/Job In Process/Partially confirmed/Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001331184538210586057100034626
| 24SDGT7 | Released | 2024-01-02 | 2024-05-04 | 2024-05-06 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0050 | 0090 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10589680 | GASKET;DRV CLUTCH,NP IRM426210101 | 1 | EA | 0 | 0 | 1 | 0 |  | 01.03 - In Transit MOT 20034 by Air, PO W451780583 x 1 Nuovo Pignone | Supply for Order 200064906, Item 9 cannot be changed 90000125 item 60 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000125 | 05 | Preparation | 0000099208 | 9 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000125_0060 | 5 | 0 | 0 |  | 2024-05-07 | AA53 | 2024-05-04 |  |  | 2024-05-09 |  |  |  |  | 2024-07-20 | 0 |  |  | 2024-05-06 | 2024-05-09 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10589680 | GASKET;DRV CLUTCH,NP IRM426210101 |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 90000125_0060 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000125 |  | 5 |  | 9 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 | 30 | 30 | 5300003442 | 80 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-06 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | In Transit to PDC from Vendor | [6 empty] | 0
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-07 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0080 | 0092 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10589680 | GASKET;DRV CLUTCH,NP IRM426210101 | 1 | EA | 0 | 0 | 1 | 0 |  | 01.03 - 1 SOH @ AA53 | Supply for Order 200082196, Item 15 cannot be changed 90000114 item 70 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000114 | 05 | Preparation | 0000117945 | 15 | 0 | [9 empty] | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000114_0070 | 7 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-03 |  |  | 2024-05-10 |  |  |  |  | 2024-06-30 | 0 |  |  | 2024-05-07 | 2024-05-10 | GT4010 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10589680 | GASKET;DRV CLUTCH,NP IRM426210101 |  | 0080 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 90000114_0070 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000114 |  | 5 |  | 15 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 | 30 | 30 | 5300003490 | 140 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance | [8 empty] | 0 | 00001179454541510589680200082196
| 24SD3410 | Released | 2024-01-02 | 2024-05-06 | 2024-05-03 | 2024-05-06 | 2024-05-18 | VALVE | 100046014 | 0020 | 0120 | 100046014 | MV-RE 2" 300# 134GAV1111 | AA53.K3410AS3B | FILT,BUFFER GAS | AA01 | 20 | No Issue identified | 10589833 | VALVE,GATE;DN50,CL300,RF,316SS,S3G1C | 1 | EA | 0 | 0 | 0 | 0 |  | 22.03 - ETA 31.03.24 PO W451779043 ex Score: In Transit CHR MOT 19924 |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006339 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000144515 | 5 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-09 | STST-5300006339_00020 | 0 | 0 | 0 |  | 2024-05-04 | AA53 | 2024-05-06 |  |  | 2024-05-06 |  |  |  |  | 2018-12-07 | 0 |  |  | 2024-05-03 | 2024-05-06 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-03 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10589833 | VALVE,GATE;DN50,CL300,RF,316SS,S3G1C |  | 0020 | Remove/Replace Valve | INT | Remove/Replace Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 20 |  | 5 |  | 0 |  | 24SD3410 | MJ | AU1072 | 1000143964 | S002 | 30 | 30 | 5300006339 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-03 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 144515 | 0 |  | 2 |  |  | RC00025003 | 2024-05-18 | 2024-05-06 | 2024-05-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | In Transit to PDC from Vendor | [6 empty] | 0
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | ROTAT | 100046883 | 0020 | 0042 | 100046883 | 409LG504 Clean Oil Sampling Valve | AA53.409LG504 | GAUGE,LEVEL GT4009V3 STARTING OIL TANK | AA01 | 255 | No Issue identified | 10601394 | VALVE,GG;SET,SS316,KLINGER LLG | 1 | EA | 0 | 0 | 1 | 2 | DR | 13.02 - In Transit Inb Del 180004337 | Supply for Order 100046883, Item 1 cannot be changed 9000028 item 10 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300002928 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004337 | 9000028 | 05 | Preparation | 0000145404 | 1 | 0 | DR |  |  | 102000000001215 | 01-Road | 1000000499 |  | 5-Completed |  | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017963 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2018-09-14 | 1 | 4900030573_2024_0001 |  | 2024-02-12 | 2024-05-03 |  | 5000017963_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004337 | 3 | L | 4900030573 | 2024 |  | 5000017963 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10601394 | VALVE,GG;SET,SS316,KLINGER LLG |  | 0020 | REMOVE / REPLACE UPPER & LOWER GAUGE | INT | REMOVE / REPLACE UPPER & LOWER GAUGE | 5 |  | 9000028_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000427 |  | 99 |  | 1 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000144753 | S002 | 30 | 30 | 5300002928 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 145404 | 0 |  | 2 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance | [8 empty] | 0 | 00001454044543110601394100046883
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-01 | 2024-05-19 | 2024-05-19 | ROTAT | 100040408 | 0030 | 0010 | 100040408 | MV-RE 40NB 300# 409BAV0034 GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 255 | No Issue identified | 10605598 | VALVE,BALL;DN40,CL300,RF,SS316,NP JXF20+ | 1 | EA | 1 | 0 | 0 | 0 |  | 27.03 - 1 SOH @ AA02 | Supply for Order 100040408, Item 3 cannot be changed 90000101 item 10 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300002200 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000101 | 05 | Preparation | 0000138900 | 3 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000101_0010 | 0 | 0 | 0 |  | 2024-05-02 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-06-08 | 0 |  |  | 2024-05-01 | 2024-05-04 | GT4009 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-01 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10605598 | VALVE,BALL;DN40,CL300,RF,SS316,NP JXF20+ |  | 0030 | Remove & Replace Valve | INT | Remove & Replace Valve | 5 |  | 90000101_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000101 |  | 99 |  | 3 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000138310 | S002 | 30 | 30 | 5300002200 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-01 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138900 | 0 |  | 2 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001389004543110605598100040408
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-23 | 2024-09-14 | VALVE | 100040577 | 0010 | 0082 | 100040577 | CV-OH 1" 300# 218PDCV506 | AA53.218PDCV506 | VALVE,2K1820E1 S/OIL PRESS CTRL | AA01 | 20 | No Issue identified | 10605918 | BUSH,PKG BX;VV,FISHER 1E839135012 | 1 | EA | 1 | 0 | 0 | 0 |  | 08.03 - 1 SOH @ AA02 | Supply for Order 100040577, Item 12 cannot be changed 90006874 item 60 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300002250 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006874 | 05 | Preparation | 0000139149 | 12 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006874_0060 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-31 | 0 |  |  | 2024-04-20 | 2024-04-23 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10605918 | BUSH,PKG BX;VV,FISHER 1E839135012 |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90006874_0060 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006874 |  | 20 |  | 12 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000138479 | S002 | 30 | 30 | 5300002250 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139149 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Order Approved/Printed/Object created/Date set by external system/Pre-costed/Released/Settlement rule created/Material shortage | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001391494540510605918100040577
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 | 2024-04-20 | 2024-04-23 | 2024-09-14 | VALVE | 100040576 | 0010 | 0092 | 100040576 | CV-OH 2" 300# 218PCV507 | AA53.218PCV507 | VALVE,2K1820E1 L/O PRESS CTRL | AA01 | 20 | No Issue identified | 10605927 | RING,PST;2",C/PTFE,FISHER 1U225705092 | 1 | EA | 1 | 0 | 0 | 0 |  | 08.03 -1 SOH @ AA02 | Supply for Order 100040576, Item 11 cannot be changed 90006873 item 60 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300002248 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006873 | 05 | Preparation | 0000139148 | 11 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006873_0060 | 0 | 0 | 0 |  | 2024-04-21 | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-31 | 0 |  |  | 2024-04-20 | 2024-04-23 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-20 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10605927 | RING,PST;2",C/PTFE,FISHER 1U225705092 |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90006873_0060 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006873 |  | 20 |  | 11 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000138478 | S002 | 30 | 30 | 5300002248 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-20 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139148 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Released/Pre-costed/Order Approved/Date set by external system/Settlement rule created/Object created/Printed/Material shortage | AM01 | Reactive Maintenance |  | SOH @ AA02 | [6 empty] | FALSE | 00001391484540510605927100040576
| 24SDFR2 | Released | 2024-01-02 | 2024-04-22 | 2024-04-19 | 2024-04-16 | 2024-04-23 | MECH | 600001793 | 0010 | 0010 | 600001793 | MOC-89056 Fab/Weld Install 218UCV112 | AA53.2E1801 | EXCH,HEAT DE-ETH REBOIL FRACT2 | AA01 | 10 | No Issue identified | 10607812 | PAINT;AL COLDSPRAY,INTERTHERM 751CSA | 2 | EA | 0 | 0 | 1 | 0 |  | 05.04 - PO W451783289 x 3 In Transit MOT DISPATCHED AKZO NOBEL | Supply for Order 600001793, Item 13 cannot be changed 90006857 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004605 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006857 | 06 | Scheduling | 0000084711 | 13 | 0 | [9 empty] | WorkPackLink |  | STONEHENGE S/D | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006857_0020 | 0 | 0 | 0 |  | 2024-04-20 | AA53 | 2024-04-22 |  |  | 2024-04-22 |  |  |  |  | 2024-12-15 | 0 |  |  | 2024-04-19 | 2024-04-22 | BLAST/PAINT |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-19 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10607812 | PAINT;AL COLDSPRAY,INTERTHERM 751CSA |  | 0010 | Erect Scaffold Access | INT | Erect Scaffold Access | 0 |  | 90006857_0020 | [7 empty] | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 | 90006857 |  | 5 |  | 13 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000084095 | S002 | 30 | 30 | 5300004605 | 80 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-19 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84711 | 0 |  | 2 |  |  | RC00018003 | 2024-04-23 | 2024-04-16 | 2024-04-16 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Material shortage/Printed | AM06 | Capital |  | In Transit to PDC from Vendor | [6 empty] | 0
| 24SDFR2 | Released | 2024-01-02 | 2024-04-22 | 2024-04-19 | 2024-04-16 | 2024-04-23 | MECH | 600001793 | 0010 | 0020 | 600001793 | MOC-89056 Fab/Weld Install 218UCV112 | AA53.2E1801 | EXCH,HEAT DE-ETH REBOIL FRACT2 | AA01 | 10 | No Issue identified | 10607813 | THINNER,PAINT;INTERTHERM 751CSA,PART B | 2 | EA | 0 | 0 | 1 | 0 |  | 05.04 - PO W451783289 x 3 In Transit MOT DISPATCHED AKZO NOBEL | Supply for Order 600001793, Item 14 cannot be changed 90006857 item 30 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004605 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006857 | 06 | Scheduling | 0000084711 | 14 | 0 | [9 empty] | WorkPackLink |  | STONEHENGE S/D | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006857_0030 | 0 | 0 | 0 |  | 2024-04-20 | AA53 | 2024-04-22 |  |  | 2024-04-22 |  |  |  |  | 2024-12-15 | 0 |  |  | 2024-04-19 | 2024-04-22 | BLAST/PAINT |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-19 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10607813 | THINNER,PAINT;INTERTHERM 751CSA,PART B |  | 0010 | Erect Scaffold Access | INT | Erect Scaffold Access | 0 |  | 90006857_0030 | [7 empty] | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 104 | Proj & Brownfields | AU00 |  | AA53 | 90006857 |  | 5 |  | 14 |  | 0 |  | 24SDFR2 | MJ | AU1072 | 1000084095 | S002 | 30 | 30 | 5300004605 | 90 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-19 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 84711 | 0 |  | 2 |  |  | RC00018003 | 2024-04-23 | 2024-04-16 | 2024-04-16 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Material shortage/Printed | AM06 | Capital |  | In Transit to PDC from Vendor | [6 empty] | 0
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-12 | 2024-05-15 | 2024-05-15 | INLEC | 100039429 | 0020 | 0050 | 100039429 | MOC-109223 Damaged Insulators Replace GT | AA53.G4008 | GEN,GAS TURBINE,G4008 | AA01 | 255 | No Issue identified | 10603662 | ISOLATOR;20KV,NP IRM047279079 | 1 | EA | 0 | 0 | 0 | 0 |  | 28.02 - **No Expedite** confirmed by Gargs to replace as reqd |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006131 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000137943 | 5 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-06 | STST-5300006131_00020 | 0 | 0 | 0 |  | 2024-05-13 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-11-30 | 0 |  |  | 2024-05-12 | 2024-05-15 | GT4008 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10603662 | ISOLATOR;20KV,NP IRM047279079 |  | 0020 | Replace Broken Insulator G4008 | INT | Replace Broken Insulator G4008 | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 99 |  | 5 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000137345 | S002 | 30 | 30 | 5300006131 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-12 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 137943 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | No Expedite Material | [6 empty] | 0
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-12 | 2024-05-15 | 2024-05-15 | INLEC | 100039429 | 0020 | 0040 | 100039429 | MOC-109223 Damaged Insulators Replace GT | AA53.G4008 | GEN,GAS TURBINE,G4008 | AA01 | 255 | No Issue identified | 10603662 | ISOLATOR;20KV,NP IRM047279079 | 11 | EA | 0 | 0 | 0 | 0 |  | 13.02 - **No Expedite** confirmed by Gargs to replace as reqd |  | STO raised (through orchestration) | SP12 | Stock at Base | 0 | AA02 | 5300006131 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000137943 | 4 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 11 |  |  | Y | 1001 | 2024-02-06 | STST-5300006131_00010 | 0 | 0 | 0 |  | 2024-05-13 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-11-30 | 0 |  |  | 2024-05-12 | 2024-05-15 | GT4008 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10603662 | ISOLATOR;20KV,NP IRM047279079 |  | 0020 | Replace Broken Insulator G4008 | INT | Replace Broken Insulator G4008 | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 |  |  | 99 |  | 4 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000137345 | S002 | 30 | 30 | 5300006131 | 10 |  |  | 0 | 11 | EA | 2001 | AA02 | 2024-05-12 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 137943 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | No Expedite Material | [6 empty] | 0
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 |  | 2024-04-23 | 2024-09-10 | WORK | 200064070 | 0060 | 0010 | 200064070 | 9Y F21 RECERTIFY SC PSV ROTABLE | AA53.218RV13 | PSV,2V1805 ON 2" LINE 2W41534 |  | 10 | No Issue identified | 10245543 | VALVE,REL,FUKUI,REC371-(A)1D2,4000-5000 | -1 | EA | 0 | 0 | 0 | 0 |  | 29.01 - Refurb item |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000098352 | 6 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-23 | [7 empty] | 2024-07-03 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10245543 | VALVE,REL,FUKUI,REC371-(A)1D2,4000-5000 |  | 0060 | RETURN PSV TO STOCK | INT | RETURN PSV TO STOCK | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000097789 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-09-10 | 2024-04-23 | 2024-04-23 | Material shortage/Date set by external system/Object created/Pre-costed/Released/Settlement rule created | AM02 | Proactive Maintenance |  | Refurb Item
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 |  | 2024-04-23 | 2024-09-09 | WORK | 200089034 | 0040 | 0010 | 200089034 | 6Y F21 RECERTIFY SC PILOT PSV ROTABLE | AA53.218RV97BP | PSV,PILOT PROP TRANS SURGE DRUM |  | 10 | No Issue identified | 10264996 | VALVE,REL,PLT,AGCO 200,1896KPAG | -1 | EA | 0 | 0 | 0 | 0 |  | 13.02 - Refurb Item |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000127312 | 2 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-23 | [7 empty] | 2024-10-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10264996 | VALVE,REL,PLT,AGCO 200,1896KPAG |  | 0040 | Punchlist & Closeout WP200089034MET001 | ENON | Punchlist & Closeout WP200089034MET001 | [10 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000126743 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-09-09 | 2024-04-23 | 2024-04-23 | Pre-costed/Object created/Date set by external system/Material shortage/Settlement rule created/Released | AM02 | Proactive Maintenance |  | Refurb Item
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-03 | WORK | 200089392 | 0020 | 0060 | 200089392 | 10Y RECERTIFY PSV ROTABLE | AA53.407RV521 | PSV,CO2 DISCH LINE GT4007A CO2 |  | 10 | No Issue identified | 10266469 | VALVE,REL,CROSBY 9611102A,PRESS 3100KPAG | -1 | EA | 0 | 0 | 0 | 0 |  | 29.01 - Refurb item |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000127702 | 6 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2024-07-18 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10266469 | VALVE,REL,CROSBY 9611102A,PRESS 3100KPAG |  | 0020 | Remove / Install PSV | INT | Remove / Install PSV | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000127064 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | Refurb Item
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 |  | 2024-05-15 | 2024-05-15 | WORK | 200089855 | 0020 | 0030 | 200089855 | 6Y RECERTIFY PSV ROTABLE | AA53.408RV501 | PSV,GAS TURB GT4008 |  | 10 | No Issue identified | 10255659 | VALVE,REL,AGCO 81PSF88-8,OIL,SET 1200KPA | -1 | EA | 0 | 0 | 0 | 0 |  | 31.01 - Refurb Item |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000128133 | 3 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-15 | [7 empty] | 2024-06-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255659 | VALVE,REL,AGCO 81PSF88-8,OIL,SET 1200KPA |  | 0020 | Remove / Install PSV | INT | Remove / Install PSV | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT8 | MJ |  | 1000127524 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | Refurb Item
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-03 | WORK | 200090101 | 0020 | 0030 | 200090101 | 6Y RECERTIFY PSV ROTABLE | AA53.410RV501 | PSV,GT4010 LUBEOIL TANK |  | 10 | No Issue identified | 10255659 | VALVE,REL,AGCO 81PSF88-8,OIL,SET 1200KPA | -1 | EA | 0 | 0 | 0 | 0 |  | 29.01 - Refurb Item |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000128339 | 3 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2024-06-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255659 | VALVE,REL,AGCO 81PSF88-8,OIL,SET 1200KPA |  | 0020 | Remove / Install PSV | INT | Remove / Install PSV | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000127750 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | Refurb Item
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-03 | WORK | 200090588 | 0020 | 0030 | 200090588 | 6Y RECERTIFY PSV ROTABLE | AA53.407RV501 | PSV,GAS TURBINE GT4007 |  | 10 | No Issue identified | 10255659 | VALVE,REL,AGCO 81PSF88-8,OIL,SET 1200KPA | -1 | EA | 0 | 0 | 0 | 0 |  | 31.01 - Refurb Item |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000128817 | 3 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2024-06-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255659 | VALVE,REL,AGCO 81PSF88-8,OIL,SET 1200KPA |  | 0020 | Remove / Install PSV | INT | Remove / Install PSV | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000128267 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | Refurb Item
| 24SD3410 | Released | 2024-01-02 | 2024-05-06 |  | 2024-05-06 | 2024-05-06 | WORK | 200090965 | 0060 | 0010 | 200090965 | 6Y F21 RECERTIFY SC PSV ROTABLE | AA53.34RV46 | PSV,SUCTION OF K3410B/BOG COMPR |  | 10 | No Issue identified | 10245570 | VALVE,REL,FUKUI,REC261-S(A)1.5F2,1700KPA | -1 | EA | 0 | 0 | 0 | 0 |  | 08.02 - Refurb Item |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000129199 | 6 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-06 | [7 empty] | 2024-10-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10245570 | VALVE,REL,FUKUI,REC261-S(A)1.5F2,1700KPA |  | 0060 | RETURN PSV TO WAREHOUSE | INT | RETURN PSV TO WAREHOUSE | 7 | Ready for Release | [8 empty] | 0065 | Ready for Execution (Order) | ZBPM0002 | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SD3410 | MJ |  | 1000128608 |  | 30 |  |  | 0 |  |  | 0 | 0 | [5 empty] | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-06 | 2024-05-06 | 2024-05-06 | Goods movement posted/Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | Refurb Item
X | 24SDGT7 | Created |  | 2024-05-02 |  | 2024-05-02 | 2024-05-04 | ROTAT | 100075217 | 0050 | 0010 | 100075217 | Inspection GT4007 - High T48 Spread | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | WO item has not been released yet | 10255343 | GASKET,SEAL;NP ISM101343254 | 5 | EA | 15 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 03 | Planning | 0000228278 | 1 | 0 | [9 empty] | WorkPackLink |  | PO7-TA GT4007 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-02 |  |  | 2024-05-02 |  |  |  |  | 2024-09-11 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255343 | GASKET,SEAL;NP ISM101343254 |  | 0050 | Test C ring Check Valves 18,16,14 | INT | Test C ring Check Valves 18,16,14 | [10 empty] | 0035 | In Planning (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000225597 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W36770 | 2024-03-25 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-02 | 2024-05-02 | Date set by external system/Material committed/Order Approval Required/Object created/Pre-costed/Created | AM01 | Reactive Maintenance |  | Created W/o
X | 24SDGT7 | Created |  | 2024-05-03 |  | 2024-05-02 | 2024-05-04 | ROTAT | 100075217 | 0080 | 0010 | 100075217 | Inspection GT4007 - High T48 Spread | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | WO item has not been released yet | 10307835 | NOZZLE,FUEL;GE L38166P02 | 3 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 03 | Planning | 0000228278 | 2 | 0 | [9 empty] | WorkPackLink |  | PO7-TA GT4007 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-09-11 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307835 | NOZZLE,FUEL;GE L38166P02 |  | 0080 | Replace Pre Mixers 14,16,18 | INT | Replace Pre Mixers 14,16,18 | [10 empty] | 0035 | In Planning (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000225597 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W36770 | 2024-03-25 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-02 | 2024-05-02 | Date set by external system/Material committed/Order Approval Required/Object created/Pre-costed/Created | AM01 | Reactive Maintenance |  | Created W/o
1 | 24SDGT7 | Created |  | 2024-05-02 |  | 2024-05-02 | 2024-05-04 | ROTAT | 100075217 | 0050 | 0020 | 100075217 | Inspection GT4007 - High T48 Spread | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | WO item has not been released yet | 10542864 | VALVE,CHK;GE L62774P01 | 3 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 03 | Planning | 0000228278 | 3 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-02 |  |  | 2024-05-02 |  |  |  |  | 2024-09-11 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10542864 | VALVE,CHK;GE L62774P01 |  | 0050 | Test C ring Check Valves 18,16,14 | INT | Test C ring Check Valves 18,16,14 | [10 empty] | 0035 | In Planning (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000225597 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W36770 | 2024-03-25 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-02 | 2024-05-02 | Date set by external system/Material committed/Order Approval Required/Object created/Pre-costed/Created | AM01 | Reactive Maintenance |  | PR Never
1 | 24SD3411 | Created |  | 2024-05-09 |  | 2024-05-08 | 2024-05-09 | VALVE | 200056933 | 0050 | 0030 | 200056933 | 10Y F21 INSP & OVERHAUL CHK VALVE S&L | AA53.34CHV0571 | VALVE,CHECK LNG BOIL OFF COMPR |  | 10 | WO item has not been released yet | 10060936 | GASKET;SWCI,300MM,CL600,316L/GR/316 | 2 | EA | 0 | 0 | 0 | 0 |  | 14.02 - At PR Never | Supply Process could not be determined for item 5, material 10060936 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 03 | Planning | 0000091255 | 5 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-09 | [7 empty] | 2024-11-01 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060936 | GASKET;SWCI,300MM,CL600,316L/GR/316 |  | 0050 | Re-Install NRV | INT | Re-Install NRV | 5 | Ready for Release | [8 empty] | 0035 | In Planning (Order) | ZBPM0002 | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SD3411 | MJ |  | 1000090652 |  | 30 |  |  | 0 |  |  | 0 | 0 | [5 empty] | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-09 | 2024-05-08 | 2024-05-08 | Pre-costed/Settlement rule created/Created/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance |  | PR Never
1 | 24SD3411 | Created |  | 2024-05-09 |  | 2024-05-08 | 2024-05-09 | VALVE | 200056933 | 0050 | 0020 | 200056933 | 10Y F21 INSP & OVERHAUL CHK VALVE S&L | AA53.34CHV0571 | VALVE,CHECK LNG BOIL OFF COMPR | AA01 | 10 | WO item has not been released yet | 10491127 | STUDBOLT;1.250" X 230MM,L7,BLK | 40 | EA | 0 | 0 | 0 | 0 |  | 14.02 - At PR Never |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 03 | Planning | 0000091255 | 4 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 40 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-09 |  |  | 2024-05-09 |  |  |  |  | 2024-11-01 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491127 | STUDBOLT;1.250" X 230MM,L7,BLK |  | 0050 | Re-Install NRV | INT | Re-Install NRV | 5 | Ready for Release | [8 empty] | 0035 | In Planning (Order) | ZBPM0002 | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SD3411 | MJ |  | 1000090652 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-09 | 2024-05-08 | 2024-05-08 | Pre-costed/Settlement rule created/Created/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance |  | PR Never
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-03 | INLEC | 100033128 | 0020 | 0010 | 100033128 | Replace C02 Load Cell Controller GT4007 | AA53.760GS65L | TXDCR,GT4007V3 CO2 TK WEIGHT LOW ALM |  | 20 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 08.02 - Delivery Staged 2023; to be added back on. |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131600 | 1 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2024-04-19 | 0 |  |  |  |  | 760GS65L |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000131030 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material committed/Order Approved/Released/Settlement rule created/Pre-costed/Object created/Date set by external system | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDTOT1 | Released | 2024-01-02 | 2024-02-29 |  | 2024-05-09 | 2024-05-09 | INLEC | 100034327 | 0020 | 0010 | 100034327 | Replace Braided Air Hose 110HV843 | AA53.110HV843 | VALVE,CTRL 1PRS RUN 4 |  | 10 | No issue identified |  |  | 1 | ASY | 0 | 0 | 0 | 0 |  | 13/02 Staged KGP Location SW3R15G01B (DWR 71080319) |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | ASY | [5 empty] | 05 | Preparation | 0000132779 | 1 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-09 | [7 empty] | 2023-09-29 | 0 |  |  |  |  | 110HV843 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 10 |  | 0 |  | 0 |  | 24SDTOT1 | MJ |  | 1000132209 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-09 | 2024-05-09 | 2024-05-09 | Printed/Material committed/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-03 | INLEC | 100035583 | 0010 | 0060 | 100035583 | MOC-72065 Modify GT7 Hard-Wired Trip S2A | AA53.S2A1A4 | FEEDER,GENERATOR G4007 INCOMER |  | 30 | No Issue identified |  |  | 100 | M | 0 | 0 | 0 | 0 |  | 14.02 - MN:10033724 Del 71073011 DELIVERY CONSUMED |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | M | [5 empty] | 05 | Preparation | 0000134055 | 5 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 100 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2024-08-02 | 0 |  |  |  |  | AU01.S2A1A4 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | MOC-72065 Modify GT7 Hard-wired trip | ENON | MOC-72065 Modify GT7 Hard-wired trip | 5 | Management of Change | [8 empty] | 0055 | In Preparation (Order) | ZBPM0001 | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000133465 |  |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | Management of Change |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT10 | Released | 2024-01-02 | 2024-05-02 |  | 2024-05-02 | 2024-05-03 | ROTAT | 100039132 | 0030 | 0010 | 100039132 | DE Sump Drain Line Update CM GT4010 | AA53.GT4010 | TURB,GAS FOR G4010 |  | 20 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | MN:10038183 Del 80916531 DELIVERY CONSUMED |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000137666 | 1 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-02 | [7 empty] | 2023-06-30 | 0 |  |  |  |  | 2100352558 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0030 | Fab/Install Section 2 Drain Line(1 Bend) | INT | Fab/Install Section 2 Drain Line(1 Bend) | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000137048 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-03 | 2024-05-02 | 2024-05-02 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT10 | Released | 2024-01-02 | 2024-05-02 |  | 2024-05-02 | 2024-05-03 | ROTAT | 100039132 | 0030 | 0020 | 100039132 | DE Sump Drain Line Update CM GT4010 | AA53.GT4010 | TURB,GAS FOR G4010 |  | 20 | No Issue identified |  |  | 2 | EA | 0 | 0 | 0 | 0 |  | MN:10047911 Del 80908306 DELIVERY CREATED – Not Loaded |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000137666 | 2 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-02 | [7 empty] | 2023-06-30 | 0 |  |  |  |  | 2100352558 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0030 | Fab/Install Section 2 Drain Line(1 Bend) | INT | Fab/Install Section 2 Drain Line(1 Bend) | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000137048 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-03 | 2024-05-02 | 2024-05-02 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 |  | 2024-05-15 | 2024-05-15 | INLEC | 100039429 | 0020 | 0030 | 100039429 | MOC-109223 Damaged Insulators Replace GT | AA53.G4008 | GEN,GAS TURBINE,G4008 |  | 255 | No Issue identified |  |  | 2 | EA | 0 | 0 | 0 | 0 |  | 08.02 - MN 10613313 Insulator; qty 2 delivered, qty 9 to be added to WO. |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000137943 | 3 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-15 | [7 empty] | 2024-11-30 | 0 |  |  |  |  | GT4008 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0020 | Replace Broken Insulator G4008 | INT | Replace Broken Insulator G4008 | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT8 | MJ |  | 1000137345 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 |  | 2024-05-15 | 2024-05-15 | INLEC | 100039429 | 0020 | 0020 | 100039429 | MOC-109223 Damaged Insulators Replace GT | AA53.G4008 | GEN,GAS TURBINE,G4008 |  | 255 | No Issue identified |  |  | 21 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10603662 Del 71008686/71009479 DELIVERY CONSUMED |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000137943 | 2 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 21 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-15 | [7 empty] | 2024-11-30 | 0 |  |  |  |  | UT Inlec |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0020 | Replace Broken Insulator G4008 | INT | Replace Broken Insulator G4008 | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT8 | MJ |  | 1000137345 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | ROTAT | 100040102 | 0030 | 0010 | 100040102 | DE Sump Drain Line Update CM GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 |  | 20 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10038183 Del 80879861 DELIVERY CONSUMED |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000138574 | 1 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 | [7 empty] | 2023-06-30 | 0 |  |  |  |  | 2100352557 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0030 | Fab/Install Section 2 Drain Line(1 Bend) | INT | Fab/Install Section 2 Drain Line(1 Bend) | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000137964 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | INLEC | 100040358 | 0010 | 0040 | 100040358 | Vibration Monitor Rack Fault GT4009 | AA53.409PT520A | TX,PRESS GT4009 COMBUST ACOUSTIC SENS |  | 10 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10536340 Del 80884560 DELIVERY CONSUMED |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000138890 | 4 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 | [7 empty] | 2022-06-07 | 0 |  |  |  |  | GT4009 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 10 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000138260 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | INLEC | 100040358 | 0010 | 0020 | 100040358 | Vibration Monitor Rack Fault GT4009 | AA53.409PT520A | TX,PRESS GT4009 COMBUST ACOUSTIC SENS |  | 10 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10536342 Del 80884560 DELIVERY CONSUMED |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000138890 | 2 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 | [7 empty] | 2022-06-07 | 0 |  |  |  |  | GT4009 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 10 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000138260 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | INLEC | 100040358 | 0010 | 0010 | 100040358 | Vibration Monitor Rack Fault GT4009 | AA53.409PT520A | TX,PRESS GT4009 COMBUST ACOUSTIC SENS |  | 10 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10314013 Del 80884560 DELIVERY CONSUMED |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000138890 | 1 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 | [7 empty] | 2022-06-07 | 0 |  |  |  |  | GT4009 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 10 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000138260 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | INLEC | 100040358 | 0010 | 0030 | 100040358 | Vibration Monitor Rack Fault GT4009 | AA53.409PT520A | TX,PRESS GT4009 COMBUST ACOUSTIC SENS |  | 10 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10255238 Del 80884560 DELIVERY CONSUMED |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000138890 | 3 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 | [7 empty] | 2022-06-07 | 0 |  |  |  |  | GT4009 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 10 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000138260 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | ROTAT | 100040409 | 0031 | 0010 | 100040409 | MV-RE 40NB 300# 410BAV0034 GT4010 | AA53.GT4010 | TURB,GAS FOR G4010 |  | 255 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10605598 Del 71075089 DELIVERY CREATED – In Quality PDC |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000138961 | 1 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2024-06-09 | 0 |  |  |  |  | 100040409 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0031 | Remove & Replace Valve | INT | Remove & Replace Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000138311 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | ROTAT | 100040480 | 0010 | 0030 | 100040480 | GT4010 - Replace bushes and bell cranks | AA53.GT4010 | TURB,GAS FOR G4010 |  | 255 | No Issue identified |  |  | 24 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10312320 Del 80888850 DELIVERY CONSUMED |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139004 | 3 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2023-04-27 | 0 |  |  |  |  | GT4010 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | GT4010 - Replace Bushes & Bell Cranks | ENON | GT4010 - Replace Bushes & Bell Cranks | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000138355 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | ROTAT | 100040480 | 0010 | 0020 | 100040480 | GT4010 - Replace bushes and bell cranks | AA53.GT4010 | TURB,GAS FOR G4010 |  | 255 | No Issue identified |  |  | 48 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10312462 Del 80888829 DELIVERY CONSUMED |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139004 | 2 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 48 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2023-04-27 | 0 |  |  |  |  | GT4010 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | GT4010 - Replace Bushes & Bell Cranks | ENON | GT4010 - Replace Bushes & Bell Cranks | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000138355 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | ROTAT | 100040480 | 0010 | 0040 | 100040480 | GT4010 - Replace bushes and bell cranks | AA53.GT4010 | TURB,GAS FOR G4010 |  | 255 | No Issue identified |  |  | 18 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10297498 Del 80881032 DELIVERY CONSUMED |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139004 | 4 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 18 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2023-04-27 | 0 |  |  |  |  | GT4010 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | GT4010 - Replace Bushes & Bell Cranks | ENON | GT4010 - Replace Bushes & Bell Cranks | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000138355 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | ROTAT | 100040480 | 0010 | 0010 | 100040480 | GT4010 - Replace bushes and bell cranks | AA53.GT4010 | TURB,GAS FOR G4010 |  | 255 | No Issue identified |  |  | 3 | ASY | 0 | 0 | 0 | 0 |  | 14.02 - MN:10313419 Del 80888785 X QY 3 DELIVERY CONSUMED |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | ASY | [5 empty] | 05 | Preparation | 0000139004 | 9 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2023-04-27 | 0 |  |  |  |  | GT4010 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | GT4010 - Replace Bushes & Bell Cranks | ENON | GT4010 - Replace Bushes & Bell Cranks | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000138355 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 |  | 2024-04-23 | 2024-09-14 | VALVE | 100040576 | 0010 | 0070 | 100040576 | CV-OH 2" 300# 218PCV507 | AA53.218PCV507 | VALVE,2K1820E1 L/O PRESS CTRL |  | 20 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 13/02 MN 10413471 Delivery Consumed (DWR 71070523) |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139148 | 4 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-23 | [7 empty] | 2024-12-31 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000138478 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Released/Pre-costed/Order Approved/Date set by external system/Settlement rule created/Object created/Printed/Material shortage | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 |  | 2024-04-23 | 2024-09-14 | VALVE | 100040576 | 0010 | 0060 | 100040576 | CV-OH 2" 300# 218PCV507 | AA53.218PCV507 | VALVE,2K1820E1 L/O PRESS CTRL |  | 20 | No Issue identified |  |  | 1 | SET | 0 | 0 | 0 | 0 |  | 13/02 MN 10531250 Delivery Consumed (DWR 71070523) |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | SET | [5 empty] | 05 | Preparation | 0000139148 | 3 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-23 | [7 empty] | 2024-12-31 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000138478 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Released/Pre-costed/Order Approved/Date set by external system/Settlement rule created/Object created/Printed/Material shortage | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 |  | 2024-04-23 | 2024-09-14 | VALVE | 100040576 | 0010 | 0050 | 100040576 | CV-OH 2" 300# 218PCV507 | AA53.218PCV507 | VALVE,2K1820E1 L/O PRESS CTRL |  | 20 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 13/02 MN 10531246 Delivery Consumed (DWR 71070523) |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139148 | 2 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-23 | [7 empty] | 2024-12-31 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000138478 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Released/Pre-costed/Order Approved/Date set by external system/Settlement rule created/Object created/Printed/Material shortage | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 |  | 2024-04-23 | 2024-09-14 | VALVE | 100040577 | 0010 | 0030 | 100040577 | CV-OH 1" 300# 218PDCV506 | AA53.218PDCV506 | VALVE,2K1820E1 S/OIL PRESS CTRL |  | 20 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 13/02 MN 10531246 Delivery Consumed (DWR 71070524) |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139149 | 3 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-23 | [7 empty] | 2024-12-31 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000138479 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Order Approved/Printed/Object created/Date set by external system/Pre-costed/Released/Settlement rule created/Material shortage | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 |  | 2024-04-23 | 2024-09-14 | VALVE | 100040577 | 0010 | 0090 | 100040577 | CV-OH 1" 300# 218PDCV506 | AA53.218PDCV506 | VALVE,2K1820E1 S/OIL PRESS CTRL |  | 20 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 13/02 MN 10605928 Delivery Consumed (DWR 71070524) |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139149 | 6 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-23 | [7 empty] | 2024-12-31 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000138479 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Order Approved/Printed/Object created/Date set by external system/Pre-costed/Released/Settlement rule created/Material shortage | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 |  | 2024-04-23 | 2024-09-14 | VALVE | 100040577 | 0010 | 0100 | 100040577 | CV-OH 1" 300# 218PDCV506 | AA53.218PDCV506 | VALVE,2K1820E1 S/OIL PRESS CTRL |  | 20 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 13/02 MN 10531246 Delivery Consumed (DWR 71070524) |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139149 | 7 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-23 | [7 empty] | 2024-12-31 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000138479 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Order Approved/Printed/Object created/Date set by external system/Pre-costed/Released/Settlement rule created/Material shortage | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDFR2 | Released | 2024-01-02 | 2024-04-23 |  | 2024-04-23 | 2024-09-14 | VALVE | 100040577 | 0010 | 0040 | 100040577 | CV-OH 1" 300# 218PDCV506 | AA53.218PDCV506 | VALVE,2K1820E1 S/OIL PRESS CTRL |  | 20 | No Issue identified |  |  | 1 | SET | 0 | 0 | 0 | 0 |  | 13/02 MN 10605950 Delivery Consumed (DWR 71070524) |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | SET | [5 empty] | 05 | Preparation | 0000139149 | 4 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-23 | [7 empty] | 2024-12-31 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000138479 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Order Approved/Printed/Object created/Date set by external system/Pre-costed/Released/Settlement rule created/Material shortage | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | INLEC | 100040989 | 0010 | 0020 | 100040989 | Generator Transducer Replace GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 |  | 10 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10504710 Del 70992886 DELIVERY CONSUMED |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139523 | 1 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 | [7 empty] | 2022-08-17 | 0 |  |  |  |  | GT9 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Punchlist & Closeout WP100040989IET001 | INT | Punchlist & Closeout WP100040989IET001 | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 10 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000138885 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Date set by external system/Object created/Settlement rule created/Released/Order Approved/Printed/Pre-costed/Material committed | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | INLEC | 100040989 | 0010 | 0050 | 100040989 | Generator Transducer Replace GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 |  | 10 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10542025 Del 71079602 DELIVERY CONSUMED |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139523 | 4 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 | [7 empty] | 2022-08-17 | 0 |  |  |  |  | GT4009 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Punchlist & Closeout WP100040989IET001 | INT | Punchlist & Closeout WP100040989IET001 | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 10 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000138885 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Date set by external system/Object created/Settlement rule created/Released/Order Approved/Printed/Pre-costed/Material committed | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | INLEC | 100040989 | 0010 | 0060 | 100040989 | Generator Transducer Replace GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 |  | 10 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10542025 Del 70993159 DELIVERY CONSUMED |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139523 | 5 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 | [7 empty] | 2022-08-17 | 0 |  |  |  |  | GT4009 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Punchlist & Closeout WP100040989IET001 | INT | Punchlist & Closeout WP100040989IET001 | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 10 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000138885 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Date set by external system/Object created/Settlement rule created/Released/Order Approved/Printed/Pre-costed/Material committed | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | INLEC | 100040989 | 0010 | 0040 | 100040989 | Generator Transducer Replace GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 |  | 10 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10542025 Del 71014344 DELIVERY CONSUMED |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139523 | 3 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 | [7 empty] | 2022-08-17 | 0 |  |  |  |  | N.Norman |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Punchlist & Closeout WP100040989IET001 | INT | Punchlist & Closeout WP100040989IET001 | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 10 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000138885 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Date set by external system/Object created/Settlement rule created/Released/Order Approved/Printed/Pre-costed/Material committed | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | INLEC | 100040989 | 0010 | 0030 | 100040989 | Generator Transducer Replace GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 |  | 10 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 08.02 - Delivery Staged: MN 10504710 TXDCR x qty 1 to be re-added |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139523 | 2 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 | [7 empty] | 2022-08-17 | 0 |  |  |  |  | GT9 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Punchlist & Closeout WP100040989IET001 | INT | Punchlist & Closeout WP100040989IET001 | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 10 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000138885 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Date set by external system/Object created/Settlement rule created/Released/Order Approved/Printed/Pre-costed/Material committed | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-03 | INLEC | 100043426 | 0010 | 0040 | 100043426 | MOC-119715 MCC Switch Replace S24D16A5RA | AA53.GT4007KM1B | MOTOR,TURB ACCOUST ENCL VENT FAN,GT4007 |  | 30 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | MN:10545015 Del 80850582 DELIVERY CREATED – In Loading Area on NWS Warehouse |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000141927 | 4 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2021-06-07 | 0 |  |  |  |  | S24D16A5RA |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Isolate & Disconnect S24D16A5RA | INT | Isolate & Disconnect S24D16A5RA | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000141296 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | ROTAT | 100044982 | 0050 | 0010 | 100044982 | GT9 Inlet Duct Leak Clean Side | AA53.GT4009 | TURB,GAS FOR G4009 |  | 30 | No Issue identified |  |  | 2 | KG | 0 | 0 | 0 | 0 |  | 14.02 - MN:10493611 Del 70795320 DELIVERY CONSUMED |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | KG | [5 empty] | 05 | Preparation | 0000143483 | 1 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 | [7 empty] | 2020-06-18 | 0 |  |  |  |  | 2100293550 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0050 | Identifiy and repair known gap in duting | INT | Identifiy and repair known gap in duting | 3 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000142872 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Estimated costs | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT7 | Released | 2024-01-02 | 2024-05-04 |  | 2024-05-04 | 2024-05-08 | ROTAT | 100067619 | 0231 | 0030 | 100067619 | MOC-111548 G4007S2M1 Louvre and Motor fa | AA53.G4007S2M1 | MOTOR,GEN AIR FILTER OUTLET LOUVRE G4007 |  | 255 | No Issue identified |  |  | 2 | EA | 0 | 0 | 0 | 0 |  | AJ 06/02- 10518113-GLUE,ADHESIVE,BOSTIK CONTACT BOND,1L- P07R10A Caged pallet |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000212678 | 4 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-04 | [7 empty] | 2024-10-10 | 0 |  |  |  |  | 2100353335 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0231 | Remediation works On Louver | INT | Remediation works On Louver | 3 | Management of Change | [8 empty] | 0060 | Ready to Schedule (Order) | ZBPM0001 | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000211796 |  |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | Management of Change |  |  | 1070 |  | 2024-03-25 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-31 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-08 | 2024-05-04 | 2024-05-04 | Released/Settlement rule created/Partially confirmed/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT7 | Released | 2024-01-02 | 2024-05-04 |  | 2024-05-04 | 2024-05-08 | ROTAT | 100067619 | 0221 | 0040 | 100067619 | MOC-111548 G4007S2M1 Louvre and Motor fa | AA53.G4007S2M1 | MOTOR,GEN AIR FILTER OUTLET LOUVRE G4007 |  | 255 | No Issue identified |  |  | 2 | CAN | 0 | 0 | 0 | 0 |  | 14.02 - MN:10428416 Del 71003879 DELIVERY CONSUMED |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | CAN | [5 empty] | 06 | Scheduling | 0000212678 | 2 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-04 | [7 empty] | 2024-10-10 | 0 |  |  |  |  | 2100353335 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0221 | Remove Louver | INT | Remove Louver | 3 | Management of Change | [8 empty] | 0060 | Ready to Schedule (Order) | ZBPM0001 | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000211796 |  |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | Management of Change |  |  | 1070 |  | 2024-03-25 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-31 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-08 | 2024-05-04 | 2024-05-04 | Released/Settlement rule created/Partially confirmed/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT7 | Released | 2024-01-02 | 2024-05-04 |  | 2024-05-04 | 2024-05-08 | ROTAT | 100067619 | 0231 | 0020 | 100067619 | MOC-111548 G4007S2M1 Louvre and Motor fa | AA53.G4007S2M1 | MOTOR,GEN AIR FILTER OUTLET LOUVRE G4007 |  | 255 | No Issue identified |  |  | 1 | SHT | 0 | 0 | 0 | 0 |  | AJ 06/02- 10057798-RUBBER,NATURAL,1200 X 1000MM,1.50MM THK- P07R10A Caged pallet |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | SHT | [5 empty] | 06 | Scheduling | 0000212678 | 3 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-04 | [7 empty] | 2024-10-10 | 0 |  |  |  |  | 2100353335 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0231 | Remediation works On Louver | INT | Remediation works On Louver | 3 | Management of Change | [8 empty] | 0060 | Ready to Schedule (Order) | ZBPM0001 | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000211796 |  |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | Management of Change |  |  | 1070 |  | 2024-03-25 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-31 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-08 | 2024-05-04 | 2024-05-04 | Released/Settlement rule created/Partially confirmed/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT7 | Released | 2024-01-02 | 2024-05-06 |  | 2024-05-04 | 2024-05-08 | ROTAT | 100067619 | 0245 | 0050 | 100067619 | MOC-111548 G4007S2M1 Louvre and Motor fa | AA53.G4007S2M1 | MOTOR,GEN AIR FILTER OUTLET LOUVRE G4007 |  | 255 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | AJ 06/02/24 - 10606094 MOTOR,AC;240VAC,5W,BELIMO GM230A - Location P07R10A cage |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000212678 | 1 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-06 | [7 empty] | 2024-10-10 | 0 |  |  |  |  | 2100353335 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0245 | Install Elbow Ducting & Tighten Bolts | INT | Install Elbow Ducting & Tighten Bolts | 3 | Management of Change | [8 empty] | 0060 | Ready to Schedule (Order) | ZBPM0001 | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000211796 |  |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | Management of Change |  |  | 1070 |  | 2024-03-25 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-31 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-08 | 2024-05-04 | 2024-05-04 | Released/Settlement rule created/Partially confirmed/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0100 | 0210 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 |  | 10 | No Issue identified |  |  | 6 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10537210 Del 71079637 DELIVERY CREATED – EXW in Transit |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000117945 | 21 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2024-06-30 | 0 |  |  |  |  | GT4010 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0100 | PCC FORWARD MOUNT BOLT WEAR | INT | PCC FORWARD MOUNT BOLT WEAR | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000117386 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | S4H Cutover Material
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0090 | 0160 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 |  | 10 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | MN:10537214 Del 71079636 DELIVERY CREATED – EXW in Transit |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000117945 | 16 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2024-06-30 | 0 |  |  |  |  | GT4010 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0090 | HYDRAULIC OIL FILTER REPLACEMENT | INT | HYDRAULIC OIL FILTER REPLACEMENT | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000117386 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | S4H Cutover Material
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 |  | 2024-05-15 | 2024-05-15 | QMI | 200083423 | 0010 | 0020 | 200083423 | 1Y Analyser Filter Replacement 408QE501 | AA53.408QE501S1 | FILT,GT4008 ANLZ SAMPLE |  | 30 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10578991 Del 80935806 DELIVERY CREATED – Not Loaded |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000120680 | 2 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-15 | [7 empty] | 2024-04-07 | 0 |  |  |  |  | 2200670025 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SDGT8 | MJ |  | 1000120092 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | S4H Cutover Material
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 |  | 2024-05-15 | 2024-05-15 | QMI | 200083423 | 0010 | 0010 | 200083423 | 1Y Analyser Filter Replacement 408QE501 | AA53.408QE501S1 | FILT,GT4008 ANLZ SAMPLE |  | 30 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10578979 Del 80935806 DELIVERY CREATED – Not Loaded |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000120680 | 1 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-15 | [7 empty] | 2024-04-07 | 0 |  |  |  |  | 2200670025 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SDGT8 | MJ |  | 1000120092 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | S4H Cutover Material
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | QMI | 200083425 | 0010 | 0020 | 200083425 | 1Y Analyser Filter Replacement 409QT501 | AA53.409QT501 | ANLZ,GT4009 FUEL GAS SUPPLY |  | 10 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10578991 Del 80935805 DELIVERY CREATED – Not Loaded |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000120726 | 2 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 | [7 empty] | 2024-06-30 | 0 |  |  |  |  | 2200670029 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000120098 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Pre-costed/Object created/Date set by external system/Printed/Material committed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | S4H Cutover Material
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | QMI | 200083425 | 0010 | 0010 | 200083425 | 1Y Analyser Filter Replacement 409QT501 | AA53.409QT501 | ANLZ,GT4009 FUEL GAS SUPPLY |  | 10 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10578979 Del 80935805 DELIVERY CREATED – Not Loaded |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000120726 | 1 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 | [7 empty] | 2024-06-30 | 0 |  |  |  |  | 2200670029 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000120098 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Pre-costed/Object created/Date set by external system/Printed/Material committed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | S4H Cutover Material
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 |  | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0090 | 0160 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 |  | 10 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10608254 Del 71079639 DELIVERY CREATED – EXW in Transit |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000121037 | 16 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-15 | [7 empty] | 2024-06-30 | 0 |  |  |  |  | 2200670051 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0090 | HYDRAULIC OIL FILTER REPLACEMENT | INT | HYDRAULIC OIL FILTER REPLACEMENT | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT8 | MJ |  | 1000120419 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | S4H Cutover Material
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 |  | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0080 | 0330 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 |  | 10 | No Issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 08.02 - PO EXW In Transit: WO line to be re-added when MN recd at PBRC. |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000121037 | 15 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-15 | [7 empty] | 2024-06-30 | 0 |  |  |  |  | 2200670051 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0080 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT8 | MJ |  | 1000120419 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | S4H Cutover Material
| 24SDTOT2 | Released | 2024-01-02 | 2024-02-12 |  | 2024-05-10 | 2024-05-10 | WORK | 200091240 | 0010 | 0010 | 200091240 | 10Y RECERTIFY PSV DISPOSABLE | AA53.47RV756 | PSV,ACTD CTRL VALVE 210UV441 |  | 10 | No issue identified |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 15.02 MN 10260758 Delivery Consumed (DWR 80850708) |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000129418 | 1 | 0 | [9 empty] | WorkPackLink |  | Delivered Pre S/4 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-03-13 | [7 empty] | 2024-08-20 | 0 |  |  |  |  | 1-99280 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | CERTIFY PSV | INT | CERTIFY PSV | 0 | [9 empty] | 0070 | Main Work Started (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDTOT2 | MJ |  | 1000128889 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  | 2024-03-13 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-10 | 2024-05-10 | 2024-05-10 | Partially confirmed/Printed/Material shortage/Date set by external system/Ready For Scheduling/Object created/Pre-costed/Settlement rule created/Released/Goods movement posted | AM02 | Proactive Maintenance |  | S4H Cutover Material
1 | 24SDLN1 | Released | 2024-01-01 | 2024-02-03 |  | 2024-05-03 | 2024-05-03 | INLEC | 100034626 | 0010 | 0010 | 100034626 | OPSD 1K1410 Turb Heat Det Fault 160TZ511 | AA53.160TZ511A | LOOP,HEAT DETECT 1KT1410 TURBINE COMPART |  | 10 | WO item has not been released yet |  |  | 1 | EA | 0 | 0 | 0 | 0 |  | 26.02 - MN: 10026434 to be readded, Available Inventory frm Legacy WO 2100367125 |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 07 | Execution | 0000133118 | 1 | 0 | [9 empty] | WorkPackLink |  | AU01-P08-OPSD | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-02-03 | [7 empty] | 2023-09-24 | 0 |  |  |  |  | 160TS511A |  | 0 | 0 | 0 | 0 | 0 |  | 2 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | OPSD Turb Heat Det Fault 160TZ511 - CNFd | INT | OPSD Turb Heat Det Fault 160TZ511 - CNFd | 5 | Opportune Shutdown | [8 empty] | 0070 | Main Work Started (Order) | ZBPM0001 | 0 | [9 empty] | 10 |  | 0 |  | 0 |  | 24SDLN1 | MJ |  | 1000132528 |  |  |  |  | 0 |  |  | 0 | 0 | [5 empty] | Opportune Shutdown |  |  | 1070 |  | 2024-02-03 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Ready For Scheduling Canceled/Part printed/Job In Process/Partially confirmed/Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT7 | Released | 2024-01-01 | 2023-06-19 |  | 2024-05-02 | 2024-05-06 | ROTAT | 100038439 | 0010 | 0010 | 100038439 | GT7 REPLACE GRAVITY DAMPERS GT4007K1A/K1 | AA53.GT4007K1A | FAN,TURB ACCOUSTIC ENCLOSURE VENT,GT4007 |  | 30 | No issue identified |  |  | 250 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10449755 Del 71032240 DELIVERY CREATED – In Loading Area on KGP Facil |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000136971 | 1 | 0 | [9 empty] | WorkPackLink |  | AU01-P08-UT | 0 |  | 0 | 0 |  | 0 | 250 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-02 | [7 empty] | 2023-12-01 | 0 |  |  |  |  | 2100356339 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0010 | Install Scaffold Access | INT | Install Scaffold Access | 0 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000136381 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-06 | 2024-05-02 | 2024-05-02 | Estimated costs/Material committed/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SDGT7 | Released | 2024-01-01 | 2023-06-19 |  | 2024-05-02 | 2024-05-06 | ROTAT | 100038439 | 0080 | 0020 | 100038439 | GT7 REPLACE GRAVITY DAMPERS GT4007K1A/K1 | AA53.GT4007K1A | FAN,TURB ACCOUSTIC ENCLOSURE VENT,GT4007 |  | 30 | No issue identified |  |  | 2 | EA | 0 | 0 | 0 | 0 |  | 14.02 - MN:10579907 Del 71057334 DELIVERY CONSUMED |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000136971 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-P08-UT | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2023-12-01 | 0 |  |  |  |  | 2100356339 |  | 0 | 0 | 0 | 0 | 0 |  | 3 | T |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  |  |  |  | 0080 | Remove & Replace K1A & K1B dampers | INT | Remove & Replace K1A & K1B dampers | 3 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000136381 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-06 | 2024-05-02 | 2024-05-02 | Estimated costs/Material committed/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | S4H Cutover Material
| 24SD3410 | Released | 2024-02-27 | 2024-03-02 | 2024-02-28 | 2024-05-06 | 2024-05-06 | INLEC | 100072705 | 0020 | 0040 | 100072705 | MoC-49660 - K3410A Seal Vulnerability | AA53.134PDT503 | TX,DIFF PRESS S/O PUMP AUTO START | AA01 | 20 | No issue identified | 10235077 | M/FOLD,BLK;AGCO AS4TVIS2NPT/1SGGYIWP | 2 | EA | 53 | 0 | 9 | 2 | EA | X 2 BOX'S | Supply for Order 100072705, Item 4 cannot be changed 9000381 item 40 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300007233 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180007934 | 9000381 | 05 | Preparation | 0000219271 | 4 | 0 | EA | 102000000002354 |  | 102000000002484 | 01-Road | 20000363 |  | 2-Loaded |  | WorkPackLink | P07YRDBAY8 | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-02-27 | GRST-5000029191_2024 | 0 | 0 | 0 |  | 2024-02-29 | AA53 | 2024-05-06 |  |  | 2024-03-02 |  |  | 100000003411 | 1020 | 2024-10-05 | 2 | 4900034037_2024_0007 |  | 2024-03-01 | 2024-03-02 | 134PT503,505 | 5000029191_2024_0004 | 0 | 2 | 0 | 2 | 0 | 180007934 | 3 | L | 4900034037 | 2024 |  | 5000029191 | 2024 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10235077 | M/FOLD,BLK;AGCO AS4TVIS2NPT/1SGGYIWP |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 9000381_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90002681 |  | 20 |  | 4 |  | 0 |  | 24SD3410 | MJ | AU1072 | 1000217166 | S002 | 30 | 30 | 5300007233 | 40 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-02-07 | 219271 | 0 |  | 1 |  |  | RC00025003 | 2024-05-06 | 2024-05-06 | 2024-05-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | Material Handed to Maintenance
| 24SD3410 | Released | 2024-02-27 | 2024-03-02 | 2024-02-28 | 2024-05-06 | 2024-05-06 | INLEC | 100072705 | 0020 | 0020 | 100072705 | MoC-49660 - K3410A Seal Vulnerability | AA53.134PDT503 | TX,DIFF PRESS S/O PUMP AUTO START | AA01 | 20 | No issue identified | 10262888 | PLATE KIT,MTG;SS316,AGCO MPA2 | 2 | EA | 33 | 0 | 7 | 2 | EA | IN GRAY TUB | Supply for Order 100072705, Item 2 cannot be changed 9000381 item 20 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300007233 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180007934 | 9000381 | 05 | Preparation | 0000219271 | 2 | 0 | EA | 102000000002425 | 102000000002412 | 102000000002484 | 01-Road | 20000363 |  | 2-Loaded |  | WorkPackLink | P07YRDBAY8 | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-02-27 | GRST-5000029191_2024 | 0 | 0 | 0 |  | 2024-02-29 | AA53 | 2024-05-06 |  |  | 2024-03-02 |  |  | 100000003411 | 1020 | 2024-10-05 | 2 | 4900034037_2024_0003 |  | 2024-03-01 | 2024-03-02 | 134PT503,505 | 5000029191_2024_0002 | 0 | 2 | 0 | 2 | 0 | 180007934 | 3 | L | 4900034037 | 2024 |  | 5000029191 | 2024 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262888 | PLATE KIT,MTG;SS316,AGCO MPA2 |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 9000381_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90002681 |  | 20 |  | 2 |  | 0 |  | 24SD3410 | MJ | AU1072 | 1000217166 | S002 | 30 | 30 | 5300007233 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-02-07 | 219271 | 0 |  | 1 |  |  | RC00025003 | 2024-05-06 | 2024-05-06 | 2024-05-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | Material Handed to Maintenance
| 24SD3410 | Released | 2024-02-27 | 2024-03-02 | 2024-02-28 | 2024-05-06 | 2024-05-06 | INLEC | 100072705 | 0020 | 0050 | 100072705 | MoC-49660 - K3410A Seal Vulnerability | AA53.134PDT503 | TX,DIFF PRESS S/O PUMP AUTO START | AA01 | 20 | No issue identified | 10486195 | FITTING,CAL,1/4",ELBOW 90DEG,BLEED VV | 4 | ASY | 70 | 0 | 18 | 4 | ASY | IN GRAY TUB | Supply for Order 100072705, Item 5 cannot be changed 9000381 item 50 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300007233 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  | 180007934 | 9000381 | 05 | Preparation | 0000219271 | 5 | 0 | ASY | 102000000002425 | 102000000002416 | 102000000002484 | 01-Road | 20000363 |  | 2-Loaded |  | WorkPackLink | P07YRDBAY8 | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y | 1001 | 2024-02-27 | GRST-5000029191_2024 | 0 | 0 | 0 |  | 2024-02-29 | AA53 | 2024-05-06 |  |  | 2024-03-02 |  |  | 100000003411 | 1020 | 2024-10-05 | 4 | 4900034037_2024_0009 |  | 2024-03-01 | 2024-03-02 | 134PT503,505 | 5000029191_2024_0005 | 0 | 2 | 0 | 4 | 0 | 180007934 | 3 | L | 4900034037 | 2024 |  | 5000029191 | 2024 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10486195 | FITTING,CAL,1/4",ELBOW 90DEG,BLEED VV |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 9000381_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90002681 |  | 20 |  | 5 |  | 0 |  | 24SD3410 | MJ | AU1072 | 1000217166 | S002 | 30 | 30 | 5300007233 | 50 |  |  | 0 | 4 | ASY | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-02-07 | 219271 | 0 |  | 1 |  |  | RC00025003 | 2024-05-06 | 2024-05-06 | 2024-05-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | Material Handed to Maintenance
| 24SD3410 | Released | 2024-02-27 | 2024-03-05 | 2024-03-03 | 2024-05-06 | 2024-05-06 | INLEC | 100072705 | 0020 | 0060 | 100072705 | MoC-49660 - K3410A Seal Vulnerability | AA53.134PDT503 | TX,DIFF PRESS S/O PUMP AUTO START | AA01 | 20 | No issue identified | 10262888 | PLATE KIT,MTG;SS316,AGCO MPA2 | 1 | EA | 33 | 0 | 7 | 1 | EA | 05.03 - 35 SOH @ AA02 | Supply for Order 100072705, Item 6 cannot be changed 90003699 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300007233 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180008234 | 90003699 | 05 | Preparation | 0000219271 | 6 | 0 | EA |  |  | 102000000002574 | 01-Road | 1000000872 |  | 1-Not Started |  | WorkPackLink | KSF-KGP-RUNNER-SML | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-27 | GRST-5000029786_2024 | 1 | 0 | 0 |  | 2024-03-03 | AA53 | 2024-05-06 |  |  | 2024-03-06 |  |  | 100000003654 | 1020 | 2024-10-05 | 1 | 4900034551_2024_0001 |  | 2024-03-05 | 2024-03-06 | S.Kinlock | 5000029786_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180008234 | 3 | L | 4900034551 | 2024 |  | 5000029786 | 2024 |  |  | 2024-03-03 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262888 | PLATE KIT,MTG;SS316,AGCO MPA2 |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 90003699_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90003699 |  | 20 |  | 6 |  | 0 |  | 24SD3410 | MJ | AU1072 | 1000217166 | S002 | 30 | 30 | 5300007233 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-03-03 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-02-07 | 219271 | 0 |  | 1 |  |  | RC00025003 | 2024-05-06 | 2024-05-06 | 2024-05-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | Material Handed to Maintenance
| 24SD3410 | Released | 2024-02-27 | 2024-03-02 | 2024-02-28 | 2024-05-06 | 2024-05-06 | INLEC | 100072705 | 0020 | 0030 | 100072705 | MoC-49660 - K3410A Seal Vulnerability | AA53.134PDT503 | TX,DIFF PRESS S/O PUMP AUTO START | AA01 | 20 | No issue identified | 10413219 | SHADE,SUN;300X200X125MM,316SS,AGCO 2S | 2 | EA | 4 | 0 | 2 | 2 | EA | IN GRAY TUB | Supply for Order 100072705, Item 3 cannot be changed 9000381 item 30 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300007233 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180007934 | 9000381 | 05 | Preparation | 0000219271 | 3 | 0 | EA | 102000000002425 | 102000000002369 | 102000000002484 | 01-Road | 20000363 |  | 2-Loaded |  | WorkPackLink | P07YRDBAY8 | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-02-27 | GRST-5000029191_2024 | 0 | 0 | 0 |  | 2024-02-29 | AA53 | 2024-05-06 |  |  | 2024-03-02 |  |  | 100000003411 | 1020 | 2024-10-05 | 2 | 4900034037_2024_0005 |  | 2024-03-01 | 2024-03-02 | 134PT503,505 | 5000029191_2024_0003 | 0 | 2 | 0 | 2 | 0 | 180007934 | 3 | L | 4900034037 | 2024 |  | 5000029191 | 2024 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10413219 | SHADE,SUN;300X200X125MM,316SS,AGCO 2S |  | 0020 | Complete Replacement | INT | Complete Replacement |  |  | 9000381_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90002681 |  | 20 |  | 3 |  | 0 |  | 24SD3410 | MJ | AU1072 | 1000217166 | S002 | 30 | 30 | 5300007233 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W41533 | 2024-02-07 | 219271 | 0 |  | 1 |  |  | RC00025003 | 2024-05-06 | 2024-05-06 | 2024-05-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | Material Handed to Maintenance
| 24SDGT9 | Released | 2024-02-08 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | ROTAT | 200079166 | 0080 | 0030 | 200079166 | 12Y P01 INT INSP PRESS VESSEL GT4009S5B | AA53.GT4009S5B | FILT,GT4009 FUEL GAS | AA01 | 10 | No Issue identified | 10008156 | FILTER,CART;GF,5.5X36",NP ISM4113520 | 1 | EA | 2 | 0 | 2 | 1 | EA | 01.04 - 2 SOH @ AA53 | Supply for Order 200079166, Item 3 cannot be changed 90000846 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006252 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004322 | 90000846 | 05 | Preparation | 0000113522 | 3 | 0 | EA | 102000000001211 |  | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-02-08 | GRST-5000017970_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-07-15 | 1 | 4900030507_2024_0001 |  | 2024-02-12 | 2024-05-03 | 200079166 | 5000017970_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004322 | 3 | L | 4900030507 | 2024 |  | 5000017970 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008156 | FILTER,CART;GF,5.5X36",NP ISM4113520 |  | 0080 | Install Filters, Top Lid / N-11 | INT | Install Filters, Top Lid / N-11 |  | Ready for Release | 90000846_0010 | [7 empty] | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000846 |  | 5 |  | 3 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000112885 | S002 | 30 | 30 | 5300006252 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  | Ready for Release | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 113522 | 0 |  | 2 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-02-08 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | ROTAT | 200079169 | 0080 | 0010 | 200079169 | 12Y P01 INT INSP PRESS VESSEL GT4009S5A | AA53.GT4009S5A | FILT,GT4009 FUEL GAS | AA01 | 10 | No Issue identified | 10008156 | FILTER,CART;GF,5.5X36",NP ISM4113520 | 1 | EA | 2 | 0 | 2 | 1 | EA | 01.04 - 2 SOH @ AA53 | Supply for Order 200079169, Item 1 cannot be changed 90000845 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006253 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004336 | 90000845 | 05 | Preparation | 0000113524 | 1 | 0 | EA | 102000000001212 |  | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-02-08 | GRST-5000017938_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-07-15 | 1 | 4900030572_2024_0001 |  | 2024-02-12 | 2024-05-03 | 200079169 | 5000017938_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004336 | 3 | L | 4900030572 | 2024 |  | 5000017938 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10008156 | FILTER,CART;GF,5.5X36",NP ISM4113520 |  | 0080 | Install Filters, Top Lid / N-11 | INT | Install Filters, Top Lid / N-11 |  |  | 90000845_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000845 |  | 5 |  | 1 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000112888 | S002 | 30 | 30 | 5300006253 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 113524 | 0 |  | 2 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-02-07 | 2024-05-15 | 2024-04-30 | 2024-02-04 | 2024-06-07 | INLEC | 100037026 | 0030 | 0030 | 100037026 | MOC-118435 CO2 Discharge Switch Replacem | AA53.860PZ653 | SW,PRESS DISCH EXT CO2 T/ENCL GT4008 | AA01 | 20 | No Issue identified | 10038174 | TUBE;0.25",1.2MM,SRL,A269-TP316L,SML | 10 | EA | 21 | 0 | 2 | 10 | EA | 28.02 - 7 Delivered to AA53, 14 coming from AA02 | Supply for Order 100037026, Item 3 cannot be changed 9000023 item 30 already exists | Material Consumed | SP12 | Stock at Base | 0 | AA02 | 5300006181 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004301 | 9000023 | 07 | Execution | 0000135527 | 3 | 0 | EA |  |  | 102000000001190 | 01-Road | 1000000499 |  | 5-Completed |  | WorkPackLink | P07YRDBAY8 | AA53-TA-P07 | 0 |  | 0 | 0 |  | 10 | 0 | 2024-02-13 |  | Y | 1001 | 2024-02-07 |  | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2023-12-31 | 10 | 4900030516_2024_0003 |  | 2024-02-12 | 2024-05-03 |  | 5000018681_2024_0001 | 0 | 2 | 0 | 10 | 0 | 180004301 | 3 | L | 4900030516 | 2024 |  | 5000018681 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10038174 | TUBE;0.25",1.2MM,SRL,A269-TP316L,SML |  | 0030 | Complete Replacement | INT | Complete Replacement |  |  | 9000023_0030 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000782 |  | 20 |  | 3 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000134916 | S002 |  | 30 | 5300006181 | 30 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  | 2024-02-04 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 135527 | 0 |  | 3 |  |  | RC00025003 | 2024-06-07 | 2024-02-04 | 2024-02-04 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Printed/Goods movement posted | AM01 | Reactive Maintenance |  | Consumed
| 24SDGT8 | Released | 2024-02-07 | 2024-05-15 | 2024-04-30 | 2024-02-04 | 2024-06-07 | INLEC | 100037026 | 0030 | 0010 | 100037026 | MOC-118435 CO2 Discharge Switch Replacem | AA53.860PZ653 | SW,PRESS DISCH EXT CO2 T/ENCL GT4008 | AA01 | 20 | No Issue identified | 10602434 | ENCLOSURE,TB;EX,AL,FUCHS FW24XBK6JB | 3 | EA | 29 | 0 | 0 | 3 | EA | 28.02 - 3 Delivered to AA53 | Supply for Order 100037026, Item 1 cannot be changed 9000023 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006181 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004301 | 9000023 | 07 | Execution | 0000135527 | 1 | 0 | EA | 102000000001185 |  | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AA53-TA-P07 | 0 | 5400000103 | 10 | 3 | EA | 0 | 3 | 2024-02-13 |  | Y | 1001 | 2024-02-07 | GRST-5000017849_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2023-12-31 | 3 | 4900030516_2024_0001 |  | 2024-02-12 | 2024-05-03 |  | 5000017849_2024_0001 | 0 | 2 | 0 | 3 | 0 | 180004301 | 3 | L | 4900030516 | 2024 |  | 5000017849 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10602434 | ENCLOSURE,TB;EX,AL,FUCHS FW24XBK6JB |  | 0030 | Complete Replacement | INT | Complete Replacement |  |  | 9000023_0010 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000782 |  | 20 |  | 1 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000134916 | S002 | 30 | 30 | 5300006181 | 10 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  | 2024-02-04 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 135527 | 0 |  | 3 |  |  | RC00025003 | 2024-06-07 | 2024-02-04 | 2024-02-04 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Printed/Goods movement posted | AM01 | Reactive Maintenance |  | KSF
| 24SDLN1 | Released | 2024-02-07 | 2024-05-02 | 2024-04-29 | 2024-04-26 | 2024-05-04 | VALVE | 100072016 | 0040 | 0030 | 100072016 | CV-OH 8" 600# 114PCV13 | AA53.114PCV13 | VALVE,PRESS CTRL 1E1405 | AA01 | 20 | No Issue identified | 10024101 | LINER;GUIDE,2" STEM,FLOWSV 057362927000 | 2 | EA | 3 | 0 | 0 | 2 | EA | IN GREY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006172 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006608 | 05 | Preparation | 0000216559 | 3 | 0 | EA | 102000000003751 |  | 102000000003733 | [5 empty] | WorkPackLink | PACKING | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-02-07 | ODST-0090006608_0030 | 0 | 0 | 0 |  | 2024-04-30 | AA53 | 2024-05-02 |  |  | 2024-05-02 |  |  |  |  | 2024-07-22 | 0 |  |  | 2024-04-29 | 2024-05-02 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10024101 | LINER;GUIDE,2" STEM,FLOWSV 057362927000 |  | 0040 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind |  |  | 90006608_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006608 |  | 20 |  | 3 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000214974 | S002 | 30 | 30 | 5300006172 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-29 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPDGT | 2024-01-24 | 216559 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-04-26 | 2024-04-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDLN1 | Released | 2024-02-07 | 2024-05-02 | 2024-04-29 | 2024-04-26 | 2024-05-04 | VALVE | 100072016 | 0040 | 0040 | 100072016 | CV-OH 8" 600# 114PCV13 | AA53.114PCV13 | VALVE,PRESS CTRL 1E1405 | AA01 | 20 | No Issue identified | 10023623 | PACKING,VEE;PTFE,FLOWSV 020760925000 | 1 | SET | 3 | 0 | 0 | 1 | SET | IN GREY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006172 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90006608 | 05 | Preparation | 0000216559 | 4 | 0 | SET | 102000000003752 |  | 102000000003733 | [5 empty] | WorkPackLink | PACKING | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-07 | ODST-0090006608_0040 | 0 | 0 | 0 |  | 2024-04-30 | AA53 | 2024-05-02 |  |  | 2024-05-02 |  |  |  |  | 2024-07-22 | 0 |  |  | 2024-04-29 | 2024-05-02 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10023623 | PACKING,VEE;PTFE,FLOWSV 020760925000 |  | 0040 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind |  |  | 90006608_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006608 |  | 20 |  | 4 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000214974 | S002 | 30 | 30 | 5300006172 | 40 |  |  | 0 | 1 | SET | 2001 | AA02 | 2024-04-29 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPDGT | 2024-01-24 | 216559 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-04-26 | 2024-04-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDLN1 | Released | 2024-02-07 | 2024-05-02 | 2024-04-29 | 2024-04-26 | 2024-05-04 | VALVE | 100072016 | 0040 | 0010 | 100072016 | CV-OH 8" 600# 114PCV13 | AA53.114PCV13 | VALVE,PRESS CTRL 1E1405 | AA01 | 20 | No Issue identified | 10024218 | GASKET,SW;202 X 208 X 3.25MM,316L/GR | 1 | EA | 3 | 0 | 0 | 1 | EA | IN GREY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006172 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006608 | 05 | Preparation | 0000216559 | 1 | 0 | EA | 102000000003744 |  | 102000000003733 | [5 empty] | WorkPackLink | PACKING | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-07 | ODST-0090006608_0010 | 0 | 0 | 0 |  | 2024-04-30 | AA53 | 2024-05-02 |  |  | 2024-05-02 |  |  |  |  | 2024-07-22 | 0 |  |  | 2024-04-29 | 2024-05-02 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10024218 | GASKET,SW;202 X 208 X 3.25MM,316L/GR |  | 0040 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind |  |  | 90006608_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006608 |  | 20 |  | 1 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000214974 | S002 |  | 30 | 5300006172 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-29 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPDGT | 2024-01-24 | 216559 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-04-26 | 2024-04-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDLN1 | Released | 2024-02-07 | 2024-05-02 | 2024-04-29 | 2024-04-26 | 2024-05-04 | VALVE | 100072016 | 0040 | 0020 | 100072016 | CV-OH 8" 600# 114PCV13 | AA53.114PCV13 | VALVE,PRESS CTRL 1E1405 | AA01 | 20 | No Issue identified | 10024219 | GASKET,SW;VALTEK 001799868000 | 1 | EA | 1 | 0 | 0 | 1 | EA | IN GREY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006172 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006608 | 05 | Preparation | 0000216559 | 2 | 0 | EA | 102000000003744 |  | 102000000003733 | [5 empty] | WorkPackLink | PACKING | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-02-07 | ODST-0090006608_0020 | 0 | 0 | 0 |  | 2024-04-30 | AA53 | 2024-05-02 |  |  | 2024-05-02 |  |  |  |  | 2024-07-22 | 0 |  |  | 2024-04-29 | 2024-05-02 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10024219 | GASKET,SW;VALTEK 001799868000 |  | 0040 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind |  |  | 90006608_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006608 |  | 20 |  | 2 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000214974 | S002 | 30 | 30 | 5300006172 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-29 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPDGT | 2024-01-24 | 216559 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-04-26 | 2024-04-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDGT9 | Released | 2024-02-06 | 2024-05-19 | 2024-04-29 | 2024-05-19 | 2024-05-19 | ROTAT | 100033767 | 0010 | 0010 | 100033767 | Replace Servo Filter and Compensator | AA53.GT4009A3 | PKG EQ,GT4009A3 HYDRAULIC STARTING SKID | AA01 | 20 | No Issue identified | 10530791 | OIL,LUB;SHELL TURBO S4 X 32,209L | 2 | DR | 0 | 2 | 2 | 2 | DR | 06.03 - 2 Delivered to AA53 | Supply for Order 100033767, Item 5 cannot be changed 9000032 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300006126 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180004325 | 9000032 | 05 | Preparation | 0000132281 | 5 | 0 | DR |  |  | 102000000001149 | 01-Road | 1000000499 |  | 5-Completed |  | WorkPackLink | P07YRDBAY8 |  | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-13 |  | Y | 1001 | 2024-02-06 | GRST-5000018218_2024 | 0 | 0 | 0 |  | 2024-04-30 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-03-13 | 2 | 4900030570_2024_0001 |  | 2024-02-12 | 2024-05-02 |  | 5000018218_2024_0001 | 0 | 2 | 0 | 2 | 0 | 180004325 | 3 | L | 4900030570 | 2024 |  | 5000018218 | 2024 |  |  | 2024-04-29 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10530791 | OIL,LUB;SHELL TURBO S4 X 32,209L |  | 0010 | Drain Oil | ENON | Drain Oil |  |  | 9000032_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000784 |  | 20 |  | 5 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000131663 | S002 | 30 | 30 | 5300006126 | 30 |  |  | 0 | 2 | DR | 2001 | AA02 | 2024-04-29 | W35069 |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132281 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | KSF
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0200 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC |  | 255 | No issue identified | 10589686 | SCREW;S/TAP,4.2X13MM,PAN HD,PHIL,SS,WSHR | 2 | PAC | 0 | 0 | 2 | 2 | PAC | 22.03 - qty 2 SOH @ AA02 | Supply for Order 100033847, Item 20 cannot be changed 9000596 item 180 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | PAC |  |  |  | 180013609 | 9000596 | 07 | Execution | 0000132381 | 20 | 0 | PAC | 102000000003649 |  | 102000000003683 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | P07-BENCH | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-15 | GRST-5000045904 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  | 100000005106 | 1020 | 2025-10-01 | 2 | 4900040481_2024_0025 |  | 2024-03-26 | 2024-05-03 |  | 5000045904_2024_0013 | 0 | 2 | 0 | 2 | 0 | 180013609 | 3 | L | 4900040481 | 2024 |  | 5000045904 | 2024 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10589686 | SCREW;S/TAP,4.2X13MM,PAN HD,PHIL,SS,WSHR |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 9000596_0180 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 20 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 200 |  |  | 0 | 2 | PAC | 2001 | AA02 | 2024-04-30 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-03-16 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0320 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10204140 | BAG,PL;1200X900MM,200UM | 5 | EA | 815 | 170 | 60 | 5 | EA | 13.03 - SOH @ AA02 | Supply for Order 100033847, Item 32 cannot be changed 9000598 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 320 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180014018 | 9000598 | 07 | Execution | 0000132381 | 32 | 0 | EA | 102000000003757 |  | 102000000003599 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | KSF-KGP P07P08 SML | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-01-15 | GRST-5000047022_2024 | 13 | 0 | 0 |  | 2024-03-04 | AA53 | 2024-03-06 |  |  | 2024-03-19 |  |  | 100000005124 | 1020 | 2025-10-01 | 5 | 4900040867_2024_0007 |  | 2024-03-27 | 2024-03-19 |  | 5000047022_2024_0004 | 0 | 2 | 0 | 5 | 0 | 180014018 | 3 | L | 4900040867 | 2024 |  | 5000047022 | 2024 |  |  | 2024-03-16 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204140 | BAG,PL;1200X900MM,200UM |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 9000598_0040 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90005862 |  | 99 |  | 32 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 320 |  |  | 0 | 5 | EA | 2001 | AA02 | 2024-03-16 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-03-16 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0280 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10258211 | WASHER,NEOPRENE,10GGE,TEK SCREW TYPE | 100 | EA | 8230 | 0 | 100 | 100 | EA | 11.03 - SOH @ AA02 | Supply for Order 100033847, Item 28 cannot be changed 9000598 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 280 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180014018 | 9000598 | 07 | Execution | 0000132381 | 28 | 0 | EA | 102000000003755 |  | 102000000003599 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | KSF-KGP P07P08 SML | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 100 |  |  | Y | 1001 | 2024-01-15 | GRST-5000047022_2024 | 13 | 0 | 0 |  | 2024-03-04 | AA53 | 2024-03-06 |  |  | 2024-03-19 |  |  | 100000005124 | 1020 | 2025-10-01 | 100 | 4900040867_2024_0001 |  | 2024-03-27 | 2024-03-19 |  | 5000047022_2024_0001 | 0 | 2 | 0 | 100 | 0 | 180014018 | 3 | L | 4900040867 | 2024 |  | 5000047022 | 2024 |  |  | 2024-03-16 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258211 | WASHER,NEOPRENE,10GGE,TEK SCREW TYPE |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 9000598_0010 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90005862 |  | 99 |  | 28 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 280 |  |  | 0 | 100 | EA | 2001 | AA02 | 2024-03-16 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0050 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10507299 | SHADECLOTH,KNITTED,1830MM X 50M,UV,GRN | 3 | ROL | 30 | 0 | 4 | 3 | ROL | 26.02 - qty 33 SOH at AA02 | Supply for Order 100033847, Item 5 cannot be changed 9000596 item 40 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180013609 | 9000596 | 07 | Execution | 0000132381 | 5 | 0 | ROL | 102000000003649 |  | 102000000003683 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | P07-BENCH | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-01-15 | GRST-5000045904 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  | 100000005106 | 1020 | 2025-10-01 | 3 | 4900040481_2024_0007 |  | 2024-03-26 | 2024-05-03 |  | 5000045904_2024_0004 | 0 | 2 | 0 | 3 | 0 | 180013609 | 3 | L | 4900040481 | 2024 |  | 5000045904 | 2024 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10507299 | SHADECLOTH,KNITTED,1830MM X 50M,UV,GRN |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 9000596_0040 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 5 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 50 |  |  | 0 | 3 | ROL | 2001 | AA02 | 2024-04-30 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0110 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10059312 | SCREW,SELF TAP,NO.10 X 13MM,PAN,PHIL,SS | 5 | BOX | 26 | 10 | 7 | 5 | BOX | 26.02 - Qty 41 SOH at AA02 | Supply for Order 100033847, Item 11 cannot be changed 9000596 item 100 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | BOX |  |  |  | 180013609 | 9000596 | 07 | Execution | 0000132381 | 11 | 0 | BOX | 102000000003649 |  | 102000000003683 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | P07-BENCH | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-01-15 | GRST-5000045904 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  | 100000005106 | 1020 | 2025-10-01 | 5 | 4900040481_2024_0019 |  | 2024-03-26 | 2024-05-03 |  | 5000045904_2024_0010 | 0 | 2 | 0 | 5 | 0 | 180013609 | 3 | L | 4900040481 | 2024 |  | 5000045904 | 2024 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059312 | SCREW,SELF TAP,NO.10 X 13MM,PAN,PHIL,SS |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 9000596_0100 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 11 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 |  | 30 | 5300004834 | 110 |  |  | 0 | 5 | BOX | 2001 | AA02 | 2024-04-30 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0230 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10562101 | BANDING;SS316L,19MM,0.5MM | 5 | ROL | 24 | 0 | 6 | 5 | ROL | 26.02 - qty 29 SOH at AA02 | Supply for Order 100033847, Item 22 cannot be changed 9000596 item 200 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 220 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180013609 | 9000596 | 07 | Execution | 0000132381 | 22 | 0 | ROL | 102000000003649 |  | 102000000003683 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | P07-BENCH | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-01-15 | GRST-5000045904 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  | 100000005106 | 1020 | 2025-10-01 | 5 | 4900040481_2024_0029 |  | 2024-03-26 | 2024-05-03 |  | 5000045904_2024_0015 | 0 | 2 | 0 | 5 | 0 | 180013609 | 3 | L | 4900040481 | 2024 |  | 5000045904 | 2024 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10562101 | BANDING;SS316L,19MM,0.5MM |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 9000596_0200 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 22 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 220 |  |  | 0 | 5 | ROL | 2001 | AA02 | 2024-04-30 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0060 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10204192 | SEALANT,SILICONE,ADVANTAGE 780,300G TUBE | 70 | TB | 215 | 0 | 71 | 70 | TB | 26.02 - Qty 285 SOH at AA02 | Supply for Order 100033847, Item 6 cannot be changed 9000596 item 50 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | TB |  |  |  | 180013609 | 9000596 | 07 | Execution | 0000132381 | 6 | 0 | TB | 102000000003648 |  | 102000000003683 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | P07-BENCH | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 70 |  |  | Y | 1001 | 2024-01-15 | GRST-5000045904 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  | 100000005106 | 1020 | 2025-10-01 | 70 | 4900040481_2024_0009 |  | 2024-03-26 | 2024-05-03 |  | 5000045904_2024_0005 | 0 | 2 | 0 | 70 | 0 | 180013609 | 3 | L | 4900040481 | 2024 |  | 5000045904 | 2024 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10204192 | SEALANT,SILICONE,ADVANTAGE 780,300G TUBE |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 9000596_0050 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 6 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 60 |  |  | 0 | 70 | TB | 2001 | AA02 | 2024-04-30 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0240 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10242501 | SEAL,BANDING;INS,SS316L,19MM | 500 | EA | 293 | 600 | 706 | 500 | EA | 21.03 - 29.03.2024 PO 4500007654 PYROTEK | Supply for Order 100033847, Item 23 cannot be changed 9000596 item 210 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180013609 | 9000596 | 07 | Execution | 0000132381 | 23 | 0 | EA | 102000000003649 |  | 102000000003683 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | P07-BENCH | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 500 |  |  | Y | 1001 | 2024-01-15 | GRST-5000045904 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  | 100000005106 | 1020 | 2025-10-01 | 500 | 4900040481_2024_0031 |  | 2024-03-26 | 2024-05-03 |  | 5000045904_2024_0016 | 0 | 2 | 0 | 500 | 0 | 180013609 | 3 | L | 4900040481 | 2024 |  | 5000045904 | 2024 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10242501 | SEAL,BANDING;INS,SS316L,19MM |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 9000596_0210 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 23 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 230 |  |  | 0 | 500 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0030 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10015665 | PLUG,APCI CRY HEAT EXCH,MODIFIED 6",AL | 10 | EA | 6 | 0 | 10 | 10 | EA | 26.02 - Qty 16 SOH at AA02 | Supply for Order 100033847, Item 3 cannot be changed 9000596 item 30 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180013609 | 9000596 | 07 | Execution | 0000132381 | 3 | 0 | EA | 102000000003649 |  | 102000000003683 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | P07-BENCH | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-01-15 | GRST-5000045904 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  | 100000005106 | 1020 | 2025-10-01 | 10 | 4900040481_2024_0005 |  | 2024-03-26 | 2024-05-03 |  | 5000045904_2024_0003 | 0 | 2 | 0 | 10 | 0 | 180013609 | 3 | L | 4900040481 | 2024 |  | 5000045904 | 2024 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10015665 | PLUG,APCI CRY HEAT EXCH,MODIFIED 6",AL |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 9000596_0030 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 3 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 |  | 30 | 5300004834 | 30 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0100 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10258207 | TAPE;CLOTH,48MM,25M,BLK,TYPE 352 | 50 | ROL | 70 | 34 | 64 | 50 | ROL | 22.03 - qty 120 SOH at AA02 | Supply for Order 100033847, Item 10 cannot be changed 9000596 item 90 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180013609 | 9000596 | 07 | Execution | 0000132381 | 10 | 0 | ROL | 102000000003648 |  | 102000000003683 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | P07-BENCH | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 50 |  |  | Y | 1001 | 2024-01-15 | GRST-5000045904 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  | 100000005106 | 1020 | 2025-10-01 | 50 | 4900040481_2024_0017 |  | 2024-03-26 | 2024-05-03 |  | 5000045904_2024_0009 | 0 | 2 | 0 | 50 | 0 | 180013609 | 3 | L | 4900040481 | 2024 |  | 5000045904 | 2024 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258207 | TAPE;CLOTH,48MM,25M,BLK,TYPE 352 |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 9000596_0090 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 10 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 100 |  |  | 0 | 50 | ROL | 2001 | AA02 | 2024-04-30 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDLN1 | Released | 2024-01-15 | 2024-05-03 | 2024-04-22 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0070 | 0010 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No Issue identified | 11401026 | KIT,TEMP SENS;FLUID,GRACO 261669 | 2 | EA | 0 | 2 | 0 | 2 | EA | 14.03 - qty 2 SOH at AA01 | Supply for Order 100033847, Item 26 cannot be changed 9001090 item 40 already exists | Material In-Transit on-01-Road | SP97 | Direct Multi-base | 4 | AA01 | 5300007337 | 10 | CPT | 7 | 1000003959 | 26 | 30002653 | BELLIS AUSTRALIA PTY LTD | 4500004702 | 10 | 2 | EA | 2024-03-01 |  | 180009584/ | 180014934 | 9001090 | 07 | Execution | 0000132381 | 26 | 0 | EA | 101000000030483 |  | 101000000030328 | 01-Road | 20000801 |  | 5-Completed |  | WorkPackLink |  | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 | 2024-04-04 | 2024-04-04 | Y | 1001 | 2024-02-29 | IDST-0180014934 | 0 | 0 | 0 | 2024-04-18 | 2024-04-28 | AA53 | 2024-05-03 |  |  | 2024-05-03 | 2024-04-20 | 2024-04-30 | 100000054661 | 1010 | 2025-10-01 | 2 | 4900042249_2024_0001 | 5000033210_2024_0001 | 2024-04-02 | 2024-03-08 | B.Vorn TA |  | 0 | 2 | 2 | 0 | 2 | 180014934 | 3 | L | 4900042249 | 2024 | 5000033210 |  | 0 | 2024 | 180009584 | 2024-04-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11401026 | KIT,TEMP SENS;FLUID,GRACO 261669 |  | 0070 | Insulation | INT | Insulation | 7 |  | 9001090_0040 |  |  |  |  | 05 | Release Completed | X | 0070 | Main Work Started (Order) |  | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 90005621 | 2024-04-05 | 99 | 2024-04-20 | 0 |  | 0 |  | 24SDLN1 | MJ | AU1009 | 1000131783 | S001 | 30 | 30 | 5300004834 | 260 |  | 5300007337 | 10 | 2 | EA | 1001 | AA02 | 2024-04-22 |  |  | 2024-04-02 | AU00 | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | In Transit Via Road
| 24SDLN1 | Released | 2024-01-15 | 2024-03-30 | 2024-03-27 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0300 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10507117 | KNIFE,SHOE,120MM | 12 | EA | 12 | 0 | 0 | 12 | EA | 05.04 - 12 SOH @ AA02 PO 4500006812 received | Supply for Order 100033847, Item 30 cannot be changed 90004536 item 20 already exists | Material avail; awaiting work-packing @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 300 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90004536 | 07 | Execution | 0000132381 | 30 | 0 | EA | 101000000026436 |  | 101000000027204 | 01-Road | 20000617 |  | 5-Completed |  | WorkPackLink |  | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 12 | 2024-03-23 | 2024-03-23 | Y | 1001 | 2024-01-15 | ODST-0090004536_0020 | 0 | 0 | 0 |  | 2024-03-28 | AA53 | 2024-03-06 |  |  | 2024-03-30 |  |  |  |  | 2025-10-01 | 0 |  |  | 2024-03-27 | 2024-03-30 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-03-27 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10507117 | KNIFE,SHOE,120MM |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 90004536_0020 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004536 |  | 99 |  | 30 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 300 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-03-27 |  |  | 2024-03-21 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0020 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10290434 | PLUG,TUBE;8.3X7.6X76.2MM LG,TAP,STD,AL | 40 | EA | 9 | 0 | 40 | 40 | EA | 26.02 - qty 49 SOH at AA02 | Supply for Order 100033847, Item 2 cannot be changed 9000596 item 20 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180013609 | 9000596 | 07 | Execution | 0000132381 | 2 | 0 | EA | 102000000003649 |  | 102000000003683 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | P07-BENCH | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 40 |  |  | Y | 1001 | 2024-01-15 | GRST-5000045904 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  | 100000005106 | 1020 | 2025-10-01 | 40 | 4900040481_2024_0003 |  | 2024-03-26 | 2024-05-03 |  | 5000045904_2024_0002 | 0 | 2 | 0 | 40 | 0 | 180013609 | 3 | L | 4900040481 | 2024 |  | 5000045904 | 2024 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10290434 | PLUG,TUBE;8.3X7.6X76.2MM LG,TAP,STD,AL |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 9000596_0020 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 2 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 20 |  |  | 0 | 40 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0080 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10258205 | DRILL,PANEL,COBALT,TWIN POINT,NO.30 | 50 | EA | 192 | 20 | 100 | 50 | EA | 26.02 - qty 272 SOH at AA02 | Supply for Order 100033847, Item 8 cannot be changed 9000596 item 70 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180013609 | 9000596 | 07 | Execution | 0000132381 | 8 | 0 | EA | 102000000003649 |  | 102000000003683 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | P07-BENCH | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 50 |  |  | Y | 1001 | 2024-01-15 | GRST-5000045904 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  | 100000005106 | 1020 | 2025-10-01 | 50 | 4900040481_2024_0013 |  | 2024-03-26 | 2024-05-03 |  | 5000045904_2024_0007 | 0 | 2 | 0 | 50 | 0 | 180013609 | 3 | L | 4900040481 | 2024 |  | 5000045904 | 2024 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258205 | DRILL,PANEL,COBALT,TWIN POINT,NO.30 |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 9000596_0070 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 8 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 |  | 30 | 5300004834 | 80 |  |  | 0 | 50 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0250 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10229643 | SEALANT,FOSTER FLEXTRA 95-50,18.9L PAIL | 1 | DR | 1 | 0 | 1 | 1 | DR | 26.02 - Qty 2 SOH at AA02; qty 1 reqd May 2024, qty 2 reqd June 2024 (CM). | Supply for Order 100033847, Item 24 cannot be changed 9000596 item 220 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 240 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180013609 | 9000596 | 07 | Execution | 0000132381 | 24 | 0 | DR | 102000000003649 |  | 102000000003683 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | P07-BENCH | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-15 | GRST-5000045904 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  | 100000005106 | 1020 | 2025-10-01 | 1 | 4900040481_2024_0033 |  | 2024-03-26 | 2024-05-03 |  | 5000045904_2024_0017 | 0 | 2 | 0 | 1 | 0 | 180013609 | 3 | L | 4900040481 | 2024 |  | 5000045904 | 2024 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10229643 | SEALANT,FOSTER FLEXTRA 95-50,18.9L PAIL |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 9000596_0220 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 24 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 |  | 30 | 5300004834 | 240 |  |  | 0 | 1 | DR | 2001 | AA02 | 2024-04-30 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-03-16 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0290 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10059584 | SPRAYER,HAND;HD,500ML,ADJ | 6 | EA | 92 | 0 | 6 | 6 | EA | 12.03 - SOH @ AA02 /AA01 | Supply for Order 100033847, Item 29 cannot be changed 9000598 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180014018 | 9000598 | 07 | Execution | 0000132381 | 29 | 0 | EA | 102000000003756 |  | 102000000003599 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | KSF-KGP P07P08 SML | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 6 |  |  | Y | 1001 | 2024-01-15 | GRST-5000047022_2024 | 13 | 0 | 0 |  | 2024-03-04 | AA53 | 2024-03-06 |  |  | 2024-03-19 |  |  | 100000005124 | 1020 | 2025-10-01 | 6 | 4900040867_2024_0003 |  | 2024-03-27 | 2024-03-19 |  | 5000047022_2024_0002 | 0 | 2 | 0 | 6 | 0 | 180014018 | 3 | L | 4900040867 | 2024 |  | 5000047022 | 2024 |  |  | 2024-03-16 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059584 | SPRAYER,HAND;HD,500ML,ADJ |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 9000598_0020 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90005862 |  | 99 |  | 29 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 |  | 30 | 5300004834 | 290 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-03-16 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0120 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10059315 | SCREW,SELF TAP,NO.10 X 19MM,PAN,PHIL,SS | 5 | BOX | 0 | 1 | 5 | 5 | BOX | 22.03 - Qty 5 SOH at AA02 | Supply for Order 100033847, Item 12 cannot be changed 9000596 item 110 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | BOX |  |  |  | 180013609 | 9000596 | 07 | Execution | 0000132381 | 12 | 0 | BOX | 102000000003649 |  | 102000000003683 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | P07-BENCH | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-01-15 | GRST-5000045904 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  | 100000005106 | 1020 | 2025-10-01 | 5 | 4900040481_2024_0021 |  | 2024-03-26 | 2024-05-03 |  | 5000045904_2024_0011 | 0 | 2 | 0 | 5 | 0 | 180013609 | 3 | L | 4900040481 | 2024 |  | 5000045904 | 2024 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059315 | SCREW,SELF TAP,NO.10 X 19MM,PAN,PHIL,SS |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 9000596_0110 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 12 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 120 |  |  | 0 | 5 | BOX | 2001 | AA02 | 2024-04-30 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-03-16 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0310 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10258204 | DRILL,PANEL,COBALT,TWIN POINT,NO.11 | 5 | EA | 14 | 0 | 5 | 5 | EA | 13.03 - 19 SOH @ AA02 | Supply for Order 100033847, Item 31 cannot be changed 9000598 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 310 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180014018 | 9000598 | 07 | Execution | 0000132381 | 31 | 0 | EA | 102000000003756 |  | 102000000003599 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | KSF-KGP P07P08 SML | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-01-15 | GRST-5000047022_2024 | 13 | 0 | 0 |  | 2024-03-04 | AA53 | 2024-03-06 |  |  | 2024-03-19 |  |  | 100000005124 | 1020 | 2025-10-01 | 5 | 4900040867_2024_0005 |  | 2024-03-27 | 2024-03-19 |  | 5000047022_2024_0003 | 0 | 2 | 0 | 5 | 0 | 180014018 | 3 | L | 4900040867 | 2024 |  | 5000047022 | 2024 |  |  | 2024-03-16 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258204 | DRILL,PANEL,COBALT,TWIN POINT,NO.11 |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 9000598_0030 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90005862 |  | 99 |  | 31 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 |  | 30 | 5300004834 | 310 |  |  | 0 | 5 | EA | 2001 | AA02 | 2024-03-16 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-04-30 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0070 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10433854 | TAPE,FOIL;TESA 7379,RL/50M | 50 | ROL | 7 | 2 | 56 | 50 | ROL | 26.02 - qty 59 SOH at AA02 | Supply for Order 100033847, Item 7 cannot be changed 9000596 item 60 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | ROL |  |  |  | 180013609 | 9000596 | 07 | Execution | 0000132381 | 7 | 0 | ROL | 102000000003648 |  | 102000000003683 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | P07-BENCH | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 50 |  |  | Y | 1001 | 2024-01-15 | GRST-5000045904 | 58 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-03-06 |  |  | 2024-05-03 |  |  | 100000005106 | 1020 | 2025-10-01 | 50 | 4900040481_2024_0011 |  | 2024-03-26 | 2024-05-03 |  | 5000045904_2024_0006 | 0 | 2 | 0 | 50 | 0 | 180013609 | 3 | L | 4900040481 | 2024 |  | 5000045904 | 2024 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10433854 | TAPE,FOIL;TESA 7379,RL/50M |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 9000596_0060 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004487 |  | 99 |  | 7 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 70 |  |  | 0 | 50 | ROL | 2001 | AA02 | 2024-04-30 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDLN1 | Released | 2024-01-15 | 2024-03-06 | 2024-03-16 | 2024-03-06 | 2024-05-08 | MECH | 100033847 | 0010 | 0330 | 100033847 | LNG1 MCHE Repair NG/HMR Tube Leak | AA53.1E1405 | EXCH,VESSEL MAIN CRYOGENIC | AA01 | 255 | No issue identified | 10249634 | LANOLIN,LIQ;LANOTEC GP0020 | 1 | DR | 3 | 0 | 1 | 1 | DR | 12.03- 5 SOH @ AA02 | Supply for Order 100033847, Item 33 cannot be changed 9000598 item 50 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004834 | 330 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180014018 | 9000598 | 07 | Execution | 0000132381 | 33 | 0 | DR | 102000000003758 |  | 102000000003599 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | KSF-KGP P07P08 SML | TA-P07 LNG1 MCHE | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-15 | GRST-5000047022_2024 | 13 | 0 | 0 |  | 2024-03-04 | AA53 | 2024-03-06 |  |  | 2024-03-19 |  |  | 100000005124 | 1020 | 2025-10-01 | 1 | 4900040867_2024_0009 |  | 2024-03-27 | 2024-03-19 |  | 5000047022_2024_0005 | 0 | 2 | 0 | 1 | 0 | 180014018 | 3 | L | 4900040867 | 2024 |  | 5000047022 | 2024 |  |  | 2024-03-16 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10249634 | LANOLIN,LIQ;LANOTEC GP0020 |  | 0010 | Pre Shut Scaffold | INT | Pre Shut Scaffold | 0 |  | 9000598_0050 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90005862 |  | 99 |  | 33 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000131783 | S002 | 30 | 30 | 5300004834 | 330 |  |  | 0 | 1 | DR | 2001 | AA02 | 2024-03-16 |  |  | 2024-03-27 |  | 1070 |  | 2024-03-06 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 132381 | 0 |  | 1 |  |  | RC00025003 | 2024-05-08 | 2024-03-06 | 2024-03-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Partially confirmed/Part printed/Ready For Scheduling Canceled | AM01 | Reactive Maintenance | M0-000001-99-01 | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-03 | INLEC | 100033128 | 0020 | 0020 | 100033128 | Replace C02 Load Cell Controller GT4007 | AA53.760GS65L | TXDCR,GT4007V3 CO2 TK WEIGHT LOW ALM |  | 20 | No Issue identified | 10530765 | MODULE,WEIGHING DEVICE,HBM 1WE2111 | 0 | EA | 0 | 0 | 0 | 0 |  | 22.02 - MN readded Delivery Staged in SW3R15D01B |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000131600 | 2 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2024-04-19 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10530765 | MODULE,WEIGHING DEVICE,HBM 1WE2111 |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000131030 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material committed/Order Approved/Released/Settlement rule created/Pre-costed/Object created/Date set by external system | AM01 | Reactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-22 | 2024-05-03 | 2024-05-03 | INLEC | 100035583 | 0005 | 0010 | 100035583 | MOC-72065 Modify GT7 Hard-Wired Trip S2A | AA53.S2A1A4 | FEEDER,GENERATOR G4007 INCOMER | AA01 | 30 | No Issue identified | 11400594 | RELAY,IF;24VACDC,6A,ABB 1SNA645019R0400 | 1 | EA | 0 | 0 | 0 | 1 | EA | 02.04 - 2 SOH @ AA01 | Supply for Order 100035583, Item 8 cannot be changed 90005621 item 10 already exists | Workpack awaiting Shipment @AA01 | SP97 | Direct Multi-base | 48 | AA01 | 5300006569 | 10 | CPT | 14 | 1000002694 | 8 | 30000411 | ABB AUSTRALIA PTY LTD | 4500004081 | 10 | 1 | EA | 2024-04-19 |  | /180013944 |  | 90005621 | 05 | Preparation | 0000134055 | 8 | 0 | EA | 101000000030454 |  | 101000000030761 | 01-Road | 20000494 |  | 5-Completed |  | WorkPackLink | KBSB |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-04-05 | 2024-04-05 | Y | 1001 | 2024-02-14 | ODST-0090005621_0010 | 0 | 0 | 0 | 2024-04-18 | 2024-04-28 | AA53 | 2024-05-03 |  |  | 2024-05-03 | 2024-04-20 | 2024-04-30 |  |  | 2024-08-02 | 0 |  | 5000049281_2024_0001 | 2024-04-22 | 2024-04-02 |  |  | 0 | 2 | 2 | 0 | 1 |  | 3 | L |  | 0 | 5000049281 |  | 0 | 2024 | /018001394 | 2024-04-22 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 11400594 | RELAY,IF;24VACDC,6A,ABB 1SNA645019R0400 |  | 0005 | Inlec Assistance | INT | Inlec Assistance | 5 | Management of Change | 90005621_0010 |  |  |  |  | 05 | Release Completed | X | 0055 | In Preparation (Order) | ZBPM0001 | 0 | 106 | AUS Operations | 106 | AUS Operations | AU00 | 0 | AA02 | 90005621 | 2024-02-23 | 30 | 2024-04-20 | 0 |  | 0 |  | 24SDGT7 | MJ | AU1009 | 1000133465 | S001 | 30 | 30 | 5300000667 | 60 |  | 5300006569 | 10 | 1 | EA | 1001 | AA02 | 2024-04-22 |  | Management of Change | 2024-04-03 | AU00 | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-05-01 | 2024-05-03 | 2024-05-03 | INLEC | 100035583 | 0010 | 0010 | 100035583 | MOC-72065 Modify GT7 Hard-Wired Trip S2A | AA53.S2A1A4 | FEEDER,GENERATOR G4007 INCOMER | AA01 | 30 | No Issue identified | 10315906 | RELAY;AUX,DPDT,110V,IDEC RH2BUDC100110V | 1 | EA | 0 | 0 | 1 | 1 | EA | 28.02 - 1 Delivered to AA53 29.01 - 1 Stocked @ AA02 | Supply for Order 100035583, Item 1 cannot be changed 9000311 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300000667 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004064 | 9000311 | 05 | Preparation | 0000134055 | 1 | 0 | EA | 102000000001073 | 102000000000929 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015646_2024 | 1 | 0 | 0 |  | 2024-05-02 | AA53 | 2024-05-03 |  |  | 2024-05-04 |  |  | 100000002114 | 1020 | 2024-08-02 | 1 | 4900030161_2024_0001 |  | 2024-02-09 | 2024-05-04 | AU01.S2A1A4 | 5000015646_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004064 | 3 | L | 4900030161 | 2024 |  | 5000015646 | 2024 |  |  | 2024-05-01 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10315906 | RELAY;AUX,DPDT,110V,IDEC RH2BUDC100110V |  | 0010 | MOC-72065 Modify GT7 Hard-wired trip | ENON | MOC-72065 Modify GT7 Hard-wired trip | 5 | Management of Change | 9000311_0010 | [7 empty] | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000120 |  | 30 |  | 1 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000133465 | S002 | 30 | 30 | 5300000667 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-01 |  | Management of Change | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 134055 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-05-01 | 2024-05-03 | 2024-05-03 | INLEC | 100035583 | 0010 | 0040 | 100035583 | MOC-72065 Modify GT7 Hard-Wired Trip S2A | AA53.S2A1A4 | FEEDER,GENERATOR G4007 INCOMER | AA01 | 30 | No Issue identified | 10032365 | RELAY,TIMER,0.05SEC-300HRS,2WSE>10535023 | 1 | EA | 0 | 0 | 1 | 1 | EA | 28.02 - 1 Delivered to AA53 | Supply for Order 100035583, Item 3 cannot be changed 9000311 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300000667 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004064 | 9000311 | 05 | Preparation | 0000134055 | 3 | 0 | EA | 102000000001073 | 102000000000929 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015646_2024 | 1 | 0 | 0 |  | 2024-05-02 | AA53 | 2024-05-03 |  |  | 2024-05-04 |  |  | 100000002114 | 1020 | 2024-08-02 | 1 | 4900030161_2024_0003 |  | 2024-02-09 | 2024-05-04 | AU01.S2A1A4 | 5000015646_2024_0002 | 0 | 2 | 0 | 1 | 0 | 180004064 | 3 | L | 4900030161 | 2024 |  | 5000015646 | 2024 |  |  | 2024-05-01 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10032365 | RELAY,TIMER,0.05SEC-300HRS,2WSE>10535023 |  | 0010 | MOC-72065 Modify GT7 Hard-wired trip | ENON | MOC-72065 Modify GT7 Hard-wired trip | 5 | Management of Change | 9000311_0030 | [7 empty] | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000120 |  | 30 |  | 3 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000133465 | S002 |  | 70 | 5300000667 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-01 |  | Management of Change | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 134055 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-05-01 | 2024-05-03 | 2024-05-03 | INLEC | 100035583 | 0010 | 0022 | 100035583 | MOC-72065 Modify GT7 Hard-Wired Trip S2A | AA53.S2A1A4 | FEEDER,GENERATOR G4007 INCOMER | AA01 | 30 | No Issue identified | 10432862 | FERRULE,BOOTLACE;CABAC BLPT150 | 5 | PKT | 4 | 0 | 6 | 5 | PKT | 28.02 - 6 Delivered to AA53 | Supply for Order 100035583, Item 6 cannot be changed 9000311 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300000667 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | PKT |  |  |  | 180004064 | 9000311 | 05 | Preparation | 0000134055 | 6 | 0 | PKT | 102000000000357 | 102000000001137 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 5 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015646_2024 | 1 | 0 | 0 |  | 2024-05-02 | AA53 | 2024-05-03 |  |  | 2024-05-04 |  |  | 100000002114 | 1020 | 2024-08-02 | 5 | 4900030161_2024_0005 |  | 2024-02-09 | 2024-05-04 | AU01.S2A1A4 | 5000015646_2024_0003 | 0 | 2 | 0 | 5 | 0 | 180004064 | 3 | L | 4900030161 | 2024 |  | 5000015646 | 2024 |  |  | 2024-05-01 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10432862 | FERRULE,BOOTLACE;CABAC BLPT150 |  | 0010 | MOC-72065 Modify GT7 Hard-wired trip | ENON | MOC-72065 Modify GT7 Hard-wired trip | 5 | Management of Change | 9000311_0040 | [7 empty] | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000120 |  | 30 |  | 6 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000133465 | S002 | 30 | 30 | 5300000667 | 40 |  |  | 0 | 5 | PKT | 2001 | AA02 | 2024-05-01 |  | Management of Change | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 134055 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | INLEC | 100036163 | 0020 | 0010 | 100036163 | Investigate/Repair Earth Fault GT4009 HM | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10258561 | DETECTOR,INSTR;WOODWARD 1751184 | 1 | EA | 1 | 0 | 1 | 1 | EA | 28.02 - 1 Delivered to AA53 19.01 - 2 SOH @ AA02 | Supply for Order 100036163, Item 1 cannot be changed 90000098 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300000972 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004327 | 90000098 | 05 | Preparation | 0000134644 | 1 | 0 | EA | 102000000000188 | 102000000000171 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017954_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-04-23 | 1 | 4900030524_2024_0001 |  | 2024-02-12 | 2024-05-03 | GT4009 | 5000017954_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004327 | 3 | L | 4900030524 | 2024 |  | 5000017954 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258561 | DETECTOR,INSTR;WOODWARD 1751184 |  | 0020 | Fault Find & Repair | INT | Fault Find & Repair | 5 |  | 90000098_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000098 |  | 10 |  | 1 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000134013 | S002 | 30 | 30 | 5300000972 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 134644 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 100036622 | 0010 | 0010 | 100036622 | GT4008 Replace VBV door hinge bushings | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 30 | No Issue identified | 10312320 | BUSH,TURB;NP 9106M39P04 | 24 | EA | 3 | 0 | 24 | 24 | EA | UserCommentLink | Supply for Order 100036622, Item 1 cannot be changed 90000271 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300001201 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004303 | 90000271 | 05 | Preparation | 0000135134 | 1 | 0 | EA | 102000000000381 | 102000000000345 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL |  | 0 |  | 0 | 0 |  | 0 | 24 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017847_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-04-26 | 24 | 4900030502_2024_0001 |  | 2024-02-12 | 2024-05-03 | GT4008 | 5000017847_2024_0001 | 0 | 2 | 0 | 24 | 0 | 180004303 | 3 | L | 4900030502 | 2024 |  | 5000017847 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10312320 | BUSH,TURB;NP 9106M39P04 |  | 0010 | GT4008 Replace VBV door hinge bushings | INT | GT4008 Replace VBV door hinge bushings | 5 | Order Requires Replanning | 90000271_0010 | [7 empty] | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000271 |  | 30 |  | 1 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000134544 | S002 |  | 30 | 5300001201 | 10 |  |  | 0 | 24 | EA | 2001 | AA02 | 2024-04-30 |  | Order Requires Replanning | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 135134 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Material committed/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 100036622 | 0010 | 0020 | 100036622 | GT4008 Replace VBV door hinge bushings | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 30 | No Issue identified | 10312462 | BUSH,TURB;PA,NP 9022M73P06 | 48 | EA | 0 | 0 | 48 | 48 | EA | 24SDGT8-SW3R02A01B | Supply for Order 100036622, Item 2 cannot be changed 90000271 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300001201 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004303 | 90000271 | 05 | Preparation | 0000135134 | 2 | 0 | EA | 102000000000381 | 102000000000345 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL |  | 0 |  | 0 | 0 |  | 0 | 48 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017847_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-04-26 | 48 | 4900030502_2024_0003 |  | 2024-02-12 | 2024-05-03 | GT4008 | 5000017847_2024_0002 | 0 | 2 | 0 | 48 | 0 | 180004303 | 3 | L | 4900030502 | 2024 |  | 5000017847 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10312462 | BUSH,TURB;PA,NP 9022M73P06 |  | 0010 | GT4008 Replace VBV door hinge bushings | INT | GT4008 Replace VBV door hinge bushings | 5 | Order Requires Replanning | 90000271_0020 | [7 empty] | 0055 | In Preparation (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000271 |  | 30 |  | 2 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000134544 | S002 |  | 30 | 5300001201 | 20 |  |  | 0 | 48 | EA | 2001 | AA02 | 2024-04-30 |  | Order Requires Replanning | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 135134 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Material committed/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 100037490 | 0010 | 0010 | 100037490 | G4010P1B LO leak from fitting | AA53.G4010P1B | PUMP,G4010 MAIN/AUX AC MINERAL LUBE OIL | AA01 | 20 | No Issue identified | 10255151 | O-RING;BUNA-N,ALLWEILER 00016347ITEM0136 | 2 | EA | 0 | 2 | 0 | 2 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 100037490, Item 1 cannot be changed 90000078 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300001581 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006804 | 90000078 | 05 | Preparation | 0000136004 | 1 | 0 | EA | 102000000000145 | 102000000000144 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006804 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000003162 | 1020 | 2023-11-17 | 2 | 4900033162_2024_0001 |  | 2024-02-27 | 2024-05-03 | 2100360625 |  | 0 | 2 | 0 | 0 | 0 | 180006804 | 3 | L | 4900033162 | 2024 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255151 | O-RING;BUNA-N,ALLWEILER 00016347ITEM0136 |  | 0010 | Clean Up Oil | INT | Clean Up Oil | 5 |  | 90000078_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000078 |  | 20 |  | 1 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000135386 | S002 |  | 30 | 5300001581 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 136004 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | KSF
| 24SD4401 | Released | 2024-01-02 | 2024-03-01 | 2024-02-28 | 2024-05-03 | 2024-05-03 | INLEC | 100039742 | 0020 | 0112 | 100039742 | MOC-113307 Transmitter Replace 344PT60 | AA53.344PT60 | TX,PRESS K4401C DISCHARGE | AA01 | 255 | No issue identified | 10025311 | SPARES KIT;316SS,R/MOUNT 0303103130013 | 1 | EA | 3 | 0 | 4 | 1 | EA | IN GRAY TUB | Supply for Order 100039742, Item 12 cannot be changed 90002679 item 110 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002055 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180007932 | 90002679 | 05 | Preparation | 0000138266 | 12 | 0 | EA | 102000000002427 | 102000000002423 | 102000000002484 | 01-Road | 20000363 |  | 2-Loaded |  | WorkPackLink | P07YRDBAY8 | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | GRST-5000029221_2024 | 1 | 0 | 0 |  | 2024-02-28 | AA53 | 2024-05-03 |  |  | 2024-03-02 |  |  | 100000003411 | 1020 | 2024-03-08 | 1 | 4900034075_2024_0021 |  | 2024-03-01 | 2024-03-02 | 344PT60 | 5000029221_2024_0011 | 0 | 2 | 0 | 1 | 0 | 180007932 | 3 | L | 4900034075 | 2024 |  | 5000029221 | 2024 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025311 | SPARES KIT;316SS,R/MOUNT 0303103130013 |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90002679_0110 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90002679 |  | 99 |  | 12 |  | 0 |  | 24SD4401 | MJ | AU1072 | 1000137597 | S002 | 30 | 30 | 5300002055 | 110 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138266 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance |  | Material Handed to Maintenance
| 24SD4401 | Released | 2024-01-02 | 2024-03-01 | 2024-02-28 | 2024-05-03 | 2024-05-03 | INLEC | 100039742 | 0020 | 0120 | 100039742 | MOC-113307 Transmitter Replace 344PT60 | AA53.344PT60 | TX,PRESS K4401C DISCHARGE | AA01 | 255 | No issue identified | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP | 1 | EA | 17 | 0 | 3 | 1 | EA | X 1 BOX | Supply for Order 100039742, Item 7 cannot be changed 90002679 item 60 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002055 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180007932 | 90002679 | 05 | Preparation | 0000138266 | 7 | 0 | EA | 102000000002358 |  | 102000000002484 | 01-Road | 20000363 |  | 2-Loaded |  | WorkPackLink | P07YRDBAY8 | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | GRST-5000029221_2024 | 1 | 0 | 0 |  | 2024-02-28 | AA53 | 2024-05-03 |  |  | 2024-03-02 |  |  | 100000003411 | 1020 | 2024-03-08 | 1 | 4900034075_2024_0011 |  | 2024-03-01 | 2024-03-02 | 344PT60 | 5000029221_2024_0006 | 0 | 2 | 0 | 1 | 0 | 180007932 | 3 | L | 4900034075 | 2024 |  | 5000029221 | 2024 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262970 | MANIFOLD,VV;AGCO AS4TVIS2NPT4SGGYIWP |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90002679_0060 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90002679 |  | 99 |  | 7 |  | 0 |  | 24SD4401 | MJ | AU1072 | 1000137597 | S002 | 30 | 30 | 5300002055 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138266 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance |  | Material Handed to Maintenance
| 24SD4401 | Released | 2024-01-02 | 2024-03-01 | 2024-02-28 | 2024-05-03 | 2024-05-03 | INLEC | 100039742 | 0020 | 0150 | 100039742 | MOC-113307 Transmitter Replace 344PT60 | AA53.344PT60 | TX,PRESS K4401C DISCHARGE | AA01 | 255 | No issue identified | 10025892 | PLATE,MTG;C/W BRACKETS | 1 | EA | 21 | 0 | 7 | 1 | EA | IN GRAY TUB | Supply for Order 100039742, Item 10 cannot be changed 90002679 item 90 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002055 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180007932 | 90002679 | 05 | Preparation | 0000138266 | 10 | 0 | EA | 102000000002427 | 102000000002413 | 102000000002484 | 01-Road | 20000363 |  | 2-Loaded |  | WorkPackLink | P07YRDBAY8 | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | GRST-5000029221_2024 | 1 | 0 | 0 |  | 2024-02-28 | AA53 | 2024-05-03 |  |  | 2024-03-02 |  |  | 100000003411 | 1020 | 2024-03-08 | 1 | 4900034075_2024_0017 |  | 2024-03-01 | 2024-03-02 | 344PT60 | 5000029221_2024_0009 | 0 | 2 | 0 | 1 | 0 | 180007932 | 3 | L | 4900034075 | 2024 |  | 5000029221 | 2024 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025892 | PLATE,MTG;C/W BRACKETS |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90002679_0090 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90002679 |  | 99 |  | 10 |  | 0 |  | 24SD4401 | MJ | AU1072 | 1000137597 | S002 | 30 | 30 | 5300002055 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138266 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance |  | Material Handed to Maintenance
| 24SD4401 | Released | 2024-01-02 | 2024-03-01 | 2024-02-28 | 2024-05-03 | 2024-05-03 | INLEC | 100039742 | 0020 | 0030 | 100039742 | MOC-113307 Transmitter Replace 344PT60 | AA53.344PT60 | TX,PRESS K4401C DISCHARGE | AA01 | 255 | No issue identified | 10408545 | GLAND,CABLE;EX,SWA,SZ 0-20S,CCG 05720 | 1 | EA | 14 | 0 | 24 | 1 | EA | IN GRAY TUB | Supply for Order 100039742, Item 1 cannot be changed 90002679 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002055 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180007932 | 90002679 | 05 | Preparation | 0000138266 | 1 | 0 | EA | 102000000002427 | 102000000002365 | 102000000002484 | 01-Road | 20000363 |  | 2-Loaded |  | WorkPackLink | P07YRDBAY8 | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | GRST-5000029221_2024 | 1 | 0 | 0 |  | 2024-02-28 | AA53 | 2024-05-03 |  |  | 2024-03-02 |  |  | 100000003411 | 1020 | 2024-03-08 | 1 | 4900034075_2024_0001 |  | 2024-03-01 | 2024-03-02 | 344PT60 | 5000029221_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180007932 | 3 | L | 4900034075 | 2024 |  | 5000029221 | 2024 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10408545 | GLAND,CABLE;EX,SWA,SZ 0-20S,CCG 05720 |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90002679_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90002679 |  | 99 |  | 1 |  | 0 |  | 24SD4401 | MJ | AU1072 | 1000137597 | S002 | 30 | 30 | 5300002055 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138266 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance |  | Material Handed to Maintenance
| 24SD4401 | Released | 2024-01-02 | 2024-03-01 | 2024-02-28 | 2024-05-03 | 2024-05-03 | INLEC | 100039742 | 0020 | 0040 | 100039742 | MOC-113307 Transmitter Replace 344PT60 | AA53.344PT60 | TX,PRESS K4401C DISCHARGE | AA01 | 255 | No issue identified | 10019831 | SEAL,AGCO MANIFOLD,AS4TVS2NPT2,RING | 2 | EA | 47 | 0 | 5 | 2 | EA | IN GRAY TUB | Supply for Order 100039742, Item 2 cannot be changed 90002679 item 20 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002055 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180007932 | 90002679 | 05 | Preparation | 0000138266 | 2 | 0 | EA | 102000000002427 | 102000000002365 | 102000000002484 | 01-Road | 20000363 |  | 2-Loaded |  | WorkPackLink | P07YRDBAY8 | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | GRST-5000029221_2024 | 1 | 0 | 0 |  | 2024-02-28 | AA53 | 2024-05-03 |  |  | 2024-03-02 |  |  | 100000003411 | 1020 | 2024-03-08 | 2 | 4900034075_2024_0003 |  | 2024-03-01 | 2024-03-02 | 344PT60 | 5000029221_2024_0002 | 0 | 2 | 0 | 2 | 0 | 180007932 | 3 | L | 4900034075 | 2024 |  | 5000029221 | 2024 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10019831 | SEAL,AGCO MANIFOLD,AS4TVS2NPT2,RING |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90002679_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90002679 |  | 99 |  | 2 |  | 0 |  | 24SD4401 | MJ | AU1072 | 1000137597 | S002 | 30 | 30 | 5300002055 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138266 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance |  | Material Handed to Maintenance
| 24SD4401 | Released | 2024-01-02 | 2024-03-01 | 2024-02-28 | 2024-05-03 | 2024-05-03 | INLEC | 100039742 | 0020 | 0130 | 100039742 | MOC-113307 Transmitter Replace 344PT60 | AA53.344PT60 | TX,PRESS K4401C DISCHARGE | AA01 | 255 | No issue identified | 10452629 | TX,PRESS;3051S1CG5A2F12A1KDA2DOK7Y2L4M5+ | 1 | EA | 2 | 0 | 1 | 1 | EA | X 1 BOX | Supply for Order 100039742, Item 8 cannot be changed 90002679 item 70 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002055 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180007932 | 90002679 | 05 | Preparation | 0000138266 | 8 | 0 | EA | 102000000002356 |  | 102000000002484 | 01-Road | 20000363 |  | 2-Loaded |  | WorkPackLink | P07YRDBAY8 | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | GRST-5000029221_2024 | 1 | 0 | 0 |  | 2024-02-28 | AA53 | 2024-05-03 |  |  | 2024-03-02 |  |  | 100000003411 | 1020 | 2024-03-08 | 1 | 4900034075_2024_0013 |  | 2024-03-01 | 2024-03-02 | 344PT60 | 5000029221_2024_0007 | 0 | 2 | 0 | 1 | 0 | 180007932 | 3 | L | 4900034075 | 2024 |  | 5000029221 | 2024 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10452629 | TX,PRESS;3051S1CG5A2F12A1KDA2DOK7Y2L4M5+ |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90002679_0070 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90002679 |  | 99 |  | 8 |  | 0 |  | 24SD4401 | MJ | AU1072 | 1000137597 | S002 | 30 | 30 | 5300002055 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138266 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance |  | Material Handed to Maintenance
| 24SD4401 | Released | 2024-01-02 | 2024-03-01 | 2024-02-28 | 2024-05-03 | 2024-05-03 | INLEC | 100039742 | 0020 | 0160 | 100039742 | MOC-113307 Transmitter Replace 344PT60 | AA53.344PT60 | TX,PRESS K4401C DISCHARGE | AA01 | 255 | No issue identified | 10408545 | GLAND,CABLE;EX,SWA,SZ 0-20S,CCG 05720 | 1 | EA | 14 | 0 | 24 | 1 | EA | IN GRAY TUB | Supply for Order 100039742, Item 13 cannot be changed 90002679 item 120 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002055 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180007932 | 90002679 | 05 | Preparation | 0000138266 | 13 | 0 | EA | 102000000002427 | 102000000002365 | 102000000002484 | 01-Road | 20000363 |  | 2-Loaded |  | WorkPackLink | P07YRDBAY8 | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | GRST-5000029221_2024 | 1 | 0 | 0 |  | 2024-02-28 | AA53 | 2024-05-03 |  |  | 2024-03-02 |  |  | 100000003411 | 1020 | 2024-03-08 | 1 | 4900034075_2024_0023 |  | 2024-03-01 | 2024-03-02 |  | 5000029221_2024_0012 | 0 | 2 | 0 | 1 | 0 | 180007932 | 3 | L | 4900034075 | 2024 |  | 5000029221 | 2024 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10408545 | GLAND,CABLE;EX,SWA,SZ 0-20S,CCG 05720 |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90002679_0120 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90002679 |  | 99 |  | 13 |  | 0 |  | 24SD4401 | MJ | AU1072 | 1000137597 | S002 | 30 | 30 | 5300002055 | 120 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138266 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance |  | Material Handed to Maintenance
| 24SD4401 | Released | 2024-01-02 | 2024-03-01 | 2024-02-28 | 2024-05-03 | 2024-05-03 | INLEC | 100039742 | 0020 | 0060 | 100039742 | MOC-113307 Transmitter Replace 344PT60 | AA53.344PT60 | TX,PRESS K4401C DISCHARGE | AA01 | 255 | No issue identified | 10047898 | CONNECTOR,COMP/M,0.375" X 0.25" NPT,SS | 2 | EA | 118 | 0 | 79 | 2 | EA | IN GRAY TUB | Supply for Order 100039742, Item 4 cannot be changed 90002679 item 40 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002055 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180007932 | 90002679 | 05 | Preparation | 0000138266 | 4 | 0 | EA | 102000000002427 | 102000000002417 | 102000000002484 | 01-Road | 20000363 |  | 2-Loaded |  | WorkPackLink | P07YRDBAY8 | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | GRST-5000029221_2024 | 1 | 0 | 0 |  | 2024-02-28 | AA53 | 2024-05-03 |  |  | 2024-03-02 |  |  | 100000003411 | 1020 | 2024-03-08 | 2 | 4900034075_2024_0007 |  | 2024-03-01 | 2024-03-02 | 344PT60 | 5000029221_2024_0004 | 0 | 2 | 0 | 2 | 0 | 180007932 | 3 | L | 4900034075 | 2024 |  | 5000029221 | 2024 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10047898 | CONNECTOR,COMP/M,0.375" X 0.25" NPT,SS |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90002679_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90002679 |  | 99 |  | 4 |  | 0 |  | 24SD4401 | MJ | AU1072 | 1000137597 | S002 | 30 | 30 | 5300002055 | 40 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138266 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance |  | Material Handed to Maintenance
| 24SD4401 | Released | 2024-01-02 | 2024-03-01 | 2024-02-28 | 2024-05-03 | 2024-05-03 | INLEC | 100039742 | 0020 | 0102 | 100039742 | MOC-113307 Transmitter Replace 344PT60 | AA53.344PT60 | TX,PRESS K4401C DISCHARGE | AA01 | 255 | No issue identified | 10464249 | TAG,E,CABLE GLAND;ALCO ALCET20 | 1 | EA | 23 | 0 | 3 | 1 | EA | IN GRAY TUB | Supply for Order 100039742, Item 11 cannot be changed 90002679 item 100 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002055 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180007932 | 90002679 | 05 | Preparation | 0000138266 | 11 | 0 | EA | 102000000002427 | 102000000002423 | 102000000002484 | 01-Road | 20000363 |  | 2-Loaded |  | WorkPackLink | P07YRDBAY8 | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | GRST-5000029221_2024 | 1 | 0 | 0 |  | 2024-02-28 | AA53 | 2024-05-03 |  |  | 2024-03-02 |  |  | 100000003411 | 1020 | 2024-03-08 | 1 | 4900034075_2024_0019 |  | 2024-03-01 | 2024-03-02 | 344PT60 | 5000029221_2024_0010 | 0 | 2 | 0 | 1 | 0 | 180007932 | 3 | L | 4900034075 | 2024 |  | 5000029221 | 2024 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10464249 | TAG,E,CABLE GLAND;ALCO ALCET20 |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90002679_0100 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90002679 |  | 99 |  | 11 |  | 0 |  | 24SD4401 | MJ | AU1072 | 1000137597 | S002 | 30 | 30 | 5300002055 | 100 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138266 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance |  | Material Handed to Maintenance
| 24SD4401 | Released | 2024-01-02 | 2024-03-01 | 2024-02-28 | 2024-05-03 | 2024-05-03 | INLEC | 100039742 | 0020 | 0090 | 100039742 | MOC-113307 Transmitter Replace 344PT60 | AA53.344PT60 | TX,PRESS K4401C DISCHARGE | AA01 | 255 | No issue identified | 10025301 | O-RING KIT;R/MOUNT 0303102340001 | 1 | KIT | 30 | 0 | 10 | 1 | KIT | IN GRAY TUB | Supply for Order 100039742, Item 6 cannot be changed 90002679 item 50 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002055 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  | 180007932 | 90002679 | 05 | Preparation | 0000138266 | 6 | 0 | KIT | 102000000002427 | 102000000002365 | 102000000002484 | 01-Road | 20000363 |  | 2-Loaded |  | WorkPackLink | P07YRDBAY8 | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | GRST-5000029221_2024 | 1 | 0 | 0 |  | 2024-02-28 | AA53 | 2024-05-03 |  |  | 2024-03-02 |  |  | 100000003411 | 1020 | 2024-03-08 | 1 | 4900034075_2024_0009 |  | 2024-03-01 | 2024-03-02 | 344PT60 | 5000029221_2024_0005 | 0 | 2 | 0 | 1 | 0 | 180007932 | 3 | L | 4900034075 | 2024 |  | 5000029221 | 2024 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10025301 | O-RING KIT;R/MOUNT 0303102340001 |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90002679_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90002679 |  | 99 |  | 6 |  | 0 |  | 24SD4401 | MJ | AU1072 | 1000137597 | S002 | 30 | 30 | 5300002055 | 50 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138266 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance |  | Material Handed to Maintenance
| 24SD4401 | Released | 2024-01-02 | 2024-03-01 | 2024-02-28 | 2024-05-03 | 2024-05-03 | INLEC | 100039742 | 0020 | 0050 | 100039742 | MOC-113307 Transmitter Replace 344PT60 | AA53.344PT60 | TX,PRESS K4401C DISCHARGE | AA01 | 255 | No issue identified | 10028105 | CONNECTOR,0.250",SS316,FILLING | 2 | EA | 71 | 0 | 14 | 2 | EA | IN GRAY TUB | Supply for Order 100039742, Item 3 cannot be changed 90002679 item 30 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002055 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180007932 | 90002679 | 05 | Preparation | 0000138266 | 3 | 0 | EA | 102000000002427 | 102000000002410 | 102000000002484 | 01-Road | 20000363 |  | 2-Loaded |  | WorkPackLink | P07YRDBAY8 | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | GRST-5000029221_2024 | 1 | 0 | 0 |  | 2024-02-28 | AA53 | 2024-05-03 |  |  | 2024-03-02 |  |  | 100000003411 | 1020 | 2024-03-08 | 2 | 4900034075_2024_0005 |  | 2024-03-01 | 2024-03-02 | 344PT60 | 5000029221_2024_0003 | 0 | 2 | 0 | 2 | 0 | 180007932 | 3 | L | 4900034075 | 2024 |  | 5000029221 | 2024 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10028105 | CONNECTOR,0.250",SS316,FILLING |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90002679_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90002679 |  | 99 |  | 3 |  | 0 |  | 24SD4401 | MJ | AU1072 | 1000137597 | S002 |  | 30 | 5300002055 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138266 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance |  | Material Handed to Maintenance
| 24SD4401 | Released | 2024-01-02 | 2024-03-01 | 2024-02-28 | 2024-05-03 | 2024-05-03 | INLEC | 100039742 | 0020 | 0140 | 100039742 | MOC-113307 Transmitter Replace 344PT60 | AA53.344PT60 | TX,PRESS K4401C DISCHARGE | AA01 | 255 | No issue identified | 10486195 | FITTING,CAL,1/4",ELBOW 90DEG,BLEED VV | 2 | ASY | 70 | 0 | 18 | 2 | ASY | IN GRAY TUB | Supply for Order 100039742, Item 9 cannot be changed 90002679 item 80 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002055 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  | 180007932 | 90002679 | 05 | Preparation | 0000138266 | 9 | 0 | ASY | 102000000002427 | 102000000002415 | 102000000002484 | 01-Road | 20000363 |  | 2-Loaded |  | WorkPackLink | P07YRDBAY8 | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | GRST-5000029221_2024 | 1 | 0 | 0 |  | 2024-02-28 | AA53 | 2024-05-03 |  |  | 2024-03-02 |  |  | 100000003411 | 1020 | 2024-03-08 | 2 | 4900034075_2024_0015 |  | 2024-03-01 | 2024-03-02 | 344PT60 | 5000029221_2024_0008 | 0 | 2 | 0 | 2 | 0 | 180007932 | 3 | L | 4900034075 | 2024 |  | 5000029221 | 2024 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10486195 | FITTING,CAL,1/4",ELBOW 90DEG,BLEED VV |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90002679_0080 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90002679 |  | 99 |  | 9 |  | 0 |  | 24SD4401 | MJ | AU1072 | 1000137597 | S002 | 30 | 30 | 5300002055 | 80 |  |  | 0 | 2 | ASY | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138266 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance |  | Material Handed to Maintenance
| 24SD4401 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100039742 | 0020 | 0170 | 100039742 | MOC-113307 Transmitter Replace 344PT60 | AA53.344PT60 | TX,PRESS K4401C DISCHARGE | AA01 | 255 | No Issue identified | 10262888 | PLATE KIT,MTG;SS316,AGCO MPA2 | 1 | EA | 33 | 0 | 7 | 1 | EA | 26.03 - 34 SOH @ AA02 | Supply for Order 100039742, Item 14 cannot be changed 90006603 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002055 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180013764 | 90006603 | 05 | Preparation | 0000138266 | 14 | 0 | EA |  |  | 102000000003672 | 01-Road | 1000001054 |  | 1-Not Started |  | WorkPackLink | P07-BENCH |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | GRST-5000047706_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000005019 | 1020 | 2024-03-08 | 1 | 4900040607_2024_0001 |  | 2024-03-26 | 2024-05-03 |  | 5000047706_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180013764 | 3 | L | 4900040607 | 2024 |  | 5000047706 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10262888 | PLATE KIT,MTG;SS316,AGCO MPA2 |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90006603_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006603 |  | 99 |  | 14 |  | 0 |  | 24SD4401 | MJ | AU1072 | 1000137597 | S002 | 30 | 30 | 5300002055 | 130 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-03-27 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138266 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance |  | Material Handed to Maintenance
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-07-27 | 2024-05-19 | 2024-05-19 | ROTAT | 100040102 | 0030 | 0020 | 100040102 | DE Sump Drain Line Update CM GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | No Issue identified | 10047911 | CONNECTOR;COMP/M,0.75X0.75",NPT,SS | 2 | EA | 4 | 0 | 8 | 2 | EA | 24SDGT9-SW3R02B01A | Supply for Order 100040102, Item 2 cannot be changed 90000099 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300002144 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004326 | 90000099 | 05 | Preparation | 0000138574 | 2 | 0 | EA | 102000000000188 | 102000000000186 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017929_2024 | 72 | 0 | 0 |  | 2024-07-28 | AA53 | 2024-05-19 |  |  | 2024-07-30 |  |  | 100000002057 | 1020 | 2023-06-30 | 2 | 4900030479_2024_0001 |  | 2024-02-12 | 2024-07-30 | 2100352557 | 5000017929_2024_0001 | 0 | 2 | 0 | 2 | 0 | 180004326 | 3 | L | 4900030479 | 2024 |  | 5000017929 | 2024 |  |  | 2024-07-27 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10047911 | CONNECTOR;COMP/M,0.75X0.75",NPT,SS |  | 0030 | Fab/Install Section 2 Drain Line(1 Bend) | INT | Fab/Install Section 2 Drain Line(1 Bend) | 5 |  | 90000099_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000099 |  | 20 |  | 2 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000137964 | S002 |  | 30 | 5300002144 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-07-27 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138574 | 0 |  | 2 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | INLEC | 100040358 | 0010 | 0060 | 100040358 | Vibration Monitor Rack Fault GT4009 | AA53.409PT520A | TX,PRESS GT4009 COMBUST ACOUSTIC SENS | AA01 | 10 | No Issue identified | 10307852 | MODULE,PIGNONE,IF DETECT VIB | 1 | EA | 1 | 0 | 0 | 1 | EA | 14.02 - Material received @ AA53 | Supply for Order 100040358, Item 6 cannot be changed 90000100 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300002196 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004329 | 90000100 | 05 | Preparation | 0000138890 | 6 | 0 | EA | 102000000000188 | 102000000000185 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017906_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2022-06-07 | 1 | 4900030469_2024_0003 |  | 2024-02-12 | 2024-05-03 | GT4009 | 5000017906_2024_0002 | 0 | 2 | 0 | 1 | 0 | 180004329 | 3 | L | 4900030469 | 2024 |  | 5000017906 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307852 | MODULE,PIGNONE,IF DETECT VIB |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90000100_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000100 |  | 10 |  | 6 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000138260 | S002 |  |  | 5300002196 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138890 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | INLEC | 100040358 | 0010 | 0050 | 100040358 | Vibration Monitor Rack Fault GT4009 | AA53.409PT520A | TX,PRESS GT4009 COMBUST ACOUSTIC SENS | AA01 | 10 | No Issue identified | 10255622 | CABLE,CONTR+SIG;NP RCO43973 | 1 | EA | 2 | 0 | 0 | 1 | EA | 14.02 - 1 SOH @ AA02 | Supply for Order 100040358, Item 5 cannot be changed 90000100 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300002196 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004329 | 90000100 | 05 | Preparation | 0000138890 | 5 | 0 | EA | 102000000000188 | 102000000000185 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL | AU01-TA-P07 | 0 | 5400000085 | 10 | 1 | EA | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017906_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2022-06-07 | 1 | 4900030469_2024_0001 |  | 2024-02-12 | 2024-05-03 | GT4009 | 5000017906_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004329 | 3 | L | 4900030469 | 2024 |  | 5000017906 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255622 | CABLE,CONTR+SIG;NP RCO43973 |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90000100_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000100 |  | 10 |  | 5 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000138260 | S002 |  | 30 | 5300002196 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 138890 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-04 | ROTAT | 100040480 | 0010 | 0080 | 100040480 | GT4010 - Replace bushes and bell cranks | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 255 | No Issue identified | 10297500 | BOLT;GE 9108M27P03 | 18 | EA | 0 | 18 | 0 | 18 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 100040480, Item 8 cannot be changed 9000349 item 50 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300002226 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006809 | 9000349 | 05 | Preparation | 0000139004 | 8 | 0 | EA | 102000000000133 | 102000000000162 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 18 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006809 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000003162 | 1020 | 2023-04-27 | 18 | 4900033163_2024_0009 |  | 2024-02-27 | 2024-05-03 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006809 | 3 | L | 4900033163 | 2024 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297500 | BOLT;GE 9108M27P03 |  | 0010 | GT4010 - Replace Bushes & Bell Cranks | ENON | GT4010 - Replace Bushes & Bell Cranks | 5 |  | 9000349_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000080 |  | 99 |  | 8 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000138355 | S002 |  | 30 | 5300002226 | 50 |  |  | 0 | 18 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139004 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-04 | ROTAT | 100040480 | 0010 | 0060 | 100040480 | GT4010 - Replace bushes and bell cranks | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 255 | No Issue identified | 10297497 | WASHER,THR;GE 9107M25P04 | 18 | EA | 0 | 18 | 0 | 18 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 100040480, Item 6 cannot be changed 9000349 item 30 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300002226 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006809 | 9000349 | 05 | Preparation | 0000139004 | 6 | 0 | EA | 102000000000133 | 102000000000161 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 18 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006809 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000003162 | 1020 | 2023-04-27 | 18 | 4900033163_2024_0005 |  | 2024-02-27 | 2024-05-03 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006809 | 3 | L | 4900033163 | 2024 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297497 | WASHER,THR;GE 9107M25P04 |  | 0010 | GT4010 - Replace Bushes & Bell Cranks | ENON | GT4010 - Replace Bushes & Bell Cranks | 5 |  | 9000349_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000080 |  | 99 |  | 6 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000138355 | S002 |  | 30 | 5300002226 | 30 |  |  | 0 | 18 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139004 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-04 | ROTAT | 100040480 | 0010 | 0070 | 100040480 | GT4010 - Replace bushes and bell cranks | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 255 | No Issue identified | 10297499 | WASHER,PLN;GE 9131M45P02 | 18 | EA | 0 | 18 | 0 | 18 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 100040480, Item 7 cannot be changed 9000349 item 40 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300002226 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006809 | 9000349 | 05 | Preparation | 0000139004 | 7 | 0 | EA | 102000000000133 | 102000000000161 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 18 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006809 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000003162 | 1020 | 2023-04-27 | 18 | 4900033163_2024_0007 |  | 2024-02-27 | 2024-05-03 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006809 | 3 | L | 4900033163 | 2024 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297499 | WASHER,PLN;GE 9131M45P02 |  | 0010 | GT4010 - Replace Bushes & Bell Cranks | ENON | GT4010 - Replace Bushes & Bell Cranks | 5 |  | 9000349_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000080 |  | 99 |  | 7 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000138355 | S002 |  | 30 | 5300002226 | 40 |  |  | 0 | 18 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139004 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-04 | ROTAT | 100040480 | 0010 | 0010 | 100040480 | GT4010 - Replace bushes and bell cranks | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 255 | No Issue identified | 10313419 | BELLCRANK,ACT;GE L43324G03 | 3 | ASY | 3 | 3 | 0 | 3 | ASY | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 100040480, Item 1 cannot be changed 9000349 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300002226 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | ASY |  |  |  | 180006809 | 9000349 | 05 | Preparation | 0000139004 | 1 | 0 | ASY | 102000000000133 | 102000000000162 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006809 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000003162 | 1020 | 2023-04-27 | 3 | 4900033163_2024_0001 |  | 2024-02-27 | 2024-05-03 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006809 | 3 | L | 4900033163 | 2024 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10313419 | BELLCRANK,ACT;GE L43324G03 |  | 0010 | GT4010 - Replace Bushes & Bell Cranks | ENON | GT4010 - Replace Bushes & Bell Cranks | 5 |  | 9000349_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000080 |  | 99 |  | 1 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000138355 | S002 |  | 30 | 5300002226 | 10 |  |  | 0 | 3 | ASY | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139004 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | KSF
| 24SD4403 | Released | 2024-01-02 | 2024-05-07 | 2024-05-04 | 2024-05-07 | 2024-05-07 | VALVE | 100041467 | 0010 | 0022 | 100041467 | CV-OH 2" 300# 44PCV523 | AA53.44PCV523 | VALVE,PRESS K4403 LUBEOIL TNK RECYC | AA01 | 30 | No Issue identified | 10022982 | GASKET;SEAT RING,316SS,GRAFOIL,536H REG | 1 | EA | 1 | 0 | 0 | 1 | EA | IN GREY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300000440 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006601 | 05 | Preparation | 0000139988 | 6 | 0 | EA | 102000000003772 |  | 102000000003738 | [5 empty] | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006601_0030 | 0 | 0 | 0 |  | 2024-05-05 | AA53 | 2024-05-07 |  |  | 2024-05-07 |  |  |  |  | 2019-09-13 | 0 |  |  | 2024-05-04 | 2024-05-07 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-04 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10022982 | GASKET;SEAT RING,316SS,GRAFOIL,536H REG |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90006601_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006601 |  | 30 |  | 6 |  | 0 |  | 24SD4403 | MJ | AU1072 | 1000139337 | S002 | 30 | 30 | 5300000440 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-04 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139988 | 0 |  | 2 |  |  | RC00025003 | 2024-05-07 | 2024-05-07 | 2024-05-07 | Printed/Material shortage/Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved | AM01 | Reactive Maintenance |  | KSF
| 24SD4403 | Released | 2024-01-02 | 2024-05-07 | 2024-05-04 | 2024-05-07 | 2024-05-07 | VALVE | 100041467 | 0010 | 0012 | 100041467 | CV-OH 2" 300# 44PCV523 | AA53.44PCV523 | VALVE,PRESS K4403 LUBEOIL TNK RECYC | AA01 | 30 | No Issue identified | 10022981 | DIAPHRAGM,MASONEILAN 536-H REG,BUNA-N | 1 | EA | 1 | 0 | 0 | 1 | EA | IN GREY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300000440 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006601 | 05 | Preparation | 0000139988 | 5 | 0 | EA | 102000000003772 |  | 102000000003738 | [5 empty] | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006601_0020 | 0 | 0 | 0 |  | 2024-05-05 | AA53 | 2024-05-07 |  |  | 2024-05-07 |  |  |  |  | 2019-09-13 | 0 |  |  | 2024-05-04 | 2024-05-07 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-04 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10022981 | DIAPHRAGM,MASONEILAN 536-H REG,BUNA-N |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 |  | 90006601_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006601 |  | 30 |  | 5 |  | 0 |  | 24SD4403 | MJ | AU1072 | 1000139337 | S002 | 30 | 30 | 5300000440 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-04 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 139988 | 0 |  | 2 |  |  | RC00025003 | 2024-05-07 | 2024-05-07 | 2024-05-07 | Printed/Material shortage/Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved | AM01 | Reactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100042088 | 0020 | 0030 | 100042088 | MOC-119 EEHA Replace JB 314QT20-1J | AA53.314QT20-1J | JB,HEAT TRACE 314QT20-1 | AA01 | 10 | No Issue identified | 10034453 | GLAND,CABLE;EXDE,UNIV,B,25MM THD | 2 | EA | 39 | 0 | 3 | 2 | EA | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300000711 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006330 | 05 | Preparation | 0000140572 | 2 | 0 | EA | 102000000003686 |  | 102000000003609 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006330_0020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-09-28 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2100334760 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034453 | GLAND,CABLE;EXDE,UNIV,B,25MM THD |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90006330_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006330 |  | 5 |  | 2 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000140003 | S002 | 30 | 30 | 5300000711 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140572 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100042088 | 0020 | 0020 | 100042088 | MOC-119 EEHA Replace JB 314QT20-1J | AA53.314QT20-1J | JB,HEAT TRACE 314QT20-1 | AA01 | 10 | No Issue identified | 10034456 | GLAND,CABLE;EXDE,UNIV,O,WXYZ,20MM | 2 | EA | 12 | 0 | 0 | 2 | EA | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300000711 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006330 | 05 | Preparation | 0000140572 | 1 | 0 | EA | 102000000003688 |  | 102000000003609 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006330_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-09-28 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2100334760 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034456 | GLAND,CABLE;EXDE,UNIV,O,WXYZ,20MM |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90006330_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006330 |  | 5 |  | 1 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000140003 | S002 | 30 | 30 | 5300000711 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140572 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100042088 | 0020 | 0012 | 100042088 | MOC-119 EEHA Replace JB 314QT20-1J | AA53.314QT20-1J | JB,HEAT TRACE 314QT20-1 | AA01 | 10 | No Issue identified | 10595964 | BOX,JCT;EX,WEIDMULLER KTBMH303020S4E1 | 1 | EA | 1 | 0 | 0 | 1 | EA | X 1 CTN |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300000711 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006330 | 05 | Preparation | 0000140572 | 3 | 0 | EA |  |  | 102000000003687 | [5 empty] | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006330_0030 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-09-28 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10595964 | BOX,JCT;EX,WEIDMULLER KTBMH303020S4E1 |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90006330_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006330 |  | 5 |  | 3 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000140003 | S002 | 30 | 30 | 5300000711 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140572 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance |  | KSF
| 24SDTOT2 | Released | 2024-01-02 | 2024-05-10 | 2024-05-07 | 2024-05-10 | 2024-05-10 | INLEC | 100042311 | 0020 | 0010 | 100042311 | CV -Service Biffi Pilot SOV 210HYD002 | AA53.210HYD002 | VALVE,BALL 2M1001 INLET | AA01 | 30 | No Issue identified | 10261979 | VALVE,PNEU;RGS 52BIS1 | 1 | EA | 1 | 0 | 0 | 1 | EA | RT TOT2 |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300007479 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006057 | 05 | Preparation | 0000140852 | 1 | 0 | EA | 102000000003213 | 102000000003249 | 102000000003214 | [5 empty] | WorkPackLink | SW3R04B01A | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-03-05 | ODST-0090006057_0010 | 0 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-10 |  |  | 2024-05-10 |  |  |  |  | 2022-12-15 | 0 |  |  | 2024-05-07 | 2024-05-10 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10261979 | VALVE,PNEU;RGS 52BIS1 |  | 0020 | Service/Replace Biffi Pilot Valve | INT | Service/Replace Biffi Pilot Valve | 5 |  | 90006057_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006057 |  | 30 |  | 1 |  | 0 |  | 24SDTOT2 | MJ | AU1072 | 1000140261 | S002 | 30 | 30 | 5300007479 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 140852 | 0 |  | 3 |  |  | RC00025003 | 2024-05-10 | 2024-05-10 | 2024-05-10 | Released/Settlement rule created/Object created/Date set by external system/Order Approved/Pre-costed/Printed/Material shortage | AM01 | Reactive Maintenance |  | KSF
| 24SD3410 | Released | 2024-01-02 | 2024-05-06 | 2024-05-03 | 2024-05-06 | 2024-05-18 | MECH | 100042777 | 0040 | 0030 | 100042777 | Replace Reservoir Sight Glass - K3410BV3 | AA53.K3410BV3 | TANK,RESERVOIR LUBE OIL | AA01 | 255 | No Issue identified | 10253626 | GLASS,REFLEX;KLINGER 581010 | 2 | EA | 3 | 0 | 0 | 2 | EA | IN GREY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300001013 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006602 | 06 | Scheduling | 0000141321 | 1 | 0 | EA | 102000000003771 |  | 102000000003736 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006602_0010 | 0 | 0 | 0 |  | 2024-05-04 | AA53 | 2024-05-06 |  |  | 2024-05-06 |  |  |  |  | 2023-03-30 | 0 |  |  | 2024-05-03 | 2024-05-06 | 100042777 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-03 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10253626 | GLASS,REFLEX;KLINGER 581010 |  | 0040 | Rem/Replace sight glass & gaskets | INT | Rem/Replace sight glass & gaskets | 5 |  | 90006602_0010 | [7 empty] | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006602 |  | 99 |  | 1 |  | 0 |  | 24SD3410 | MJ | AU1072 | 1000140692 | S002 |  | 30 | 5300001013 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-05-03 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141321 | 0 |  | 2 |  |  | RC00025003 | 2024-05-18 | 2024-05-06 | 2024-05-06 | Object created/Material shortage/Pre-costed/Order Approved/Date set by external system/Released/Settlement rule created/Printed/Ready For Scheduling | AM01 | Reactive Maintenance |  | KSF
| 24SD3410 | Released | 2024-01-02 | 2024-05-06 | 2024-05-03 | 2024-05-06 | 2024-05-06 | VALVE | 100043193 | 0040 | 0010 | 100043193 | CV-IS 3" 300# Re-Packing 34LCV21 | AA53.34LCV21 | VALVE,CTRL LEVEL BOG COMP SUCT DRUM | AA01 | 20 | No Issue identified | 10021468 | KIT,FISHER 80MM ET CV,STD TEMP,GASKET | 1 | KIT | 1 | 0 | 0 | 1 | KIT | IN GREY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300001173 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90006606 | 05 | Preparation | 0000141717 | 1 | 0 | KIT | 102000000003719 |  | 102000000003735 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006606_0010 | 0 | 0 | 0 |  | 2024-05-04 | AA53 | 2024-05-06 |  |  | 2024-05-06 |  |  |  |  | 2021-01-02 | 0 |  |  | 2024-05-03 | 2024-05-06 | 34LCV21 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-03 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021468 | KIT,FISHER 80MM ET CV,STD TEMP,GASKET |  | 0040 | Remove Actuator | ENON | Remove Actuator | 5 |  | 90006606_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006606 |  | 20 |  | 1 |  | 0 |  | 24SD3410 | MJ | AU1072 | 1000141148 | S002 |  | 30 | 5300001173 | 10 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-05-03 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141717 | 0 |  | 3 |  |  | RC00025003 | 2024-05-06 | 2024-05-06 | 2024-05-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | KSF
| 24SD3410 | Released | 2024-01-02 | 2024-05-06 | 2024-05-03 | 2024-05-06 | 2024-05-06 | VALVE | 100043193 | 0040 | 0020 | 100043193 | CV-IS 3" 300# Re-Packing 34LCV21 | AA53.34LCV21 | VALVE,CTRL LEVEL BOG COMP SUCT DRUM | AA01 | 20 | No Issue identified | 10020825 | PACKING,FISHER 1 OR 2 PORT VV,0.50" STEM | 1 | SET | 9 | 0 | 0 | 1 | SET | IN GREY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300001173 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | SET |  |  |  |  | 90006606 | 05 | Preparation | 0000141717 | 2 | 0 | SET | 102000000003719 |  | 102000000003735 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006606_0020 | 0 | 0 | 0 |  | 2024-05-04 | AA53 | 2024-05-06 |  |  | 2024-05-06 |  |  |  |  | 2021-01-02 | 0 |  |  | 2024-05-03 | 2024-05-06 | 34LCV21 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-03 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10020825 | PACKING,FISHER 1 OR 2 PORT VV,0.50" STEM |  | 0040 | Remove Actuator | ENON | Remove Actuator | 5 |  | 90006606_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006606 |  | 20 |  | 2 |  | 0 |  | 24SD3410 | MJ | AU1072 | 1000141148 | S002 |  | 30 | 5300001173 | 20 |  |  | 0 | 1 | SET | 2001 | AA02 | 2024-05-03 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141717 | 0 |  | 3 |  |  | RC00025003 | 2024-05-06 | 2024-05-06 | 2024-05-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | KSF
| 24SD3410 | Released | 2024-01-02 | 2024-05-06 | 2024-05-03 | 2024-05-06 | 2024-05-06 | VALVE | 100043193 | 0040 | 0050 | 100043193 | CV-IS 3" 300# Re-Packing 34LCV21 | AA53.34LCV21 | VALVE,CTRL LEVEL BOG COMP SUCT DRUM | AA01 | 20 | No Issue identified | 10021821 | DIAPHRAGM,ACT;FISHER 2E859502202 | 1 | EA | 2 | 0 | 0 | 1 | EA | IN GREY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300001173 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006606 | 05 | Preparation | 0000141717 | 4 | 0 | EA | 102000000003719 |  | 102000000003735 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006606_0040 | 0 | 0 | 0 |  | 2024-05-04 | AA53 | 2024-05-06 |  |  | 2024-05-06 |  |  |  |  | 2021-01-02 | 0 |  |  | 2024-05-03 | 2024-05-06 | 34LCV21 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-03 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021821 | DIAPHRAGM,ACT;FISHER 2E859502202 |  | 0040 | Remove Actuator | ENON | Remove Actuator | 5 |  | 90006606_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006606 |  | 20 |  | 4 |  | 0 |  | 24SD3410 | MJ | AU1072 | 1000141148 | S002 | 30 | 30 | 5300001173 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-03 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141717 | 0 |  | 3 |  |  | RC00025003 | 2024-05-06 | 2024-05-06 | 2024-05-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | KSF
| 24SD3410 | Released | 2024-01-02 | 2024-05-06 | 2024-05-03 | 2024-05-06 | 2024-05-06 | VALVE | 100043193 | 0040 | 0040 | 100043193 | CV-IS 3" 300# Re-Packing 34LCV21 | AA53.34LCV21 | VALVE,CTRL LEVEL BOG COMP SUCT DRUM | AA01 | 20 | No Issue identified | 10021200 | RING,FISHER 50X33MM EHD ET VV,PKG | 1 | EA | 1 | 0 | 0 | 1 | EA | IN GREY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300001173 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006606 | 05 | Preparation | 0000141717 | 3 | 0 | EA | 102000000003719 |  | 102000000003735 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006606_0030 | 0 | 0 | 0 |  | 2024-05-04 | AA53 | 2024-05-06 |  |  | 2024-05-06 |  |  |  |  | 2021-01-02 | 0 |  |  | 2024-05-03 | 2024-05-06 | 34LCV21 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-03 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10021200 | RING,FISHER 50X33MM EHD ET VV,PKG |  | 0040 | Remove Actuator | ENON | Remove Actuator | 5 |  | 90006606_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006606 |  | 20 |  | 3 |  | 0 |  | 24SD3410 | MJ | AU1072 | 1000141148 | S002 | 30 | 30 | 5300001173 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-03 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141717 | 0 |  | 3 |  |  | RC00025003 | 2024-05-06 | 2024-05-06 | 2024-05-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100043426 | 0010 | 0060 | 100043426 | MOC-119715 MCC Switch Replace S24D16A5RA | AA53.GT4007KM1B | MOTOR,TURB ACCOUST ENCL VENT FAN,GT4007 | AA01 | 30 | No Issue identified | 10251584 | CONTACT,AUX;ABB 1SCA022456R7410 | 2 | EA | 2 | 0 | 4 | 2 | EA | 28.02 - 4 Delivered to AA53 | Supply for Order 100043426, Item 6 cannot be changed 90000121 item 40 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300001299 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004058 | 90000121 | 05 | Preparation | 0000141927 | 6 | 0 | EA | 102000000000416 | 102000000000998 | 102000000000357 | [5 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | GRST-5000015676 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2021-06-07 | 2 | 4900030171_2024_0007 |  | 2024-02-09 | 2024-05-03 | S24D16A5RA | 5000015676_2024_0004 | 0 | 2 | 0 | 2 | 0 | 180004058 | 3 | L | 4900030171 | 2024 |  | 5000015676 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10251584 | CONTACT,AUX;ABB 1SCA022456R7410 |  | 0010 | Isolate & Disconnect S24D16A5RA | INT | Isolate & Disconnect S24D16A5RA | 5 |  | 90000121_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000121 |  | 30 |  | 6 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000141296 | S002 |  | 30 | 5300001299 | 40 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141927 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100043426 | 0010 | 0050 | 100043426 | MOC-119715 MCC Switch Replace S24D16A5RA | AA53.GT4007KM1B | MOTOR,TURB ACCOUST ENCL VENT FAN,GT4007 | AA01 | 30 | No Issue identified | 10251582 | CONTACT,AUX;ABB 1SCA022353R4970 | 2 | EA | 8 | 0 | 4 | 2 | EA | 28.02 - 4 Delivered to AA53, | Supply for Order 100043426, Item 5 cannot be changed 90000121 item 30 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300001299 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004058 | 90000121 | 05 | Preparation | 0000141927 | 5 | 0 | EA | 102000000000416 | 102000000000998 | 102000000000357 | [5 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | GRST-5000015676 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2021-06-07 | 2 | 4900030171_2024_0005 |  | 2024-02-09 | 2024-05-03 | S24D16A5RA | 5000015676_2024_0003 | 0 | 2 | 0 | 2 | 0 | 180004058 | 3 | L | 4900030171 | 2024 |  | 5000015676 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10251582 | CONTACT,AUX;ABB 1SCA022353R4970 |  | 0010 | Isolate & Disconnect S24D16A5RA | INT | Isolate & Disconnect S24D16A5RA | 5 |  | 90000121_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000121 |  | 30 |  | 5 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000141296 | S002 | 30 | 30 | 5300001299 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141927 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100043426 | 0010 | 0020 | 100043426 | MOC-119715 MCC Switch Replace S24D16A5RA | AA53.GT4007KM1B | MOTOR,TURB ACCOUST ENCL VENT FAN,GT4007 | AA01 | 30 | No Issue identified | 10251582 | CONTACT,AUX;ABB 1SCA022353R4970 | 2 | EA | 8 | 0 | 4 | 2 | EA | 28.02 - 4 Delivered to AA53, | Supply for Order 100043426, Item 2 cannot be changed 90000121 item 10 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300001299 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004058 | 90000121 | 05 | Preparation | 0000141927 | 2 | 0 | EA | 102000000000416 | 102000000000998 | 102000000000357 | [5 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | GRST-5000015676 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2021-06-07 | 2 | 4900030171_2024_0001 |  | 2024-02-09 | 2024-05-03 | S24D16A5RA | 5000015676_2024_0001 | 0 | 2 | 0 | 2 | 0 | 180004058 | 3 | L | 4900030171 | 2024 |  | 5000015676 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10251582 | CONTACT,AUX;ABB 1SCA022353R4970 |  | 0010 | Isolate & Disconnect S24D16A5RA | INT | Isolate & Disconnect S24D16A5RA | 5 |  | 90000121_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000121 |  | 30 |  | 2 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000141296 | S002 | 30 | 30 | 5300001299 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141927 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100043426 | 0010 | 0030 | 100043426 | MOC-119715 MCC Switch Replace S24D16A5RA | AA53.GT4007KM1B | MOTOR,TURB ACCOUST ENCL VENT FAN,GT4007 | AA01 | 30 | No Issue identified | 10251584 | CONTACT,AUX;ABB 1SCA022456R7410 | 2 | EA | 2 | 0 | 4 | 2 | EA | 28.02 - 4 Delivered to AA53 | Supply for Order 100043426, Item 3 cannot be changed 90000121 item 20 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300001299 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004058 | 90000121 | 05 | Preparation | 0000141927 | 3 | 0 | EA | 102000000000416 | 102000000000998 | 102000000000357 | [5 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | GRST-5000015676 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2021-06-07 | 2 | 4900030171_2024_0003 |  | 2024-02-09 | 2024-05-03 | S24D16A5RA | 5000015676_2024_0002 | 0 | 2 | 0 | 2 | 0 | 180004058 | 3 | L | 4900030171 | 2024 |  | 5000015676 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10251584 | CONTACT,AUX;ABB 1SCA022456R7410 |  | 0010 | Isolate & Disconnect S24D16A5RA | INT | Isolate & Disconnect S24D16A5RA | 5 |  | 90000121_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000121 |  | 30 |  | 3 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000141296 | S002 |  | 30 | 5300001299 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 141927 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100043648 | 0020 | 0012 | 100043648 | EEHA Replace Anaconda S63HTP1R02J4 | AA53.S63HTP1R02J4 | JB,HEAT TRACE TERM V1450 | AA01 | 10 | No Issue identified | 10592546 | CONDUIT;FLEX M,FLEXICON FLXLTP25B25M | 25 | M | 175 | 0 | 25 | 25 | M | X 1 LOOSE ROLL | Supply for Order 100043648, Item 3 cannot be changed 90006331 item 30 already exists | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300001376 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | M |  |  |  |  | 90006331 | 05 | Preparation | 0000142169 | 3 | 0 | M |  |  | 102000000003664 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 25 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006331_0030 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-07-31 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2100315062 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10592546 | CONDUIT;FLEX M,FLEXICON FLXLTP25B25M |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90006331_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006331 |  | 5 |  | 3 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000141538 | S002 | 30 | 30 | 5300001376 | 30 |  |  | 0 | 25 | M | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142169 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100043648 | 0020 | 0020 | 100043648 | EEHA Replace Anaconda S63HTP1R02J4 | AA53.S63HTP1R02J4 | JB,HEAT TRACE TERM V1450 | AA01 | 10 | No Issue identified | 10592547 | ADAPTOR;EX,M25,FLEXICON FLXLTP25M25EXE | 10 | EA | 14 | 0 | 0 | 10 | EA | IN GRAY TUB | Supply for Order 100043648, Item 1 cannot be changed 90006331 item 10 already exists | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300001376 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006331 | 05 | Preparation | 0000142169 | 1 | 0 | EA | 102000000003621 |  | 102000000003609 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006331_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-07-31 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2100315062 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10592547 | ADAPTOR;EX,M25,FLEXICON FLXLTP25M25EXE |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90006331_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006331 |  | 5 |  | 1 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000141538 | S002 | 30 | 30 | 5300001376 | 10 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142169 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100043648 | 0020 | 0030 | 100043648 | EEHA Replace Anaconda S63HTP1R02J4 | AA53.S63HTP1R02J4 | JB,HEAT TRACE TERM V1450 | AA01 | 10 | No Issue identified | 10034453 | GLAND,CABLE;EXDE,UNIV,B,25MM THD | 10 | EA | 39 | 0 | 3 | 10 | EA | IN GRAY TUB | Supply for Order 100043648, Item 2 cannot be changed 90006331 item 20 already exists | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300001376 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006331 | 05 | Preparation | 0000142169 | 2 | 0 | EA | 102000000003621 |  | 102000000003609 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006331_0020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-07-31 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2100315062 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034453 | GLAND,CABLE;EXDE,UNIV,B,25MM THD |  | 0020 | Complete Replacement | INT | Complete Replacement | 5 |  | 90006331_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006331 |  | 5 |  | 2 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000141538 | S002 | 30 | 30 | 5300001376 | 20 |  |  | 0 | 10 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 142169 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | KSF
| 24SD3410 | Released | 2024-01-02 | 2024-03-02 | 2024-02-28 | 2024-05-06 | 2024-05-06 | INLEC | 100044581 | 0020 | 0020 | 100044581 | Unsupported/Rubbing Tubing repair K3410A | AA53.K3410A | COMPR,LNG BOIL OFF | AA01 | 30 | No issue identified | 10038178 | TUBE,SML,0.375"OD,A269-TP316L,1.65MM WT | 5 | EA | 30 | 0 | 11 | 5 | EA | 6M PVC TUBE | Supply for Order 100044581, Item 2 cannot be changed 90002680 item 20 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002389 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180007931 | 90002680 | 05 | Preparation | 0000143033 | 2 | 0 | EA | 102000000002420 |  | 102000000002483 | 01-Road | 20000363 |  | 2-Loaded |  | WorkPackLink | P07YRDBAY8 | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y | 1001 | 2024-01-02 | GRST-5000029222_2024 | 0 | 0 | 0 |  | 2024-02-29 | AA53 | 2024-05-06 |  |  | 2024-03-02 |  |  | 100000003411 | 1020 | 2020-10-22 | 5 | 4900034076_2024_0003 |  | 2024-03-01 | 2024-03-02 | 2100301794 | 5000029222_2024_0001 | 0 | 2 | 0 | 5 | 0 | 180007931 | 3 | L | 4900034076 | 2024 |  | 5000029222 | 2024 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10038178 | TUBE,SML,0.375"OD,A269-TP316L,1.65MM WT |  | 0020 | Complete Tubing Replacement | INT | Complete Tubing Replacement | 5 |  | 90002680_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90002680 |  | 30 |  | 2 |  | 0 |  | 24SD3410 | MJ | AU1072 | 1000142443 | S002 | 30 | 30 | 5300002389 | 20 |  |  | 0 | 5 | EA | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 143033 | 0 |  | 3 |  |  | RC00025003 | 2024-05-06 | 2024-05-06 | 2024-05-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance |  | Material Handed to Maintenance
| 24SD3410 | Released | 2024-01-02 | 2024-03-02 | 2024-02-28 | 2024-05-06 | 2024-05-06 | INLEC | 100044581 | 0020 | 0010 | 100044581 | Unsupported/Rubbing Tubing repair K3410A | AA53.K3410A | COMPR,LNG BOIL OFF | AA01 | 30 | No issue identified | 10059551 | CLAMP;TBG,DBL,9.5X9.5MM,PA | 20 | KIT | 5 | 0 | 20 | 20 | KIT | IN GRAY TUB | Supply for Order 100044581, Item 1 cannot be changed 90002680 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300002389 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  | 180007931 | 90002680 | 05 | Preparation | 0000143033 | 1 | 0 | KIT | 102000000002424 | 102000000002418 | 102000000002484 | 01-Road | 20000363 |  | 2-Loaded |  | WorkPackLink | P07YRDBAY8 | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-01-02 | GRST-5000029187_2024 | 0 | 0 | 0 |  | 2024-02-29 | AA53 | 2024-05-06 |  |  | 2024-03-02 |  |  | 100000003411 | 1020 | 2020-10-22 | 20 | 4900034076_2024_0001 |  | 2024-03-01 | 2024-03-02 | 2100301794 | 5000029187_2024_0001 | 0 | 2 | 0 | 20 | 0 | 180007931 | 3 | L | 4900034076 | 2024 |  | 5000029187 | 2024 |  |  | 2024-02-28 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10059551 | CLAMP;TBG,DBL,9.5X9.5MM,PA |  | 0020 | Complete Tubing Replacement | INT | Complete Tubing Replacement | 5 |  | 90002680_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90002680 |  | 30 |  | 1 |  | 0 |  | 24SD3410 | MJ | AU1072 | 1000142443 | S002 | 30 | 30 | 5300002389 | 10 |  |  | 0 | 20 | KIT | 2001 | AA02 | 2024-02-28 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 143033 | 0 |  | 3 |  |  | RC00025003 | 2024-05-06 | 2024-05-06 | 2024-05-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material committed | AM01 | Reactive Maintenance |  | Material Handed to Maintenance
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 100044895 | 0010 | 0012 | 100044895 | TURBINE ENCLOSURE WINDOW CRACKED | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 255 | No Issue identified | 10575272 | WINDOW ASY;GLASS,NP ISM9963204001 | 1 | EA | 0 | 0 | 1 | 1 | EA | UserCommentLink | Supply for Order 100044895, Item 1 cannot be changed 90000122 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300002442 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004052 | 90000122 | 05 | Preparation | 0000143427 | 1 | 0 | EA | 102000000001138 |  | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015680_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2020-12-31 | 1 | 4900030119_2024_0001 |  | 2024-02-09 | 2024-05-03 |  | 5000015680_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004052 | 3 | L | 4900030119 | 2024 |  | 5000015680 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10575272 | WINDOW ASY;GLASS,NP ISM9963204001 |  | 0010 | Replace Turbine Enclosure Window | ENON | Replace Turbine Enclosure Window | 5 |  | 90000122_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000122 |  | 99 |  | 1 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000142777 | S002 | 30 | 30 | 5300002442 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 143427 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100045101 | 0010 | 0102 | 100045101 | Lighting Replacements/ Repairs GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 30 | No Issue identified | 10528195 | BALLAST;36W,CO.SI.ME. EVF36TX | 2 | EA | 0 | 0 | 2 | 2 | EA | X 1 SKID with mat 10481209 | Supply for Order 100045101, Item 10 cannot be changed 90000123 item 100 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300002473 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004060 | 90000123 | 05 | Preparation | 0000143613 | 10 | 0 | EA | 102000000000850 |  | 102000000001023 | 01-Road | 1000000427 |  | 5-Completed |  | WorkPackLink | R10P07WHFLR | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015695_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2020-04-27 | 2 | 4900030174_2024_0019 |  | 2024-02-09 | 2024-05-03 |  | 5000015695_2024_0003 | 0 | 2 | 0 | 2 | 0 | 180004060 | 3 | L | 4900030174 | 2024 |  | 5000015695 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10528195 | BALLAST;36W,CO.SI.ME. EVF36TX |  | 0010 | Complete Lighting Repairs/Replacement | INT | Complete Lighting Repairs/Replacement | 5 |  | 90000123_0100 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000123 |  | 30 |  | 10 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000143003 | S002 | 30 | 30 | 5300002473 | 100 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 143613 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material committed | AM01 | Reactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100045101 | 0010 | 0012 | 100045101 | Lighting Replacements/ Repairs GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 30 | No Issue identified | 10473913 | FIXTURE,LGT;EX,COSIME EVFC236XX230V | 6 | EA | 0 | 0 | 6 | 6 | EA | X 1 SKID with mat 10481209, 10528195 | Supply for Order 100045101, Item 8 cannot be changed 90000123 item 80 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300002473 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004060 | 90000123 | 05 | Preparation | 0000143613 | 8 | 0 | EA | 102000000000801 |  | 102000000001021 | 01-Road | 1000000427 |  | 5-Completed |  | WorkPackLink | R10P07WHFLR | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 6 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015695_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2020-04-27 | 6 | 4900030174_2024_0015 |  | 2024-02-09 | 2024-05-03 |  | 5000015695_2024_0001 | 0 | 2 | 0 | 6 | 0 | 180004060 | 3 | L | 4900030174 | 2024 |  | 5000015695 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10473913 | FIXTURE,LGT;EX,COSIME EVFC236XX230V |  | 0010 | Complete Lighting Repairs/Replacement | INT | Complete Lighting Repairs/Replacement | 5 |  | 90000123_0080 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000123 |  | 30 |  | 8 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000143003 | S002 | 30 | 30 | 5300002473 | 80 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 143613 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material committed | AM01 | Reactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100045101 | 0010 | 0030 | 100045101 | Lighting Replacements/ Repairs GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 30 | No Issue identified | 10266862 | LAMP,FLURO;240V,18W,AURA LIGHT 430214 | 20 | EA | 192 | 0 | 20 | 20 | EA | 28.02 - 20 Delivered to AA53 | Supply for Order 100045101, Item 2 cannot be changed 90000123 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300002473 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004060 | 90000123 | 05 | Preparation | 0000143613 | 2 | 0 | EA | 102000000000306 |  | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 20 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015654_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2020-04-27 | 20 | 4900030174_2024_0003 |  | 2024-02-09 | 2024-05-03 | GT4007 | 5000015654_2024_0002 | 0 | 2 | 0 | 20 | 0 | 180004060 | 3 | L | 4900030174 | 2024 |  | 5000015654 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10266862 | LAMP,FLURO;240V,18W,AURA LIGHT 430214 |  | 0010 | Complete Lighting Repairs/Replacement | INT | Complete Lighting Repairs/Replacement | 5 |  | 90000123_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000123 |  | 30 |  | 2 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000143003 | S002 | 30 | 30 | 5300002473 | 20 |  |  | 0 | 20 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 143613 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material committed | AM01 | Reactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100045101 | 0010 | 0050 | 100045101 | Lighting Replacements/ Repairs GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 30 | No Issue identified | 10532206 | GLAND,CABLE;M25,EX,HAWKE PSG553RACBM25 | 8 | EA | 27 | 0 | 10 | 8 | EA | 28.02 - 8 Delivered to AA53 | Supply for Order 100045101, Item 4 cannot be changed 90000123 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300002473 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004060 | 90000123 | 05 | Preparation | 0000143613 | 4 | 0 | EA | 102000000000358 | 102000000000430 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 8 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015654_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2020-04-27 | 8 | 4900030174_2024_0007 |  | 2024-02-09 | 2024-05-03 | GT4007 | 5000015654_2024_0004 | 0 | 2 | 0 | 8 | 0 | 180004060 | 3 | L | 4900030174 | 2024 |  | 5000015654 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10532206 | GLAND,CABLE;M25,EX,HAWKE PSG553RACBM25 |  | 0010 | Complete Lighting Repairs/Replacement | INT | Complete Lighting Repairs/Replacement | 5 |  | 90000123_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000123 |  | 30 |  | 4 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000143003 | S002 | 30 | 30 | 5300002473 | 40 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 143613 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material committed | AM01 | Reactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100045101 | 0010 | 0070 | 100045101 | Lighting Replacements/ Repairs GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 30 | No Issue identified | 10532230 | SEAL,GLAND;SIZE B,HAWKE SEALPSG553B | 3 | EA | 19 | 0 | 3 | 3 | EA | 28.02 - 3 Delivered to AA53 | Supply for Order 100045101, Item 6 cannot be changed 90000123 item 60 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300002473 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004060 | 90000123 | 05 | Preparation | 0000143613 | 6 | 0 | EA | 102000000000358 | 102000000000305 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 3 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015654_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2020-04-27 | 3 | 4900030174_2024_0011 |  | 2024-02-09 | 2024-05-03 | GT4007 | 5000015654_2024_0006 | 0 | 2 | 0 | 3 | 0 | 180004060 | 3 | L | 4900030174 | 2024 |  | 5000015654 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10532230 | SEAL,GLAND;SIZE B,HAWKE SEALPSG553B |  | 0010 | Complete Lighting Repairs/Replacement | INT | Complete Lighting Repairs/Replacement | 5 |  | 90000123_0060 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000123 |  | 30 |  | 6 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000143003 | S002 | 30 | 30 | 5300002473 | 60 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 143613 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material committed | AM01 | Reactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100045101 | 0010 | 0112 | 100045101 | Lighting Replacements/ Repairs GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 30 | No Issue identified | 10577708 | LAMP,LED;E27,240VAC,10W,SAL LGS10840E27 | 25 | EA | 0 | 0 | 25 | 25 | EA | 28.02 - 4 Delivered to AA53 | Supply for Order 100045101, Item 7 cannot be changed 90000123 item 70 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300002473 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004060 | 90000123 | 05 | Preparation | 0000143613 | 7 | 0 | EA | 102000000000359 |  | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 25 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015654_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2020-04-27 | 25 | 4900030174_2024_0013 |  | 2024-02-09 | 2024-05-03 |  | 5000015654_2024_0007 | 0 | 2 | 0 | 25 | 0 | 180004060 | 3 | L | 4900030174 | 2024 |  | 5000015654 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10577708 | LAMP,LED;E27,240VAC,10W,SAL LGS10840E27 |  | 0010 | Complete Lighting Repairs/Replacement | INT | Complete Lighting Repairs/Replacement | 5 |  | 90000123_0070 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000123 |  | 30 |  | 7 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000143003 | S002 | 30 | 30 | 5300002473 | 70 |  |  | 0 | 25 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 143613 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material committed | AM01 | Reactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100045101 | 0010 | 0060 | 100045101 | Lighting Replacements/ Repairs GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 30 | No Issue identified | 10532209 | SEAL,GLAND;SIZE A,HAWKE SEALPSG553A | 3 | EA | 29 | 0 | 3 | 3 | EA | 28.02 - 3 Delivered to AA53 | Supply for Order 100045101, Item 5 cannot be changed 90000123 item 50 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300002473 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004060 | 90000123 | 05 | Preparation | 0000143613 | 5 | 0 | EA | 102000000000358 | 102000000000305 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 3 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015654_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2020-04-27 | 3 | 4900030174_2024_0009 |  | 2024-02-09 | 2024-05-03 | GT4007 | 5000015654_2024_0005 | 0 | 2 | 0 | 3 | 0 | 180004060 | 3 | L | 4900030174 | 2024 |  | 5000015654 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10532209 | SEAL,GLAND;SIZE A,HAWKE SEALPSG553A |  | 0010 | Complete Lighting Repairs/Replacement | INT | Complete Lighting Repairs/Replacement | 5 |  | 90000123_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000123 |  | 30 |  | 5 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000143003 | S002 | 30 | 30 | 5300002473 | 50 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 143613 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material committed | AM01 | Reactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100045101 | 0010 | 0040 | 100045101 | Lighting Replacements/ Repairs GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 30 | No Issue identified | 10532205 | GLAND,CABLE;M20,EX,HAWKE PSG553RACAM20 | 8 | EA | 43 | 0 | 17 | 8 | EA | UserCommentLink | Supply for Order 100045101, Item 3 cannot be changed 90000123 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300002473 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004060 | 90000123 | 05 | Preparation | 0000143613 | 3 | 0 | EA | 102000000000358 | 102000000000430 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 8 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015654_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2020-04-27 | 8 | 4900030174_2024_0005 |  | 2024-02-09 | 2024-05-03 | GT4007 | 5000015654_2024_0003 | 0 | 2 | 0 | 8 | 0 | 180004060 | 3 | L | 4900030174 | 2024 |  | 5000015654 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10532205 | GLAND,CABLE;M20,EX,HAWKE PSG553RACAM20 |  | 0010 | Complete Lighting Repairs/Replacement | INT | Complete Lighting Repairs/Replacement | 5 |  | 90000123_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000123 |  | 30 |  | 3 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000143003 | S002 | 30 | 30 | 5300002473 | 30 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 143613 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material committed | AM01 | Reactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100045101 | 0010 | 0092 | 100045101 | Lighting Replacements/ Repairs GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 30 | No Issue identified | 10481209 | GUARD,LIGHT FTG,CO.SI.ME EVF47 | 4 | EA | 0 | 0 | 4 | 4 | EA | X 1 SKID with mat 10473913, 10528195 | Supply for Order 100045101, Item 9 cannot be changed 90000123 item 90 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300002473 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004060 | 90000123 | 05 | Preparation | 0000143613 | 9 | 0 | EA | 102000000000794 |  | 102000000001022 | 01-Road | 1000000427 |  | 5-Completed |  | WorkPackLink | R10P07WHFLR | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 4 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015695_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2020-04-27 | 4 | 4900030174_2024_0017 |  | 2024-02-09 | 2024-05-03 |  | 5000015695_2024_0002 | 0 | 2 | 0 | 4 | 0 | 180004060 | 3 | L | 4900030174 | 2024 |  | 5000015695 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10481209 | GUARD,LIGHT FTG,CO.SI.ME EVF47 |  | 0010 | Complete Lighting Repairs/Replacement | INT | Complete Lighting Repairs/Replacement | 5 |  | 90000123_0090 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000123 |  | 30 |  | 9 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000143003 | S002 | 30 | 30 | 5300002473 | 90 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 143613 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material committed | AM01 | Reactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 100045101 | 0010 | 0020 | 100045101 | Lighting Replacements/ Repairs GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 30 | No Issue identified | 10035145 | FIXTURE,LGT;EX,CHAMLIT PRGE218BIIEC | 4 | EA | 14 | 0 | 4 | 4 | EA | 28.02 - 4 Delivered to AA53, 7 coming from AA02 | Supply for Order 100045101, Item 1 cannot be changed 90000123 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300002473 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004060 | 90000123 | 05 | Preparation | 0000143613 | 1 | 0 | EA | 102000000000306 |  | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 4 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015654_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2020-04-27 | 4 | 4900030174_2024_0001 |  | 2024-02-09 | 2024-05-03 | GT4007 | 5000015654_2024_0001 | 0 | 2 | 0 | 4 | 0 | 180004060 | 3 | L | 4900030174 | 2024 |  | 5000015654 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10035145 | FIXTURE,LGT;EX,CHAMLIT PRGE218BIIEC |  | 0010 | Complete Lighting Repairs/Replacement | INT | Complete Lighting Repairs/Replacement | 5 |  | 90000123_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000123 |  | 30 |  | 1 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000143003 | S002 | 30 | 30 | 5300002473 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 143613 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material committed | AM01 | Reactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | ROTAT | 100046883 | 0020 | 0042 | 100046883 | 409LG504 Clean Oil Sampling Valve | AA53.409LG504 | GAUGE,LEVEL GT4009V3 STARTING OIL TANK | AA01 | 255 | No Issue identified | 10601394 | VALVE,GG;SET,SS316,KLINGER LLG | 1 | EA | 0 | 0 | 1 | 1 | EA | 13.02 - In Transit Inb Del 180004337 | Supply for Order 100046883, Item 1 cannot be changed 9000028 item 10 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300002928 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004337 | 9000028 | 05 | Preparation | 0000145404 | 1 | 0 | EA | 102000000000118 | 102000000001213 | 102000000000119 | [5 empty] | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | GRST-5000017963 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2018-09-14 | 1 | 4900030573_2024_0001 |  | 2024-02-12 | 2024-05-03 |  | 5000017963_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004337 | 3 | L | 4900030573 | 2024 |  | 5000017963 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10601394 | VALVE,GG;SET,SS316,KLINGER LLG |  | 0020 | REMOVE / REPLACE UPPER & LOWER GAUGE | INT | REMOVE / REPLACE UPPER & LOWER GAUGE | 5 |  | 9000028_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000427 |  | 99 |  | 1 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000144753 | S002 | 30 | 30 | 5300002928 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 145404 | 0 |  | 2 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | ROTAT | 100046883 | 0030 | 0010 | 100046883 | 409LG504 Clean Oil Sampling Valve | AA53.409LG504 | GAUGE,LEVEL GT4009V3 STARTING OIL TANK | AA01 | 255 | No Issue identified | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR | 2 | EA | 65 | 2 | 8 | 2 | EA | 13.02 - In Transit Inb Del 180004337 | Supply for Order 100046883, Item 2 cannot be changed 9000028 item 20 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300002928 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004337 | 9000028 | 05 | Preparation | 0000145404 | 2 | 0 | EA |  |  | 102000000000238 | [5 empty] | WorkPackLink |  | AU01P08UT | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | IDST-0180004337 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2018-09-14 | 2 | 4900030573_2024_0003 |  | 2024-02-12 | 2024-05-03 | GT4009 |  | 0 | 2 | 0 | 0 | 0 | 180004337 | 3 | L | 4900030573 | 2024 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060916 | GASKET;SWCI,20MM,CL300-600,316L,GR |  | 0030 | REPLACE WITH NEW OIL | INT | REPLACE WITH NEW OIL | 5 |  | 9000028_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000427 |  | 99 |  | 2 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000144753 | S002 | 30 | 30 | 5300002928 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 145404 | 0 |  | 2 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-07 | 2024-05-10 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0210 | 0240 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10255281 | ELEMENT,FLT;5" LG,GE ACB244F2440Y1 | 1 | EA | 3 | 1 | 3 | 1 | EA | 19.01 - 4 scheduled for delivery 08.05.24 | Supply for Order 200064906, Item 24 cannot be changed 90000129 item 50 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 220 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004076 | 90000129 | 05 | Preparation | 0000099208 | 24 | 0 | EA | 102000000001073 | 102000000001029 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015648_2024 | 6 | 0 | 0 |  | 2024-05-11 | AA53 | 2024-05-07 |  |  | 2024-05-13 |  |  | 100000002114 | 1020 | 2024-07-20 | 1 | 4900030181_2024_0009 |  | 2024-02-09 | 2024-05-13 |  | 5000015648_2024_0005 | 0 | 2 | 0 | 1 | 0 | 180004076 | 3 | L | 4900030181 | 2024 |  | 5000015648 | 2024 |  |  | 2024-05-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255281 | ELEMENT,FLT;5" LG,GE ACB244F2440Y1 |  | 0210 | HYDRAULIC CONTROL UNIT FILTER REPL | INT | HYDRAULIC CONTROL UNIT FILTER REPL | 5 |  | 90000129_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000129 |  | 5 |  | 24 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 |  | 30 | 5300003442 | 220 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-10 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-04 | 2024-05-06 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0050 | 0030 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10255158 | O-RING;32.92MM ID X 3.53MM DIA,FKM | 2 | EA | 5 | 2 | 6 | 2 | EA | 31.01 - 9 SOH @ AA02 | Supply for Order 200064906, Item 3 cannot be changed 9000313 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004083 | 9000313 | 05 | Preparation | 0000099208 | 3 | 0 | EA | 102000000000358 | 102000000001134 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015678_2024 | 5 | 0 | 0 |  | 2024-05-07 | AA53 | 2024-05-04 |  |  | 2024-05-09 |  |  | 100000002114 | 1020 | 2024-07-20 | 2 | 4900030175_2024_0001 |  | 2024-02-09 | 2024-05-09 |  | 5000015678_2024_0001 | 0 | 2 | 0 | 2 | 0 | 180004083 | 3 | L | 4900030175 | 2024 |  | 5000015678 | 2024 |  |  | 2024-05-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255158 | O-RING;32.92MM ID X 3.53MM DIA,FKM |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 9000313_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000125 |  | 5 |  | 3 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 | 30 | 30 | 5300003442 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-05-06 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-07 | 2024-05-10 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0210 | 0280 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10537214 | O-RING;HCU FILTER,GE M832481110 | 1 | EA | 4 | 0 | 2 | 1 | EA | 19.01 - sheduled for delivery | Supply for Order 200064906, Item 28 cannot be changed 90000129 item 90 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004076 | 90000129 | 05 | Preparation | 0000099208 | 28 | 0 | EA | 102000000001074 | 102000000001028 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015648_2024 | 6 | 0 | 0 |  | 2024-05-11 | AA53 | 2024-05-07 |  |  | 2024-05-13 |  |  | 100000002114 | 1020 | 2024-07-20 | 1 | 4900030181_2024_0017 |  | 2024-02-09 | 2024-05-13 |  | 5000015648_2024_0009 | 0 | 2 | 0 | 1 | 0 | 180004076 | 3 | L | 4900030181 | 2024 |  | 5000015648 | 2024 |  |  | 2024-05-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10537214 | O-RING;HCU FILTER,GE M832481110 |  | 0210 | HYDRAULIC CONTROL UNIT FILTER REPL | INT | HYDRAULIC CONTROL UNIT FILTER REPL | 5 |  | 90000129_0090 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000129 |  | 5 |  | 28 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 | 30 | 30 | 5300003442 | 260 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-10 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-06 | 2024-05-07 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0100 | 0130 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10480513 | WIRE,RET;NP 1697M73P02 | 1 | EA | 6 | 1 | 3 | 1 | EA | 19.01 - sheduled for delivery | Supply for Order 200064906, Item 13 cannot be changed 90000126 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004075 | 90000126 | 05 | Preparation | 0000099208 | 13 | 0 | EA | 102000000001074 | 102000000001135 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015669_2024 | 4 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-06 |  |  | 2024-05-10 |  |  | 100000002114 | 1020 | 2024-07-20 | 1 | 4900030135_2024_0007 |  | 2024-02-09 | 2024-05-10 |  | 5000015669_2024_0004 | 0 | 2 | 0 | 1 | 0 | 180004075 | 3 | L | 4900030135 | 2024 |  | 5000015669 | 2024 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10480513 | WIRE,RET;NP 1697M73P02 |  | 0100 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 5 |  | 90000126_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000126 |  | 5 |  | 13 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 | 30 | 30 | 5300003442 | 120 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-04 | 2024-05-06 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0050 | 0060 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10255353 | PACKING;PF,1.852" ID,GE J221P134 | 1 | EA | 6 | 2 | 5 | 1 | EA | 19.01 - scheduled for delivery | Supply for Order 200064906, Item 6 cannot be changed 9000313 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004083 | 9000313 | 05 | Preparation | 0000099208 | 6 | 0 | EA | 102000000000358 | 102000000001134 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015678_2024 | 5 | 0 | 0 |  | 2024-05-07 | AA53 | 2024-05-04 |  |  | 2024-05-09 |  |  | 100000002114 | 1020 | 2024-07-20 | 1 | 4900030175_2024_0005 |  | 2024-02-09 | 2024-05-09 |  | 5000015678_2024_0003 | 0 | 2 | 0 | 1 | 0 | 180004083 | 3 | L | 4900030175 | 2024 |  | 5000015678 | 2024 |  |  | 2024-05-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255353 | PACKING;PF,1.852" ID,GE J221P134 |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 9000313_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000125 |  | 5 |  | 6 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 |  | 30 | 5300003442 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-06 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-07 | 2024-05-12 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0260 | 0320 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10258557 | GASKET;GE 1538M42P01 | 2 | EA | 27 | 2 | 6 | 2 | EA | 19.01 - Scheduled for delivery | Supply for Order 200064906, Item 32 cannot be changed 90000131 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 300 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004053 | 90000131 | 05 | Preparation | 0000099208 | 32 | 0 | EA | 102000000001074 | 102000000001070 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015628_2024 | 8 | 0 | 0 |  | 2024-05-13 | AA53 | 2024-05-07 |  |  | 2024-05-15 |  |  | 100000002114 | 1020 | 2024-07-20 | 2 | 4900030151_2024_0001 |  | 2024-02-09 | 2024-05-15 |  | 5000015628_2024_0001 | 0 | 2 | 0 | 2 | 0 | 180004053 | 3 | L | 4900030151 | 2024 |  | 5000015628 | 2024 |  |  | 2024-05-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258557 | GASKET;GE 1538M42P01 |  | 0260 | P48 INLET PROBE INSPECTION | INT | P48 INLET PROBE INSPECTION | 5 |  | 90000131_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000131 |  | 5 |  | 32 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 |  | 30 | 5300003442 | 300 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-05-12 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-06 | 2024-05-09 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0180 | 0170 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10255346 | GASKET;GE J219P04 | 1 | EA | 32 | 1 | 3 | 1 | EA | 31.01 - 36 SOH @ AA02 | Supply for Order 200064906, Item 17 cannot be changed 90000128 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004071 | 90000128 | 05 | Preparation | 0000099208 | 17 | 0 | EA | 102000000001073 | 102000000001026 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015667_2024 | 6 | 0 | 0 |  | 2024-05-10 | AA53 | 2024-05-06 |  |  | 2024-05-12 |  |  | 100000002114 | 1020 | 2024-07-20 | 1 | 4900030180_2024_0001 |  | 2024-02-09 | 2024-05-12 |  | 5000015667_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004071 | 3 | L | 4900030180 | 2024 |  | 5000015667 | 2024 |  |  | 2024-05-09 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255346 | GASKET;GE J219P04 |  | 0180 | STROKE CHECK VARIABLE BYPASS VALVE | INT | STROKE CHECK VARIABLE BYPASS VALVE | 5 |  | 90000128_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000128 |  | 5 |  | 17 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 |  | 30 | 5300003442 | 150 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-09 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-07 | 2024-05-10 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0200 | 0200 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10297294 | BUSH,FLG,COMP;GE L44861P01 | 12 | EA | 473 | 12 | 228 | 12 | EA | 19.01 - Enough SOH @ AA02, Inv PO W451779919 18.7.24 | Supply for Order 200064906, Item 20 cannot be changed 90000129 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004076 | 90000129 | 05 | Preparation | 0000099208 | 20 | 0 | EA | 102000000001074 | 102000000001028 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 12 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015648_2024 | 6 | 0 | 0 |  | 2024-05-11 | AA53 | 2024-05-07 |  |  | 2024-05-13 |  |  | 100000002114 | 1020 | 2024-07-20 | 12 | 4900030181_2024_0001 |  | 2024-02-09 | 2024-05-13 |  | 5000015648_2024_0001 | 0 | 2 | 0 | 12 | 0 | 180004076 | 3 | L | 4900030181 | 2024 |  | 5000015648 | 2024 |  |  | 2024-05-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297294 | BUSH,FLG,COMP;GE L44861P01 |  | 0200 | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | INT | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | 5 |  | 90000129_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000129 |  | 5 |  | 20 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 | 30 | 30 | 5300003442 | 180 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-05-10 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-07 | 2024-05-10 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0210 | 0270 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10297418 | PACKING,PF;COMP,GE M832481904 | 1 | EA | 6 | 1 | 3 | 1 | EA | 19.01 - sheduled for delivery | Supply for Order 200064906, Item 27 cannot be changed 90000129 item 80 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004076 | 90000129 | 05 | Preparation | 0000099208 | 27 | 0 | EA | 102000000001074 | 102000000001028 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015648_2024 | 6 | 0 | 0 |  | 2024-05-11 | AA53 | 2024-05-07 |  |  | 2024-05-13 |  |  | 100000002114 | 1020 | 2024-07-20 | 1 | 4900030181_2024_0015 |  | 2024-02-09 | 2024-05-13 |  | 5000015648_2024_0008 | 0 | 2 | 0 | 1 | 0 | 180004076 | 3 | L | 4900030181 | 2024 |  | 5000015648 | 2024 |  |  | 2024-05-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297418 | PACKING,PF;COMP,GE M832481904 |  | 0210 | HYDRAULIC CONTROL UNIT FILTER REPL | INT | HYDRAULIC CONTROL UNIT FILTER REPL | 5 |  | 90000129_0080 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000129 |  | 5 |  | 27 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 |  | 30 | 5300003442 | 250 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-10 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-07 | 2024-05-11 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0240 | 0310 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10255264 | GASKET;GE 9379M93P01 | 8 | EA | 17 | 8 | 27 | 8 | EA | 19.01 - sheduled for delivery | Supply for Order 200064906, Item 31 cannot be changed 90000130 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004079 | 90000130 | 05 | Preparation | 0000099208 | 31 | 0 | EA | 102000000001074 | 102000000001072 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 8 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015647_2024 | 7 | 0 | 0 |  | 2024-05-12 | AA53 | 2024-05-07 |  |  | 2024-05-14 |  |  | 100000002114 | 1020 | 2024-07-20 | 8 | 4900030136_2024_0003 |  | 2024-02-09 | 2024-05-14 |  | 5000015647_2024_0002 | 0 | 2 | 0 | 8 | 0 | 180004079 | 3 | L | 4900030136 | 2024 |  | 5000015647 | 2024 |  |  | 2024-05-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255264 | GASKET;GE 9379M93P01 |  | 0240 | T48 THERMOCOUPLE INSPECTION | INT | T48 THERMOCOUPLE INSPECTION | 5 |  | 90000130_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000130 |  | 5 |  | 31 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 |  | 30 | 5300003442 | 290 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-05-11 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-06 | 2024-05-07 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0090 | 0100 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10255363 | PACKING,GBX,TFR;GE J221P905 | 3 | EA | 19 | 7 | 9 | 3 | EA | 19.01 - sheduled for delivery, Inv PO W451780752 22.6.24 | Supply for Order 200064906, Item 10 cannot be changed 90000126 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004075 | 90000126 | 05 | Preparation | 0000099208 | 10 | 0 | EA | 102000000001074 | 102000000000997 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 3 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015669_2024 | 4 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-06 |  |  | 2024-05-10 |  |  | 100000002114 | 1020 | 2024-07-20 | 3 | 4900030135_2024_0001 |  | 2024-02-09 | 2024-05-10 |  | 5000015669_2024_0001 | 0 | 2 | 0 | 3 | 0 | 180004075 | 3 | L | 4900030135 | 2024 |  | 5000015669 | 2024 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255363 | PACKING,GBX,TFR;GE J221P905 |  | 0090 | CHIP DETECTOR CHECK | INT | CHIP DETECTOR CHECK | 5 |  | 90000126_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000126 |  | 5 |  | 10 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 |  | 30 | 5300003442 | 90 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-05-07 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-07 | 2024-05-10 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0210 | 0250 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10297412 | PACKING,PF;GE M832481243 | 1 | EA | 19 | 1 | 3 | 1 | EA | 19.01 - Scheduled for delivery | Supply for Order 200064906, Item 25 cannot be changed 90000129 item 60 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004076 | 90000129 | 05 | Preparation | 0000099208 | 25 | 0 | EA | 102000000001074 | 102000000001028 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015648_2024 | 6 | 0 | 0 |  | 2024-05-11 | AA53 | 2024-05-07 |  |  | 2024-05-13 |  |  | 100000002114 | 1020 | 2024-07-20 | 1 | 4900030181_2024_0011 |  | 2024-02-09 | 2024-05-13 |  | 5000015648_2024_0006 | 0 | 2 | 0 | 1 | 0 | 180004076 | 3 | L | 4900030181 | 2024 |  | 5000015648 | 2024 |  |  | 2024-05-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297412 | PACKING,PF;GE M832481243 |  | 0210 | HYDRAULIC CONTROL UNIT FILTER REPL | INT | HYDRAULIC CONTROL UNIT FILTER REPL | 5 |  | 90000129_0060 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000129 |  | 5 |  | 25 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 |  | 30 | 5300003442 | 230 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-10 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-07 | 2024-05-10 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0200 | 0210 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10297295 | BUSH,FLG,COMP;GE L44861P07 | 12 | EA | 84 | 12 | 152 | 12 | EA | 24SDGT7-SW3R02A01A | Supply for Order 200064906, Item 21 cannot be changed 90000129 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004076 | 90000129 | 05 | Preparation | 0000099208 | 21 | 0 | EA | 102000000001074 | 102000000001028 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 12 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015648_2024 | 6 | 0 | 0 |  | 2024-05-11 | AA53 | 2024-05-07 |  |  | 2024-05-13 |  |  | 100000002114 | 1020 | 2024-07-20 | 12 | 4900030181_2024_0003 |  | 2024-02-09 | 2024-05-13 |  | 5000015648_2024_0002 | 0 | 2 | 0 | 12 | 0 | 180004076 | 3 | L | 4900030181 | 2024 |  | 5000015648 | 2024 |  |  | 2024-05-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297295 | BUSH,FLG,COMP;GE L44861P07 |  | 0200 | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | INT | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | 5 |  | 90000129_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000129 |  | 5 |  | 21 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 | 30 | 30 | 5300003442 | 190 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-05-10 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-04 | 2024-05-06 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0050 | 0050 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10255250 | GASKET;GE 9107M23P02 | 1 | EA | 8 | 1 | 3 | 1 | EA | 31.01 - 12 SOH @ AA02 | Supply for Order 200064906, Item 5 cannot be changed 9000313 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004083 | 9000313 | 05 | Preparation | 0000099208 | 5 | 0 | EA | 102000000000358 | 102000000001134 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015678_2024 | 5 | 0 | 0 |  | 2024-05-07 | AA53 | 2024-05-04 |  |  | 2024-05-09 |  |  | 100000002114 | 1020 | 2024-07-20 | 1 | 4900030175_2024_0003 |  | 2024-02-09 | 2024-05-09 |  | 5000015678_2024_0002 | 0 | 2 | 0 | 1 | 0 | 180004083 | 3 | L | 4900030175 | 2024 |  | 5000015678 | 2024 |  |  | 2024-05-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255250 | GASKET;GE 9107M23P02 |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 9000313_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000125 |  | 5 |  | 5 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 |  | 30 | 5300003442 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-06 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-06 | 2024-05-09 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0180 | 0190 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10307833 | GASKET,SW;GE J219P03 | 1 | EA | 38 | 1 | 4 | 1 | EA | 19.01 - sheduled for delivery | Supply for Order 200064906, Item 19 cannot be changed 90000128 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004071 | 90000128 | 05 | Preparation | 0000099208 | 19 | 0 | EA | 102000000001073 | 102000000001026 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015667_2024 | 6 | 0 | 0 |  | 2024-05-10 | AA53 | 2024-05-06 |  |  | 2024-05-12 |  |  | 100000002114 | 1020 | 2024-07-20 | 1 | 4900030180_2024_0005 |  | 2024-02-09 | 2024-05-12 |  | 5000015667_2024_0003 | 0 | 2 | 0 | 1 | 0 | 180004071 | 3 | L | 4900030180 | 2024 |  | 5000015667 | 2024 |  |  | 2024-05-09 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307833 | GASKET,SW;GE J219P03 |  | 0180 | STROKE CHECK VARIABLE BYPASS VALVE | INT | STROKE CHECK VARIABLE BYPASS VALVE | 5 |  | 90000128_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000128 |  | 5 |  | 19 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 |  | 30 | 5300003442 | 170 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-09 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-04 | 2024-05-06 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0050 | 0080 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10307721 | SEAL,GEN,GAS;NP 9032M84P02 | 1 | EA | 0 | 1 | 3 | 1 | EA | 19.01 - scheduled for delivery | Supply for Order 200064906, Item 8 cannot be changed 9000313 item 50 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004083 | 9000313 | 05 | Preparation | 0000099208 | 8 | 0 | EA | 102000000000358 | 102000000001134 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015678_2024 | 5 | 0 | 0 |  | 2024-05-07 | AA53 | 2024-05-04 |  |  | 2024-05-09 |  |  | 100000002114 | 1020 | 2024-07-20 | 1 | 4900030175_2024_0009 |  | 2024-02-09 | 2024-05-09 |  | 5000015678_2024_0005 | 0 | 2 | 0 | 1 | 0 | 180004083 | 3 | L | 4900030175 | 2024 |  | 5000015678 | 2024 |  |  | 2024-05-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307721 | SEAL,GEN,GAS;NP 9032M84P02 |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 9000313_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000125 |  | 5 |  | 8 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 | 30 | 30 | 5300003442 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-06 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-06 | 2024-05-07 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0100 | 0110 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10258644 | GASKET;GE 9608M08G48 | 1 | EA | 22 | 1 | 3 | 1 | EA | 19.01 - sheduled for delivery | Supply for Order 200064906, Item 11 cannot be changed 90000126 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004075 | 90000126 | 05 | Preparation | 0000099208 | 11 | 0 | EA | 102000000001074 | 102000000000997 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015669_2024 | 4 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-06 |  |  | 2024-05-10 |  |  | 100000002114 | 1020 | 2024-07-20 | 1 | 4900030135_2024_0003 |  | 2024-02-09 | 2024-05-10 |  | 5000015669_2024_0002 | 0 | 2 | 0 | 1 | 0 | 180004075 | 3 | L | 4900030135 | 2024 |  | 5000015669 | 2024 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258644 | GASKET;GE 9608M08G48 |  | 0100 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 5 |  | 90000126_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000126 |  | 5 |  | 11 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 |  | 30 | 5300003442 | 100 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-07 | 2024-05-10 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0210 | 0260 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10297416 | PACKING,PF;COMP,GE M832481139 | 2 | EA | 35 | 2 | 6 | 2 | EA | 19.01 - Scheduled for delivery | Supply for Order 200064906, Item 26 cannot be changed 90000129 item 70 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004076 | 90000129 | 05 | Preparation | 0000099208 | 26 | 0 | EA | 102000000001074 | 102000000001028 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015648_2024 | 6 | 0 | 0 |  | 2024-05-11 | AA53 | 2024-05-07 |  |  | 2024-05-13 |  |  | 100000002114 | 1020 | 2024-07-20 | 2 | 4900030181_2024_0013 |  | 2024-02-09 | 2024-05-13 |  | 5000015648_2024_0007 | 0 | 2 | 0 | 2 | 0 | 180004076 | 3 | L | 4900030181 | 2024 |  | 5000015648 | 2024 |  |  | 2024-05-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297416 | PACKING,PF;COMP,GE M832481139 |  | 0210 | HYDRAULIC CONTROL UNIT FILTER REPL | INT | HYDRAULIC CONTROL UNIT FILTER REPL | 5 |  | 90000129_0070 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000129 |  | 5 |  | 26 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 |  | 30 | 5300003442 | 240 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-05-10 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-06 | 2024-05-07 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0100 | 0120 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10316866 | GASKET;PIGNONE,L61917P01,TRF DRAIN | 1 | EA | 0 | 1 | 3 | 1 | EA | 19.01 - sheduled for delivery | Supply for Order 200064906, Item 12 cannot be changed 90000126 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004075 | 90000126 | 05 | Preparation | 0000099208 | 12 | 0 | EA | 102000000001074 | 102000000000997 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015669_2024 | 4 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-06 |  |  | 2024-05-10 |  |  | 100000002114 | 1020 | 2024-07-20 | 1 | 4900030135_2024_0005 |  | 2024-02-09 | 2024-05-10 |  | 5000015669_2024_0003 | 0 | 2 | 0 | 1 | 0 | 180004075 | 3 | L | 4900030135 | 2024 |  | 5000015669 | 2024 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10316866 | GASKET;PIGNONE,L61917P01,TRF DRAIN |  | 0100 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 5 |  | 90000126_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000126 |  | 5 |  | 12 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 | 30 | 30 | 5300003442 | 110 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-07 | 2024-05-10 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0200 | 0230 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10297297 | WASHER,PLN;GE L44862P03 | 12 | EA | 44 | 12 | 152 | 12 | EA | 24SDGT7-SW3R02A01A | Supply for Order 200064906, Item 23 cannot be changed 90000129 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004076 | 90000129 | 05 | Preparation | 0000099208 | 23 | 0 | EA | 102000000001074 | 102000000001028 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 12 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015648_2024 | 6 | 0 | 0 |  | 2024-05-11 | AA53 | 2024-05-07 |  |  | 2024-05-13 |  |  | 100000002114 | 1020 | 2024-07-20 | 12 | 4900030181_2024_0007 |  | 2024-02-09 | 2024-05-13 |  | 5000015648_2024_0004 | 0 | 2 | 0 | 12 | 0 | 180004076 | 3 | L | 4900030181 | 2024 |  | 5000015648 | 2024 |  |  | 2024-05-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297297 | WASHER,PLN;GE L44862P03 |  | 0200 | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | INT | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | 5 |  | 90000129_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000129 |  | 5 |  | 23 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 | 30 | 30 | 5300003442 | 210 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-05-10 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-04 | 2024-05-06 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0050 | 0070 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10255358 | PACKING,PF;1.478" ID,GE J221P222 | 1 | EA | 344 | 1 | 3 | 1 | EA | 19.01 - sheduled for delivery | Supply for Order 200064906, Item 7 cannot be changed 9000313 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004083 | 9000313 | 05 | Preparation | 0000099208 | 7 | 0 | EA | 102000000000358 | 102000000001134 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015678_2024 | 5 | 0 | 0 |  | 2024-05-07 | AA53 | 2024-05-04 |  |  | 2024-05-09 |  |  | 100000002114 | 1020 | 2024-07-20 | 1 | 4900030175_2024_0007 |  | 2024-02-09 | 2024-05-09 |  | 5000015678_2024_0004 | 0 | 2 | 0 | 1 | 0 | 180004083 | 3 | L | 4900030175 | 2024 |  | 5000015678 | 2024 |  |  | 2024-05-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255358 | PACKING,PF;1.478" ID,GE J221P222 |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 9000313_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000125 |  | 5 |  | 7 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 |  | 30 | 5300003442 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-06 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-06 | 2024-05-08 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0130 | 0150 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10307736 | RING,PST;GE 1473M46P04 | 1 | EA | 5 | 1 | 3 | 1 | EA | 19.01 - sheduled for delivery | Supply for Order 200064906, Item 15 cannot be changed 9000314 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004081 | 9000314 | 05 | Preparation | 0000099208 | 15 | 0 | EA | 102000000001074 | 102000000001133 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015675_2024 | 5 | 0 | 0 |  | 2024-05-09 | AA53 | 2024-05-06 |  |  | 2024-05-11 |  |  | 100000002114 | 1020 | 2024-07-20 | 1 | 4900030137_2024_0001 |  | 2024-02-09 | 2024-05-11 |  | 5000015675_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004081 | 3 | L | 4900030137 | 2024 |  | 5000015675 | 2024 |  |  | 2024-05-08 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307736 | RING,PST;GE 1473M46P04 |  | 0130 | PCC FORWARD MOUNT BOLT WEAR INSPECTION | INT | PCC FORWARD MOUNT BOLT WEAR INSPECTION | 5 |  | 9000314_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000127 |  | 5 |  | 15 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 | 30 | 30 | 5300003442 | 130 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-08 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-07 | 2024-05-10 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0200 | 0220 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10297296 | WASHER,PLN;GE L44862P02 | 12 | EA | 146 | 12 | 228 | 12 | EA | 24SDGT7-SW3R02A01A | Supply for Order 200064906, Item 22 cannot be changed 90000129 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004076 | 90000129 | 05 | Preparation | 0000099208 | 22 | 0 | EA | 102000000001074 | 102000000001028 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 12 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015648_2024 | 6 | 0 | 0 |  | 2024-05-11 | AA53 | 2024-05-07 |  |  | 2024-05-13 |  |  | 100000002114 | 1020 | 2024-07-20 | 12 | 4900030181_2024_0005 |  | 2024-02-09 | 2024-05-13 |  | 5000015648_2024_0003 | 0 | 2 | 0 | 12 | 0 | 180004076 | 3 | L | 4900030181 | 2024 |  | 5000015648 | 2024 |  |  | 2024-05-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297296 | WASHER,PLN;GE L44862P02 |  | 0200 | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | INT | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | 5 |  | 90000129_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000129 |  | 5 |  | 22 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 | 30 | 30 | 5300003442 | 200 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-05-10 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-06 | 2024-05-09 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0180 | 0180 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10297501 | BOLT,RDHD;GE 9107M21P06 | 12 | EA | 24 | 12 | 36 | 12 | EA | 19.01 - 12 scheduled for delivery | Supply for Order 200064906, Item 18 cannot be changed 90000128 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004071 | 90000128 | 05 | Preparation | 0000099208 | 18 | 0 | EA | 102000000001073 | 102000000001027 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 12 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015667_2024 | 6 | 0 | 0 |  | 2024-05-10 | AA53 | 2024-05-06 |  |  | 2024-05-12 |  |  | 100000002114 | 1020 | 2024-07-20 | 12 | 4900030180_2024_0003 |  | 2024-02-09 | 2024-05-12 |  | 5000015667_2024_0002 | 0 | 2 | 0 | 12 | 0 | 180004071 | 3 | L | 4900030180 | 2024 |  | 5000015667 | 2024 |  |  | 2024-05-09 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297501 | BOLT,RDHD;GE 9107M21P06 |  | 0180 | STROKE CHECK VARIABLE BYPASS VALVE | INT | STROKE CHECK VARIABLE BYPASS VALVE | 5 |  | 90000128_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000128 |  | 5 |  | 18 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 |  | 30 | 5300003442 | 160 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-05-09 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-07 | 2024-05-11 | 2024-05-03 | 2024-05-08 | ROTAT | 200064906 | 0230 | 0290 | 200064906 | 1Y P03 GT4007 TURB MECH MAINTENANCE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 10 | No Issue identified | 10258555 | WASHER,PLN;GE 133A1624P37 | 1 | EA | 7 | 0 | 3 | 1 | EA | 12.03- 5 SOH @ AA02 | Supply for Order 200064906, Item 29 cannot be changed 90000130 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003442 | 270 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004079 | 90000130 | 05 | Preparation | 0000099208 | 29 | 0 | EA | 102000000001074 | 102000000001071 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015647_2024 | 7 | 0 | 0 |  | 2024-05-12 | AA53 | 2024-05-07 |  |  | 2024-05-14 |  |  | 100000002114 | 1020 | 2024-07-20 | 1 | 4900030136_2024_0001 |  | 2024-02-09 | 2024-05-14 |  | 5000015647_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004079 | 3 | L | 4900030136 | 2024 |  | 5000015647 | 2024 |  |  | 2024-05-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258555 | WASHER,PLN;GE 133A1624P37 |  | 0230 | IGNITER PLUG INSPECTION | INT | IGNITER PLUG INSPECTION | 5 |  | 90000130_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000130 |  | 5 |  | 29 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000098625 | S002 |  | 30 | 5300003442 | 270 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-11 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99208 | 0 |  | 3 |  |  | RC00025003 | 2024-05-08 | 2024-05-03 | 2024-05-03 | Object created/Pre-costed/Settlement rule created/Released/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 200065053 | 0010 | 0070 | 200065053 | 3Y GT4008 STARTER PKG FILTER REPLACEMENT | AA53.GT4008S7 | FILT,HYDRAULIC STARTER OIL GT4008 | AA01 | 20 | No Issue identified | 10571169 | FILTER;FILTREC R241G10 | 2 | EA | 4 | 0 | 0 | 2 | EA | IN GRAY TUB | Supply for Order 200065053, Item 4 cannot be changed 90006339 item 10 already exists | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006426 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006339 | 05 | Preparation | 0000099402 | 4 | 0 | EA | 102000000003505 |  | 102000000003513 | [5 empty] | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-02-12 | ODST-0090006339_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-09-30 | 0 |  |  | 2024-04-30 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10571169 | FILTER;FILTREC R241G10 |  | 0010 | Remove & Replace Filters | INT | Remove & Replace Filters | 5 |  | 90006339_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006339 |  | 20 |  | 4 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000098772 | S002 | 30 | 30 | 5300006426 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 99402 | 0 |  | 2 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 200066255 | 0010 | 0010 | 200066255 | 6Y P03 TURB F/HOSE REPL GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10255671 | PIPE,FLEX;NP SMR7741895 | 1 | EA | 0 | 0 | 1 | 1 | EA | UserCommentLink | Supply for Order 200066255, Item 1 cannot be changed 9000019 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004178 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004302 | 9000019 | 05 | Preparation | 0000100557 | 1 | 0 | EA |  |  | 102000000000216 | 01-Road | 1000000499 |  | 5-Completed |  | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017897_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-07-15 | 1 | 4900030517_2024_0001 |  | 2024-02-12 | 2024-05-03 | GT4008 | 5000017897_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004302 | 3 | L | 4900030517 | 2024 |  | 5000017897 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255671 | PIPE,FLEX;NP SMR7741895 |  | 0010 | ROT EQUIP TURB FUEL HOSE REPL | INT | ROT EQUIP TURB FUEL HOSE REPL | 5 |  | 9000019_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000272 |  | 5 |  | 1 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000099994 | S002 |  | 30 | 5300004178 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100557 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 200066255 | 0010 | 0060 | 200066255 | 6Y P03 TURB F/HOSE REPL GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10255604 | GASKET,RING;SS316GR,NP KFZ269880144 | 3 | EA | 7 | 0 | 0 | 3 | EA | IN GRAY TUB | Supply for Order 200066255, Item 6 cannot be changed 90006336 item 20 already exists | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004178 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006336 | 05 | Preparation | 0000100557 | 6 | 0 | EA | 102000000003510 |  | 102000000003513 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006336_0020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-07-15 | 0 |  |  | 2024-04-30 | 2024-05-03 | GT4008 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255604 | GASKET,RING;SS316GR,NP KFZ269880144 |  | 0010 | ROT EQUIP TURB FUEL HOSE REPL | INT | ROT EQUIP TURB FUEL HOSE REPL | 5 |  | 90006336_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006336 |  | 5 |  | 6 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000099994 | S002 |  | 30 | 5300004178 | 60 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100557 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 200066255 | 0010 | 0040 | 200066255 | 6Y P03 TURB F/HOSE REPL GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 6 | EA | 83 | 0 | 21 | 6 | EA | 31.01 - 113 SOH @ AA02 | Supply for Order 200066255, Item 4 cannot be changed 9000019 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004178 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004302 | 9000019 | 05 | Preparation | 0000100557 | 4 | 0 | EA | 102000000000283 | 102000000000217 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 6 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017884_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-07-15 | 6 | 4900030517_2024_0005 |  | 2024-02-12 | 2024-05-03 | GT4008 | 5000017884_2024_0001 | 0 | 2 | 0 | 6 | 0 | 180004302 | 3 | L | 4900030517 | 2024 |  | 5000017884 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 |  | 0010 | ROT EQUIP TURB FUEL HOSE REPL | INT | ROT EQUIP TURB FUEL HOSE REPL | 5 |  | 9000019_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000272 |  | 5 |  | 4 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000099994 | S002 | 30 | 30 | 5300004178 | 40 |  |  | 0 | 6 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100557 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 200066255 | 0010 | 0020 | 200066255 | 6Y P03 TURB F/HOSE REPL GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10255672 | PIPE,FLEX;NP SMR7741896 | 1 | EA | 1 | 0 | 0 | 1 | EA | X 1 CRATE | Supply for Order 200066255, Item 2 cannot be changed 90000272 item 20 already exists | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004178 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000272 | 05 | Preparation | 0000100557 | 2 | 0 | EA |  |  | 102000000003502 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000272_0020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-07-15 | 0 |  |  | 2024-04-30 | 2024-05-03 | GT4008 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255672 | PIPE,FLEX;NP SMR7741896 |  | 0010 | ROT EQUIP TURB FUEL HOSE REPL | INT | ROT EQUIP TURB FUEL HOSE REPL | 5 |  | 90000272_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000272 |  | 5 |  | 2 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000099994 | S002 |  | 30 | 5300004178 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100557 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 200066255 | 0010 | 0030 | 200066255 | 6Y P03 TURB F/HOSE REPL GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10255673 | PIPE,FLEX;NP SMR7741897 | 1 | EA | 0 | 0 | 1 | 1 | EA | UserCommentLink | Supply for Order 200066255, Item 3 cannot be changed 9000019 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004178 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004302 | 9000019 | 05 | Preparation | 0000100557 | 3 | 0 | EA |  |  | 102000000000216 | 01-Road | 1000000499 |  | 5-Completed |  | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017897_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-07-15 | 1 | 4900030517_2024_0003 |  | 2024-02-12 | 2024-05-03 | GT4008 | 5000017897_2024_0002 | 0 | 2 | 0 | 1 | 0 | 180004302 | 3 | L | 4900030517 | 2024 |  | 5000017897 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255673 | PIPE,FLEX;NP SMR7741897 |  | 0010 | ROT EQUIP TURB FUEL HOSE REPL | INT | ROT EQUIP TURB FUEL HOSE REPL | 5 |  | 9000019_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000272 |  | 5 |  | 3 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000099994 | S002 |  | 30 | 5300004178 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100557 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 200066255 | 0010 | 0050 | 200066255 | 6Y P03 TURB F/HOSE REPL GT4008 | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10255603 | GASKET,SW;2.000",NP KFZ269860144 | 3 | EA | 5 | 0 | 0 | 3 | EA | IN GRAY TUB | Supply for Order 200066255, Item 5 cannot be changed 90006336 item 10 already exists | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004178 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006336 | 05 | Preparation | 0000100557 | 5 | 0 | EA | 102000000003509 |  | 102000000003513 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006336_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-07-15 | 0 |  |  | 2024-04-30 | 2024-05-03 | GT4008 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255603 | GASKET,SW;2.000",NP KFZ269860144 |  | 0010 | ROT EQUIP TURB FUEL HOSE REPL | INT | ROT EQUIP TURB FUEL HOSE REPL | 5 |  | 90006336_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006336 |  | 5 |  | 5 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000099994 | S002 |  | 30 | 5300004178 | 50 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 100557 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | QMI | 200069813 | 0010 | 0050 | 200069813 | 2Y ANALYSER CHECK GT4007 | AA53.407QT501 | ANLZ,GT4007 FUEL GAS SUPPLY | AA01 | 10 | No Issue identified | 10579002 | SENSOR;ZIRCONIA,CER,HOBRE HI207299 | 1 | EA | 1 | 0 | 1 | 1 | EA | UserCommentLink | Supply for Order 200069813, Item 1 cannot be changed 90000134 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003542 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004065 | 90000134 | 05 | Preparation | 0000104115 | 1 | 0 | EA | 102000000000357 | 102000000000410 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015691_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-08-01 | 1 | 4900030173_2024_0001 |  | 2024-02-09 | 2024-05-03 |  | 5000015691_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004065 | 3 | L | 4900030173 | 2024 |  | 5000015691 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10579002 | SENSOR;ZIRCONIA,CER,HOBRE HI207299 |  | 0010 | Complete PRT | INT | Complete PRT | 5 |  | 90000134_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000134 |  | 5 |  | 1 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000103532 | S002 | 30 | 30 | 5300003542 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 104115 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | QMI | 200069813 | 0010 | 0060 | 200069813 | 2Y ANALYSER CHECK GT4007 | AA53.407QT501 | ANLZ,GT4007 FUEL GAS SUPPLY | AA01 | 10 | No Issue identified | 10584554 | SCREW;HEX,ORIF,30UM,HOBRE HI106309 | 1 | EA | 5 | 0 | 1 | 1 | EA | UserCommentLink | Supply for Order 200069813, Item 2 cannot be changed 90000134 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003542 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004065 | 90000134 | 05 | Preparation | 0000104115 | 2 | 0 | EA | 102000000000357 | 102000000000410 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015691_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-08-01 | 1 | 4900030173_2024_0003 |  | 2024-02-09 | 2024-05-03 |  | 5000015691_2024_0002 | 0 | 2 | 0 | 1 | 0 | 180004065 | 3 | L | 4900030173 | 2024 |  | 5000015691 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10584554 | SCREW;HEX,ORIF,30UM,HOBRE HI106309 |  | 0010 | Complete PRT | INT | Complete PRT | 5 |  | 90000134_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000134 |  | 5 |  | 2 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000103532 | S002 | 30 | 30 | 5300003542 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 104115 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | QMI | 200069813 | 0010 | 0032 | 200069813 | 2Y ANALYSER CHECK GT4007 | AA53.407QT501 | ANLZ,GT4007 FUEL GAS SUPPLY | AA01 | 10 | No Issue identified | 10605820 | O-RING;ZE MIX CHAMBER,HOBRE HI106904 | 1 | EA | 0 | 0 | 1 | 1 | EA | UserCommentLink | Supply for Order 200069813, Item 6 cannot be changed 90000134 item 60 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003542 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004065 | 90000134 | 05 | Preparation | 0000104115 | 6 | 0 | EA | 102000000001074 | 102000000001025 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015691_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-08-01 | 1 | 4900030173_2024_0011 |  | 2024-02-09 | 2024-05-03 |  | 5000015691_2024_0006 | 0 | 2 | 0 | 1 | 0 | 180004065 | 3 | L | 4900030173 | 2024 |  | 5000015691 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10605820 | O-RING;ZE MIX CHAMBER,HOBRE HI106904 |  | 0010 | Complete PRT | INT | Complete PRT | 5 |  | 90000134_0060 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000134 |  | 5 |  | 6 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000103532 | S002 | 30 | 30 | 5300003542 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 104115 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | QMI | 200069813 | 0010 | 0042 | 200069813 | 2Y ANALYSER CHECK GT4007 | AA53.407QT501 | ANLZ,GT4007 FUEL GAS SUPPLY | AA01 | 10 | No Issue identified | 10605821 | O-RING;ZE MIX CHAMBER,HOBRE HI108885 | 1 | EA | 0 | 0 | 1 | 1 | EA | UserCommentLink | Supply for Order 200069813, Item 7 cannot be changed 90000134 item 70 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003542 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004065 | 90000134 | 05 | Preparation | 0000104115 | 7 | 0 | EA | 102000000001074 | 102000000001025 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015691_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-08-01 | 1 | 4900030173_2024_0013 |  | 2024-02-09 | 2024-05-03 |  | 5000015691_2024_0007 | 0 | 2 | 0 | 1 | 0 | 180004065 | 3 | L | 4900030173 | 2024 |  | 5000015691 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10605821 | O-RING;ZE MIX CHAMBER,HOBRE HI108885 |  | 0010 | Complete PRT | INT | Complete PRT | 5 |  | 90000134_0070 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000134 |  | 5 |  | 7 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000103532 | S002 | 30 | 30 | 5300003542 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 104115 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | QMI | 200069813 | 0010 | 0070 | 200069813 | 2Y ANALYSER CHECK GT4007 | AA53.407QT501 | ANLZ,GT4007 FUEL GAS SUPPLY | AA01 | 10 | No Issue identified | 10579006 | ORIFICE;TBG,0.125"OD,HOBRE HI102152 | 1 | EA | 2 | 0 | 1 | 1 | EA | UserCommentLink | Supply for Order 200069813, Item 3 cannot be changed 90000134 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003542 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004065 | 90000134 | 05 | Preparation | 0000104115 | 3 | 0 | EA | 102000000000357 | 102000000000410 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015691_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-08-01 | 1 | 4900030173_2024_0005 |  | 2024-02-09 | 2024-05-03 |  | 5000015691_2024_0003 | 0 | 2 | 0 | 1 | 0 | 180004065 | 3 | L | 4900030173 | 2024 |  | 5000015691 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10579006 | ORIFICE;TBG,0.125"OD,HOBRE HI102152 |  | 0010 | Complete PRT | INT | Complete PRT | 5 |  | 90000134_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000134 |  | 5 |  | 3 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000103532 | S002 | 30 | 30 | 5300003542 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 104115 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | QMI | 200069813 | 0010 | 0012 | 200069813 | 2Y ANALYSER CHECK GT4007 | AA53.407QT501 | ANLZ,GT4007 FUEL GAS SUPPLY | AA01 | 10 | No Issue identified | 10605758 | RING;HD,25X16X1.5MM,GR,HOBRE HI003565 | 1 | EA | 0 | 0 | 1 | 1 | EA | UserCommentLink | Supply for Order 200069813, Item 4 cannot be changed 90000134 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003542 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004065 | 90000134 | 05 | Preparation | 0000104115 | 4 | 0 | EA | 102000000001073 | 102000000001024 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015691_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-08-01 | 1 | 4900030173_2024_0007 |  | 2024-02-09 | 2024-05-03 |  | 5000015691_2024_0004 | 0 | 2 | 0 | 1 | 0 | 180004065 | 3 | L | 4900030173 | 2024 |  | 5000015691 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10605758 | RING;HD,25X16X1.5MM,GR,HOBRE HI003565 |  | 0010 | Complete PRT | INT | Complete PRT | 5 |  | 90000134_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000134 |  | 5 |  | 4 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000103532 | S002 | 30 | 30 | 5300003542 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 104115 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | QMI | 200069813 | 0010 | 0022 | 200069813 | 2Y ANALYSER CHECK GT4007 | AA53.407QT501 | ANLZ,GT4007 FUEL GAS SUPPLY | AA01 | 10 | No Issue identified | 10605759 | SCREW,HEX;5/16"-24,SS,HOBRE HI106308 | 1 | EA | 0 | 0 | 1 | 1 | EA | UserCommentLink | Supply for Order 200069813, Item 5 cannot be changed 90000134 item 50 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003542 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004065 | 90000134 | 05 | Preparation | 0000104115 | 5 | 0 | EA | 102000000001073 | 102000000001024 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015691_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-08-01 | 1 | 4900030173_2024_0009 |  | 2024-02-09 | 2024-05-03 |  | 5000015691_2024_0005 | 0 | 2 | 0 | 1 | 0 | 180004065 | 3 | L | 4900030173 | 2024 |  | 5000015691 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10605759 | SCREW,HEX;5/16"-24,SS,HOBRE HI106308 |  | 0010 | Complete PRT | INT | Complete PRT | 5 |  | 90000134_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000134 |  | 5 |  | 5 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000103532 | S002 | 30 | 30 | 5300003542 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 104115 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | QMI | 200069815 | 0010 | 0020 | 200069815 | 1Y ANALYSER FILTER REPLACEMENT 407QT501 | AA53.407QT501 | ANLZ,GT4007 FUEL GAS SUPPLY | AA01 | 10 | No Issue identified | 10578991 | FILTER KIT;HPFF,0.45UM,HOBRE HI105071 | 2 | EA | 3 | 0 | 4 | 2 | EA | 28.02 - 4 Delivered to AA53 | Supply for Order 200069815, Item 2 cannot be changed 90000135 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003544 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004059 | 90000135 | 05 | Preparation | 0000104117 | 2 | 0 | EA | 102000000000358 | 102000000000411 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015682_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-08-01 | 2 | 4900030172_2024_0003 |  | 2024-02-09 | 2024-05-03 |  | 5000015682_2024_0002 | 0 | 2 | 0 | 2 | 0 | 180004059 | 3 | L | 4900030172 | 2024 |  | 5000015682 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10578991 | FILTER KIT;HPFF,0.45UM,HOBRE HI105071 |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90000135_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000135 |  | 5 |  | 2 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000103534 | S002 | 30 | 30 | 5300003544 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 104117 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | QMI | 200069815 | 0010 | 0032 | 200069815 | 1Y ANALYSER FILTER REPLACEMENT 407QT501 | AA53.407QT501 | ANLZ,GT4007 FUEL GAS SUPPLY | AA01 | 10 | No Issue identified | 10605822 | FILTER,HYD;HOBRE HI100706 | 2 | EA | 0 | 0 | 2 | 2 | EA | 28.02 - 2 Delivered to AA53 | Supply for Order 200069815, Item 3 cannot be changed 90000135 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003544 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004059 | 90000135 | 05 | Preparation | 0000104117 | 3 | 0 | EA | 102000000001074 | 102000000000308 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015682_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-08-01 | 2 | 4900030172_2024_0005 |  | 2024-02-09 | 2024-05-03 |  | 5000015682_2024_0003 | 0 | 2 | 0 | 2 | 0 | 180004059 | 3 | L | 4900030172 | 2024 |  | 5000015682 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10605822 | FILTER,HYD;HOBRE HI100706 |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90000135_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000135 |  | 5 |  | 3 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000103534 | S002 | 30 | 30 | 5300003544 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 104117 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | QMI | 200069815 | 0010 | 0010 | 200069815 | 1Y ANALYSER FILTER REPLACEMENT 407QT501 | AA53.407QT501 | ANLZ,GT4007 FUEL GAS SUPPLY | AA01 | 10 | No Issue identified | 10578979 | ELEMENT,FLT;HOBRE HI004502 | 2 | EA | 0 | 0 | 4 | 2 | EA | 28.02 - 4 Delivered to AA53 | Supply for Order 200069815, Item 1 cannot be changed 90000135 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003544 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004059 | 90000135 | 05 | Preparation | 0000104117 | 1 | 0 | EA | 102000000000358 | 102000000000411 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015682_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-08-01 | 2 | 4900030172_2024_0001 |  | 2024-02-09 | 2024-05-03 |  | 5000015682_2024_0001 | 0 | 2 | 0 | 2 | 0 | 180004059 | 3 | L | 4900030172 | 2024 |  | 5000015682 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10578979 | ELEMENT,FLT;HOBRE HI004502 |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90000135_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000135 |  | 5 |  | 1 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000103534 | S002 | 30 | 30 | 5300003544 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 104117 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | ROTAT | 200070157 | 0020 | 0030 | 200070157 | 2Y G4009 AIR SYSTEM FILTERS CHANGE OUT | AA53.G4009S2 | FILT,GENERATOR INLET AIR GT4009 | AA01 | 20 | No Issue identified | 10255442 | NUT,ELEM,FIXATION;DONALD P770920 | 180 | EA | 228 | 180 | 180 | 180 | EA | 13.02 - In Transit Inb Del 180004323 | Supply for Order 200070157, Item 3 cannot be changed 9000031 item 30 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003716 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004323 | 9000031 | 05 | Preparation | 0000104459 | 3 | 0 | EA |  |  | 102000000000239 | [5 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 180 |  |  | Y | 1001 | 2024-01-02 | IDST-0180004323 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-10-31 | 180 | 4900030489_2024_0001 |  | 2024-02-12 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 | 180004323 | 3 | L | 4900030489 | 2024 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255442 | NUT,ELEM,FIXATION;DONALD P770920 |  | 0020 | REPLACE GENERATOR AIR FILTERS | INT | REPLACE GENERATOR AIR FILTERS | 5 |  | 9000031_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000425 |  | 20 |  | 3 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000103876 | S002 |  | 30 | 5300003716 | 30 |  |  | 0 | 180 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 104459 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | INLEC | 200070294 | 0010 | 0010 | 200070294 | 3Y Instrument Replacement (2) GT4008 | AA53.408XT513A | DET,FLAME COMB CHAMBER,GT4008 | AA01 | 10 | No Issue identified | 10255526 | SENSOR,FLAME;GE L44819P01 | 2 | EA | 7 | 0 | 2 | 2 | EA | 28.02 - 2 Delivered to AA53 | Supply for Order 200070294, Item 1 cannot be changed 90000275 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003744 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004295 | 90000275 | 05 | Preparation | 0000104643 | 1 | 0 | EA | 102000000000360 |  | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017875_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-07 | 2 | 4900030474_2024_0001 |  | 2024-02-12 | 2024-05-03 | 2200693652 | 5000017875_2024_0001 | 0 | 2 | 0 | 2 | 0 | 180004295 | 3 | L | 4900030474 | 2024 |  | 5000017875 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255526 | SENSOR,FLAME;GE L44819P01 |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90000275_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000275 |  | 10 |  | 1 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000104013 | S002 |  | 30 | 5300003744 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 104643 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Material committed/Printed/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 200070297 | 0020 | 0030 | 200070297 | 2Y G4008 AIR SYSTEM FILTERS CHANGE OUT | AA53.G4008S2 | FILT,GENERATOR INLET AIR G4008 | AA01 | 20 | No Issue identified | 10255442 | NUT,ELEM,FIXATION;DONALD P770920 | 180 | EA | 228 | 180 | 180 | 180 | EA | 24SDGT8-SW3R02A01B | Supply for Order 200070297, Item 3 cannot be changed 9000027 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003745 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004305 | 9000027 | 05 | Preparation | 0000104646 | 3 | 0 | EA | 102000000000381 | 102000000001187 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL |  | 0 |  | 0 | 0 |  | 0 | 180 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017846_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-08 | 180 | 4900030514_2024_0001 |  | 2024-02-12 | 2024-05-03 |  | 5000017846_2024_0001 | 0 | 2 | 0 | 180 | 0 | 180004305 | 3 | L | 4900030514 | 2024 |  | 5000017846 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255442 | NUT,ELEM,FIXATION;DONALD P770920 |  | 0020 | REPLACE GENERATOR AIR FILTERS | INT | REPLACE GENERATOR AIR FILTERS | 5 |  | 9000027_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000276 |  | 20 |  | 3 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000104016 | S002 |  | 30 | 5300003745 | 30 |  |  | 0 | 180 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 104646 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-06 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0050 | 0090 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10589680 | GASKET;DRV CLUTCH,NP IRM426210101 | 1 | EA | 0 | 0 | 1 | 1 | EA | 01.03 -In Transit MOT 20034 by Air, PO W451780583 x 1 Nuovo Pignone | Supply for Order 200071136, Item 9 cannot be changed 90000084 item 60 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004339 | 90000084 | 05 | Preparation | 0000105457 | 9 | 0 | EA | 102000000000119 | 102000000000138 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017937_2024 | 0 | 0 | 0 |  | 2024-05-07 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 1 | 4900030566_2024_0011 |  | 2024-02-12 | 2024-05-09 |  | 5000017937_2024_0006 | 0 | 2 | 0 | 1 | 0 | 180004339 | 3 | L | 4900030566 | 2024 |  | 5000017937 | 2024 |  |  | 2024-05-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10589680 | GASKET;DRV CLUTCH,NP IRM426210101 |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 90000084_0060 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000084 |  | 5 |  | 9 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 | 30 | 30 | 5300004106 | 80 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-06 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-10 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0200 | 0230 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10297297 | WASHER,PLN;GE L44862P03 | 12 | EA | 44 | 12 | 152 | 12 | EA | 24SDGT9-SW3R02B01A | Supply for Order 200071136, Item 23 cannot be changed 90000088 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004334 | 90000088 | 05 | Preparation | 0000105457 | 23 | 0 | EA | 102000000000119 | 102000000000152 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 12 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017980_2024 | 0 | 0 | 0 |  | 2024-05-11 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 12 | 4900030562_2024_0007 |  | 2024-02-12 | 2024-05-13 |  | 5000017980_2024_0004 | 0 | 2 | 0 | 12 | 0 | 180004334 | 3 | L | 4900030562 | 2024 |  | 5000017980 | 2024 |  |  | 2024-05-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297297 | WASHER,PLN;GE L44862P03 |  | 0200 | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | INT | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | 5 |  | 90000088_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000088 |  | 5 |  | 23 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 | 30 | 30 | 5300004106 | 210 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-05-10 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-12 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0260 | 0320 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10258557 | GASKET;GE 1538M42P01 | 2 | EA | 27 | 2 | 6 | 2 | EA | UserCommentLink | Supply for Order 200071136, Item 32 cannot be changed 90000090 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 300 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004344 | 90000090 | 05 | Preparation | 0000105457 | 32 | 0 | EA | 102000000000119 | 102000000000153 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017971_2024 | 0 | 0 | 0 |  | 2024-05-13 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 2 | 4900030578_2024_0001 |  | 2024-02-12 | 2024-05-15 |  | 5000017971_2024_0001 | 0 | 2 | 0 | 2 | 0 | 180004344 | 3 | L | 4900030578 | 2024 |  | 5000017971 | 2024 |  |  | 2024-05-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258557 | GASKET;GE 1538M42P01 |  | 0260 | P48 INLET PROBE INSPECTION | INT | P48 INLET PROBE INSPECTION | 5 |  | 90000090_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000090 |  | 5 |  | 32 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 |  | 30 | 5300004106 | 300 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-05-12 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-11 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0230 | 0290 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10258555 | WASHER,PLN;GE 133A1624P37 | 1 | EA | 7 | 0 | 3 | 1 | EA | 12.03- 5 SOH @ AA02 | Supply for Order 200071136, Item 29 cannot be changed 90000089 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 270 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004338 | 90000089 | 05 | Preparation | 0000105457 | 29 | 0 | EA | 102000000000119 | 102000000000136 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017953_2024 | 0 | 0 | 0 |  | 2024-05-12 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 1 | 4900030564_2024_0001 |  | 2024-02-12 | 2024-05-14 |  | 5000017953_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004338 | 3 | L | 4900030564 | 2024 |  | 5000017953 | 2024 |  |  | 2024-05-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258555 | WASHER,PLN;GE 133A1624P37 |  | 0230 | IGNITER PLUG INSPECTION | INT | IGNITER PLUG INSPECTION | 5 |  | 90000089_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000089 |  | 5 |  | 29 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 |  | 30 | 5300004106 | 270 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-11 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-10 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0200 | 0210 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10297295 | BUSH,FLG,COMP;GE L44861P07 | 12 | EA | 84 | 12 | 152 | 12 | EA | 24SDGT9-SW3R02B01A | Supply for Order 200071136, Item 21 cannot be changed 90000088 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004334 | 90000088 | 05 | Preparation | 0000105457 | 21 | 0 | EA | 102000000000119 | 102000000000134 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 12 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017980_2024 | 0 | 0 | 0 |  | 2024-05-11 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 12 | 4900030562_2024_0003 |  | 2024-02-12 | 2024-05-13 |  | 5000017980_2024_0002 | 0 | 2 | 0 | 12 | 0 | 180004334 | 3 | L | 4900030562 | 2024 |  | 5000017980 | 2024 |  |  | 2024-05-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297295 | BUSH,FLG,COMP;GE L44861P07 |  | 0200 | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | INT | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | 5 |  | 90000088_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000088 |  | 5 |  | 21 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 | 30 | 30 | 5300004106 | 190 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-05-10 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-10 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0200 | 0220 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10297296 | WASHER,PLN;GE L44862P02 | 12 | EA | 146 | 12 | 228 | 12 | EA | 24SDGT9-SW3R02B01A | Supply for Order 200071136, Item 22 cannot be changed 90000088 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004334 | 90000088 | 05 | Preparation | 0000105457 | 22 | 0 | EA | 102000000000119 | 102000000000152 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 12 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017980_2024 | 0 | 0 | 0 |  | 2024-05-11 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 12 | 4900030562_2024_0005 |  | 2024-02-12 | 2024-05-13 |  | 5000017980_2024_0003 | 0 | 2 | 0 | 12 | 0 | 180004334 | 3 | L | 4900030562 | 2024 |  | 5000017980 | 2024 |  |  | 2024-05-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297296 | WASHER,PLN;GE L44862P02 |  | 0200 | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | INT | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | 5 |  | 90000088_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000088 |  | 5 |  | 22 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 | 30 | 30 | 5300004106 | 200 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-05-10 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-09 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0180 | 0170 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10255346 | GASKET;GE J219P04 | 1 | EA | 32 | 1 | 3 | 1 | EA | 31.01 - 36 SOH @ AA02 | Supply for Order 200071136, Item 17 cannot be changed 90000087 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004345 | 90000087 | 05 | Preparation | 0000105457 | 17 | 0 | EA | 102000000000119 | 102000000000181 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017972_2024 | 0 | 0 | 0 |  | 2024-05-10 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 1 | 4900030591_2024_0001 |  | 2024-02-12 | 2024-05-12 |  | 5000017972_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004345 | 3 | L | 4900030591 | 2024 |  | 5000017972 | 2024 |  |  | 2024-05-09 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255346 | GASKET;GE J219P04 |  | 0180 | STROKE CHECK VARIABLE BYPASS VALVE | INT | STROKE CHECK VARIABLE BYPASS VALVE | 5 |  | 90000087_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000087 |  | 5 |  | 17 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 |  | 30 | 5300004106 | 150 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-09 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-06 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0050 | 0060 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10255353 | PACKING;PF,1.852" ID,GE J221P134 | 1 | EA | 6 | 2 | 5 | 1 | EA | UserCommentLink | Supply for Order 200071136, Item 6 cannot be changed 90000084 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004339 | 90000084 | 05 | Preparation | 0000105457 | 6 | 0 | EA | 102000000000119 | 102000000000118 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017937_2024 | 0 | 0 | 0 |  | 2024-05-07 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 1 | 4900030566_2024_0005 |  | 2024-02-12 | 2024-05-09 |  | 5000017937_2024_0003 | 0 | 2 | 0 | 1 | 0 | 180004339 | 3 | L | 4900030566 | 2024 |  | 5000017937 | 2024 |  |  | 2024-05-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255353 | PACKING;PF,1.852" ID,GE J221P134 |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 90000084_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000084 |  | 5 |  | 6 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 |  | 30 | 5300004106 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-06 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-06 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0050 | 0070 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10255358 | PACKING,PF;1.478" ID,GE J221P222 | 1 | EA | 344 | 1 | 3 | 1 | EA | UserCommentLink | Supply for Order 200071136, Item 7 cannot be changed 90000084 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004339 | 90000084 | 05 | Preparation | 0000105457 | 7 | 0 | EA | 102000000000119 | 102000000000118 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017937_2024 | 0 | 0 | 0 |  | 2024-05-07 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 1 | 4900030566_2024_0007 |  | 2024-02-12 | 2024-05-09 |  | 5000017937_2024_0004 | 0 | 2 | 0 | 1 | 0 | 180004339 | 3 | L | 4900030566 | 2024 |  | 5000017937 | 2024 |  |  | 2024-05-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255358 | PACKING,PF;1.478" ID,GE J221P222 |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 90000084_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000084 |  | 5 |  | 7 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 |  | 30 | 5300004106 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-06 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-06 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0050 | 0080 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10307721 | SEAL,GEN,GAS;NP 9032M84P02 | 1 | EA | 0 | 1 | 3 | 1 | EA | UserCommentLink | Supply for Order 200071136, Item 8 cannot be changed 90000084 item 50 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004339 | 90000084 | 05 | Preparation | 0000105457 | 8 | 0 | EA | 102000000000119 | 102000000000118 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017937_2024 | 0 | 0 | 0 |  | 2024-05-07 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 1 | 4900030566_2024_0009 |  | 2024-02-12 | 2024-05-09 |  | 5000017937_2024_0005 | 0 | 2 | 0 | 1 | 0 | 180004339 | 3 | L | 4900030566 | 2024 |  | 5000017937 | 2024 |  |  | 2024-05-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307721 | SEAL,GEN,GAS;NP 9032M84P02 |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 90000084_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000084 |  | 5 |  | 8 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 | 30 | 30 | 5300004106 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-06 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-07 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0090 | 0100 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10255363 | PACKING,GBX,TFR;GE J221P905 | 3 | EA | 19 | 7 | 9 | 3 | EA | UserCommentLink | Supply for Order 200071136, Item 10 cannot be changed 90000085 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004343 | 90000085 | 05 | Preparation | 0000105457 | 10 | 0 | EA | 102000000000119 | 102000000000151 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 3 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017907_2024 | 0 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 3 | 4900030590_2024_0001 |  | 2024-02-12 | 2024-05-10 |  | 5000017907_2024_0001 | 0 | 2 | 0 | 3 | 0 | 180004343 | 3 | L | 4900030590 | 2024 |  | 5000017907 | 2024 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255363 | PACKING,GBX,TFR;GE J221P905 |  | 0090 | CHIP DETECTOR CHECK | INT | CHIP DETECTOR CHECK | 5 |  | 90000085_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000085 |  | 5 |  | 10 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 |  | 30 | 5300004106 | 90 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-05-07 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-07 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0100 | 0110 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10258644 | GASKET;GE 9608M08G48 | 1 | EA | 22 | 1 | 3 | 1 | EA | UserCommentLink | Supply for Order 200071136, Item 11 cannot be changed 90000085 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004343 | 90000085 | 05 | Preparation | 0000105457 | 11 | 0 | EA | 102000000000119 | 102000000000151 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017907_2024 | 0 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 1 | 4900030590_2024_0003 |  | 2024-02-12 | 2024-05-10 |  | 5000017907_2024_0002 | 0 | 2 | 0 | 1 | 0 | 180004343 | 3 | L | 4900030590 | 2024 |  | 5000017907 | 2024 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258644 | GASKET;GE 9608M08G48 |  | 0100 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 5 |  | 90000085_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000085 |  | 5 |  | 11 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 |  | 30 | 5300004106 | 100 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-07 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0100 | 0120 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10316866 | GASKET;PIGNONE,L61917P01,TRF DRAIN | 1 | EA | 0 | 1 | 3 | 1 | EA | UserCommentLink | Supply for Order 200071136, Item 12 cannot be changed 90000085 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004343 | 90000085 | 05 | Preparation | 0000105457 | 12 | 0 | EA | 102000000000119 | 102000000000151 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017907_2024 | 0 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 1 | 4900030590_2024_0005 |  | 2024-02-12 | 2024-05-10 |  | 5000017907_2024_0003 | 0 | 2 | 0 | 1 | 0 | 180004343 | 3 | L | 4900030590 | 2024 |  | 5000017907 | 2024 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10316866 | GASKET;PIGNONE,L61917P01,TRF DRAIN |  | 0100 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 5 |  | 90000085_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000085 |  | 5 |  | 12 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 | 30 | 30 | 5300004106 | 110 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-07 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0100 | 0130 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10480513 | WIRE,RET;NP 1697M73P02 | 1 | EA | 6 | 1 | 3 | 1 | EA | UserCommentLink | Supply for Order 200071136, Item 13 cannot be changed 90000085 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004343 | 90000085 | 05 | Preparation | 0000105457 | 13 | 0 | EA | 102000000000119 | 102000000000184 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017907_2024 | 0 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 1 | 4900030590_2024_0007 |  | 2024-02-12 | 2024-05-10 |  | 5000017907_2024_0004 | 0 | 2 | 0 | 1 | 0 | 180004343 | 3 | L | 4900030590 | 2024 |  | 5000017907 | 2024 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10480513 | WIRE,RET;NP 1697M73P02 |  | 0100 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 5 |  | 90000085_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000085 |  | 5 |  | 13 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 | 30 | 30 | 5300004106 | 120 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-08 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0130 | 0150 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10307736 | RING,PST;GE 1473M46P04 | 1 | EA | 5 | 1 | 3 | 1 | EA | UserCommentLink | Supply for Order 200071136, Item 15 cannot be changed 9000030 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004341 | 9000030 | 05 | Preparation | 0000105457 | 15 | 0 | EA | 102000000000119 | 102000000000149 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017952_2024 | 0 | 0 | 0 |  | 2024-05-09 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 1 | 4900030509_2024_0001 |  | 2024-02-12 | 2024-05-11 |  | 5000017952_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004341 | 3 | L | 4900030509 | 2024 |  | 5000017952 | 2024 |  |  | 2024-05-08 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307736 | RING,PST;GE 1473M46P04 |  | 0130 | PCC FORWARD MOUNT BOLT WEAR INSPECTION | INT | PCC FORWARD MOUNT BOLT WEAR INSPECTION | 5 |  | 9000030_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000086 |  | 5 |  | 15 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 | 30 | 30 | 5300004106 | 130 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-08 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-09 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0180 | 0180 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10297501 | BOLT,RDHD;GE 9107M21P06 | 12 | EA | 24 | 12 | 36 | 12 | EA | UserCommentLink | Supply for Order 200071136, Item 18 cannot be changed 90000087 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004345 | 90000087 | 05 | Preparation | 0000105457 | 18 | 0 | EA | 102000000000119 | 102000000000089 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 12 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017972_2024 | 0 | 0 | 0 |  | 2024-05-10 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 12 | 4900030591_2024_0003 |  | 2024-02-12 | 2024-05-12 |  | 5000017972_2024_0002 | 0 | 2 | 0 | 12 | 0 | 180004345 | 3 | L | 4900030591 | 2024 |  | 5000017972 | 2024 |  |  | 2024-05-09 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297501 | BOLT,RDHD;GE 9107M21P06 |  | 0180 | STROKE CHECK VARIABLE BYPASS VALVE | INT | STROKE CHECK VARIABLE BYPASS VALVE | 5 |  | 90000087_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000087 |  | 5 |  | 18 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 |  | 30 | 5300004106 | 160 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-05-09 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-11 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0240 | 0310 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10255264 | GASKET;GE 9379M93P01 | 8 | EA | 17 | 8 | 27 | 8 | EA | UserCommentLink | Supply for Order 200071136, Item 31 cannot be changed 90000089 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 290 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004338 | 90000089 | 05 | Preparation | 0000105457 | 31 | 0 | EA | 102000000000119 | 102000000000085 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 8 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017953_2024 | 0 | 0 | 0 |  | 2024-05-12 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 8 | 4900030564_2024_0005 |  | 2024-02-12 | 2024-05-14 |  | 5000017953_2024_0003 | 0 | 2 | 0 | 8 | 0 | 180004338 | 3 | L | 4900030564 | 2024 |  | 5000017953 | 2024 |  |  | 2024-05-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255264 | GASKET;GE 9379M93P01 |  | 0240 | T48 THERMOCOUPLE INSPECTION | INT | T48 THERMOCOUPLE INSPECTION | 5 |  | 90000089_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000089 |  | 5 |  | 31 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 |  | 30 | 5300004106 | 290 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-05-11 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-09 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0180 | 0190 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10307833 | GASKET,SW;GE J219P03 | 1 | EA | 38 | 1 | 4 | 1 | EA | UserCommentLink | Supply for Order 200071136, Item 19 cannot be changed 90000087 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004345 | 90000087 | 05 | Preparation | 0000105457 | 19 | 0 | EA | 102000000000119 | 102000000000181 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017972_2024 | 0 | 0 | 0 |  | 2024-05-10 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 1 | 4900030591_2024_0005 |  | 2024-02-12 | 2024-05-12 |  | 5000017972_2024_0003 | 0 | 2 | 0 | 1 | 0 | 180004345 | 3 | L | 4900030591 | 2024 |  | 5000017972 | 2024 |  |  | 2024-05-09 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307833 | GASKET,SW;GE J219P03 |  | 0180 | STROKE CHECK VARIABLE BYPASS VALVE | INT | STROKE CHECK VARIABLE BYPASS VALVE | 5 |  | 90000087_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000087 |  | 5 |  | 19 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 |  | 30 | 5300004106 | 170 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-09 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-10 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0210 | 0280 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10537214 | O-RING;HCU FILTER,GE M832481110 | 1 | EA | 4 | 0 | 2 | 1 | EA | UserCommentLink | Supply for Order 200071136, Item 28 cannot be changed 90000088 item 90 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004334 | 90000088 | 05 | Preparation | 0000105457 | 28 | 0 | EA | 102000000000119 | 102000000000152 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017980_2024 | 0 | 0 | 0 |  | 2024-05-11 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 1 | 4900030562_2024_0017 |  | 2024-02-12 | 2024-05-13 |  | 5000017980_2024_0009 | 0 | 2 | 0 | 1 | 0 | 180004334 | 3 | L | 4900030562 | 2024 |  | 5000017980 | 2024 |  |  | 2024-05-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10537214 | O-RING;HCU FILTER,GE M832481110 |  | 0210 | HYDRAULIC CONTROL UNIT FILTER REPL | INT | HYDRAULIC CONTROL UNIT FILTER REPL | 5 |  | 90000088_0090 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000088 |  | 5 |  | 28 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 | 30 | 30 | 5300004106 | 260 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-10 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-10 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0210 | 0270 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10297418 | PACKING,PF;COMP,GE M832481904 | 1 | EA | 6 | 1 | 3 | 1 | EA | UserCommentLink | Supply for Order 200071136, Item 27 cannot be changed 90000088 item 80 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004334 | 90000088 | 05 | Preparation | 0000105457 | 27 | 0 | EA | 102000000000119 | 102000000000152 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017980_2024 | 0 | 0 | 0 |  | 2024-05-11 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 1 | 4900030562_2024_0015 |  | 2024-02-12 | 2024-05-13 |  | 5000017980_2024_0008 | 0 | 2 | 0 | 1 | 0 | 180004334 | 3 | L | 4900030562 | 2024 |  | 5000017980 | 2024 |  |  | 2024-05-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297418 | PACKING,PF;COMP,GE M832481904 |  | 0210 | HYDRAULIC CONTROL UNIT FILTER REPL | INT | HYDRAULIC CONTROL UNIT FILTER REPL | 5 |  | 90000088_0080 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000088 |  | 5 |  | 27 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 |  | 30 | 5300004106 | 250 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-10 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-10 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0210 | 0260 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10297416 | PACKING,PF;COMP,GE M832481139 | 2 | EA | 35 | 2 | 6 | 2 | EA | UserCommentLink | Supply for Order 200071136, Item 26 cannot be changed 90000088 item 70 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004334 | 90000088 | 05 | Preparation | 0000105457 | 26 | 0 | EA | 102000000000119 | 102000000000152 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017980_2024 | 0 | 0 | 0 |  | 2024-05-11 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 2 | 4900030562_2024_0013 |  | 2024-02-12 | 2024-05-13 |  | 5000017980_2024_0007 | 0 | 2 | 0 | 2 | 0 | 180004334 | 3 | L | 4900030562 | 2024 |  | 5000017980 | 2024 |  |  | 2024-05-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297416 | PACKING,PF;COMP,GE M832481139 |  | 0210 | HYDRAULIC CONTROL UNIT FILTER REPL | INT | HYDRAULIC CONTROL UNIT FILTER REPL | 5 |  | 90000088_0070 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000088 |  | 5 |  | 26 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 |  | 30 | 5300004106 | 240 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-05-10 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-06 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0050 | 0050 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10255250 | GASKET;GE 9107M23P02 | 1 | EA | 8 | 1 | 3 | 1 | EA | 31.01 - 12 SOH @ AA02 | Supply for Order 200071136, Item 5 cannot be changed 90000084 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004339 | 90000084 | 05 | Preparation | 0000105457 | 5 | 0 | EA | 102000000000119 | 102000000000118 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017937_2024 | 0 | 0 | 0 |  | 2024-05-07 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 1 | 4900030566_2024_0003 |  | 2024-02-12 | 2024-05-09 |  | 5000017937_2024_0002 | 0 | 2 | 0 | 1 | 0 | 180004339 | 3 | L | 4900030566 | 2024 |  | 5000017937 | 2024 |  |  | 2024-05-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255250 | GASKET;GE 9107M23P02 |  | 0050 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 90000084_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000084 |  | 5 |  | 5 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 |  | 30 | 5300004106 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-06 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-10 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0200 | 0200 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10297294 | BUSH,FLG,COMP;GE L44861P01 | 12 | EA | 473 | 12 | 228 | 12 | EA | UserCommentLink | Supply for Order 200071136, Item 20 cannot be changed 90000088 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004334 | 90000088 | 05 | Preparation | 0000105457 | 20 | 0 | EA | 102000000000119 | 102000000000152 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 12 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017980_2024 | 0 | 0 | 0 |  | 2024-05-11 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 12 | 4900030562_2024_0001 |  | 2024-02-12 | 2024-05-13 |  | 5000017980_2024_0001 | 0 | 2 | 0 | 12 | 0 | 180004334 | 3 | L | 4900030562 | 2024 |  | 5000017980 | 2024 |  |  | 2024-05-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297294 | BUSH,FLG,COMP;GE L44861P01 |  | 0200 | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | INT | REPL VSV BUSH S3-5 ABOVE & BELOW SPLIT | 5 |  | 90000088_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000088 |  | 5 |  | 20 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 | 30 | 30 | 5300004106 | 180 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-05-10 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-10 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0210 | 0240 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10255281 | ELEMENT,FLT;5" LG,GE ACB244F2440Y1 | 1 | EA | 3 | 1 | 3 | 1 | EA | UserCommentLink | Supply for Order 200071136, Item 24 cannot be changed 90000088 item 50 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 220 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004334 | 90000088 | 05 | Preparation | 0000105457 | 24 | 0 | EA | 102000000000119 | 102000000000087 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017980_2024 | 0 | 0 | 0 |  | 2024-05-11 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 1 | 4900030562_2024_0009 |  | 2024-02-12 | 2024-05-13 |  | 5000017980_2024_0005 | 0 | 2 | 0 | 1 | 0 | 180004334 | 3 | L | 4900030562 | 2024 |  | 5000017980 | 2024 |  |  | 2024-05-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255281 | ELEMENT,FLT;5" LG,GE ACB244F2440Y1 |  | 0210 | HYDRAULIC CONTROL UNIT FILTER REPL | INT | HYDRAULIC CONTROL UNIT FILTER REPL | 5 |  | 90000088_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000088 |  | 5 |  | 24 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 |  | 30 | 5300004106 | 220 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-10 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-10 | 2024-05-19 | 2024-05-21 | ROTAT | 200071136 | 0210 | 0250 | 200071136 | 1Y P03 GT4009 TURB MECH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 10 | No Issue identified | 10297412 | PACKING,PF;GE M832481243 | 1 | EA | 19 | 1 | 3 | 1 | EA | UserCommentLink | Supply for Order 200071136, Item 25 cannot be changed 90000088 item 60 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004106 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004334 | 90000088 | 05 | Preparation | 0000105457 | 25 | 0 | EA | 102000000000119 | 102000000000152 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017980_2024 | 0 | 0 | 0 |  | 2024-05-11 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 1 | 4900030562_2024_0011 |  | 2024-02-12 | 2024-05-13 |  | 5000017980_2024_0006 | 0 | 2 | 0 | 1 | 0 | 180004334 | 3 | L | 4900030562 | 2024 |  | 5000017980 | 2024 |  |  | 2024-05-10 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297412 | PACKING,PF;GE M832481243 |  | 0210 | HYDRAULIC CONTROL UNIT FILTER REPL | INT | HYDRAULIC CONTROL UNIT FILTER REPL | 5 |  | 90000088_0060 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000088 |  | 5 |  | 25 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000104855 | S002 |  | 30 | 5300004106 | 230 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-10 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 105457 | 0 |  | 3 |  |  | RC00025003 | 2024-05-21 | 2024-05-19 | 2024-05-19 | Pre-costed/Settlement rule created/Released/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-12 | 2024-05-03 | 2024-05-06 | ROTAT | 200072093 | 0170 | 0010 | 200072093 | 1Y GT4010 PACKAGE INSPECTION | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 20 | No Issue identified | 10018655 | ELEMENT,FLT;OIL,PALL HC8400FRS16Z | 2 | EA | 6 | 2 | 8 | 2 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200072093, Item 1 cannot be changed 9000348 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300004286 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006807 | 9000348 | 05 | Preparation | 0000106395 | 1 | 0 | EA | 102000000001016 |  | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006807 | 12 | 0 | 0 |  | 2024-05-13 | AA53 | 2024-05-03 |  |  | 2024-05-15 |  |  | 100000003162 | 1020 | 2024-06-08 | 2 | 4900033154_2024_0001 |  | 2024-02-27 | 2024-05-15 | GT10-MLO |  | 0 | 2 | 0 | 0 | 0 | 180006807 | 3 | L | 4900033154 | 2024 |  |  | 0 |  |  | 2024-05-12 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018655 | ELEMENT,FLT;OIL,PALL HC8400FRS16Z |  | 0170 | REPLACE MINERAL LUBE OIL FILTERS | INT | REPLACE MINERAL LUBE OIL FILTERS | 5 |  | 9000348_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000106 |  | 20 |  | 1 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000105812 | S002 | 30 | 30 | 5300004286 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-05-12 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 106395 | 0 |  | 3 |  |  | RC00025003 | 2024-05-06 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 200072095 | 0020 | 0010 | 200072095 | 6Y Replace Geometry Valve CDP Bleed 410X | AA53.410XV575 | VALVE,GT4010 HP COMP BLEED ACTUATION |  | 20 | No Issue identified | 10253545 | VALVE,BLEED;GE L47329PO5 | 1 | EA | 4 | 0 | 1 | 1 | EA | ALLY CASE | Supply for Order 200072095, Item 1 cannot be changed 90000105 item 10 already exists | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004287 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  | NEW |  |  | 90000105 | 05 | Preparation | 0000106398 | 1 | 0 | EA |  |  | 102000000003503 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000105_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-06-02 | 0 |  |  | 2024-04-30 | 2024-05-03 | 410XV575 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10253545 | VALVE,BLEED;GE L47329PO5 |  | 0020 | Remove/replace Bleed Valve | INT | Remove/replace Bleed Valve | 5 |  | 90000105_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000105 |  | 20 |  | 1 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000105814 | S002 | 30 | 30 | 5300004287 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 106398 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 200072095 | 0020 | 0020 | 200072095 | 6Y Replace Geometry Valve CDP Bleed 410X | AA53.410XV575 | VALVE,GT4010 HP COMP BLEED ACTUATION | AA01 | 20 | No Issue identified | 10258551 | RING,BLEED;AIR,GE 0946 | 2 | EA | 8 | 0 | 3 | 2 | EA | IN GRAY TUB | Supply for Order 200072095, Item 2 cannot be changed 90000105 item 20 already exists | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004287 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000105 | 05 | Preparation | 0000106398 | 2 | 0 | EA | 102000000003501 |  | 102000000003511 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000105_0020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-06-02 | 0 |  |  | 2024-04-30 | 2024-05-03 | 410XV575 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258551 | RING,BLEED;AIR,GE 0946 |  | 0020 | Remove/replace Bleed Valve | INT | Remove/replace Bleed Valve | 5 |  | 90000105_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000105 |  | 20 |  | 2 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000105814 | S002 |  | 30 | 5300004287 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 106398 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 200072097 | 0020 | 0010 | 200072097 | 6Y GT4010 GEOMETRY VALVE 8TH STAGE | AA53.410XV576 | VALVE,GT4010 8TH STAGE BLEED VLV ACTUAT |  | 20 | No Issue identified | 30000462 | VALVE,LM6000,6.0",8 TH STAGE BLEED AIR | 1 | EA | 1 | 1 | 1 | 1 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200072097, Item 1 cannot be changed 90000103 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300004288 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006805 | 90000103 | 05 | Preparation | 0000106400 | 1 | 0 | EA | 102000000001015 |  | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006805 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000003162 | 1020 | 2024-06-02 | 1 | 4900033143_2024_0001 |  | 2024-02-27 | 2024-05-03 | 2200693213 |  | 0 | 2 | 0 | 0 | 0 | 180006805 | 3 | L | 4900033143 | 2024 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 30000462 | VALVE,LM6000,6.0",8 TH STAGE BLEED AIR |  | 0020 | Remove/replace Bleed Valve | INT | Remove/replace Bleed Valve | 5 |  | 90000103_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000103 |  | 20 |  | 1 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000105816 | S002 | 30 | 30 | 5300004288 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 106400 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 200072097 | 0020 | 0020 | 200072097 | 6Y GT4010 GEOMETRY VALVE 8TH STAGE | AA53.410XV576 | VALVE,GT4010 8TH STAGE BLEED VLV ACTUAT | AA01 | 20 | No Issue identified | 10255178 | RING,BLEED;AIR,GE 2873600 | 2 | EA | 4 | 2 | 2 | 2 | EA | 31.01 - 8 SOH @ AA02 | Supply for Order 200072097, Item 2 cannot be changed 90000103 item 20 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300004288 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006805 | 90000103 | 05 | Preparation | 0000106400 | 2 | 0 | EA | 102000000000145 | 102000000001014 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006805 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000003162 | 1020 | 2024-06-02 | 2 | 4900033143_2024_0003 |  | 2024-02-27 | 2024-05-03 | 2200693213 |  | 0 | 2 | 0 | 0 | 0 | 180006805 | 3 | L | 4900033143 | 2024 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255178 | RING,BLEED;AIR,GE 2873600 |  | 0020 | Remove/replace Bleed Valve | INT | Remove/replace Bleed Valve | 5 |  | 90000103_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000103 |  | 20 |  | 2 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000105816 | S002 | 30 | 30 | 5300004288 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 106400 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | KSF
| 24SDTOT1 | Released | 2024-01-02 | 2024-03-13 | 2024-03-08 | 2024-05-09 | 2024-05-09 | WORK | 200073226 | 0010 | 0010 | 200073226 | 12Y RECERTIFY PSV DISPOSABLE | AA53.47RV745 | PSV,ACTD CTRL VALVE 110UV421 | AA01 | 10 | No issue identified | 10260758 | VALVE,REL,NGI G14,700KPAG | 1 | EA | 1 | 6 | 0 | 1 | EA | 22.03 - in Transit to AA53 | Supply for Order 200073226, Item 2 cannot be changed 90004386 item 10 already exists | Material In-Transit on-01-Road | SP12 | Stock at Base | 0 | AA03 | 5300005101 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180010051 | 90004386 | 07 | Execution | 0000107515 | 2 | 0 | EA | 119000000002667 |  | 119000000002670 | 01-Road | 20000585 |  | 1-Not Started |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-17 | IDST-0180010051 | 0 | 0 | 0 |  | 2024-03-08 | AA53 | 2024-03-13 |  |  | 2024-03-13 |  |  | 100000000676 | 1190 | 2024-05-11 | 1 | 4900036282_2024_0001 |  | 2024-03-11 | 2024-03-13 |  |  | 0 | 2 | 0 | 0 | 0 | 180010051 | 3 | L | 4900036282 | 2024 |  |  | 0 |  |  | 2024-03-08 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10260758 | VALVE,REL,NGI G14,700KPAG |  | 0010 | CERTIFY PSV | INT | CERTIFY PSV | 5 |  | 90004386_0010 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004386 |  | 5 |  | 2 |  | 0 |  | 24SDTOT1 | MJ | AU1098 | 1000106945 | S003 | 30 | 30 | 5300005101 | 10 |  |  | 0 | 1 | EA | 2001 | AA03 | 2024-03-08 |  |  |  |  | 1070 |  | 2024-03-13 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 107515 | 0 |  | 3 |  |  | RC00025003 | 2024-05-09 | 2024-05-09 | 2024-05-09 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed/Partially confirmed/Goods movement posted | AM02 | Proactive Maintenance |  | In Transit Via Road
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | INLEC | 200073248 | 0010 | 0010 | 200073248 | 2Y F&G FUNCTION CHECK (28) 3KT1410 | AA53.360TS501A | DET,HEAT 3KT1410 AUXILIARY COMPARTMENT | AA01 | 10 | No Issue identified | 10026434 | DETECTOR,TEMP;RATE COMP,450DEGF,SS,EXD | 2 | EA | 74 | 0 | 0 | 2 | EA | IN GRAY TUB | Supply for Order 200073248, Item 1 cannot be changed 90006345 item 10 already exists | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300007471 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006345 | 05 | Preparation | 0000107550 | 1 | 0 | EA | 102000000003507 |  | 102000000003609 | [5 empty] | WorkPackLink | PACKING | P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-03-05 | ODST-0090006345_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-30 | 0 |  |  | 2024-04-30 | 2024-05-03 | 360TZ511 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026434 | DETECTOR,TEMP;RATE COMP,450DEGF,SS,EXD |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 5 |  | 90006345_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006345 |  | 5 |  | 1 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000106967 | S002 | 30 | 30 | 5300007471 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 107550 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Part printed | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-04 | INLEC | 200073254 | 0010 | 0010 | 200073254 | 2Y F19 CO2 FUNCTION CHECK (73) 3KT1420 | AA53.360GS542A | SW,3KT1420 MAIN INIT CO2 BOTTLE EMPTY | AA01 | 10 | No Issue identified | 10024515 | GLASS,BREAK ALARM,VERSHOVEN EDC21011C | 3 | EA | 92 | 0 | 0 | 3 | EA | IN GRAY TUB | Supply for Order 200073254, Item 1 cannot be changed 90006332 item 10 already exists | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003293 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006332 | 05 | Preparation | 0000107557 | 1 | 0 | EA | 102000000003605 |  | 102000000003609 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006332_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-30 | 0 |  |  | 2024-04-30 | 2024-05-03 | 3KT1420 CO2 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 | 10PRE | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10024515 | GLASS,BREAK ALARM,VERSHOVEN EDC21011C |  | 0010 | Erect Scaffold Access | INT | Erect Scaffold Access | 5 |  | 90006332_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006332 |  | 5 |  | 1 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000106973 | S002 | 30 | 30 | 5300003293 | 10 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  | 2024-03-24 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 107557 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed/Partially confirmed | AM02 | Proactive Maintenance |  | KSF
| 24SDTOT1 | Released | 2024-01-02 | 2024-03-13 | 2024-03-08 | 2024-05-09 | 2024-05-09 | WORK | 200074130 | 0010 | 0010 | 200074130 | 12Y RECERTIFY PSV DISPOSABLE | AA53.47RV744 | PSV,ACTD CTRL VALVE 110UV411 | AA01 | 10 | No issue identified | 10260758 | VALVE,REL,NGI G14,700KPAG | 1 | EA | 1 | 6 | 0 | 1 | EA | 22.03 - in Transit to AA53 | Supply for Order 200074130, Item 2 cannot be changed 90004387 item 10 already exists | Material In-Transit on-01-Road | SP12 | Stock at Base | 0 | AA03 | 5300005112 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180010049 | 90004387 | 07 | Execution | 0000108465 | 2 | 0 | EA | 119000000002663 |  | 119000000002670 | 01-Road | 20000585 |  | 1-Not Started |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-17 | IDST-0180010049 | 0 | 0 | 0 |  | 2024-03-08 | AA53 | 2024-03-13 |  |  | 2024-03-13 |  |  | 100000000676 | 1190 | 2024-10-30 | 1 | 4900036273_2024_0001 |  | 2024-03-11 | 2024-03-13 |  |  | 0 | 2 | 0 | 0 | 0 | 180010049 | 3 | L | 4900036273 | 2024 |  |  | 0 |  |  | 2024-03-08 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10260758 | VALVE,REL,NGI G14,700KPAG |  | 0010 | CERTIFY PSV | INT | CERTIFY PSV | 5 |  | 90004387_0010 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004387 |  | 5 |  | 2 |  | 0 |  | 24SDTOT1 | MJ | AU1098 | 1000107849 | S003 | 30 | 30 | 5300005112 | 10 |  |  | 0 | 1 | EA | 2001 | AA03 | 2024-03-08 |  |  |  |  | 1070 |  | 2024-03-13 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108465 | 0 |  | 3 |  |  | RC00025003 | 2024-05-09 | 2024-05-09 | 2024-05-09 | Released/Settlement rule created/Pre-costed/Object created/Goods movement posted/Date set by external system/Material shortage/Printed/Partially confirmed | AM02 | Proactive Maintenance |  | In Transit Via Road
| 24SDTOT1 | Released | 2024-01-02 | 2024-05-09 | 2024-03-08 | 2024-05-09 | 2024-05-10 | WORK | 200074132 | 0010 | 0010 | 200074132 | 12Y RECERTIFY PSV DISPOSABLE | AA53.47RV761 | PSV,ACTD CTRL VALVE 110HV811 | AA01 | 10 | No Issue identified | 10260758 | VALVE,REL,NGI G14,700KPAG | 1 | EA | 1 | 6 | 0 | 1 | EA | 22.03 - in Transit to AA53 |  | Material In-Transit on-01-Road | SP12 | Stock at Base | 0 | AA03 | 5300005113 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180010046 | 90004388 | 07 | Execution | 0000108467 | 2 | 0 | EA | 119000000002669 |  | 119000000002670 | 01-Road | 20000585 |  | 1-Not Started |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-17 | IDST-0180010046 | 0 | 0 | 0 |  | 2024-03-08 | AA53 | 2024-05-09 |  |  | 2024-05-09 |  |  | 100000000676 | 1190 | 2024-10-30 | 1 | 4900036272_2024_0001 |  | 2024-03-11 | 2024-03-13 |  |  | 0 | 2 | 0 | 0 | 0 | 180010046 | 3 | L | 4900036272 | 2024 |  |  | 0 |  |  | 2024-03-08 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10260758 | VALVE,REL,NGI G14,700KPAG |  | 0010 | CERTIFY PSV | INT | CERTIFY PSV | 5 |  | 90004388_0010 | [7 empty] | 0065 | Ready for Execution (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004388 |  | 5 |  | 2 |  | 0 |  | 24SDTOT1 | MJ | AU1098 | 1000107851 | S003 | 30 | 30 | 5300005113 | 10 |  |  | 0 | 1 | EA | 2001 | AA03 | 2024-03-08 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 108467 | 0 |  | 3 |  |  | RC00025003 | 2024-05-10 | 2024-05-09 | 2024-05-09 | Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed/Released | AM02 | Proactive Maintenance |  | In Transit Via Road
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-07 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0090 | 0190 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10297412 | PACKING,PF;GE M832481243 | 1 | EA | 19 | 1 | 3 | 1 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 19 cannot be changed 9000346 item 100 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006820 | 9000346 | 05 | Preparation | 0000117945 | 19 | 0 | EA | 102000000000145 | 102000000001128 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006820 | 7 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-03 |  |  | 2024-05-10 |  |  | 100000003162 | 1020 | 2024-06-30 | 1 | 4900033164_2024_0017 |  | 2024-02-27 | 2024-05-10 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006820 | 3 | L | 4900033164 | 2024 |  |  | 0 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297412 | PACKING,PF;GE M832481243 |  | 0090 | HYDRAULIC OIL FILTER REPLACEMENT | INT | HYDRAULIC OIL FILTER REPLACEMENT | 5 |  | 9000346_0100 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000114 |  | 5 |  | 19 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 |  | 30 | 5300003490 | 170 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-07 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0070 | 0080 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10255363 | PACKING,GBX,TFR;GE J221P905 | 3 | EA | 19 | 7 | 9 | 3 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 8 cannot be changed 9000346 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006820 | 9000346 | 05 | Preparation | 0000117945 | 8 | 0 | EA | 102000000000145 | 102000000001128 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006820 | 7 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-03 |  |  | 2024-05-10 |  |  | 100000003162 | 1020 | 2024-06-30 | 3 | 4900033164_2024_0001 |  | 2024-02-27 | 2024-05-10 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006820 | 3 | L | 4900033164 | 2024 |  |  | 0 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255363 | PACKING,GBX,TFR;GE J221P905 |  | 0070 | CHIP DETECTOR CHECK | INT | CHIP DETECTOR CHECK | 5 |  | 9000346_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000114 |  | 5 |  | 8 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 |  | 30 | 5300003490 | 80 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-05-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-07 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0080 | 0100 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10307721 | SEAL,GEN,GAS;NP 9032M84P02 | 1 | EA | 0 | 1 | 3 | 1 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 9 cannot be changed 9000346 item 20 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006820 | 9000346 | 05 | Preparation | 0000117945 | 9 | 0 | EA | 102000000000145 | 102000000001127 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006820 | 7 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-03 |  |  | 2024-05-10 |  |  | 100000003162 | 1020 | 2024-06-30 | 1 | 4900033164_2024_0003 |  | 2024-02-27 | 2024-05-10 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006820 | 3 | L | 4900033164 | 2024 |  |  | 0 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307721 | SEAL,GEN,GAS;NP 9032M84P02 |  | 0080 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 9000346_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000114 |  | 5 |  | 9 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 | 30 | 30 | 5300003490 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-11 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0220 | 0310 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10316866 | GASKET;PIGNONE,L61917P01,TRF DRAIN | 1 | EA | 0 | 1 | 3 | 1 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 31 cannot be changed 90000117 item 50 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 270 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006806 | 90000117 | 05 | Preparation | 0000117945 | 31 | 0 | EA | 102000000000133 | 102000000001221 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006806 | 11 | 0 | 0 |  | 2024-05-12 | AA53 | 2024-05-03 |  |  | 2024-05-14 |  |  | 100000003162 | 1020 | 2024-06-30 | 1 | 4900033170_2024_0009 |  | 2024-02-27 | 2024-05-14 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006806 | 3 | L | 4900033170 | 2024 |  |  | 0 |  |  | 2024-05-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10316866 | GASKET;PIGNONE,L61917P01,TRF DRAIN |  | 0220 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 5 |  | 90000117_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000117 |  | 5 |  | 31 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 | 30 | 30 | 5300003490 | 270 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-11 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-11 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0220 | 0300 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10480513 | WIRE,RET;NP 1697M73P02 | 1 | EA | 6 | 1 | 3 | 1 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 30 cannot be changed 90000117 item 40 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006806 | 90000117 | 05 | Preparation | 0000117945 | 30 | 0 | EA | 102000000000133 | 102000000001224 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006806 | 11 | 0 | 0 |  | 2024-05-12 | AA53 | 2024-05-03 |  |  | 2024-05-14 |  |  | 100000003162 | 1020 | 2024-06-30 | 1 | 4900033170_2024_0007 |  | 2024-02-27 | 2024-05-14 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006806 | 3 | L | 4900033170 | 2024 |  |  | 0 |  |  | 2024-05-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10480513 | WIRE,RET;NP 1697M73P02 |  | 0220 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 5 |  | 90000117_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000117 |  | 5 |  | 30 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 | 30 | 30 | 5300003490 | 260 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-11 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-11 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0220 | 0320 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10258644 | GASKET;GE 9608M08G48 | 1 | EA | 22 | 1 | 3 | 1 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 32 cannot be changed 90000117 item 60 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 280 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006806 | 90000117 | 05 | Preparation | 0000117945 | 32 | 0 | EA | 102000000000133 | 102000000001068 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006806 | 11 | 0 | 0 |  | 2024-05-12 | AA53 | 2024-05-03 |  |  | 2024-05-14 |  |  | 100000003162 | 1020 | 2024-06-30 | 1 | 4900033170_2024_0011 |  | 2024-02-27 | 2024-05-14 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006806 | 3 | L | 4900033170 | 2024 |  |  | 0 |  |  | 2024-05-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258644 | GASKET;GE 9608M08G48 |  | 0220 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 5 |  | 90000117_0060 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000117 |  | 5 |  | 32 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 |  | 30 | 5300003490 | 280 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-11 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-07 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0080 | 0110 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10255358 | PACKING,PF;1.478" ID,GE J221P222 | 1 | EA | 344 | 1 | 3 | 1 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 10 cannot be changed 9000346 item 30 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006820 | 9000346 | 05 | Preparation | 0000117945 | 10 | 0 | EA | 102000000000145 | 102000000001128 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006820 | 7 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-03 |  |  | 2024-05-10 |  |  | 100000003162 | 1020 | 2024-06-30 | 1 | 4900033164_2024_0005 |  | 2024-02-27 | 2024-05-10 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006820 | 3 | L | 4900033164 | 2024 |  |  | 0 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255358 | PACKING,PF;1.478" ID,GE J221P222 |  | 0080 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 9000346_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000114 |  | 5 |  | 10 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 |  | 30 | 5300003490 | 100 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-07 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0090 | 0200 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10255281 | ELEMENT,FLT;5" LG,GE ACB244F2440Y1 | 1 | EA | 3 | 1 | 3 | 1 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 20 cannot be changed 9000346 item 110 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 180 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006820 | 9000346 | 05 | Preparation | 0000117945 | 20 | 0 | EA | 102000000000145 | 102000000001129 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006820 | 7 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-03 |  |  | 2024-05-10 |  |  | 100000003162 | 1020 | 2024-06-30 | 1 | 4900033164_2024_0019 |  | 2024-02-27 | 2024-05-10 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006820 | 3 | L | 4900033164 | 2024 |  |  | 0 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255281 | ELEMENT,FLT;5" LG,GE ACB244F2440Y1 |  | 0090 | HYDRAULIC OIL FILTER REPLACEMENT | INT | HYDRAULIC OIL FILTER REPLACEMENT | 5 |  | 9000346_0110 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000114 |  | 5 |  | 20 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 |  | 30 | 5300003490 | 180 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-11 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0200 | 0280 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10255346 | GASKET;GE J219P04 | 1 | EA | 32 | 1 | 3 | 1 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 28 cannot be changed 90000117 item 30 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006806 | 90000117 | 05 | Preparation | 0000117945 | 28 | 0 | EA | 102000000000133 | 102000000001068 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006806 | 11 | 0 | 0 |  | 2024-05-12 | AA53 | 2024-05-03 |  |  | 2024-05-14 |  |  | 100000003162 | 1020 | 2024-06-30 | 1 | 4900033170_2024_0005 |  | 2024-02-27 | 2024-05-14 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006806 | 3 | L | 4900033170 | 2024 |  |  | 0 |  |  | 2024-05-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255346 | GASKET;GE J219P04 |  | 0200 | STROKE CHECK VARIABLE BYPASS VALVE | INT | STROKE CHECK VARIABLE BYPASS VALVE | 5 |  | 90000117_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000117 |  | 5 |  | 28 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 |  | 30 | 5300003490 | 250 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-11 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-06 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0050 | 0070 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10258555 | WASHER,PLN;GE 133A1624P37 | 1 | EA | 7 | 0 | 3 | 1 | EA | IN GRAY TUB | Supply for Order 200082196, Item 7 cannot be changed 90000113 item 10 already exists | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000113 | 05 | Preparation | 0000117945 | 7 | 0 | EA | 102000000003500 |  | 102000000003511 | [5 empty] | WorkPackLink | PACKING | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000113_0010 | 6 | 0 | 0 |  | 2024-05-07 | AA53 | 2024-05-03 |  |  | 2024-05-09 |  |  |  |  | 2024-06-30 | 0 |  |  | 2024-05-06 | 2024-05-09 | GT4010 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258555 | WASHER,PLN;GE 133A1624P37 |  | 0050 | IGNITER PLUG INSPECTION | INT | IGNITER PLUG INSPECTION | 5 |  | 90000113_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000113 |  | 5 |  | 7 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 |  | 30 | 5300003490 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-06 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-05 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0030 | 0060 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10297294 | BUSH,FLG,COMP;GE L44861P01 | 12 | EA | 473 | 12 | 228 | 12 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 6 cannot be changed 90000112 item 40 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006810 | 90000112 | 05 | Preparation | 0000117945 | 6 | 0 | EA | 102000000000133 | 102000000001174 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006810 | 5 | 0 | 0 |  | 2024-05-06 | AA53 | 2024-05-03 |  |  | 2024-05-08 |  |  | 100000003162 | 1020 | 2024-06-30 | 12 | 4900033086_2024_0007 |  | 2024-02-27 | 2024-05-08 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006810 | 3 | L | 4900033086 | 2024 |  |  | 0 |  |  | 2024-05-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297294 | BUSH,FLG,COMP;GE L44861P01 |  | 0030 | VSV BUSHES STAGES 3-5 SPLITLINE | INT | VSV BUSHES STAGES 3-5 SPLITLINE | 5 |  | 90000112_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000112 |  | 5 |  | 6 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 | 30 | 30 | 5300003490 | 60 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-05-05 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-07 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0090 | 0170 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10297418 | PACKING,PF;COMP,GE M832481904 | 1 | EA | 6 | 1 | 3 | 1 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 17 cannot be changed 9000346 item 80 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006820 | 9000346 | 05 | Preparation | 0000117945 | 17 | 0 | EA | 102000000000145 | 102000000001128 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006820 | 7 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-03 |  |  | 2024-05-10 |  |  | 100000003162 | 1020 | 2024-06-30 | 1 | 4900033164_2024_0013 |  | 2024-02-27 | 2024-05-10 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006820 | 3 | L | 4900033164 | 2024 |  |  | 0 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297418 | PACKING,PF;COMP,GE M832481904 |  | 0090 | HYDRAULIC OIL FILTER REPLACEMENT | INT | HYDRAULIC OIL FILTER REPLACEMENT | 5 |  | 9000346_0080 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000114 |  | 5 |  | 17 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 |  | 30 | 5300003490 | 150 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-07 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0080 | 0130 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10255250 | GASKET;GE 9107M23P02 | 1 | EA | 8 | 1 | 3 | 1 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 12 cannot be changed 9000346 item 50 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006820 | 9000346 | 05 | Preparation | 0000117945 | 12 | 0 | EA | 102000000000145 | 102000000001127 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006820 | 7 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-03 |  |  | 2024-05-10 |  |  | 100000003162 | 1020 | 2024-06-30 | 1 | 4900033164_2024_0009 |  | 2024-02-27 | 2024-05-10 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006820 | 3 | L | 4900033164 | 2024 |  |  | 0 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255250 | GASKET;GE 9107M23P02 |  | 0080 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 9000346_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000114 |  | 5 |  | 12 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 |  | 30 | 5300003490 | 120 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-08 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0100 | 0220 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10307736 | RING,PST;GE 1473M46P04 | 1 | EA | 5 | 1 | 3 | 1 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 22 cannot be changed 90000115 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006814 | 90000115 | 05 | Preparation | 0000117945 | 22 | 0 | EA | 102000000000133 | 102000000001223 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006814 | 8 | 0 | 0 |  | 2024-05-09 | AA53 | 2024-05-03 |  |  | 2024-05-11 |  |  | 100000003162 | 1020 | 2024-06-30 | 1 | 4900033180_2024_0001 |  | 2024-02-27 | 2024-05-11 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006814 | 3 | L | 4900033180 | 2024 |  |  | 0 |  |  | 2024-05-08 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307736 | RING,PST;GE 1473M46P04 |  | 0100 | PCC FORWARD MOUNT BOLT WEAR | INT | PCC FORWARD MOUNT BOLT WEAR | 5 |  | 90000115_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000115 |  | 5 |  | 22 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 | 30 | 30 | 5300003490 | 190 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-08 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-08 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0120 | 0230 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10258557 | GASKET;GE 1538M42P01 | 2 | EA | 27 | 2 | 6 | 2 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 23 cannot be changed 90000115 item 20 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006814 | 90000115 | 05 | Preparation | 0000117945 | 23 | 0 | EA | 102000000000133 | 102000000001069 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006814 | 8 | 0 | 0 |  | 2024-05-09 | AA53 | 2024-05-03 |  |  | 2024-05-11 |  |  | 100000003162 | 1020 | 2024-06-30 | 2 | 4900033180_2024_0003 |  | 2024-02-27 | 2024-05-11 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006814 | 3 | L | 4900033180 | 2024 |  |  | 0 |  |  | 2024-05-08 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258557 | GASKET;GE 1538M42P01 |  | 0120 | P48 INLET PROBE INSPECTION MECH ASSIST | INT | P48 INLET PROBE INSPECTION MECH ASSIST | 5 |  | 90000115_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000115 |  | 5 |  | 23 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 |  | 30 | 5300003490 | 200 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-05-08 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-07 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0080 | 0120 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10255353 | PACKING;PF,1.852" ID,GE J221P134 | 1 | EA | 6 | 2 | 5 | 1 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 11 cannot be changed 9000346 item 40 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006820 | 9000346 | 05 | Preparation | 0000117945 | 11 | 0 | EA | 102000000000145 | 102000000001128 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006820 | 7 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-03 |  |  | 2024-05-10 |  |  | 100000003162 | 1020 | 2024-06-30 | 1 | 4900033164_2024_0007 |  | 2024-02-27 | 2024-05-10 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006820 | 3 | L | 4900033164 | 2024 |  |  | 0 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255353 | PACKING;PF,1.852" ID,GE J221P134 |  | 0080 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 9000346_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000114 |  | 5 |  | 11 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 |  | 30 | 5300003490 | 110 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-05 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0030 | 0050 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10297295 | BUSH,FLG,COMP;GE L44861P07 | 12 | EA | 84 | 12 | 152 | 12 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 5 cannot be changed 90000112 item 30 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006810 | 90000112 | 05 | Preparation | 0000117945 | 5 | 0 | EA | 102000000000133 | 102000000001175 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006810 | 5 | 0 | 0 |  | 2024-05-06 | AA53 | 2024-05-03 |  |  | 2024-05-08 |  |  | 100000003162 | 1020 | 2024-06-30 | 12 | 4900033086_2024_0005 |  | 2024-02-27 | 2024-05-08 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006810 | 3 | L | 4900033086 | 2024 |  |  | 0 |  |  | 2024-05-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297295 | BUSH,FLG,COMP;GE L44861P07 |  | 0030 | VSV BUSHES STAGES 3-5 SPLITLINE | INT | VSV BUSHES STAGES 3-5 SPLITLINE | 5 |  | 90000112_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000112 |  | 5 |  | 5 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 | 30 | 30 | 5300003490 | 50 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-05-05 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-07 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0090 | 0180 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10297416 | PACKING,PF;COMP,GE M832481139 | 2 | EA | 35 | 2 | 6 | 2 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 18 cannot be changed 9000346 item 90 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006820 | 9000346 | 05 | Preparation | 0000117945 | 18 | 0 | EA | 102000000000145 | 102000000001128 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006820 | 7 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-03 |  |  | 2024-05-10 |  |  | 100000003162 | 1020 | 2024-06-30 | 2 | 4900033164_2024_0015 |  | 2024-02-27 | 2024-05-10 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006820 | 3 | L | 4900033164 | 2024 |  |  | 0 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297416 | PACKING,PF;COMP,GE M832481139 |  | 0090 | HYDRAULIC OIL FILTER REPLACEMENT | INT | HYDRAULIC OIL FILTER REPLACEMENT | 5 |  | 9000346_0090 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000114 |  | 5 |  | 18 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 |  | 30 | 5300003490 | 160 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-05-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-11 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0200 | 0270 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10297501 | BOLT,RDHD;GE 9107M21P06 | 12 | EA | 24 | 12 | 36 | 12 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 27 cannot be changed 90000117 item 20 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006806 | 90000117 | 05 | Preparation | 0000117945 | 27 | 0 | EA | 102000000000133 | 102000000001224 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006806 | 11 | 0 | 0 |  | 2024-05-12 | AA53 | 2024-05-03 |  |  | 2024-05-14 |  |  | 100000003162 | 1020 | 2024-06-30 | 12 | 4900033170_2024_0003 |  | 2024-02-27 | 2024-05-14 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006806 | 3 | L | 4900033170 | 2024 |  |  | 0 |  |  | 2024-05-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297501 | BOLT,RDHD;GE 9107M21P06 |  | 0200 | STROKE CHECK VARIABLE BYPASS VALVE | INT | STROKE CHECK VARIABLE BYPASS VALVE | 5 |  | 90000117_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000117 |  | 5 |  | 27 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 |  | 30 | 5300003490 | 240 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-05-11 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-05 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0030 | 0030 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10297297 | WASHER,PLN;GE L44862P03 | 12 | EA | 44 | 12 | 152 | 12 | EA | 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 3 cannot be changed 90000112 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006810 | 90000112 | 05 | Preparation | 0000117945 | 3 | 0 | EA | 102000000000133 | 102000000001174 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006810 | 5 | 0 | 0 |  | 2024-05-06 | AA53 | 2024-05-03 |  |  | 2024-05-08 |  |  | 100000003162 | 1020 | 2024-06-30 | 12 | 4900033086_2024_0001 |  | 2024-02-27 | 2024-05-08 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006810 | 3 | L | 4900033086 | 2024 |  |  | 0 |  |  | 2024-05-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297297 | WASHER,PLN;GE L44862P03 |  | 0030 | VSV BUSHES STAGES 3-5 SPLITLINE | INT | VSV BUSHES STAGES 3-5 SPLITLINE | 5 |  | 90000112_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000112 |  | 5 |  | 3 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 | 30 | 30 | 5300003490 | 30 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-05-05 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-07 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0080 | 0150 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10255158 | O-RING;32.92MM ID X 3.53MM DIA,FKM | 2 | EA | 5 | 2 | 6 | 2 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 14 cannot be changed 9000346 item 60 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006820 | 9000346 | 05 | Preparation | 0000117945 | 14 | 0 | EA | 102000000000145 | 102000000001127 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006820 | 7 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-03 |  |  | 2024-05-10 |  |  | 100000003162 | 1020 | 2024-06-30 | 2 | 4900033164_2024_0011 |  | 2024-02-27 | 2024-05-10 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006820 | 3 | L | 4900033164 | 2024 |  |  | 0 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255158 | O-RING;32.92MM ID X 3.53MM DIA,FKM |  | 0080 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 9000346_0060 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000114 |  | 5 |  | 14 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 | 30 | 30 | 5300003490 | 130 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-05-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-11 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0200 | 0260 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10307833 | GASKET,SW;GE J219P03 | 1 | EA | 38 | 1 | 4 | 1 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 26 cannot be changed 90000117 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006806 | 90000117 | 05 | Preparation | 0000117945 | 26 | 0 | EA | 102000000000133 | 102000000001068 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006806 | 11 | 0 | 0 |  | 2024-05-12 | AA53 | 2024-05-03 |  |  | 2024-05-14 |  |  | 100000003162 | 1020 | 2024-06-30 | 1 | 4900033170_2024_0001 |  | 2024-02-27 | 2024-05-14 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006806 | 3 | L | 4900033170 | 2024 |  |  | 0 |  |  | 2024-05-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307833 | GASKET,SW;GE J219P03 |  | 0200 | STROKE CHECK VARIABLE BYPASS VALVE | INT | STROKE CHECK VARIABLE BYPASS VALVE | 5 |  | 90000117_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000117 |  | 5 |  | 26 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 |  | 30 | 5300003490 | 230 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-11 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-09 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0140 | 0240 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10255264 | GASKET;GE 9379M93P01 | 8 | EA | 17 | 8 | 27 | 8 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 24 cannot be changed 90000116 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006816 | 90000116 | 05 | Preparation | 0000117945 | 24 | 0 | EA | 102000000000133 | 102000000001220 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006816 | 9 | 0 | 0 |  | 2024-05-10 | AA53 | 2024-05-03 |  |  | 2024-05-12 |  |  | 100000003162 | 1020 | 2024-06-30 | 8 | 4900033171_2024_0001 |  | 2024-02-27 | 2024-05-12 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006816 | 3 | L | 4900033171 | 2024 |  |  | 0 |  |  | 2024-05-09 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255264 | GASKET;GE 9379M93P01 |  | 0140 | T48 INLET PROBE INSPECTION MECH ASSIST | INT | T48 INLET PROBE INSPECTION MECH ASSIST | 5 |  | 90000116_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000116 |  | 5 |  | 24 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 |  | 30 | 5300003490 | 210 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-05-09 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-05-05 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0030 | 0040 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10297296 | WASHER,PLN;GE L44862P02 | 12 | EA | 146 | 12 | 228 | 12 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 4 cannot be changed 90000112 item 20 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006810 | 90000112 | 05 | Preparation | 0000117945 | 4 | 0 | EA | 102000000000133 | 102000000001174 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006810 | 5 | 0 | 0 |  | 2024-05-06 | AA53 | 2024-05-03 |  |  | 2024-05-08 |  |  | 100000003162 | 1020 | 2024-06-30 | 12 | 4900033086_2024_0003 |  | 2024-02-27 | 2024-05-08 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006810 | 3 | L | 4900033086 | 2024 |  |  | 0 |  |  | 2024-05-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297296 | WASHER,PLN;GE L44862P02 |  | 0030 | VSV BUSHES STAGES 3-5 SPLITLINE | INT | VSV BUSHES STAGES 3-5 SPLITLINE | 5 |  | 90000112_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000112 |  | 5 |  | 4 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 | 30 | 30 | 5300003490 | 40 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-05-05 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-02 | 2024-04-30 | 2024-05-02 | 2024-05-05 | ROTAT | 200082196 | 0010 | 0020 | 200082196 | 1Y P03 GT4010 TURB MECH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 10 | No Issue identified | 10255347 | GASKET;GE J219P05 | 2 | EA | 21 | 2 | 4 | 2 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200082196, Item 2 cannot be changed 90000111 item 20 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003490 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006819 | 90000111 | 05 | Preparation | 0000117945 | 2 | 0 | EA | 102000000001017 |  | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006819 | 1 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-02 |  |  | 2024-05-03 |  |  | 100000003162 | 1020 | 2024-06-30 | 2 | 4900033156_2024_0003 |  | 2024-02-27 | 2024-05-03 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006819 | 3 | L | 4900033156 | 2024 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255347 | GASKET;GE J219P05 |  | 0010 | BORESCOPE INSPECTION | INT | BORESCOPE INSPECTION | 5 |  | 90000111_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000111 |  | 5 |  | 2 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000117386 | S002 | 30 | 30 | 5300003490 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 117945 | 0 |  | 3 |  |  | RC00025003 | 2024-05-05 | 2024-05-02 | 2024-05-02 | Pre-costed/Object created/Date set by external system/Material shortage/Printed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-07 | ROTAT | 200083164 | 0030 | 0070 | 200083164 | 1Y GT4007 TURB VSV REPLACEMENT | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | No Issue identified | 10297297 | WASHER,PLN;GE L44862P03 | 58 | EA | 44 | 12 | 152 | 58 | EA | 24SDGT7-SW3R02A01A | Supply for Order 200083164, Item 7 cannot be changed 9000312 item 70 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003891 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004062 | 9000312 | 05 | Preparation | 0000120013 | 7 | 0 | EA | 102000000000357 | 102000000000415 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 58 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015639_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-05-20 | 58 | 4900030155_2024_0011 |  | 2024-02-09 | 2024-05-03 | GT7STG 5 WAS | 5000015639_2024_0006 | 0 | 2 | 0 | 58 | 0 | 180004062 | 3 | L | 4900030155 | 2024 |  | 5000015639 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297297 | WASHER,PLN;GE L44862P03 |  | 0030 | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | INT | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | 5 | Ready for Release | 9000312_0070 | [7 empty] | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000252 |  | 20 |  | 7 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000119503 | S002 | 30 | 30 | 5300003891 | 70 |  |  | 0 | 58 | EA | 2001 | AA02 | 2024-04-30 |  | Ready for Release | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120013 | 0 |  | 1 |  |  | RC00025003 | 2024-05-07 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-07 | ROTAT | 200083164 | 0010 | 0010 | 200083164 | 1Y GT4007 TURB VSV REPLACEMENT | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | No Issue identified | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 4 | EA | 68 | 0 | 19 | 4 | EA | 31.01 - 87 SOH @ AA02 | Supply for Order 200083164, Item 1 cannot be changed 9000312 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003891 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004062 | 9000312 | 05 | Preparation | 0000120013 | 1 | 0 | EA | 102000000000357 | 102000000000416 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 4 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015639_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-05-20 | 4 | 4900030155_2024_0001 |  | 2024-02-09 | 2024-05-03 | Spades | 5000015639_2024_0001 | 0 | 2 | 0 | 4 | 0 | 180004062 | 3 | L | 4900030155 | 2024 |  | 5000015639 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 |  | 0010 | SPADE (Materials ordered can't DEL) | INT | SPADE (Materials ordered can't DEL) | 5 | Ready for Release | 9000312_0010 | [7 empty] | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000252 |  | 20 |  | 1 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000119503 | S002 | 30 | 30 | 5300003891 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-04-30 |  | Ready for Release | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120013 | 0 |  | 1 |  |  | RC00025003 | 2024-05-07 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-07 | ROTAT | 200083164 | 0030 | 0040 | 200083164 | 1Y GT4007 TURB VSV REPLACEMENT | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | No Issue identified | 10297294 | BUSH,FLG,COMP;GE L44861P01 | 96 | EA | 473 | 12 | 228 | 96 | EA | UserCommentLink | Supply for Order 200083164, Item 4 cannot be changed 9000312 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003891 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004062 | 9000312 | 05 | Preparation | 0000120013 | 4 | 0 | EA | 102000000000357 | 102000000000415 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 96 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015639_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-05-20 | 96 | 4900030155_2024_0005 |  | 2024-02-09 | 2024-05-03 | GT7STG 3/4 B | 5000015639_2024_0003 | 0 | 2 | 0 | 96 | 0 | 180004062 | 3 | L | 4900030155 | 2024 |  | 5000015639 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297294 | BUSH,FLG,COMP;GE L44861P01 |  | 0030 | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | INT | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | 5 | Ready for Release | 9000312_0040 | [7 empty] | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000252 |  | 20 |  | 4 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000119503 | S002 | 30 | 30 | 5300003891 | 40 |  |  | 0 | 96 | EA | 2001 | AA02 | 2024-04-30 |  | Ready for Release | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120013 | 0 |  | 1 |  |  | RC00025003 | 2024-05-07 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-07 | ROTAT | 200083164 | 0030 | 0060 | 200083164 | 1Y GT4007 TURB VSV REPLACEMENT | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | No Issue identified | 10297295 | BUSH,FLG,COMP;GE L44861P07 | 58 | EA | 84 | 12 | 152 | 58 | EA | 24SDGT7-SW3R02A01A | Supply for Order 200083164, Item 6 cannot be changed 9000312 item 60 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003891 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004062 | 9000312 | 05 | Preparation | 0000120013 | 6 | 0 | EA | 102000000000357 | 102000000000415 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 58 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015639_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-05-20 | 58 | 4900030155_2024_0009 |  | 2024-02-09 | 2024-05-03 | GT7STG 5 BSH | 5000015639_2024_0005 | 0 | 2 | 0 | 58 | 0 | 180004062 | 3 | L | 4900030155 | 2024 |  | 5000015639 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297295 | BUSH,FLG,COMP;GE L44861P07 |  | 0030 | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | INT | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | 5 | Ready for Release | 9000312_0060 | [7 empty] | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000252 |  | 20 |  | 6 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000119503 | S002 | 30 | 30 | 5300003891 | 60 |  |  | 0 | 58 | EA | 2001 | AA02 | 2024-04-30 |  | Ready for Release | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120013 | 0 |  | 1 |  |  | RC00025003 | 2024-05-07 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-07 | ROTAT | 200083164 | 0010 | 0030 | 200083164 | 1Y GT4007 TURB VSV REPLACEMENT | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | No Issue identified | 10060915 | GASKET;SWCI,15MM,CL300/600,316L/GR/316 | 8 | EA | 147 | 0 | 30 | 8 | EA | 18.01 - Enough SOH @ AA02 | Supply for Order 200083164, Item 3 cannot be changed 9000312 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003891 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004062 | 9000312 | 05 | Preparation | 0000120013 | 3 | 0 | EA | 102000000000357 | 102000000000416 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 8 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015639_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-05-20 | 8 | 4900030155_2024_0003 |  | 2024-02-09 | 2024-05-03 | Spades | 5000015639_2024_0002 | 0 | 2 | 0 | 8 | 0 | 180004062 | 3 | L | 4900030155 | 2024 |  | 5000015639 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET;SWCI,15MM,CL300/600,316L/GR/316 |  | 0010 | SPADE (Materials ordered can't DEL) | INT | SPADE (Materials ordered can't DEL) | 5 | Ready for Release | 9000312_0030 | [7 empty] | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000252 |  | 20 |  | 3 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000119503 | S002 | 30 | 30 | 5300003891 | 30 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-04-30 |  | Ready for Release | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120013 | 0 |  | 1 |  |  | RC00025003 | 2024-05-07 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-07 | ROTAT | 200083164 | 0030 | 0050 | 200083164 | 1Y GT4007 TURB VSV REPLACEMENT | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | No Issue identified | 10297296 | WASHER,PLN;GE L44862P02 | 96 | EA | 146 | 12 | 228 | 96 | EA | 24SDGT7-SW3R02A01A | Supply for Order 200083164, Item 5 cannot be changed 9000312 item 50 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003891 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004062 | 9000312 | 05 | Preparation | 0000120013 | 5 | 0 | EA | 102000000000357 | 102000000000415 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 96 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015639_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-05-20 | 96 | 4900030155_2024_0007 |  | 2024-02-09 | 2024-05-03 | GT7STG 3/4 W | 5000015639_2024_0004 | 0 | 2 | 0 | 96 | 0 | 180004062 | 3 | L | 4900030155 | 2024 |  | 5000015639 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297296 | WASHER,PLN;GE L44862P02 |  | 0030 | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | INT | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | 5 | Ready for Release | 9000312_0050 | [7 empty] | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000252 |  | 20 |  | 5 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000119503 | S002 | 30 | 30 | 5300003891 | 50 |  |  | 0 | 96 | EA | 2001 | AA02 | 2024-04-30 |  | Ready for Release | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120013 | 0 |  | 1 |  |  | RC00025003 | 2024-05-07 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-07 | ROTAT | 200083164 | 0030 | 0100 | 200083164 | 1Y GT4007 TURB VSV REPLACEMENT | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | No Issue identified | 10297383 | NUT,HEX;0.250"X28UN,GE AN316C4R | 60 | EA | 0 | 0 | 100 | 60 | EA | 24SDGT7-SW3R02A01A | Supply for Order 200083164, Item 10 cannot be changed 9000312 item 100 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003891 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004062 | 9000312 | 05 | Preparation | 0000120013 | 10 | 0 | EA | 102000000000357 | 102000000000416 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 60 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015639_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-05-20 | 60 | 4900030155_2024_0017 |  | 2024-02-09 | 2024-05-03 | GT7VSV JNut | 5000015639_2024_0009 | 0 | 2 | 0 | 60 | 0 | 180004062 | 3 | L | 4900030155 | 2024 |  | 5000015639 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297383 | NUT,HEX;0.250"X28UN,GE AN316C4R |  | 0030 | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | INT | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | 5 | Ready for Release | 9000312_0100 | [7 empty] | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000252 |  | 20 |  | 10 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000119503 | S002 |  | 30 | 5300003891 | 100 |  |  | 0 | 60 | EA | 2001 | AA02 | 2024-04-30 |  | Ready for Release | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120013 | 0 |  | 1 |  |  | RC00025003 | 2024-05-07 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-07 | ROTAT | 200083164 | 0030 | 0080 | 200083164 | 1Y GT4007 TURB VSV REPLACEMENT | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | No Issue identified | 10297384 | NUT,LK;0.250"X28UN,GE J574P02 | 54 | EA | 52 | 0 | 108 | 54 | EA | UserCommentLink | Supply for Order 200083164, Item 8 cannot be changed 9000312 item 80 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003891 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004062 | 9000312 | 05 | Preparation | 0000120013 | 8 | 0 | EA | 102000000000357 | 102000000000416 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-P07-TA | 0 |  | 0 | 0 |  | 0 | 54 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015639_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-05-20 | 54 | 4900030155_2024_0013 |  | 2024-02-09 | 2024-05-03 | GT7VSV Nut | 5000015639_2024_0007 | 0 | 2 | 0 | 54 | 0 | 180004062 | 3 | L | 4900030155 | 2024 |  | 5000015639 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297384 | NUT,LK;0.250"X28UN,GE J574P02 |  | 0030 | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | INT | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | 5 | Ready for Release | 9000312_0080 | [7 empty] | 0055 | In Preparation (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000252 |  | 20 |  | 8 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000119503 | S002 |  | 30 | 5300003891 | 80 |  |  | 0 | 54 | EA | 2001 | AA02 | 2024-04-30 |  | Ready for Release | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120013 | 0 |  | 1 |  |  | RC00025003 | 2024-05-07 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-01 | 2024-05-15 | 2024-05-15 | ROTAT | 200083165 | 0030 | 0040 | 200083165 | 1Y GT4008 TURB VSV REPLACEMENT | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | No Issue identified | 10297294 | BUSH,FLG,COMP;GE L44861P01 | 96 | EA | 473 | 12 | 228 | 96 | EA | UserCommentLink | Supply for Order 200083165, Item 4 cannot be changed 9000024 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003892 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004309 | 9000024 | 05 | Preparation | 0000120014 | 4 | 0 | EA | 102000000000283 | 102000000000219 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 96 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017867_2024 | 0 | 0 | 0 |  | 2024-05-02 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-05-20 | 96 | 4900030498_2024_0001 |  | 2024-02-12 | 2024-05-04 | GT4008 | 5000017867_2024_0001 | 0 | 2 | 0 | 96 | 0 | 180004309 | 3 | L | 4900030498 | 2024 |  | 5000017867 | 2024 |  |  | 2024-05-01 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297294 | BUSH,FLG,COMP;GE L44861P01 |  | 0030 | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | INT | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | 5 |  | 9000024_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000278 |  | 20 |  | 4 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000119504 | S002 | 30 | 30 | 5300003892 | 40 |  |  | 0 | 96 | EA | 2001 | AA02 | 2024-05-01 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120014 | 0 |  | 1 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-01 | 2024-05-15 | 2024-05-15 | ROTAT | 200083165 | 0030 | 0050 | 200083165 | 1Y GT4008 TURB VSV REPLACEMENT | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | No Issue identified | 10297296 | WASHER,PLN;GE L44862P02 | 96 | EA | 146 | 12 | 228 | 96 | EA | 24SDGT8-SW3R02A01B | Supply for Order 200083165, Item 5 cannot be changed 9000024 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003892 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004309 | 9000024 | 05 | Preparation | 0000120014 | 5 | 0 | EA | 102000000000283 | 102000000000219 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 96 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017867_2024 | 0 | 0 | 0 |  | 2024-05-02 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-05-20 | 96 | 4900030498_2024_0003 |  | 2024-02-12 | 2024-05-04 | GT4008 | 5000017867_2024_0002 | 0 | 2 | 0 | 96 | 0 | 180004309 | 3 | L | 4900030498 | 2024 |  | 5000017867 | 2024 |  |  | 2024-05-01 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297296 | WASHER,PLN;GE L44862P02 |  | 0030 | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | INT | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | 5 |  | 9000024_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000278 |  | 20 |  | 5 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000119504 | S002 | 30 | 30 | 5300003892 | 50 |  |  | 0 | 96 | EA | 2001 | AA02 | 2024-05-01 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120014 | 0 |  | 1 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 200083165 | 0010 | 0010 | 200083165 | 1Y GT4008 TURB VSV REPLACEMENT | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | No Issue identified | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 4 | EA | 68 | 0 | 19 | 4 | EA | 31.01 - 87 SOH @ AA02 | Supply for Order 200083165, Item 1 cannot be changed 9000025 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003892 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004300 | 9000025 | 05 | Preparation | 0000120014 | 1 | 0 | EA | 102000000000283 | 102000000000218 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017865_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-05-20 | 4 | 4900030515_2024_0001 |  | 2024-02-12 | 2024-05-03 | GT4008 | 5000017865_2024_0001 | 0 | 2 | 0 | 4 | 0 | 180004300 | 3 | L | 4900030515 | 2024 |  | 5000017865 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 |  | 0010 | PERFORM SPADE | INT | PERFORM SPADE | 5 |  | 9000025_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000277 |  | 20 |  | 1 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000119504 | S002 | 30 | 30 | 5300003892 | 10 |  |  | 0 | 4 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120014 | 0 |  | 1 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 200083165 | 0010 | 0030 | 200083165 | 1Y GT4008 TURB VSV REPLACEMENT | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | No Issue identified | 10060915 | GASKET;SWCI,15MM,CL300/600,316L/GR/316 | 8 | EA | 147 | 0 | 30 | 8 | EA | 18.01 - Enough SOH @ AA02 | Supply for Order 200083165, Item 3 cannot be changed 9000025 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003892 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004300 | 9000025 | 05 | Preparation | 0000120014 | 3 | 0 | EA | 102000000000283 | 102000000000218 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017865_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-05-20 | 8 | 4900030515_2024_0003 |  | 2024-02-12 | 2024-05-03 | GT4008 | 5000017865_2024_0002 | 0 | 2 | 0 | 8 | 0 | 180004300 | 3 | L | 4900030515 | 2024 |  | 5000017865 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET;SWCI,15MM,CL300/600,316L/GR/316 |  | 0010 | PERFORM SPADE | INT | PERFORM SPADE | 5 |  | 9000025_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000277 |  | 20 |  | 3 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000119504 | S002 | 30 | 30 | 5300003892 | 30 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120014 | 0 |  | 1 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-01 | 2024-05-15 | 2024-05-15 | ROTAT | 200083165 | 0030 | 0060 | 200083165 | 1Y GT4008 TURB VSV REPLACEMENT | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | No Issue identified | 10297295 | BUSH,FLG,COMP;GE L44861P07 | 58 | EA | 84 | 12 | 152 | 58 | EA | 24SDGT8-SW3R02A01B | Supply for Order 200083165, Item 6 cannot be changed 9000024 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003892 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004309 | 9000024 | 05 | Preparation | 0000120014 | 6 | 0 | EA | 102000000000283 | 102000000000219 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 58 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017867_2024 | 0 | 0 | 0 |  | 2024-05-02 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-05-20 | 58 | 4900030498_2024_0005 |  | 2024-02-12 | 2024-05-04 | GT4008 | 5000017867_2024_0003 | 0 | 2 | 0 | 58 | 0 | 180004309 | 3 | L | 4900030498 | 2024 |  | 5000017867 | 2024 |  |  | 2024-05-01 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297295 | BUSH,FLG,COMP;GE L44861P07 |  | 0030 | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | INT | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | 5 |  | 9000024_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000278 |  | 20 |  | 6 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000119504 | S002 | 30 | 30 | 5300003892 | 60 |  |  | 0 | 58 | EA | 2001 | AA02 | 2024-05-01 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120014 | 0 |  | 1 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-01 | 2024-05-15 | 2024-05-15 | ROTAT | 200083165 | 0030 | 0080 | 200083165 | 1Y GT4008 TURB VSV REPLACEMENT | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | No Issue identified | 10297384 | NUT,LK;0.250"X28UN,GE J574P02 | 54 | EA | 52 | 0 | 108 | 54 | EA | UserCommentLink | Supply for Order 200083165, Item 8 cannot be changed 9000024 item 50 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003892 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004309 | 9000024 | 05 | Preparation | 0000120014 | 8 | 0 | EA | 102000000000283 | 102000000000300 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 54 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017867_2024 | 0 | 0 | 0 |  | 2024-05-02 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-05-20 | 54 | 4900030498_2024_0009 |  | 2024-02-12 | 2024-05-04 | GT4008 | 5000017867_2024_0005 | 0 | 2 | 0 | 54 | 0 | 180004309 | 3 | L | 4900030498 | 2024 |  | 5000017867 | 2024 |  |  | 2024-05-01 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297384 | NUT,LK;0.250"X28UN,GE J574P02 |  | 0030 | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | INT | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | 5 |  | 9000024_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000278 |  | 20 |  | 8 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000119504 | S002 |  | 30 | 5300003892 | 80 |  |  | 0 | 54 | EA | 2001 | AA02 | 2024-05-01 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120014 | 0 |  | 1 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-01 | 2024-05-15 | 2024-05-15 | ROTAT | 200083165 | 0030 | 0070 | 200083165 | 1Y GT4008 TURB VSV REPLACEMENT | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | No Issue identified | 10297297 | WASHER,PLN;GE L44862P03 | 58 | EA | 44 | 12 | 152 | 58 | EA | 24SDGT8-SW3R02A01B | Supply for Order 200083165, Item 7 cannot be changed 9000024 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003892 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004309 | 9000024 | 05 | Preparation | 0000120014 | 7 | 0 | EA | 102000000000283 | 102000000000219 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 58 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017867_2024 | 0 | 0 | 0 |  | 2024-05-02 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-05-20 | 58 | 4900030498_2024_0007 |  | 2024-02-12 | 2024-05-04 | GT4008 | 5000017867_2024_0004 | 0 | 2 | 0 | 58 | 0 | 180004309 | 3 | L | 4900030498 | 2024 |  | 5000017867 | 2024 |  |  | 2024-05-01 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297297 | WASHER,PLN;GE L44862P03 |  | 0030 | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | INT | INSTL NEW VSV BUSHES HPC STAGES 3, 4 & 5 | 5 |  | 9000024_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000278 |  | 20 |  | 7 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000119504 | S002 | 30 | 30 | 5300003892 | 70 |  |  | 0 | 58 | EA | 2001 | AA02 | 2024-05-01 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120014 | 0 |  | 1 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | QMI | 200083423 | 0010 | 0030 | 200083423 | 1Y Analyser Filter Replacement 408QE501 | AA53.408QE501S1 | FILT,GT4008 ANLZ SAMPLE | AA01 | 30 | No Issue identified | 10578979 | ELEMENT,FLT;HOBRE HI004502 | 1 | EA | 0 | 0 | 4 | 1 | EA | 28.02 - 4 Delivered to AA53 | Supply for Order 200083423, Item 3 cannot be changed 90000279 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003947 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004297 | 90000279 | 05 | Preparation | 0000120680 | 3 | 0 | EA | 102000000000283 | 102000000000301 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017885_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-04-07 | 1 | 4900030463_2024_0001 |  | 2024-02-12 | 2024-05-03 | 2200670025 | 5000017885_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004297 | 3 | L | 4900030463 | 2024 |  | 5000017885 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10578979 | ELEMENT,FLT;HOBRE HI004502 |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90000279_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000279 |  | 30 |  | 3 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120092 | S002 | 30 | 30 | 5300003947 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120680 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | QMI | 200083423 | 0010 | 0040 | 200083423 | 1Y Analyser Filter Replacement 408QE501 | AA53.408QE501S1 | FILT,GT4008 ANLZ SAMPLE | AA01 | 30 | No Issue identified | 10578991 | FILTER KIT;HPFF,0.45UM,HOBRE HI105071 | 1 | EA | 3 | 0 | 4 | 1 | EA | 28.02 - 4 Delivered to AA53 | Supply for Order 200083423, Item 4 cannot be changed 90000279 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003947 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004297 | 90000279 | 05 | Preparation | 0000120680 | 4 | 0 | EA | 102000000000283 | 102000000000301 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017885_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-04-07 | 1 | 4900030463_2024_0003 |  | 2024-02-12 | 2024-05-03 | 2200670025 | 5000017885_2024_0002 | 0 | 2 | 0 | 1 | 0 | 180004297 | 3 | L | 4900030463 | 2024 |  | 5000017885 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10578991 | FILTER KIT;HPFF,0.45UM,HOBRE HI105071 |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90000279_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000279 |  | 30 |  | 4 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120092 | S002 | 30 | 30 | 5300003947 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120680 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | QMI | 200083425 | 0010 | 0030 | 200083425 | 1Y Analyser Filter Replacement 409QT501 | AA53.409QT501 | ANLZ,GT4009 FUEL GAS SUPPLY | AA01 | 10 | No Issue identified | 10578979 | ELEMENT,FLT;HOBRE HI004502 | 1 | EA | 0 | 0 | 4 | 1 | EA | 28.02 - 4 Delivered to AA53 | Supply for Order 200083425, Item 3 cannot be changed 90000299 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003949 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004328 | 90000299 | 05 | Preparation | 0000120726 | 3 | 0 | EA | 102000000000188 | 102000000000166 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017908_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 1 | 4900030557_2024_0001 |  | 2024-02-12 | 2024-05-03 | 2200670029 | 5000017908_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004328 | 3 | L | 4900030557 | 2024 |  | 5000017908 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10578979 | ELEMENT,FLT;HOBRE HI004502 |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90000299_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000299 |  | 5 |  | 3 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000120098 | S002 | 30 | 30 | 5300003949 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120726 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Pre-costed/Object created/Date set by external system/Printed/Material committed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | QMI | 200083425 | 0010 | 0040 | 200083425 | 1Y Analyser Filter Replacement 409QT501 | AA53.409QT501 | ANLZ,GT4009 FUEL GAS SUPPLY | AA01 | 10 | No Issue identified | 10578991 | FILTER KIT;HPFF,0.45UM,HOBRE HI105071 | 1 | EA | 3 | 0 | 4 | 1 | EA | 28.02 - 4 Delivered to AA53 | Supply for Order 200083425, Item 4 cannot be changed 90000299 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003949 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004328 | 90000299 | 05 | Preparation | 0000120726 | 4 | 0 | EA | 102000000000188 | 102000000000166 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL | AA53-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017908_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-06-30 | 1 | 4900030557_2024_0003 |  | 2024-02-12 | 2024-05-03 | 2200670029 | 5000017908_2024_0002 | 0 | 2 | 0 | 1 | 0 | 180004328 | 3 | L | 4900030557 | 2024 |  | 5000017908 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10578991 | FILTER KIT;HPFF,0.45UM,HOBRE HI105071 |  | 0010 | Complete Replacement | INT | Complete Replacement | 5 |  | 90000299_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000299 |  | 5 |  | 4 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000120098 | S002 | 30 | 30 | 5300003949 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120726 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Pre-costed/Object created/Date set by external system/Printed/Material committed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 200083436 | 0020 | 0030 | 200083436 | 2Y G4010 AIR SYSTEM FILTERS CHANGE OUT | AA53.G4010S2 | FILT,GENERATOR INLET AIR GT4010 | AA01 | 20 | No Issue identified | 10255442 | NUT,ELEM,FIXATION;DONALD P770920 | 180 | EA | 228 | 180 | 180 | 180 | EA | IN GRAY TUB | Supply for Order 200083436, Item 3 cannot be changed 90000109 item 30 already exists | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003951 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90000109 | 05 | Preparation | 0000120885 | 3 | 0 | EA | 102000000003479 |  | 102000000003511 | [5 empty] | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 180 |  |  | Y | 1001 | 2024-01-02 | ODST-0090000109_0030 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-05-14 | 0 |  |  | 2024-04-30 | 2024-05-03 | GT4010 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255442 | NUT,ELEM,FIXATION;DONALD P770920 |  | 0020 | REPLACE GENERATOR AIR FILTERS | INT | REPLACE GENERATOR AIR FILTERS | 5 |  | 90000109_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000109 |  | 20 |  | 3 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000120238 | S002 |  | 30 | 5300003951 | 30 |  |  | 0 | 180 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 120885 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-07 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0090 | 0180 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10297416 | PACKING,PF;COMP,GE M832481139 | 2 | EA | 35 | 2 | 6 | 2 | EA | UserCommentLink | Supply for Order 200083506, Item 18 cannot be changed 90000283 item 80 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 150 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004308 | 90000283 | 05 | Preparation | 0000121037 | 18 | 0 | EA | 102000000000281 | 102000000000256 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017858_2024 | 0 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 2 | 4900030519_2024_0015 |  | 2024-02-12 | 2024-05-10 | 2200670051 | 5000017858_2024_0008 | 0 | 2 | 0 | 2 | 0 | 180004308 | 3 | L | 4900030519 | 2024 |  | 5000017858 | 2024 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297416 | PACKING,PF;COMP,GE M832481139 |  | 0090 | HYDRAULIC OIL FILTER REPLACEMENT | INT | HYDRAULIC OIL FILTER REPLACEMENT | 5 |  | 90000283_0080 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000283 |  | 5 |  | 18 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 |  | 30 | 5300003974 | 150 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-05-07 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-07 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0080 | 0110 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10255358 | PACKING,PF;1.478" ID,GE J221P222 | 1 | EA | 344 | 1 | 3 | 1 | EA | UserCommentLink | Supply for Order 200083506, Item 10 cannot be changed 90000283 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004308 | 90000283 | 05 | Preparation | 0000121037 | 10 | 0 | EA | 102000000000281 | 102000000000256 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017858_2024 | 0 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 1 | 4900030519_2024_0005 |  | 2024-02-12 | 2024-05-10 | 2200670051 | 5000017858_2024_0003 | 0 | 2 | 0 | 1 | 0 | 180004308 | 3 | L | 4900030519 | 2024 |  | 5000017858 | 2024 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255358 | PACKING,PF;1.478" ID,GE J221P222 |  | 0080 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 90000283_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000283 |  | 5 |  | 10 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 |  | 30 | 5300003974 | 100 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-07 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0090 | 0190 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10297412 | PACKING,PF;GE M832481243 | 1 | EA | 19 | 1 | 3 | 1 | EA | UserCommentLink | Supply for Order 200083506, Item 19 cannot be changed 90000283 item 90 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 160 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004308 | 90000283 | 05 | Preparation | 0000121037 | 19 | 0 | EA | 102000000000281 | 102000000000256 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017858_2024 | 0 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 1 | 4900030519_2024_0017 |  | 2024-02-12 | 2024-05-10 | 2200670051 | 5000017858_2024_0009 | 0 | 2 | 0 | 1 | 0 | 180004308 | 3 | L | 4900030519 | 2024 |  | 5000017858 | 2024 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297412 | PACKING,PF;GE M832481243 |  | 0090 | HYDRAULIC OIL FILTER REPLACEMENT | INT | HYDRAULIC OIL FILTER REPLACEMENT | 5 |  | 90000283_0090 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000283 |  | 5 |  | 19 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 |  | 30 | 5300003974 | 160 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-07 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0080 | 0120 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10255353 | PACKING;PF,1.852" ID,GE J221P134 | 1 | EA | 6 | 2 | 5 | 1 | EA | UserCommentLink | Supply for Order 200083506, Item 11 cannot be changed 90000283 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004308 | 90000283 | 05 | Preparation | 0000121037 | 11 | 0 | EA | 102000000000281 | 102000000000256 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017858_2024 | 0 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 1 | 4900030519_2024_0007 |  | 2024-02-12 | 2024-05-10 | 2200670051 | 5000017858_2024_0004 | 0 | 2 | 0 | 1 | 0 | 180004308 | 3 | L | 4900030519 | 2024 |  | 5000017858 | 2024 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255353 | PACKING;PF,1.852" ID,GE J221P134 |  | 0080 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 90000283_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000283 |  | 5 |  | 11 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 |  | 30 | 5300003974 | 110 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-07 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0090 | 0170 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10297418 | PACKING,PF;COMP,GE M832481904 | 1 | EA | 6 | 1 | 3 | 1 | EA | UserCommentLink | Supply for Order 200083506, Item 17 cannot be changed 90000283 item 70 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 140 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004308 | 90000283 | 05 | Preparation | 0000121037 | 17 | 0 | EA | 102000000000281 | 102000000000256 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017858_2024 | 0 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 1 | 4900030519_2024_0013 |  | 2024-02-12 | 2024-05-10 | 2200670051 | 5000017858_2024_0007 | 0 | 2 | 0 | 1 | 0 | 180004308 | 3 | L | 4900030519 | 2024 |  | 5000017858 | 2024 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297418 | PACKING,PF;COMP,GE M832481904 |  | 0090 | HYDRAULIC OIL FILTER REPLACEMENT | INT | HYDRAULIC OIL FILTER REPLACEMENT | 5 |  | 90000283_0070 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000283 |  | 5 |  | 17 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 |  | 30 | 5300003974 | 140 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-07 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0080 | 0100 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10307721 | SEAL,GEN,GAS;NP 9032M84P02 | 1 | EA | 0 | 1 | 3 | 1 | EA | UserCommentLink | Supply for Order 200083506, Item 9 cannot be changed 90000283 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004308 | 90000283 | 05 | Preparation | 0000121037 | 9 | 0 | EA | 102000000000281 | 102000000000252 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017858_2024 | 0 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 1 | 4900030519_2024_0003 |  | 2024-02-12 | 2024-05-10 | 2200670051 | 5000017858_2024_0002 | 0 | 2 | 0 | 1 | 0 | 180004308 | 3 | L | 4900030519 | 2024 |  | 5000017858 | 2024 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307721 | SEAL,GEN,GAS;NP 9032M84P02 |  | 0080 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 90000283_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000283 |  | 5 |  | 9 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 | 30 | 30 | 5300003974 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-07 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0070 | 0080 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10255363 | PACKING,GBX,TFR;GE J221P905 | 3 | EA | 19 | 7 | 9 | 3 | EA | UserCommentLink | Supply for Order 200083506, Item 8 cannot be changed 90000283 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004308 | 90000283 | 05 | Preparation | 0000121037 | 8 | 0 | EA | 102000000000281 | 102000000000256 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 3 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017858_2024 | 0 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 3 | 4900030519_2024_0001 |  | 2024-02-12 | 2024-05-10 | 2200670051 | 5000017858_2024_0001 | 0 | 2 | 0 | 3 | 0 | 180004308 | 3 | L | 4900030519 | 2024 |  | 5000017858 | 2024 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255363 | PACKING,GBX,TFR;GE J221P905 |  | 0070 | CHIP DETECTOR CHECK | INT | CHIP DETECTOR CHECK | 5 |  | 90000283_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000283 |  | 5 |  | 8 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 |  | 30 | 5300003974 | 80 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-05-07 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-05 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0030 | 0060 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10297294 | BUSH,FLG,COMP;GE L44861P01 | 12 | EA | 473 | 12 | 228 | 12 | EA | UserCommentLink | Supply for Order 200083506, Item 6 cannot be changed 90000281 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004313 | 90000281 | 05 | Preparation | 0000121037 | 6 | 0 | EA | 102000000000381 | 102000000000288 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 12 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017890_2024 | 0 | 0 | 0 |  | 2024-05-06 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 12 | 4900030476_2024_0007 |  | 2024-02-12 | 2024-05-08 | 2200670051 | 5000017890_2024_0004 | 0 | 2 | 0 | 12 | 0 | 180004313 | 3 | L | 4900030476 | 2024 |  | 5000017890 | 2024 |  |  | 2024-05-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297294 | BUSH,FLG,COMP;GE L44861P01 |  | 0030 | VSV BUSHES STAGES 3-5 SPLITLINE | INT | VSV BUSHES STAGES 3-5 SPLITLINE | 5 |  | 90000281_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000281 |  | 5 |  | 6 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 | 30 | 30 | 5300003974 | 60 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-05-05 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-05 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0030 | 0050 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10297295 | BUSH,FLG,COMP;GE L44861P07 | 12 | EA | 84 | 12 | 152 | 12 | EA | 24SDGT8-SW3R02A01B | Supply for Order 200083506, Item 5 cannot be changed 90000281 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004313 | 90000281 | 05 | Preparation | 0000121037 | 5 | 0 | EA | 102000000000381 | 102000000000370 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 12 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017890_2024 | 0 | 0 | 0 |  | 2024-05-06 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 12 | 4900030476_2024_0005 |  | 2024-02-12 | 2024-05-08 | 2200670051 | 5000017890_2024_0003 | 0 | 2 | 0 | 12 | 0 | 180004313 | 3 | L | 4900030476 | 2024 |  | 5000017890 | 2024 |  |  | 2024-05-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297295 | BUSH,FLG,COMP;GE L44861P07 |  | 0030 | VSV BUSHES STAGES 3-5 SPLITLINE | INT | VSV BUSHES STAGES 3-5 SPLITLINE | 5 |  | 90000281_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000281 |  | 5 |  | 5 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 | 30 | 30 | 5300003974 | 50 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-05-05 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-11 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0200 | 0280 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10255346 | GASKET;GE J219P04 | 1 | EA | 32 | 1 | 3 | 1 | EA | 31.01 - 36 SOH @ AA02 | Supply for Order 200083506, Item 28 cannot be changed 90000286 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 250 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004315 | 90000286 | 05 | Preparation | 0000121037 | 28 | 0 | EA | 102000000000381 | 102000000000371 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017900_2024 | 0 | 0 | 0 |  | 2024-05-12 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 1 | 4900030466_2024_0005 |  | 2024-02-12 | 2024-05-14 | 2200670051 | 5000017900_2024_0003 | 0 | 2 | 0 | 1 | 0 | 180004315 | 3 | L | 4900030466 | 2024 |  | 5000017900 | 2024 |  |  | 2024-05-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255346 | GASKET;GE J219P04 |  | 0200 | STROKE CHECK VARIABLE BYPASS VALVE | INT | STROKE CHECK VARIABLE BYPASS VALVE | 5 |  | 90000286_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000286 |  | 5 |  | 28 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 |  | 30 | 5300003974 | 250 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-11 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-07 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0080 | 0150 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10255158 | O-RING;32.92MM ID X 3.53MM DIA,FKM | 2 | EA | 5 | 2 | 6 | 2 | EA | 31.01 - 9 SOH @ AA02 | Supply for Order 200083506, Item 14 cannot be changed 90000283 item 60 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 130 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004308 | 90000283 | 05 | Preparation | 0000121037 | 14 | 0 | EA | 102000000000281 | 102000000000252 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017858_2024 | 0 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 2 | 4900030519_2024_0011 |  | 2024-02-12 | 2024-05-10 | 2200670051 | 5000017858_2024_0006 | 0 | 2 | 0 | 2 | 0 | 180004308 | 3 | L | 4900030519 | 2024 |  | 5000017858 | 2024 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255158 | O-RING;32.92MM ID X 3.53MM DIA,FKM |  | 0080 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 90000283_0060 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000283 |  | 5 |  | 14 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 | 30 | 30 | 5300003974 | 130 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-05-07 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-11 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0220 | 0300 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10480513 | WIRE,RET;NP 1697M73P02 | 1 | EA | 6 | 1 | 3 | 1 | EA | UserCommentLink | Supply for Order 200083506, Item 30 cannot be changed 90000286 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 260 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004315 | 90000286 | 05 | Preparation | 0000121037 | 30 | 0 | EA | 102000000000381 | 102000000000380 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017900_2024 | 0 | 0 | 0 |  | 2024-05-12 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 1 | 4900030466_2024_0007 |  | 2024-02-12 | 2024-05-14 | 2200670051 | 5000017900_2024_0004 | 0 | 2 | 0 | 1 | 0 | 180004315 | 3 | L | 4900030466 | 2024 |  | 5000017900 | 2024 |  |  | 2024-05-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10480513 | WIRE,RET;NP 1697M73P02 |  | 0220 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 5 |  | 90000286_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000286 |  | 5 |  | 30 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 | 30 | 30 | 5300003974 | 260 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-11 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-11 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0220 | 0310 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10316866 | GASKET;PIGNONE,L61917P01,TRF DRAIN | 1 | EA | 0 | 1 | 3 | 1 | EA | UserCommentLink | Supply for Order 200083506, Item 31 cannot be changed 90000286 item 50 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 270 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004315 | 90000286 | 05 | Preparation | 0000121037 | 31 | 0 | EA | 102000000000381 | 102000000000376 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017900_2024 | 0 | 0 | 0 |  | 2024-05-12 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 1 | 4900030466_2024_0009 |  | 2024-02-12 | 2024-05-14 | 2200670051 | 5000017900_2024_0005 | 0 | 2 | 0 | 1 | 0 | 180004315 | 3 | L | 4900030466 | 2024 |  | 5000017900 | 2024 |  |  | 2024-05-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10316866 | GASKET;PIGNONE,L61917P01,TRF DRAIN |  | 0220 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 5 |  | 90000286_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000286 |  | 5 |  | 31 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 | 30 | 30 | 5300003974 | 270 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-11 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-11 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0220 | 0320 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10258644 | GASKET;GE 9608M08G48 | 1 | EA | 22 | 1 | 3 | 1 | EA | UserCommentLink | Supply for Order 200083506, Item 32 cannot be changed 90000286 item 60 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 280 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004315 | 90000286 | 05 | Preparation | 0000121037 | 32 | 0 | EA | 102000000000381 | 102000000000374 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017900_2024 | 0 | 0 | 0 |  | 2024-05-12 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 1 | 4900030466_2024_0011 |  | 2024-02-12 | 2024-05-14 | 2200670051 | 5000017900_2024_0006 | 0 | 2 | 0 | 1 | 0 | 180004315 | 3 | L | 4900030466 | 2024 |  | 5000017900 | 2024 |  |  | 2024-05-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258644 | GASKET;GE 9608M08G48 |  | 0220 | D/E SUMP INTERFACE INSP/CLEAN | INT | D/E SUMP INTERFACE INSP/CLEAN | 5 |  | 90000286_0060 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000286 |  | 5 |  | 32 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 |  | 30 | 5300003974 | 280 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-11 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-11 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0200 | 0270 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10297501 | BOLT,RDHD;GE 9107M21P06 | 12 | EA | 24 | 12 | 36 | 12 | EA | UserCommentLink | Supply for Order 200083506, Item 27 cannot be changed 90000286 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 240 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004315 | 90000286 | 05 | Preparation | 0000121037 | 27 | 0 | EA | 102000000000381 | 102000000000380 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 12 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017900_2024 | 0 | 0 | 0 |  | 2024-05-12 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 12 | 4900030466_2024_0003 |  | 2024-02-12 | 2024-05-14 | 2200670051 | 5000017900_2024_0002 | 0 | 2 | 0 | 12 | 0 | 180004315 | 3 | L | 4900030466 | 2024 |  | 5000017900 | 2024 |  |  | 2024-05-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297501 | BOLT,RDHD;GE 9107M21P06 |  | 0200 | STROKE CHECK VARIABLE BYPASS VALVE | INT | STROKE CHECK VARIABLE BYPASS VALVE | 5 |  | 90000286_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000286 |  | 5 |  | 27 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 |  | 30 | 5300003974 | 240 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-05-11 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-07 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0080 | 0130 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10255250 | GASKET;GE 9107M23P02 | 1 | EA | 8 | 1 | 3 | 1 | EA | 31.01 - 12 SOH @ AA02 | Supply for Order 200083506, Item 12 cannot be changed 90000283 item 50 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 120 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004308 | 90000283 | 05 | Preparation | 0000121037 | 12 | 0 | EA | 102000000000177 |  | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017858_2024 | 0 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 1 | 4900030519_2024_0009 |  | 2024-02-12 | 2024-05-10 | 2200670051 | 5000017858_2024_0005 | 0 | 2 | 0 | 1 | 0 | 180004308 | 3 | L | 4900030519 | 2024 |  | 5000017858 | 2024 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255250 | GASKET;GE 9107M23P02 |  | 0080 | HYD STARTER, CLUTCH & CARBON SEAL INSP | INT | HYD STARTER, CLUTCH & CARBON SEAL INSP | 5 |  | 90000283_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000283 |  | 5 |  | 12 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 |  | 30 | 5300003974 | 120 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-11 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0200 | 0260 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10307833 | GASKET,SW;GE J219P03 | 1 | EA | 38 | 1 | 4 | 1 | EA | UserCommentLink | Supply for Order 200083506, Item 26 cannot be changed 90000286 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 230 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004315 | 90000286 | 05 | Preparation | 0000121037 | 26 | 0 | EA | 102000000000381 | 102000000000289 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017900_2024 | 0 | 0 | 0 |  | 2024-05-12 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 1 | 4900030466_2024_0001 |  | 2024-02-12 | 2024-05-14 | 2200670051 | 5000017900_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004315 | 3 | L | 4900030466 | 2024 |  | 5000017900 | 2024 |  |  | 2024-05-11 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307833 | GASKET,SW;GE J219P03 |  | 0200 | STROKE CHECK VARIABLE BYPASS VALVE | INT | STROKE CHECK VARIABLE BYPASS VALVE | 5 |  | 90000286_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000286 |  | 5 |  | 26 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 |  | 30 | 5300003974 | 230 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-11 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-06 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0050 | 0070 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10258555 | WASHER,PLN;GE 133A1624P37 | 1 | EA | 7 | 0 | 3 | 1 | EA | 12.03- 5 SOH @ AA02 | Supply for Order 200083506, Item 7 cannot be changed 90000282 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004296 | 90000282 | 05 | Preparation | 0000121037 | 7 | 0 | EA | 102000000000381 | 102000000000372 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017848_2024 | 0 | 0 | 0 |  | 2024-05-07 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 1 | 4900030473_2024_0001 |  | 2024-02-12 | 2024-05-09 | 2200670051 | 5000017848_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004296 | 3 | L | 4900030473 | 2024 |  | 5000017848 | 2024 |  |  | 2024-05-06 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258555 | WASHER,PLN;GE 133A1624P37 |  | 0050 | IGNITER PLUG INSPECTION | INT | IGNITER PLUG INSPECTION | 5 |  | 90000282_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000282 |  | 5 |  | 7 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 |  | 30 | 5300003974 | 70 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-06 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-05 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0030 | 0030 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10297297 | WASHER,PLN;GE L44862P03 | 12 | EA | 44 | 12 | 152 | 12 | EA | 24SDGT8-SW3R02A01B | Supply for Order 200083506, Item 3 cannot be changed 90000281 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004313 | 90000281 | 05 | Preparation | 0000121037 | 3 | 0 | EA | 102000000000381 | 102000000000378 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 12 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017890_2024 | 0 | 0 | 0 |  | 2024-05-06 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 12 | 4900030476_2024_0001 |  | 2024-02-12 | 2024-05-08 |  | 5000017890_2024_0001 | 0 | 2 | 0 | 12 | 0 | 180004313 | 3 | L | 4900030476 | 2024 |  | 5000017890 | 2024 |  |  | 2024-05-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297297 | WASHER,PLN;GE L44862P03 |  | 0030 | VSV BUSHES STAGES 3-5 SPLITLINE | INT | VSV BUSHES STAGES 3-5 SPLITLINE | 5 |  | 90000281_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000281 |  | 5 |  | 3 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 | 30 | 30 | 5300003974 | 30 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-05-05 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-09 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0140 | 0240 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10255264 | GASKET;GE 9379M93P01 | 8 | EA | 17 | 8 | 27 | 8 | EA | UserCommentLink | Supply for Order 200083506, Item 24 cannot be changed 90000285 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 210 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004314 | 90000285 | 05 | Preparation | 0000121037 | 24 | 0 | EA | 102000000000381 | 102000000000375 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 8 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017883_2024 | 0 | 0 | 0 |  | 2024-05-10 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 8 | 4900030530_2024_0001 |  | 2024-02-12 | 2024-05-12 | 2200670051 | 5000017883_2024_0001 | 0 | 2 | 0 | 8 | 0 | 180004314 | 3 | L | 4900030530 | 2024 |  | 5000017883 | 2024 |  |  | 2024-05-09 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255264 | GASKET;GE 9379M93P01 |  | 0140 | T48 INLET PROBE INSPECTION MECH ASSIST | INT | T48 INLET PROBE INSPECTION MECH ASSIST | 5 |  | 90000285_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000285 |  | 5 |  | 24 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 |  | 30 | 5300003974 | 210 |  |  | 0 | 8 | EA | 2001 | AA02 | 2024-05-09 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-05 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0030 | 0040 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10297296 | WASHER,PLN;GE L44862P02 | 12 | EA | 146 | 12 | 228 | 12 | EA | 24SDGT8-SW3R02A01B | Supply for Order 200083506, Item 4 cannot be changed 90000281 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004313 | 90000281 | 05 | Preparation | 0000121037 | 4 | 0 | EA | 102000000000381 | 102000000000377 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 12 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017890_2024 | 0 | 0 | 0 |  | 2024-05-06 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 12 | 4900030476_2024_0003 |  | 2024-02-12 | 2024-05-08 | 2200670051 | 5000017890_2024_0002 | 0 | 2 | 0 | 12 | 0 | 180004313 | 3 | L | 4900030476 | 2024 |  | 5000017890 | 2024 |  |  | 2024-05-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10297296 | WASHER,PLN;GE L44862P02 |  | 0030 | VSV BUSHES STAGES 3-5 SPLITLINE | INT | VSV BUSHES STAGES 3-5 SPLITLINE | 5 |  | 90000281_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000281 |  | 5 |  | 4 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 | 30 | 30 | 5300003974 | 40 |  |  | 0 | 12 | EA | 2001 | AA02 | 2024-05-05 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-07 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0090 | 0200 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10255281 | ELEMENT,FLT;5" LG,GE ACB244F2440Y1 | 1 | EA | 3 | 1 | 3 | 1 | EA | UserCommentLink | Supply for Order 200083506, Item 20 cannot be changed 90000283 item 100 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 170 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004308 | 90000283 | 05 | Preparation | 0000121037 | 20 | 0 | EA | 102000000000281 | 102000000000257 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017858_2024 | 0 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 1 | 4900030519_2024_0019 |  | 2024-02-12 | 2024-05-10 | 2200670051 | 5000017858_2024_0010 | 0 | 2 | 0 | 1 | 0 | 180004308 | 3 | L | 4900030519 | 2024 |  | 5000017858 | 2024 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255281 | ELEMENT,FLT;5" LG,GE ACB244F2440Y1 |  | 0090 | HYDRAULIC OIL FILTER REPLACEMENT | INT | HYDRAULIC OIL FILTER REPLACEMENT | 5 |  | 90000283_0100 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000283 |  | 5 |  | 20 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 |  | 30 | 5300003974 | 170 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-08 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0120 | 0230 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10258557 | GASKET;GE 1538M42P01 | 2 | EA | 27 | 2 | 6 | 2 | EA | UserCommentLink | Supply for Order 200083506, Item 23 cannot be changed 9000021 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 200 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004317 | 9000021 | 05 | Preparation | 0000121037 | 23 | 0 | EA | 102000000000381 | 102000000000373 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017866_2024 | 0 | 0 | 0 |  | 2024-05-09 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 2 | 4900030531_2024_0003 |  | 2024-02-12 | 2024-05-11 | 2200670051 | 5000017866_2024_0002 | 0 | 2 | 0 | 2 | 0 | 180004317 | 3 | L | 4900030531 | 2024 |  | 5000017866 | 2024 |  |  | 2024-05-08 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258557 | GASKET;GE 1538M42P01 |  | 0120 | P48 INLET PROBE INSPECTION MECH ASSIST | INT | P48 INLET PROBE INSPECTION MECH ASSIST | 5 |  | 9000021_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000284 |  | 5 |  | 23 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 |  | 30 | 5300003974 | 200 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-05-08 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-08 | 2024-05-15 | 2024-05-17 | ROTAT | 200083506 | 0100 | 0220 | 200083506 | 1Y P03 GT4008 TURB MECH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 10 | No Issue identified | 10307736 | RING,PST;GE 1473M46P04 | 1 | EA | 5 | 1 | 3 | 1 | EA | UserCommentLink | Supply for Order 200083506, Item 22 cannot be changed 9000021 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003974 | 190 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004317 | 9000021 | 05 | Preparation | 0000121037 | 22 | 0 | EA | 102000000000381 | 102000000000379 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017866_2024 | 0 | 0 | 0 |  | 2024-05-09 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-06-30 | 1 | 4900030531_2024_0001 |  | 2024-02-12 | 2024-05-11 | 2200670051 | 5000017866_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004317 | 3 | L | 4900030531 | 2024 |  | 5000017866 | 2024 |  |  | 2024-05-08 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10307736 | RING,PST;GE 1473M46P04 |  | 0100 | PCC FORWARD MOUNT BOLT WEAR | INT | PCC FORWARD MOUNT BOLT WEAR | 5 |  | 9000021_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000284 |  | 5 |  | 22 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000120419 | S002 | 30 | 30 | 5300003974 | 190 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-08 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121037 | 0 |  | 3 |  |  | RC00025003 | 2024-05-17 | 2024-05-15 | 2024-05-15 | Goods movement posted/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-05-09 | 2024-05-19 | 2024-05-19 | ROTAT | 200083838 | 0280 | 0030 | 200083838 | 1Y GT4009 TURB OFF-ENGINE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | No Issue identified | 10018655 | ELEMENT,FLT;OIL,PALL HC8400FRS16Z | 2 | EA | 6 | 2 | 8 | 2 | EA | 28.02 - 24SDGT9-SW3R02B01A | Supply for Order 200083838, Item 1 cannot be changed 9000034 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004043 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004332 | 9000034 | 05 | Preparation | 0000121806 | 1 | 0 | EA | 102000000000205 |  | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017962_2024 | 0 | 0 | 0 |  | 2024-05-10 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-04-22 | 2 | 4900030508_2024_0001 |  | 2024-02-12 | 2024-05-12 | GT9 S1A/B | 5000017962_2024_0001 | 0 | 2 | 0 | 2 | 0 | 180004332 | 3 | L | 4900030508 | 2024 |  | 5000017962 | 2024 |  |  | 2024-05-09 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018655 | ELEMENT,FLT;OIL,PALL HC8400FRS16Z |  | 0280 | REPLACE MINERAL LUBE OIL FILTERS | INT | REPLACE MINERAL LUBE OIL FILTERS | 5 |  | 9000034_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000298 |  | 20 |  | 1 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000121198 | S002 | 30 | 30 | 5300004043 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-05-09 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121806 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-04 | 2024-05-15 | 2024-05-15 | ROTAT | 200083886 | 0200 | 0010 | 200083886 | 1Y GT4008 TURB OFF-ENGINE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | No Issue identified | 10347550 | O-RING;24.99X3.53MM,FKM,NP KHA024903501 | 1 | EA | 1 | 0 | 1 | 1 | EA | 31.01 - 2 SOH @ AA02 | Supply for Order 200083886, Item 1 cannot be changed 90000287 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004051 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004298 | 90000287 | 05 | Preparation | 0000121836 | 1 | 0 | EA | 102000000000283 | 102000000000258 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017882_2024 | 0 | 0 | 0 |  | 2024-05-05 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-05-16 | 1 | 4900030497_2024_0001 |  | 2024-02-12 | 2024-05-07 | GT4008 | 5000017882_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004298 | 3 | L | 4900030497 | 2024 |  | 5000017882 | 2024 |  |  | 2024-05-04 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10347550 | O-RING;24.99X3.53MM,FKM,NP KHA024903501 |  | 0200 | HYDRAULIC STARTER CLUTCH MECH ASSIST | INT | HYDRAULIC STARTER CLUTCH MECH ASSIST | 5 |  | 90000287_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000287 |  | 20 |  | 1 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000121239 | S002 |  | 30 | 5300004051 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-04 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121836 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-05-05 | 2024-05-15 | 2024-05-15 | ROTAT | 200083886 | 0280 | 0020 | 200083886 | 1Y GT4008 TURB OFF-ENGINE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | No Issue identified | 10060889 | GASKET;SWCI,200MM,CL150,316L/GR/316 | 2 | EA | 25 | 0 | 11 | 2 | EA | 31.01 - 47 SOH @ AA02 | Supply for Order 200083886, Item 2 cannot be changed 90000288 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004051 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004312 | 90000288 | 05 | Preparation | 0000121836 | 2 | 0 | EA | 102000000000283 | 102000000000259 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017809_2024 | 0 | 0 | 0 |  | 2024-05-06 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-05-16 | 2 | 4900030475_2024_0001 |  | 2024-02-12 | 2024-05-08 | GT4008 | 5000017809_2024_0001 | 0 | 2 | 0 | 2 | 0 | 180004312 | 3 | L | 4900030475 | 2024 |  | 5000017809 | 2024 |  |  | 2024-05-05 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060889 | GASKET;SWCI,200MM,CL150,316L/GR/316 |  | 0280 | REPLACE MINERAL LUBE OIL FILTERS | INT | REPLACE MINERAL LUBE OIL FILTERS | 5 |  | 90000288_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000288 |  | 20 |  | 2 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000121239 | S002 | 30 | 30 | 5300004051 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-05-05 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121836 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 200083886 | 0280 | 0030 | 200083886 | 1Y GT4008 TURB OFF-ENGINE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | No Issue identified | 10018655 | ELEMENT,FLT;OIL,PALL HC8400FRS16Z | 2 | EA | 6 | 2 | 8 | 2 | EA | 28.02 - 24SDGT8-SW3R02A01B | Supply for Order 200083886, Item 3 cannot be changed 90000783 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004051 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004307 | 90000783 | 05 | Preparation | 0000121836 | 3 | 0 | EA | 102000000001188 |  | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017876_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-05-16 | 2 | 4900030465_2024_0001 |  | 2024-02-12 | 2024-05-03 | GT4008 | 5000017876_2024_0001 | 0 | 2 | 0 | 2 | 0 | 180004307 | 3 | L | 4900030465 | 2024 |  | 5000017876 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018655 | ELEMENT,FLT;OIL,PALL HC8400FRS16Z |  | 0280 | REPLACE MINERAL LUBE OIL FILTERS | INT | REPLACE MINERAL LUBE OIL FILTERS | 5 |  | 90000783_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000783 |  | 20 |  | 3 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000121239 | S002 | 30 | 30 | 5300004051 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121836 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-05-09 | 2024-05-03 | 2024-05-03 | ROTAT | 200083947 | 0280 | 0030 | 200083947 | 1Y GT4007 TURB OFF-ENGINE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | No Issue identified | 10018655 | ELEMENT,FLT;OIL,PALL HC8400FRS16Z | 2 | EA | 6 | 2 | 8 | 2 | EA | 28.02 - 24SDGT7-SW3R02A01A | Supply for Order 200083947, Item 1 cannot be changed 9000310 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004065 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004056 | 9000310 | 05 | Preparation | 0000121876 | 1 | 0 | EA | 102000000000309 |  | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015668_2024 | 9 | 0 | 0 |  | 2024-05-10 | AA53 | 2024-05-03 |  |  | 2024-05-12 |  |  | 100000002114 | 1020 | 2024-04-28 | 2 | 4900030134_2024_0001 |  | 2024-02-09 | 2024-05-12 |  | 5000015668_2024_0001 | 0 | 2 | 0 | 2 | 0 | 180004056 | 3 | L | 4900030134 | 2024 |  | 5000015668 | 2024 |  |  | 2024-05-09 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018655 | ELEMENT,FLT;OIL,PALL HC8400FRS16Z |  | 0280 | REPLACE MINERAL LUBE OIL FILTERS | INT | REPLACE MINERAL LUBE OIL FILTERS | 5 |  | 9000310_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000255 |  | 20 |  | 1 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000121326 | S002 | 30 | 30 | 5300004065 | 10 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-05-09 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121876 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-05-09 | 2024-05-03 | 2024-05-03 | ROTAT | 200083947 | 0280 | 0040 | 200083947 | 1Y GT4007 TURB OFF-ENGINE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | No Issue identified | 10349278 | GASKET;C4430,KLINGER 864432121 | 2 | KIT | 2 | 0 | 0 | 2 | KIT | 13.03- Materials workpacked @ AA02 | Supply for Order 200083947, Item 2 cannot be changed 90000255 item 20 already exists | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004065 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90000255 | 05 | Preparation | 0000121876 | 2 | 0 | KIT | 101000000022681 |  | 101000000022682 | 01-Road | 20000327 |  | 3-In Transit |  | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 2 |  | 2024-03-07 | Y | 1001 | 2024-01-02 | ODST-0090000255_0020 | 9 | 0 | 0 |  | 2024-05-10 | AA53 | 2024-05-03 |  |  | 2024-05-12 |  |  |  |  | 2024-04-28 | 0 |  |  | 2024-05-09 | 2024-05-12 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-09 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10349278 | GASKET;C4430,KLINGER 864432121 |  | 0280 | REPLACE MINERAL LUBE OIL FILTERS | INT | REPLACE MINERAL LUBE OIL FILTERS | 5 |  | 90000255_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000255 |  | 20 |  | 2 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000121326 | S002 | 30 | 30 | 5300004065 | 20 |  |  | 0 | 2 | KIT | 2001 | AA02 | 2024-05-09 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121876 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-04 | 2024-05-03 | 2024-05-03 | 2024-05-04 | ROTAT | 200083948 | 0130 | 0030 | 200083948 | 2Y GT4007 TURB OFF-ENGINE | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | No Issue identified | 10255359 | FILTER,WASHING;ROCHEM FTSSWAG | 1 | EA | 4 | 0 | 1 | 1 | EA | UserCommentLink | Supply for Order 200083948, Item 1 cannot be changed 90000256 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004066 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004054 | 90000256 | 05 | Preparation | 0000121877 | 1 | 0 | EA | 102000000000358 | 102000000000412 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015637_2024 | 2 | 0 | 0 |  | 2024-05-04 | AA53 | 2024-05-04 |  |  | 2024-05-06 |  |  | 100000002114 | 1020 | 2024-04-25 | 1 | 4900030153_2024_0001 |  | 2024-02-09 | 2024-05-06 | GT4007 | 5000015637_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004054 | 3 | L | 4900030153 | 2024 |  | 5000015637 | 2024 |  |  | 2024-05-03 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255359 | FILTER,WASHING;ROCHEM FTSSWAG |  | 0130 | REPLACE OFFLINE W/W FILTER | INT | REPLACE OFFLINE W/W FILTER | 5 |  | 90000256_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000256 |  | 20 |  | 1 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000121327 | S002 |  | 30 | 5300004066 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-03 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121877 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Material committed/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-02 | 2024-05-03 | ROTAT | 200083949 | 0020 | 0010 | 200083949 | 6Y REPLACE GEOMETERY CDP BLEED VALVE (1) | AA53.407XV575 | VALVE,FLOW CONT HPC BLEED |  | 20 | No Issue identified | 10253545 | VALVE,BLEED;GE L47329PO5 | 1 | EA | 4 | 0 | 1 | 1 | EA | 31.01 - 5 SOH @ AA02, 3 Scheduled for Delivery to AA53 | Supply for Order 200083949, Item 1 cannot be changed 90000257 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004067 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  | NEW |  | 180004063 | 90000257 | 05 | Preparation | 0000121878 | 1 | 0 | EA | 102000000000417 |  | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015677_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-04-22 | 1 | 4900030170_2024_0001 |  | 2024-02-09 | 2024-05-03 | 407XV575 | 5000015677_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004063 | 3 | L | 4900030170 | 2024 |  | 5000015677 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10253545 | VALVE,BLEED;GE L47329PO5 |  | 0020 | Remove & Replace Valve | INT | Remove & Replace Valve | 5 |  | 90000257_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000257 |  | 20 |  | 1 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000121328 | S002 | 30 | 30 | 5300004067 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121878 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-02 | 2024-05-02 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-02 | 2024-05-03 | ROTAT | 200083949 | 0020 | 0020 | 200083949 | 6Y REPLACE GEOMETERY CDP BLEED VALVE (1) | AA53.407XV575 | VALVE,FLOW CONT HPC BLEED | AA01 | 20 | No Issue identified | 10258551 | RING,BLEED;AIR,GE 0946 | 2 | EA | 8 | 0 | 3 | 2 | EA | UserCommentLink | Supply for Order 200083949, Item 2 cannot be changed 90000257 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004067 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004063 | 90000257 | 05 | Preparation | 0000121878 | 2 | 0 | EA | 102000000001073 | 102000000001034 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015677_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-04-22 | 2 | 4900030170_2024_0003 |  | 2024-02-09 | 2024-05-03 | 407XV575 | 5000015677_2024_0002 | 0 | 2 | 0 | 2 | 0 | 180004063 | 3 | L | 4900030170 | 2024 |  | 5000015677 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258551 | RING,BLEED;AIR,GE 0946 |  | 0020 | Remove & Replace Valve | INT | Remove & Replace Valve | 5 |  | 90000257_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000257 |  | 20 |  | 2 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000121328 | S002 |  | 30 | 5300004067 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121878 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-02 | 2024-05-02 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-02 | 2024-05-03 | ROTAT | 200083950 | 0020 | 0010 | 200083950 | 6Y REPLACE GEOMETERY 8TH STAGE VALVE (1) | AA53.407XV576 | VALVE,FLOW CONT 8TH STAGE BLEED GT4007 |  | 20 | No Issue identified | 30000462 | VALVE,LM6000,6.0",8 TH STAGE BLEED AIR | 1 | EA | 1 | 1 | 1 | 1 | EA | On pallet in protective case with material 10255625 | Supply for Order 200083950, Item 1 cannot be changed 90000258 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004069 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004055 | 90000258 | 05 | Preparation | 0000121879 | 1 | 0 | EA |  |  | 102000000001121 | 01-Road | 1000000427 |  | 5-Completed |  | WorkPackLink | R10P07WHFLR | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015686_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-04-22 | 1 | 4900030160_2024_0001 |  | 2024-02-09 | 2024-05-03 | 407XV576 | 5000015686_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004055 | 3 | L | 4900030160 | 2024 |  | 5000015686 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 30000462 | VALVE,LM6000,6.0",8 TH STAGE BLEED AIR |  | 0020 | Remove & Replace Valve | INT | Remove & Replace Valve | 5 |  | 90000258_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000258 |  | 20 |  | 1 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000121329 | S002 | 30 | 30 | 5300004069 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121879 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-02 | 2024-05-02 | Object created/Date set by external system/Printed/Material committed/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-02 | 2024-05-03 | ROTAT | 200083950 | 0020 | 0020 | 200083950 | 6Y REPLACE GEOMETERY 8TH STAGE VALVE (1) | AA53.407XV576 | VALVE,FLOW CONT 8TH STAGE BLEED GT4007 | AA01 | 20 | No Issue identified | 10255178 | RING,BLEED;AIR,GE 2873600 | 2 | EA | 4 | 2 | 2 | 2 | EA | 31.01 - 8 SOH @ AA02 | Supply for Order 200083950, Item 2 cannot be changed 90000258 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300004069 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004055 | 90000258 | 05 | Preparation | 0000121879 | 2 | 0 | EA | 102000000001073 | 102000000001035 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015681_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-04-22 | 2 | 4900030160_2024_0003 |  | 2024-02-09 | 2024-05-03 | 407XV576 | 5000015681_2024_0001 | 0 | 2 | 0 | 2 | 0 | 180004055 | 3 | L | 4900030160 | 2024 |  | 5000015681 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255178 | RING,BLEED;AIR,GE 2873600 |  | 0020 | Remove & Replace Valve | INT | Remove & Replace Valve | 5 |  | 90000258_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000258 |  | 20 |  | 2 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000121329 | S002 | 30 | 30 | 5300004069 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 121879 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-02 | 2024-05-02 | Object created/Date set by external system/Printed/Material committed/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 200085913 | 0040 | 0060 | 200085913 | 1Y Waterwash Maintenance GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | No Issue identified | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 3 | EA | 6 | 3 | 8 | 3 | EA | UserCommentLink | Supply for Order 200085913, Item 3 cannot be changed 9000308 item 30 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003547 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004066 | 9000308 | 05 | Preparation | 0000124191 | 3 | 0 | EA |  |  | 102000000001152 | 01-Road | 1000000427 |  | 5-Completed |  | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 3 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015685 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-03-17 | 3 | 4900030154_2024_0005 |  | 2024-02-09 | 2024-05-03 | GT4007 | 5000015685_2024_0001 | 0 | 2 | 0 | 3 | 0 | 180004066 | 3 | L | 4900030154 | 2024 |  | 5000015685 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 9000308_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000132 |  | 20 |  | 3 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000123582 | S002 | 30 | 30 | 5300003547 | 30 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124191 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 200085913 | 0040 | 0050 | 200085913 | 1Y Waterwash Maintenance GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | No Issue identified | 10255397 | GASKET;GE L43073P01 | 2 | EA | 23 | 4 | 4 | 2 | EA | UserCommentLink | Supply for Order 200085913, Item 2 cannot be changed 9000308 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003547 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004066 | 9000308 | 05 | Preparation | 0000124191 | 2 | 0 | EA | 102000000001073 | 102000000001036 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015638_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-03-17 | 2 | 4900030154_2024_0003 |  | 2024-02-09 | 2024-05-03 | GT4007 | 5000015638_2024_0002 | 0 | 2 | 0 | 2 | 0 | 180004066 | 3 | L | 4900030154 | 2024 |  | 5000015638 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255397 | GASKET;GE L43073P01 |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 9000308_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000132 |  | 20 |  | 2 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000123582 | S002 |  | 30 | 5300003547 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124191 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 200085913 | 0040 | 0040 | 200085913 | 1Y Waterwash Maintenance GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 |  | 20 | No Issue identified | 10256255 | SOLVENT;ROCHEM FYREWASH F1,25L | 1 | DR | 3 | 1 | 3 | 1 | DR | UserCommentLink | Supply for Order 200085913, Item 1 cannot be changed 9000308 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003547 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180004066 | 9000308 | 05 | Preparation | 0000124191 | 1 | 0 | DR | 102000000001136 |  | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015638_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-03-17 | 1 | 4900030154_2024_0001 |  | 2024-02-09 | 2024-05-03 | GT4007 | 5000015638_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004066 | 3 | L | 4900030154 | 2024 |  | 5000015638 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10256255 | SOLVENT;ROCHEM FYREWASH F1,25L |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 9000308_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000132 |  | 20 |  | 1 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000123582 | S002 | 30 | 30 | 5300003547 | 10 |  |  | 0 | 1 | DR | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124191 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 200085913 | 0040 | 0070 | 200085913 | 1Y Waterwash Maintenance GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | No Issue identified | 10289918 | CABLE,SAF;GE C1022450 | 1 | KIT | 25 | 1 | 3 | 1 | KIT | UserCommentLink | Supply for Order 200085913, Item 4 cannot be changed 9000308 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003547 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  | 180004066 | 9000308 | 05 | Preparation | 0000124191 | 4 | 0 | KIT | 102000000001073 | 102000000001037 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015638_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-03-17 | 1 | 4900030154_2024_0007 |  | 2024-02-09 | 2024-05-03 | GT4007 | 5000015638_2024_0003 | 0 | 2 | 0 | 1 | 0 | 180004066 | 3 | L | 4900030154 | 2024 |  | 5000015638 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10289918 | CABLE,SAF;GE C1022450 |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 9000308_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000132 |  | 20 |  | 4 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000123582 | S002 |  | 30 | 5300003547 | 40 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124191 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | ROTAT | 200085913 | 0040 | 0080 | 200085913 | 1Y Waterwash Maintenance GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 20 | No Issue identified | 10420917 | ELEMENT,FLT;CAMFIL FARR HF903566 | 1 | EA | 4 | 2 | 2 | 1 | EA | UserCommentLink | Supply for Order 200085913, Item 5 cannot be changed 9000308 item 50 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003547 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004066 | 9000308 | 05 | Preparation | 0000124191 | 5 | 0 | EA | 102000000001038 |  | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015638_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-03-17 | 1 | 4900030154_2024_0009 |  | 2024-02-09 | 2024-05-03 | GT4007 | 5000015638_2024_0004 | 0 | 2 | 0 | 1 | 0 | 180004066 | 3 | L | 4900030154 | 2024 |  | 5000015638 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10420917 | ELEMENT,FLT;CAMFIL FARR HF903566 |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 9000308_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000132 |  | 20 |  | 5 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000123582 | S002 |  | 30 | 5300003547 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124191 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 200085915 | 0040 | 0080 | 200085915 | 1Y GT4008 WATERWASH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | No Issue identified | 10420917 | ELEMENT,FLT;CAMFIL FARR HF903566 | 1 | EA | 4 | 2 | 2 | 1 | EA | UserCommentLink | Supply for Order 200085915, Item 5 cannot be changed 9000022 item 50 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003548 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004306 | 9000022 | 05 | Preparation | 0000124193 | 5 | 0 | EA | 102000000000405 |  | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017892_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-03-17 | 1 | 4900030464_2024_0009 |  | 2024-02-12 | 2024-05-03 | GT4008 | 5000017892_2024_0005 | 0 | 2 | 0 | 1 | 0 | 180004306 | 3 | L | 4900030464 | 2024 |  | 5000017892 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10420917 | ELEMENT,FLT;CAMFIL FARR HF903566 |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 9000022_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000289 |  | 20 |  | 5 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000123584 | S002 |  | 30 | 5300003548 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124193 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 200085915 | 0040 | 0070 | 200085915 | 1Y GT4008 WATERWASH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | No Issue identified | 10289918 | CABLE,SAF;GE C1022450 | 1 | KIT | 25 | 1 | 3 | 1 | KIT | UserCommentLink | Supply for Order 200085915, Item 4 cannot be changed 9000022 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003548 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  | 180004306 | 9000022 | 05 | Preparation | 0000124193 | 4 | 0 | KIT | 102000000000381 | 102000000001189 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017892_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-03-17 | 1 | 4900030464_2024_0007 |  | 2024-02-12 | 2024-05-03 | GT4008 | 5000017892_2024_0004 | 0 | 2 | 0 | 1 | 0 | 180004306 | 3 | L | 4900030464 | 2024 |  | 5000017892 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10289918 | CABLE,SAF;GE C1022450 |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 9000022_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000289 |  | 20 |  | 4 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000123584 | S002 |  | 30 | 5300003548 | 40 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124193 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 200085915 | 0040 | 0060 | 200085915 | 1Y GT4008 WATERWASH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | No Issue identified | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 3 | EA | 6 | 3 | 8 | 3 | EA | UserCommentLink | Supply for Order 200085915, Item 3 cannot be changed 9000022 item 30 already exists | Material is received @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003548 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004306 | 9000022 | 05 | Preparation | 0000124193 | 3 | 0 | EA |  |  | 102000000000346 | 01-Road | 1000000499 |  | 5-Completed |  | WorkPackLink | P07YRDBAY8 |  | 0 |  | 0 | 0 |  | 0 | 3 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017892 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-03-17 | 3 | 4900030464_2024_0005 |  | 2024-02-12 | 2024-05-03 | GT4008 | 5000017892_2024_0003 | 0 | 2 | 0 | 3 | 0 | 180004306 | 3 | L | 4900030464 | 2024 |  | 5000017892 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 9000022_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000289 |  | 20 |  | 3 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000123584 | S002 | 30 | 30 | 5300003548 | 30 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124193 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 200085915 | 0040 | 0040 | 200085915 | 1Y GT4008 WATERWASH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 |  | 20 | No Issue identified | 10256255 | SOLVENT;ROCHEM FYREWASH F1,25L | 1 | DR | 3 | 1 | 3 | 1 | DR | UserCommentLink | Supply for Order 200085915, Item 1 cannot be changed 9000022 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003548 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180004306 | 9000022 | 05 | Preparation | 0000124193 | 1 | 0 | DR | 102000000000405 |  | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017892_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-03-17 | 1 | 4900030464_2024_0001 |  | 2024-02-12 | 2024-05-03 | GT4008 | 5000017892_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004306 | 3 | L | 4900030464 | 2024 |  | 5000017892 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10256255 | SOLVENT;ROCHEM FYREWASH F1,25L |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 9000022_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000289 |  | 20 |  | 1 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000123584 | S002 | 30 | 30 | 5300003548 | 10 |  |  | 0 | 1 | DR | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124193 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | KSF
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | ROTAT | 200085915 | 0040 | 0050 | 200085915 | 1Y GT4008 WATERWASH MAINTENANCE | AA53.GT4008 | TURB,GAS FOR G4008 | AA01 | 20 | No Issue identified | 10255397 | GASKET;GE L43073P01 | 2 | EA | 23 | 4 | 4 | 2 | EA | UserCommentLink | Supply for Order 200085915, Item 2 cannot be changed 9000022 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003548 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004306 | 9000022 | 05 | Preparation | 0000124193 | 2 | 0 | EA | 102000000000381 | 102000000000404 | 102000000000282 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT8-SW3R02A01B | WorkPackLink | P07WH-R8FL |  | 0 |  | 0 | 0 |  | 0 | 2 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017892_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000002054 | 1020 | 2024-03-17 | 2 | 4900030464_2024_0003 |  | 2024-02-12 | 2024-05-03 | GT4008 | 5000017892_2024_0002 | 0 | 2 | 0 | 2 | 0 | 180004306 | 3 | L | 4900030464 | 2024 |  | 5000017892 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255397 | GASKET;GE L43073P01 |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 9000022_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000289 |  | 20 |  | 2 |  | 0 |  | 24SDGT8 | MJ | AU1072 | 1000123584 | S002 |  | 30 | 5300003548 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124193 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | ROTAT | 200085917 | 0040 | 0050 | 200085917 | 1Y GT4009 WATERWASH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | No Issue identified | 10255397 | GASKET;GE L43073P01 | 2 | EA | 23 | 4 | 4 | 2 | EA | 13.02 - In Transit Inb Del 180004335 | Supply for Order 200085917, Item 2 cannot be changed 9000035 item 20 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003549 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004335 | 9000035 | 05 | Preparation | 0000124195 | 2 | 0 | EA |  |  | 102000000000236 | [5 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | IDST-0180004335 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-03-17 | 2 | 4900030571_2024_0003 |  | 2024-02-12 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 | 180004335 | 3 | L | 4900030571 | 2024 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255397 | GASKET;GE L43073P01 |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 9000035_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000426 |  | 20 |  | 2 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000123586 | S002 |  | 30 | 5300003549 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124195 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | ROTAT | 200085917 | 0040 | 0080 | 200085917 | 1Y GT4009 WATERWASH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | No Issue identified | 10420917 | ELEMENT,FLT;CAMFIL FARR HF903566 | 1 | EA | 4 | 2 | 2 | 1 | EA | 13.02 - In Transit Inb Del 180004335 | Supply for Order 200085917, Item 5 cannot be changed 9000035 item 50 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003549 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004335 | 9000035 | 05 | Preparation | 0000124195 | 5 | 0 | EA |  |  | 102000000000237 | [5 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | IDST-0180004335 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-03-17 | 1 | 4900030571_2024_0009 |  | 2024-02-12 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 | 180004335 | 3 | L | 4900030571 | 2024 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10420917 | ELEMENT,FLT;CAMFIL FARR HF903566 |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 9000035_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000426 |  | 20 |  | 5 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000123586 | S002 |  | 30 | 5300003549 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124195 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | ROTAT | 200085917 | 0040 | 0070 | 200085917 | 1Y GT4009 WATERWASH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | No Issue identified | 10289918 | CABLE,SAF;GE C1022450 | 1 | KIT | 25 | 1 | 3 | 1 | KIT | UserCommentLink | Supply for Order 200085917, Item 4 cannot be changed 9000035 item 40 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003549 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  | 180004335 | 9000035 | 05 | Preparation | 0000124195 | 4 | 0 | KIT | 102000000000119 | 102000000001214 | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017955_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-03-17 | 1 | 4900030571_2024_0007 |  | 2024-02-12 | 2024-05-03 |  | 5000017955_2024_0002 | 0 | 2 | 0 | 1 | 0 | 180004335 | 3 | L | 4900030571 | 2024 |  | 5000017955 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10289918 | CABLE,SAF;GE C1022450 |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 9000035_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000426 |  | 20 |  | 4 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000123586 | S002 |  | 30 | 5300003549 | 40 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124195 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | ROTAT | 200085917 | 0040 | 0060 | 200085917 | 1Y GT4009 WATERWASH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | No Issue identified | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 3 | EA | 6 | 3 | 8 | 3 | EA | UserCommentLink | Supply for Order 200085917, Item 3 cannot be changed 9000035 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003549 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004335 | 9000035 | 05 | Preparation | 0000124195 | 3 | 0 | EA |  |  | 102000000001217 | 01-Road | 1000000499 |  | 5-Completed |  | WorkPackLink | P07YRDBAY8 |  | 0 |  | 0 | 0 |  | 0 | 3 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017974_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-03-17 | 3 | 4900030571_2024_0005 |  | 2024-02-12 | 2024-05-03 |  | 5000017974_2024_0001 | 0 | 2 | 0 | 3 | 0 | 180004335 | 3 | L | 4900030571 | 2024 |  | 5000017974 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 9000035_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000426 |  | 20 |  | 3 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000123586 | S002 | 30 | 30 | 5300003549 | 30 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124195 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT9 | Released | 2024-01-02 | 2024-05-19 | 2024-04-30 | 2024-05-19 | 2024-05-19 | ROTAT | 200085917 | 0040 | 0040 | 200085917 | 1Y GT4009 WATERWASH MAINTENANCE | AA53.GT4009 | TURB,GAS FOR G4009 |  | 20 | No Issue identified | 10256255 | SOLVENT;ROCHEM FYREWASH F1,25L | 1 | DR | 3 | 1 | 3 | 1 | DR | UserCommentLink | Supply for Order 200085917, Item 1 cannot be changed 9000035 item 10 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003549 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180004335 | 9000035 | 05 | Preparation | 0000124195 | 1 | 0 | DR | 102000000001216 |  | 102000000000142 | 01-Road | 1000000499 |  | 5-Completed | 24SDGT9-SW3R02B01A | WorkPackLink | P07WHR10FL |  | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-13 |  | Y | 1001 | 2024-01-02 | GRST-5000017955_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  | 100000002057 | 1020 | 2024-03-17 | 1 | 4900030571_2024_0001 |  | 2024-02-12 | 2024-05-03 |  | 5000017955_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004335 | 3 | L | 4900030571 | 2024 |  | 5000017955 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10256255 | SOLVENT;ROCHEM FYREWASH F1,25L |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 9000035_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000426 |  | 20 |  | 1 |  | 0 |  | 24SDGT9 | MJ | AU1072 | 1000123586 | S002 | 30 | 30 | 5300003549 | 10 |  |  | 0 | 1 | DR | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-13 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124195 | 0 |  | 3 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-04 | ROTAT | 200085919 | 0040 | 0080 | 200085919 | 1Y GT4010 WATERWASH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 20 | No Issue identified | 10420917 | ELEMENT,FLT;CAMFIL FARR HF903566 | 1 | EA | 4 | 2 | 2 | 1 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200085919, Item 5 cannot be changed 9000347 item 50 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003552 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006808 | 9000347 | 05 | Preparation | 0000124197 | 5 | 0 | EA | 102000000000133 | 102000000001172 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006808 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000003162 | 1020 | 2024-03-17 | 1 | 4900033155_2024_0007 |  | 2024-02-27 | 2024-05-03 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006808 | 3 | L | 4900033155 | 2024 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10420917 | ELEMENT,FLT;CAMFIL FARR HF903566 |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 9000347_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000110 |  | 20 |  | 5 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000123588 | S002 |  | 30 | 5300003552 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124197 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-04 | ROTAT | 200085919 | 0040 | 0060 | 200085919 | 1Y GT4010 WATERWASH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 20 | No Issue identified | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 | 3 | EA | 6 | 3 | 8 | 3 | EA | UserCommentLink | Supply for Order 200085919, Item 3 cannot be changed 9000706 item 30 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003552 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180009576 | 9000706 | 05 | Preparation | 0000124197 | 3 | 0 | EA |  |  | 102000000001228 | 01-Road | 1000000904 |  | 3-In Transit |  | WorkPackLink | P07YRDBAY8 |  | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y | 1001 | 2024-01-02 | GRST-5000034654_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002889 | 1020 | 2024-03-17 | 3 | 4900035549_2024_0001 |  | 2024-03-08 | 2024-05-03 | GT4010 | 5000034654_2024_0001 | 0 | 2 | 0 | 3 | 0 | 180009576 | 3 | L | 4900035549 | 2024 |  | 5000034654 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10300759 | CONTAINER,INTER BULK;SCHUTZ 4042289 |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 9000706_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000110 |  | 20 |  | 3 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000123588 | S002 | 30 | 30 | 5300003552 | 30 |  |  | 0 | 3 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124197 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-04 | ROTAT | 200085919 | 0040 | 0040 | 200085919 | 1Y GT4010 WATERWASH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 |  | 20 | No Issue identified | 10256255 | SOLVENT;ROCHEM FYREWASH F1,25L | 1 | DR | 3 | 1 | 3 | 1 | DR | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200085919, Item 1 cannot be changed 9000347 item 10 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003552 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | DR |  |  |  | 180006808 | 9000347 | 05 | Preparation | 0000124197 | 1 | 0 | DR | 102000000000133 | 102000000001172 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006808 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000003162 | 1020 | 2024-03-17 | 1 | 4900033155_2024_0001 |  | 2024-02-27 | 2024-05-03 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006808 | 3 | L | 4900033155 | 2024 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10256255 | SOLVENT;ROCHEM FYREWASH F1,25L |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 9000347_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000110 |  | 20 |  | 1 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000123588 | S002 | 30 | 30 | 5300003552 | 10 |  |  | 0 | 1 | DR | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124197 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-04 | ROTAT | 200085919 | 0040 | 0050 | 200085919 | 1Y GT4010 WATERWASH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 20 | No Issue identified | 10255397 | GASKET;GE L43073P01 | 2 | EA | 23 | 4 | 4 | 2 | EA | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200085919, Item 2 cannot be changed 9000347 item 20 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003552 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180006808 | 9000347 | 05 | Preparation | 0000124197 | 2 | 0 | EA | 102000000000133 | 102000000001171 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006808 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000003162 | 1020 | 2024-03-17 | 2 | 4900033155_2024_0003 |  | 2024-02-27 | 2024-05-03 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006808 | 3 | L | 4900033155 | 2024 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255397 | GASKET;GE L43073P01 |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 9000347_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000110 |  | 20 |  | 2 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000123588 | S002 |  | 30 | 5300003552 | 20 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124197 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | KSF
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-04 | ROTAT | 200085919 | 0040 | 0070 | 200085919 | 1Y GT4010 WATERWASH MAINTENANCE | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 20 | No Issue identified | 10289918 | CABLE,SAF;GE C1022450 | 1 | KIT | 25 | 1 | 3 | 1 | KIT | 28.02 - 24SDGT10-SW3R02B01B | Supply for Order 200085919, Item 4 cannot be changed 9000347 item 40 already exists |  | SP12 | Stock at Base | 0 | AA02 | 5300003552 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  | 180006808 | 9000347 | 05 | Preparation | 0000124197 | 4 | 0 | KIT | 102000000000133 | 102000000001173 | 102000000000143 |  |  |  |  | 24SDGT10-SW3R02B01B | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | IDST-0180006808 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000003162 | 1020 | 2024-03-17 | 1 | 4900033155_2024_0005 |  | 2024-02-27 | 2024-05-03 | GT4010 |  | 0 | 2 | 0 | 0 | 0 | 180006808 | 3 | L | 4900033155 | 2024 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10289918 | CABLE,SAF;GE C1022450 |  | 0040 | WATERWASH TURBINE AND CRANK DRY | INT | WATERWASH TURBINE AND CRANK DRY | 5 |  | 9000347_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000110 |  | 20 |  | 4 |  | 0 |  | 24SDGT10 | MJ | AU1072 | 1000123588 | S002 |  | 30 | 5300003552 | 40 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 124197 | 0 |  | 3 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088845 | 0010 | 0010 | 200088845 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1190 | AA53.3A1190 | PKG EQ,PWR PK ESD HYD VALVE 311HYD01 | AA01 | 10 | No Issue identified | 10018835 | SEAL KIT;O-RING,HYDAC 313828 | 1 | KIT | 3 | 0 | 0 | 1 | KIT | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004057 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90006333 | 05 | Preparation | 0000127075 | 1 | 0 | KIT | 102000000003488 |  | 102000000003572 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006333_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646647 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018835 | SEAL KIT;O-RING,HYDAC 313828 |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006333_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006333 |  | 5 |  | 1 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126477 | S002 | 30 | 30 | 5300004057 | 10 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127075 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088845 | 0010 | 0030 | 200088845 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1190 | AA53.3A1190 | PKG EQ,PWR PK ESD HYD VALVE 311HYD01 | AA01 | 10 | No Issue identified | 10018832 | REPAIR KIT;HYDAC 304311 | 1 | KIT | 13 | 0 | 0 | 1 | KIT | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004057 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90006333 | 05 | Preparation | 0000127075 | 3 | 0 | KIT | 102000000003580 |  | 102000000003572 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006333_0030 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646647 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018832 | REPAIR KIT;HYDAC 304311 |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006333_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006333 |  | 5 |  | 3 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126477 | S002 | 30 | 30 | 5300004057 | 30 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127075 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088845 | 0010 | 0020 | 200088845 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1190 | AA53.3A1190 | PKG EQ,PWR PK ESD HYD VALVE 311HYD01 | AA01 | 10 | No Issue identified | 10018845 | SEAL KIT;FILTER,HYDAC RF60G11 | 1 | KIT | 8 | 0 | 0 | 1 | KIT | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004057 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90006333 | 05 | Preparation | 0000127075 | 2 | 0 | KIT | 102000000003488 |  | 102000000003572 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006333_0020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646647 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018845 | SEAL KIT;FILTER,HYDAC RF60G11 |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006333_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006333 |  | 5 |  | 2 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126477 | S002 | 30 | 30 | 5300004057 | 20 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127075 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088845 | 0010 | 0070 | 200088845 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1190 | AA53.3A1190 | PKG EQ,PWR PK ESD HYD VALVE 311HYD01 | AA01 | 10 | No Issue identified | 10018833 | REPAIR KIT;HYDAC REPARATURSATZEDF160G10 | 2 | KIT | 7 | 0 | 0 | 2 | KIT | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004057 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90006333 | 05 | Preparation | 0000127075 | 7 | 0 | KIT | 102000000003580 |  | 102000000003572 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006333_0070 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646647 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018833 | REPAIR KIT;HYDAC REPARATURSATZEDF160G10 |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006333_0070 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006333 |  | 5 |  | 7 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126477 | S002 |  | 30 | 5300004057 | 70 |  |  | 0 | 2 | KIT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127075 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088845 | 0010 | 0040 | 200088845 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1190 | AA53.3A1190 | PKG EQ,PWR PK ESD HYD VALVE 311HYD01 | AA01 | 10 | No Issue identified | 10018848 | KIT,HYDAC RFON330F10B1.1 FILTER,SEAL | 1 | KIT | 5 | 0 | 0 | 1 | KIT | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004057 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90006333 | 05 | Preparation | 0000127075 | 4 | 0 | KIT | 102000000003582 |  | 102000000003572 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006333_0040 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646647 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018848 | KIT,HYDAC RFON330F10B1.1 FILTER,SEAL |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006333_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006333 |  | 5 |  | 4 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126477 | S002 |  | 30 | 5300004057 | 40 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127075 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088845 | 0010 | 0100 | 200088845 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1190 | AA53.3A1190 | PKG EQ,PWR PK ESD HYD VALVE 311HYD01 | AA01 | 10 | No Issue identified | 10018774 | ELEMENT,FLT;10UM,HYDAC 0060R010ON | 1 | EA | 8 | 0 | 0 | 1 | EA | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004057 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006333 | 05 | Preparation | 0000127075 | 10 | 0 | EA | 102000000003602 |  | 102000000003572 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006333_0100 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646647 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018774 | ELEMENT,FLT;10UM,HYDAC 0060R010ON |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006333_0100 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006333 |  | 5 |  | 10 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126477 | S002 |  | 30 | 5300004057 | 100 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127075 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088845 | 0010 | 0060 | 200088845 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1190 | AA53.3A1190 | PKG EQ,PWR PK ESD HYD VALVE 311HYD01 | AA01 | 10 | No Issue identified | 10018778 | ELEMENT,FLT;12UM,PALL HC2237FHS6Z | 1 | EA | 5 | 0 | 0 | 1 | EA | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004057 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006333 | 05 | Preparation | 0000127075 | 6 | 0 | EA | 102000000003586 |  | 102000000003572 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006333_0060 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646647 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018778 | ELEMENT,FLT;12UM,PALL HC2237FHS6Z |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006333_0060 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006333 |  | 5 |  | 6 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126477 | S002 |  | 30 | 5300004057 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127075 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088845 | 0010 | 0090 | 200088845 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1190 | AA53.3A1190 | PKG EQ,PWR PK ESD HYD VALVE 311HYD01 | AA01 | 10 | No Issue identified | 10243768 | ELEMENT,FLT,CART;1UM,PALL PFD12 | 1 | EA | 9 | 0 | 2 | 1 | EA | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004057 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006333 | 05 | Preparation | 0000127075 | 9 | 0 | EA | 102000000003584 |  | 102000000003572 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006333_0090 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646647 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10243768 | ELEMENT,FLT,CART;1UM,PALL PFD12 |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006333_0090 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006333 |  | 5 |  | 9 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126477 | S002 | 30 | 30 | 5300004057 | 90 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127075 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088845 | 0010 | 0110 | 200088845 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1190 | AA53.3A1190 | PKG EQ,PWR PK ESD HYD VALVE 311HYD01 | AA01 | 10 | No Issue identified | 10018773 | ELEMENT,FLT;HYD,12UM,PALL HC2207FHS3Z | 1 | EA | 16 | 0 | 0 | 1 | EA | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004057 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006333 | 05 | Preparation | 0000127075 | 11 | 0 | EA | 102000000003604 |  | 102000000003572 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006333_0110 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646647 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018773 | ELEMENT,FLT;HYD,12UM,PALL HC2207FHS3Z |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006333_0110 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006333 |  | 5 |  | 11 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126477 | S002 | 30 | 30 | 5300004057 | 110 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127075 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088845 | 0010 | 0030 | 200088845 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1190 | AA53.3A1190 | PKG EQ,PWR PK ESD HYD VALVE 311HYD01 | AA01 | 10 | No Issue identified | 10018832 | REPAIR KIT;HYDAC 304311 | 1 | KIT | 13 | 0 | 0 | 1 | KIT | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004057 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90006333 | 05 | Preparation | 0000127075 | 3 | 0 | KIT | 102000000003580 |  | 102000000003572 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006333_0030 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646647 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018832 | REPAIR KIT;HYDAC 304311 |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006333_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006333 |  | 5 |  | 3 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126477 | S002 | 30 | 30 | 5300004057 | 30 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127075 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088845 | 0010 | 0110 | 200088845 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1190 | AA53.3A1190 | PKG EQ,PWR PK ESD HYD VALVE 311HYD01 | AA01 | 10 | No Issue identified | 10018773 | ELEMENT,FLT;HYD,12UM,PALL HC2207FHS3Z | 1 | EA | 16 | 0 | 0 | 1 | EA | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004057 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006333 | 05 | Preparation | 0000127075 | 11 | 0 | EA | 102000000003604 |  | 102000000003572 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006333_0110 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646647 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018773 | ELEMENT,FLT;HYD,12UM,PALL HC2207FHS3Z |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006333_0110 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006333 |  | 5 |  | 11 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126477 | S002 | 30 | 30 | 5300004057 | 110 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127075 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088846 | 0010 | 0080 | 200088846 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1490 | AA53.3A1490 | PKG EQ,PWR PK ESD VLV 314HYD02/03/19/124 | AA01 | 10 | No Issue identified | 10243768 | ELEMENT,FLT,CART;1UM,PALL PFD12 | 1 | EA | 9 | 0 | 2 | 1 | EA | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004060 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006334 | 05 | Preparation | 0000127076 | 8 | 0 | EA | 102000000003468 |  | 102000000003667 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006334_0080 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646650 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10243768 | ELEMENT,FLT,CART;1UM,PALL PFD12 |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006334_0080 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006334 |  | 5 |  | 8 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126478 | S002 | 30 | 30 | 5300004060 | 80 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127076 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088846 | 0010 | 0100 | 200088846 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1490 | AA53.3A1490 | PKG EQ,PWR PK ESD VLV 314HYD02/03/19/124 | AA01 | 10 | No Issue identified | 10018774 | ELEMENT,FLT;10UM,HYDAC 0060R010ON | 1 | EA | 8 | 0 | 0 | 1 | EA | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004060 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006334 | 05 | Preparation | 0000127076 | 10 | 0 | EA | 102000000003662 |  | 102000000003667 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006334_0100 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646650 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018774 | ELEMENT,FLT;10UM,HYDAC 0060R010ON |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006334_0100 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006334 |  | 5 |  | 10 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126478 | S002 |  | 30 | 5300004060 | 100 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127076 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088846 | 0010 | 0020 | 200088846 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1490 | AA53.3A1490 | PKG EQ,PWR PK ESD VLV 314HYD02/03/19/124 | AA01 | 10 | No Issue identified | 10018778 | ELEMENT,FLT;12UM,PALL HC2237FHS6Z | 1 | EA | 5 | 0 | 0 | 1 | EA | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004060 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006334 | 05 | Preparation | 0000127076 | 2 | 0 | EA | 102000000003469 |  | 102000000003667 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006334_0020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646650 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018778 | ELEMENT,FLT;12UM,PALL HC2237FHS6Z |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006334_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006334 |  | 5 |  | 2 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126478 | S002 |  | 30 | 5300004060 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127076 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088846 | 0010 | 0010 | 200088846 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1490 | AA53.3A1490 | PKG EQ,PWR PK ESD VLV 314HYD02/03/19/124 | AA01 | 10 | No Issue identified | 10018773 | ELEMENT,FLT;HYD,12UM,PALL HC2207FHS3Z | 1 | EA | 16 | 0 | 0 | 1 | EA | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004060 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006334 | 05 | Preparation | 0000127076 | 1 | 0 | EA | 102000000003663 |  | 102000000003667 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006334_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646650 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018773 | ELEMENT,FLT;HYD,12UM,PALL HC2207FHS3Z |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006334_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006334 |  | 5 |  | 1 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126478 | S002 | 30 | 30 | 5300004060 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127076 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088846 | 0010 | 0090 | 200088846 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1490 | AA53.3A1490 | PKG EQ,PWR PK ESD VLV 314HYD02/03/19/124 | AA01 | 10 | No Issue identified | 10018833 | REPAIR KIT;HYDAC REPARATURSATZEDF160G10 | 2 | KIT | 7 | 0 | 0 | 2 | KIT | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004060 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90006334 | 05 | Preparation | 0000127076 | 9 | 0 | KIT | 102000000003466 |  | 102000000003667 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006334_0090 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646650 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018833 | REPAIR KIT;HYDAC REPARATURSATZEDF160G10 |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006334_0090 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006334 |  | 5 |  | 9 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126478 | S002 |  | 30 | 5300004060 | 90 |  |  | 0 | 2 | KIT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127076 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088846 | 0010 | 0070 | 200088846 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1490 | AA53.3A1490 | PKG EQ,PWR PK ESD VLV 314HYD02/03/19/124 | AA01 | 10 | No Issue identified | 10018835 | SEAL KIT;O-RING,HYDAC 313828 | 1 | KIT | 3 | 0 | 0 | 1 | KIT | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004060 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90006334 | 05 | Preparation | 0000127076 | 7 | 0 | KIT | 102000000003465 |  | 102000000003667 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006334_0070 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646650 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018835 | SEAL KIT;O-RING,HYDAC 313828 |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006334_0070 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006334 |  | 5 |  | 7 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126478 | S002 | 30 | 30 | 5300004060 | 70 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127076 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088846 | 0010 | 0050 | 200088846 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1490 | AA53.3A1490 | PKG EQ,PWR PK ESD VLV 314HYD02/03/19/124 | AA01 | 10 | No Issue identified | 10018845 | SEAL KIT;FILTER,HYDAC RF60G11 | 1 | KIT | 8 | 0 | 0 | 1 | KIT | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004060 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90006334 | 05 | Preparation | 0000127076 | 5 | 0 | KIT | 102000000003465 |  | 102000000003667 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006334_0050 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646650 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018845 | SEAL KIT;FILTER,HYDAC RF60G11 |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006334_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006334 |  | 5 |  | 5 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126478 | S002 | 30 | 30 | 5300004060 | 50 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127076 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088846 | 0010 | 0110 | 200088846 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1490 | AA53.3A1490 | PKG EQ,PWR PK ESD VLV 314HYD02/03/19/124 | AA01 | 10 | No Issue identified | 10018775 | FILTER,ELEM;HYD,12UM,PALL HC2217FHS4Z | 2 | EA | 7 | 0 | 0 | 2 | EA | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004060 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006334 | 05 | Preparation | 0000127076 | 11 | 0 | EA | 102000000003661 |  | 102000000003667 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006334_0110 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646650 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018775 | FILTER,ELEM;HYD,12UM,PALL HC2217FHS4Z |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006334_0110 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006334 |  | 5 |  | 11 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126478 | S002 | 30 | 30 | 5300004060 | 110 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127076 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088846 | 0010 | 0030 | 200088846 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1490 | AA53.3A1490 | PKG EQ,PWR PK ESD VLV 314HYD02/03/19/124 | AA01 | 10 | No Issue identified | 10018832 | REPAIR KIT;HYDAC 304311 | 1 | KIT | 13 | 0 | 0 | 1 | KIT | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004060 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90006334 | 05 | Preparation | 0000127076 | 3 | 0 | KIT | 102000000003466 |  | 102000000003667 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006334_0030 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646650 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018832 | REPAIR KIT;HYDAC 304311 |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006334_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006334 |  | 5 |  | 3 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126478 | S002 | 30 | 30 | 5300004060 | 30 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127076 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088846 | 0010 | 0060 | 200088846 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1490 | AA53.3A1490 | PKG EQ,PWR PK ESD VLV 314HYD02/03/19/124 | AA01 | 10 | No Issue identified | 10018848 | KIT,HYDAC RFON330F10B1.1 FILTER,SEAL | 1 | KIT | 5 | 0 | 0 | 1 | KIT | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004060 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90006334 | 05 | Preparation | 0000127076 | 6 | 0 | KIT | 102000000003467 |  | 102000000003667 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006334_0060 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646650 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018848 | KIT,HYDAC RFON330F10B1.1 FILTER,SEAL |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006334_0060 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006334 |  | 5 |  | 6 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126478 | S002 |  | 30 | 5300004060 | 60 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127076 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088846 | 0010 | 0040 | 200088846 | 2Y F06 SIF HYD PACKAGE F/TEST 3A1490 | AA53.3A1490 | PKG EQ,PWR PK ESD VLV 314HYD02/03/19/124 | AA01 | 10 | No Issue identified | 10018779 | ELEMENT,FLT;12UM,PALL HC2246FRS6H50 | 1 | EA | 4 | 0 | 0 | 1 | EA | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004060 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006334 | 05 | Preparation | 0000127076 | 4 | 0 | EA | 102000000003660 |  | 102000000003667 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006334_0040 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646650 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018779 | ELEMENT,FLT;12UM,PALL HC2246FRS6H50 |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006334_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006334 |  | 5 |  | 4 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126478 | S002 |  | 30 | 5300004060 | 40 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127076 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088847 | 0010 | 0040 | 200088847 | 2Y F06 SIF 3A1491 HYD PACKAGE F/TEST | AA53.3A1491 | PKG EQ,PWR PK ESD HYD VALVE 314HYD01 | AA01 | 10 | No Issue identified | 10018833 | REPAIR KIT;HYDAC REPARATURSATZEDF160G10 | 2 | KIT | 7 | 0 | 0 | 2 | KIT | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004062 | 40 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90006335 | 05 | Preparation | 0000127077 | 4 | 0 | KIT | 102000000003489 |  | 102000000003607 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006335_0040 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646653 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018833 | REPAIR KIT;HYDAC REPARATURSATZEDF160G10 |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006335_0040 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006335 |  | 5 |  | 4 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126479 | S002 |  | 30 | 5300004062 | 40 |  |  | 0 | 2 | KIT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127077 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088847 | 0010 | 0110 | 200088847 | 2Y F06 SIF 3A1491 HYD PACKAGE F/TEST | AA53.3A1491 | PKG EQ,PWR PK ESD HYD VALVE 314HYD01 | AA01 | 10 | No Issue identified | 10018773 | ELEMENT,FLT;HYD,12UM,PALL HC2207FHS3Z | 1 | EA | 16 | 0 | 0 | 1 | EA | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004062 | 110 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006335 | 05 | Preparation | 0000127077 | 11 | 0 | EA | 102000000003603 |  | 102000000003607 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006335_0110 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646653 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018773 | ELEMENT,FLT;HYD,12UM,PALL HC2207FHS3Z |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006335_0110 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006335 |  | 5 |  | 11 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126479 | S002 | 30 | 30 | 5300004062 | 110 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127077 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088847 | 0010 | 0070 | 200088847 | 2Y F06 SIF 3A1491 HYD PACKAGE F/TEST | AA53.3A1491 | PKG EQ,PWR PK ESD HYD VALVE 314HYD01 | AA01 | 10 | No Issue identified | 10018845 | SEAL KIT;FILTER,HYDAC RF60G11 | 1 | KIT | 8 | 0 | 0 | 1 | KIT | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004062 | 70 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90006335 | 05 | Preparation | 0000127077 | 7 | 0 | KIT | 102000000003487 |  | 102000000003607 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006335_0070 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646653 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018845 | SEAL KIT;FILTER,HYDAC RF60G11 |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006335_0070 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006335 |  | 5 |  | 7 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126479 | S002 | 30 | 30 | 5300004062 | 70 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127077 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088847 | 0010 | 0090 | 200088847 | 2Y F06 SIF 3A1491 HYD PACKAGE F/TEST | AA53.3A1491 | PKG EQ,PWR PK ESD HYD VALVE 314HYD01 | AA01 | 10 | No Issue identified | 10018835 | SEAL KIT;O-RING,HYDAC 313828 | 1 | KIT | 3 | 0 | 0 | 1 | KIT | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004062 | 90 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90006335 | 05 | Preparation | 0000127077 | 9 | 0 | KIT | 102000000003487 |  | 102000000003607 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006335_0090 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646653 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018835 | SEAL KIT;O-RING,HYDAC 313828 |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006335_0090 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006335 |  | 5 |  | 9 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126479 | S002 | 30 | 30 | 5300004062 | 90 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127077 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088847 | 0010 | 0100 | 200088847 | 2Y F06 SIF 3A1491 HYD PACKAGE F/TEST | AA53.3A1491 | PKG EQ,PWR PK ESD HYD VALVE 314HYD01 | AA01 | 10 | No Issue identified | 10018832 | REPAIR KIT;HYDAC 304311 | 1 | KIT | 13 | 0 | 0 | 1 | KIT | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004062 | 100 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90006335 | 05 | Preparation | 0000127077 | 10 | 0 | KIT | 102000000003489 |  | 102000000003607 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006335_0100 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646653 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018832 | REPAIR KIT;HYDAC 304311 |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006335_0100 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006335 |  | 5 |  | 10 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126479 | S002 | 30 | 30 | 5300004062 | 100 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127077 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088847 | 0010 | 0030 | 200088847 | 2Y F06 SIF 3A1491 HYD PACKAGE F/TEST | AA53.3A1491 | PKG EQ,PWR PK ESD HYD VALVE 314HYD01 | AA01 | 10 | No Issue identified | 10018775 | FILTER,ELEM;HYD,12UM,PALL HC2217FHS4Z | 2 | EA | 7 | 0 | 0 | 2 | EA | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004062 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006335 | 05 | Preparation | 0000127077 | 3 | 0 | EA | 102000000003589 |  | 102000000003607 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006335_0030 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646653 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018775 | FILTER,ELEM;HYD,12UM,PALL HC2217FHS4Z |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006335_0030 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006335 |  | 5 |  | 3 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126479 | S002 | 30 | 30 | 5300004062 | 30 |  |  | 0 | 2 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127077 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088847 | 0010 | 0060 | 200088847 | 2Y F06 SIF 3A1491 HYD PACKAGE F/TEST | AA53.3A1491 | PKG EQ,PWR PK ESD HYD VALVE 314HYD01 | AA01 | 10 | No Issue identified | 10243768 | ELEMENT,FLT,CART;1UM,PALL PFD12 | 1 | EA | 9 | 0 | 2 | 1 | EA | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004062 | 60 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006335 | 05 | Preparation | 0000127077 | 6 | 0 | EA | 102000000003583 |  | 102000000003607 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006335_0060 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646653 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10243768 | ELEMENT,FLT,CART;1UM,PALL PFD12 |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006335_0060 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006335 |  | 5 |  | 6 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126479 | S002 | 30 | 30 | 5300004062 | 60 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127077 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088847 | 0010 | 0010 | 200088847 | 2Y F06 SIF 3A1491 HYD PACKAGE F/TEST | AA53.3A1491 | PKG EQ,PWR PK ESD HYD VALVE 314HYD01 | AA01 | 10 | No Issue identified | 10018779 | ELEMENT,FLT;12UM,PALL HC2246FRS6H50 | 1 | EA | 4 | 0 | 0 | 1 | EA | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004062 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006335 | 05 | Preparation | 0000127077 | 1 | 0 | EA | 102000000003587 |  | 102000000003607 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006335_0010 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646653 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018779 | ELEMENT,FLT;12UM,PALL HC2246FRS6H50 |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006335_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006335 |  | 5 |  | 1 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126479 | S002 |  | 30 | 5300004062 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127077 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088847 | 0010 | 0020 | 200088847 | 2Y F06 SIF 3A1491 HYD PACKAGE F/TEST | AA53.3A1491 | PKG EQ,PWR PK ESD HYD VALVE 314HYD01 | AA01 | 10 | No Issue identified | 10018848 | KIT,HYDAC RFON330F10B1.1 FILTER,SEAL | 1 | KIT | 5 | 0 | 0 | 1 | KIT | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004062 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | KIT |  |  |  |  | 90006335 | 05 | Preparation | 0000127077 | 2 | 0 | KIT | 102000000003581 |  | 102000000003607 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006335_0020 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646653 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018848 | KIT,HYDAC RFON330F10B1.1 FILTER,SEAL |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006335_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006335 |  | 5 |  | 2 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126479 | S002 |  | 30 | 5300004062 | 20 |  |  | 0 | 1 | KIT | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127077 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088847 | 0010 | 0080 | 200088847 | 2Y F06 SIF 3A1491 HYD PACKAGE F/TEST | AA53.3A1491 | PKG EQ,PWR PK ESD HYD VALVE 314HYD01 | AA01 | 10 | No Issue identified | 10018774 | ELEMENT,FLT;10UM,HYDAC 0060R010ON | 1 | EA | 8 | 0 | 0 | 1 | EA | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004062 | 80 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006335 | 05 | Preparation | 0000127077 | 8 | 0 | EA | 102000000003601 |  | 102000000003607 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006335_0080 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646653 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018774 | ELEMENT,FLT;10UM,HYDAC 0060R010ON |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006335_0080 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006335 |  | 5 |  | 8 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126479 | S002 |  | 30 | 5300004062 | 80 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127077 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDLN3 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | VALVE | 200088847 | 0010 | 0050 | 200088847 | 2Y F06 SIF 3A1491 HYD PACKAGE F/TEST | AA53.3A1491 | PKG EQ,PWR PK ESD HYD VALVE 314HYD01 | AA01 | 10 | No Issue identified | 10018778 | ELEMENT,FLT;12UM,PALL HC2237FHS6Z | 1 | EA | 5 | 0 | 0 | 1 | EA | IN GRAY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004062 | 50 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006335 | 05 | Preparation | 0000127077 | 5 | 0 | EA | 102000000003585 |  | 102000000003607 | [5 empty] | WorkPackLink | PACKING | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006335_0050 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-19 | 0 |  |  | 2024-04-30 | 2024-05-03 | 2200646653 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10018778 | ELEMENT,FLT;12UM,PALL HC2237FHS6Z |  | 0010 | Inlec Assistance | INT | Inlec Assistance | 5 |  | 90006335_0050 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006335 |  | 5 |  | 5 |  | 0 |  | 24SDLN3 | MJ | AU1072 | 1000126479 | S002 |  | 30 | 5300004062 | 50 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127077 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | WORK | 200089392 | 0020 | 0020 | 200089392 | 10Y RECERTIFY PSV ROTABLE | AA53.407RV521 | PSV,CO2 DISCH LINE GT4007A CO2 | AA01 | 10 | No Issue identified | 10060915 | GASKET;SWCI,15MM,CL300/600,316L/GR/316 | 1 | EA | 147 | 0 | 30 | 1 | EA | 22.03 - qty 147 SOH at AA02 | Supply for Order 200089392, Item 3 cannot be changed 9000309 item 20 already exists | Material work-packed @AA53 | SP12 | Stock at Base | 0 | AA02 | 5300003819 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180004057 | 9000309 | 05 | Preparation | 0000127702 | 3 | 0 | EA | 102000000001074 | 102000000001033 | 102000000000356 | 01-Road | 1000000427 |  | 5-Completed | 24SDGT7-SW3R02A01A | WorkPackLink | R10P07WHFLR | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-02-09 |  | Y | 1001 | 2024-01-02 | GRST-5000015629_2024 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000002114 | 1020 | 2024-07-18 | 1 | 4900030133_2024_0001 |  | 2024-02-09 | 2024-05-03 | 2200628652 | 5000015629_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180004057 | 3 | L | 4900030133 | 2024 |  | 5000015629 | 2024 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060915 | GASKET;SWCI,15MM,CL300/600,316L/GR/316 |  | 0020 | Remove / Install PSV | INT | Remove / Install PSV | 5 |  | 9000309_0020 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000133 |  | 5 |  | 3 |  | 0 |  | 24SDGT7 | MJ | AU1072 | 1000127064 | S002 | 30 | 30 | 5300003819 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-04-30 |  |  | 2024-02-09 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127702 | 0 |  | 2 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | KSF
| 24SDGT7 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | WORK | 200089392 | 0010 | 0020 | 200089392 | 10Y RECERTIFY PSV ROTABLE | AA53.407RV521 | PSV,CO2 DISCH LINE GT4007A CO2 |  | 10 | No Issue identified | 10266469 | VALVE,REL,CROSBY 9611102A,PRESS 3100KPAG | 1 | EA | 1 | 1 | 0 | 1 | EA | 29.01 - 2 SOH @ AA02 | Supply for Order 200089392, Item 8 cannot be changed 90000260 item 10 already exists | Material In-Transit on-01-Road | SP12 | Stock at Base | 0 | AA03 | 5300005159 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180012553 | 90000260 | 05 | Preparation | 0000127702 | 8 | 0 | EA | 119000000001570 |  | 119000000002627 | 01-Road | 20000662 |  | 3-In Transit |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-17 | IDST-0180012553 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000000344 | 1190 | 2024-07-18 | 1 | 4900039127_2024_0001 |  | 2024-03-21 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 | 180012553 | 3 | L | 4900039127 | 2024 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10266469 | VALVE,REL,CROSBY 9611102A,PRESS 3100KPAG |  | 0010 | Certify PSV | INT | Certify PSV | 5 |  | 90000260_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000260 |  | 5 |  | 8 |  | 0 |  | 24SDGT7 | MJ | AU1098 | 1000127064 | S003 | 30 | 30 | 5300005159 | 20 |  |  | 0 | 1 | EA | 2001 | AA03 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 127702 | 0 |  | 2 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | In Transit Via Road
| 24SDGT8 | Released | 2024-01-02 | 2024-05-15 | 2024-04-30 | 2024-05-15 | 2024-05-15 | WORK | 200089855 | 0010 | 0010 | 200089855 | 6Y RECERTIFY PSV ROTABLE | AA53.408RV501 | PSV,GAS TURB GT4008 |  | 10 | No Issue identified | 10255659 | VALVE,REL,AGCO 81PSF88-8,OIL,SET 1200KPA | 1 | EA | 0 | 2 | 0 | 1 | EA | 26.02 - W/O 400000046, confirmed by Stan Vaccaro | Supply for Order 200089855, Item 4 cannot be changed 90000471 item 10 already exists | Material In-Transit on-01-Road | SP12 | Stock at Base | 0 | AA03 | 5300005161 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180012564 | 90000471 | 05 | Preparation | 0000128133 | 4 | 0 | EA | 119000000002695 |  | 119000000002627 | 01-Road | 20000662 |  | 3-In Transit |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-17 | IDST-0180012564 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  | 100000000344 | 1190 | 2024-06-30 | 1 | 4900039117_2024_0001 |  | 2024-03-21 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 | 180012564 | 3 | L | 4900039117 | 2024 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255659 | VALVE,REL,AGCO 81PSF88-8,OIL,SET 1200KPA |  | 0010 | Certify PSV | INT | Certify PSV | 5 |  | 90000471_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000471 |  | 5 |  | 4 |  | 0 |  | 24SDGT8 | MJ | AU1098 | 1000127524 | S003 | 30 | 30 | 5300005161 | 10 |  |  | 0 | 1 | EA | 2001 | AA03 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128133 | 0 |  | 3 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | In Transit Via Road
| 24SDTOT2 | Released | 2024-01-02 | 2024-05-10 | 2024-05-07 | 2024-05-10 | 2024-05-10 | INLEC | 200089995 | 0010 | 0020 | 200089995 | 4Y Beach Valve Function Test 210HYD001 | AA53.210HYD001 | VALVE,BALL 2TL BEACH VALVE | AA01 | 10 | No Issue identified | 10026910 | VALVE,CONTR;25MM,CL150,B16.5,RF | 1 | EA | 3 | 0 | 0 | 1 | EA | X1 BOX |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300003964 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006056 | 06 | Scheduling | 0000128269 | 1 | 0 | EA | 102000000003248 |  | 102000000003214 | [5 empty] | WorkPackLink | SW3R04B01A | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006056_0010 | 0 | 0 | 0 |  | 2024-05-08 | AA53 | 2024-05-10 |  |  | 2024-05-10 |  |  |  |  | 2024-09-09 | 0 |  |  | 2024-05-07 | 2024-05-10 | 210HYD001 |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-07 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026910 | VALVE,CONTR;25MM,CL150,B16.5,RF |  | 0010 | Operations Assistance | INT | Operations Assistance | 5 |  | 90006056_0010 | [7 empty] | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006056 |  | 5 |  | 1 |  | 0 |  | 24SDTOT2 | MJ | AU1072 | 1000127638 | S002 | 30 | 30 | 5300003964 | 10 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-07 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128269 | 0 |  | 1 |  |  | RC00025003 | 2024-05-10 | 2024-05-10 | 2024-05-10 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SDTOT2 | Released | 2024-01-02 | 2024-03-20 | 2024-03-18 | 2024-05-10 | 2024-05-10 | INLEC | 200089995 | 0010 | 0040 | 200089995 | 4Y Beach Valve Function Test 210HYD001 | AA53.210HYD001 | VALVE,BALL 2TL BEACH VALVE | AA01 | 10 | Del to Maintenance after Reqmt Date | 10038561 | VALVE,CHK;25MM,CL150,RF,VALTEK MKIV1MK41 | 1 | EA | 0 | 0 | 1 | 1 | EA | 12.03 - 1 SOH @ AA01 | Supply for Order 200089995, Item 3 cannot be changed 90005922 item 10 already exists | Materials handed over to w/ Maintenance | SP12 | Stock at Base | 0 | AA02 | 5300003964 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180012967 | 90005922 | 06 | Scheduling | 0000128269 | 3 | 0 | EA |  |  | 101000000021494 | 06-Air Passenger | 1000000997 |  | 5-Completed |  | WorkPackLink | KSF-POP-JOB-BENCH | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 | 2024-03-22 |  | Y | 1001 | 2024-01-02 | GRST-5000043677_2024 | 1 | 0 | 0 |  | 2024-03-18 | AA53 | 2024-05-10 |  |  | 2024-03-21 |  |  | 100000004265 | 1020 | 2024-09-09 | 1 | 4900039572_2024_0001 |  | 2024-03-22 | 2024-03-21 | 210HYD001 | 5000043677_2024_0001 | 0 | 2 | 0 | 1 | 0 | 180012967 | 1 | L | 4900039572 | 2024 |  | 5000043677 | 2024 |  |  | 2024-03-18 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10038561 | VALVE,CHK;25MM,CL150,RF,VALTEK MKIV1MK41 |  | 0010 | Operations Assistance | INT | Operations Assistance | 5 |  | 90005922_0010 | [7 empty] | 0060 | Ready to Schedule (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90005922 |  | 5 |  | 3 |  | 0 |  | 24SDTOT2 | MJ | AU1072 | 1000127638 | S002 | 30 | 30 | 5300003964 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-03-18 |  |  | 2024-03-21 |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128269 | 0 |  | 1 |  |  | RC00025003 | 2024-05-10 | 2024-05-10 | 2024-05-10 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | Material Handed to Maintenance
| 24SDGT10 | Released | 2024-01-02 | 2024-05-03 | 2024-04-30 | 2024-05-03 | 2024-05-03 | WORK | 200090101 | 0010 | 0010 | 200090101 | 6Y RECERTIFY PSV ROTABLE | AA53.410RV501 | PSV,GT4010 LUBEOIL TANK |  | 10 | No Issue identified | 10255659 | VALVE,REL,AGCO 81PSF88-8,OIL,SET 1200KPA | 1 | EA | 0 | 2 | 0 | 1 | EA | 26.02 - 1 SOH @ AA02 | Supply for Order 200090101, Item 4 cannot be changed 90000102 item 10 already exists | Material In-Transit on-01-Road | SP12 | Stock at Base | 0 | AA03 | 5300005162 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180012556 | 90000102 | 05 | Preparation | 0000128339 | 4 | 0 | EA | 119000000000660 |  | 119000000002627 | 01-Road | 20000662 |  | 3-In Transit |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-17 | IDST-0180012556 | 0 | 0 | 0 |  | 2024-05-01 | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  | 100000000344 | 1190 | 2024-06-30 | 1 | 4900039109_2024_0001 |  | 2024-03-21 | 2024-05-03 |  |  | 0 | 2 | 0 | 0 | 0 | 180012556 | 3 | L | 4900039109 | 2024 |  |  | 0 |  |  | 2024-04-30 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10255659 | VALVE,REL,AGCO 81PSF88-8,OIL,SET 1200KPA |  | 0010 | Certify PSV | INT | Certify PSV | 5 |  | 90000102_0010 | [7 empty] | 0055 | In Preparation (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90000102 |  | 5 |  | 4 |  | 0 |  | 24SDGT10 | MJ | AU1098 | 1000127750 | S003 | 30 | 30 | 5300005162 | 10 |  |  | 0 | 1 | EA | 2001 | AA03 | 2024-04-30 |  |  |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 128339 | 0 |  | 3 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | In Transit Via Road
| 24SD3410 | Released | 2024-01-02 | 2024-05-06 | 2024-05-03 | 2024-05-06 | 2024-05-06 | WORK | 200090965 | 0020 | 0030 | 200090965 | 6Y F21 RECERTIFY SC PSV ROTABLE | AA53.34RV46 | PSV,SUCTION OF K3410B/BOG COMPR | AA01 | 10 | No Issue identified | 10060352 | GASKET;CNAF,50MM,CL300,RF,1.5MM,1.0% PSM | 1 | EA | 40 | 0 | 0 | 1 | EA | IN GREY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004334 | 30 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006604 | 07 | Execution | 0000129199 | 3 | 0 | EA | 102000000003770 |  | 102000000003732 | [5 empty] | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006604_0020 | 0 | 0 | 0 |  | 2024-05-04 | AA53 | 2024-05-06 |  |  | 2024-05-06 |  |  |  |  | 2024-10-30 | 0 |  |  | 2024-05-03 | 2024-05-06 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-03 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060352 | GASKET;CNAF,50MM,CL300,RF,1.5MM,1.0% PSM |  | 0020 | REMOVE / INSTALL PSV | INT | REMOVE / INSTALL PSV | 5 | Ready for Release | 90006604_0020 | [7 empty] | 0065 | Ready for Execution (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006604 |  | 5 |  | 3 |  | 0 |  | 24SD3410 | MJ | AU1072 | 1000128608 | S002 |  | 30 | 5300004334 | 30 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-03 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129199 | 0 |  | 3 |  |  | RC00025003 | 2024-05-06 | 2024-05-06 | 2024-05-06 | Goods movement posted/Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SD3410 | Released | 2024-01-02 | 2024-05-06 | 2024-05-03 | 2024-05-06 | 2024-05-06 | WORK | 200090965 | 0020 | 0020 | 200090965 | 6Y F21 RECERTIFY SC PSV ROTABLE | AA53.34RV46 | PSV,SUCTION OF K3410B/BOG COMPR | AA01 | 10 | No Issue identified | 10060351 | GASKET;CNAF,40MM,CL300,RF,1.5MM,1.0% PSM | 1 | EA | 12 | 0 | 0 | 1 | EA | IN GREY TUB |  | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300004334 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90006604 | 07 | Execution | 0000129199 | 2 | 0 | EA | 102000000003770 |  | 102000000003732 | [5 empty] | WorkPackLink | PACKING |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-02 | ODST-0090006604_0010 | 0 | 0 | 0 |  | 2024-05-04 | AA53 | 2024-05-06 |  |  | 2024-05-06 |  |  |  |  | 2024-10-30 | 0 |  |  | 2024-05-03 | 2024-05-06 |  |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-05-03 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060351 | GASKET;CNAF,40MM,CL300,RF,1.5MM,1.0% PSM |  | 0020 | REMOVE / INSTALL PSV | INT | REMOVE / INSTALL PSV | 5 | Ready for Release | 90006604_0010 | [7 empty] | 0065 | Ready for Execution (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90006604 |  | 5 |  | 2 |  | 0 |  | 24SD3410 | MJ | AU1072 | 1000128608 | S002 |  | 30 | 5300004334 | 20 |  |  | 0 | 1 | EA | 2001 | AA02 | 2024-05-03 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129199 | 0 |  | 3 |  |  | RC00025003 | 2024-05-06 | 2024-05-06 | 2024-05-06 | Goods movement posted/Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | KSF
| 24SD3410 | Released | 2024-01-02 | 2024-05-06 | 2024-03-08 | 2024-05-06 | 2024-05-06 | WORK | 200090965 | 0020 | 0040 | 200090965 | 6Y F21 RECERTIFY SC PSV ROTABLE | AA53.34RV46 | PSV,SUCTION OF K3410B/BOG COMPR |  | 10 | No Issue identified | 10245570 | VALVE,REL,FUKUI,REC261-S(A)1.5F2,1700KPA | 1 | EA | 3 | 1 | 0 | 1 | EA | 11.03 - 4 SOH @ AA03 |  | Material In-Transit on-01-Road | SP12 | Stock at Base | 0 | AA03 | 5300005167 | 20 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180010047 | 90004389 | 07 | Execution | 0000129199 | 7 | 0 | EA | 119000000002665 | 119000000000554 | 119000000002670 | 01-Road | 20000585 |  | 1-Not Started |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-17 | IDST-0180010047 | 0 | 0 | 0 |  | 2024-03-08 | AA53 | 2024-05-06 |  |  | 2024-05-06 |  |  | 100000000676 | 1190 | 2024-10-30 | 1 | 4900036281_2024_0001 |  | 2024-03-11 | 2024-03-13 |  |  | 0 | 2 | 0 | 0 | 0 | 180010047 | 3 | L | 4900036281 | 2024 |  |  | 0 |  |  | 2024-03-08 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10245570 | VALVE,REL,FUKUI,REC261-S(A)1.5F2,1700KPA |  | 0020 | REMOVE / INSTALL PSV | INT | REMOVE / INSTALL PSV | 5 | Ready for Release | 90004389_0010 | [7 empty] | 0065 | Ready for Execution (Order) | ZBPM0002 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004389 |  | 5 |  | 7 |  | 0 |  | 24SD3410 | MJ | AU1098 | 1000128608 | S003 | 30 | 30 | 5300005167 | 20 |  |  | 0 | 1 | EA | 2001 | AA03 | 2024-03-08 |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129199 | 0 |  | 3 |  |  | RC00025003 | 2024-05-06 | 2024-05-06 | 2024-05-06 | Goods movement posted/Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | In Transit Via Road
| 24SDTOT2 | Released | 2024-01-02 | 2024-03-13 | 2024-03-08 | 2024-05-10 | 2024-05-10 | WORK | 200091240 | 0010 | 0020 | 200091240 | 10Y RECERTIFY PSV DISPOSABLE | AA53.47RV756 | PSV,ACTD CTRL VALVE 210UV441 | AA01 | 10 | No issue identified | 10260758 | VALVE,REL,NGI G14,700KPAG | 1 | EA | 1 | 6 | 0 | 1 | EA | 22.03 - in Transit to AA53 | Supply for Order 200091240, Item 2 cannot be changed 90004392 item 10 already exists | Material In-Transit on-01-Road | SP12 | Stock at Base | 0 | AA03 | 5300007640 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180010048 | 90004392 | 07 | Execution | 0000129418 | 2 | 0 | EA | 119000000002662 |  | 119000000002670 | 01-Road | 20000585 |  | 1-Not Started |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-03-08 | IDST-0180010048 | 0 | 0 | 0 |  | 2024-03-08 | AA53 | 2024-03-13 |  |  | 2024-03-13 |  |  | 100000000676 | 1190 | 2024-08-20 | 1 | 4900036209_2024_0001 |  | 2024-03-11 | 2024-03-13 |  |  | 0 | 2 | 0 | 0 | 0 | 180010048 | 3 | L | 4900036209 | 2024 |  |  | 0 |  |  | 2024-03-08 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10260758 | VALVE,REL,NGI G14,700KPAG |  | 0010 | CERTIFY PSV | INT | CERTIFY PSV | 0 |  | 90004392_0010 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004392 |  | 5 |  | 2 |  | 0 |  | 24SDTOT2 | MJ | AU1098 | 1000128889 | S003 | 30 | 30 | 5300007640 | 10 |  |  | 0 | 1 | EA | 2001 | AA03 | 2024-03-08 |  |  |  |  | 1070 |  | 2024-03-13 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129418 | 0 |  | 3 |  |  | RC00025003 | 2024-05-10 | 2024-05-10 | 2024-05-10 | Partially confirmed/Printed/Material shortage/Date set by external system/Ready For Scheduling/Object created/Pre-costed/Settlement rule created/Released/Goods movement posted | AM02 | Proactive Maintenance |  | In Transit Via Road
| 24SDTOT2 | Released | 2024-01-02 | 2024-03-13 | 2024-03-08 | 2024-05-10 | 2024-05-10 | WORK | 200091241 | 0010 | 0020 | 200091241 | 10Y RECERTIFY PSV DISPOSABLE | AA53.47RV768 | PSV,ACTD CTRL VALVE 210HV811 | AA01 | 10 | No issue identified | 10260758 | VALVE,REL,NGI G14,700KPAG | 1 | EA | 1 | 6 | 0 | 1 | EA | 22.03 - in Transit to AA53 | Supply for Order 200091241, Item 2 cannot be changed 90004391 item 10 already exists | Material In-Transit on-01-Road | SP12 | Stock at Base | 0 | AA03 | 5300007563 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180010052 | 90004391 | 07 | Execution | 0000129419 | 2 | 0 | EA | 119000000002668 |  | 119000000002670 | 01-Road | 20000585 |  | 1-Not Started |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-03-07 | IDST-0180010052 | 0 | 0 | 0 |  | 2024-03-08 | AA53 | 2024-03-13 |  |  | 2024-03-13 |  |  | 100000000676 | 1190 | 2024-08-20 | 1 | 4900036283_2024_0001 |  | 2024-03-11 | 2024-03-13 |  |  | 0 | 2 | 0 | 0 | 0 | 180010052 | 3 | L | 4900036283 | 2024 |  |  | 0 |  |  | 2024-03-08 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10260758 | VALVE,REL,NGI G14,700KPAG |  | 0010 | CERTIFY PSV | INT | CERTIFY PSV | 0 |  | 90004391_0010 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004391 |  | 5 |  | 2 |  | 0 |  | 24SDTOT2 | MJ | AU1098 | 1000128890 | S003 | 30 | 30 | 5300007563 | 10 |  |  | 0 | 1 | EA | 2001 | AA03 | 2024-03-08 |  |  |  |  | 1070 |  | 2024-03-13 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129419 | 0 |  | 3 |  |  | RC00025003 | 2024-05-10 | 2024-05-10 | 2024-05-10 | Partially confirmed/Printed/Material shortage/Date set by external system/Ready For Scheduling/Object created/Pre-costed/Settlement rule created/Released/Goods movement posted | AM02 | Proactive Maintenance |  | In Transit Via Road
| 24SDTOT2 | Released | 2024-01-02 | 2024-03-13 | 2024-03-08 | 2024-05-10 | 2024-05-10 | WORK | 200091250 | 0010 | 0010 | 200091250 | 10Y RECERTIFY PSV DISPOSABLE | AA53.47RV753 | PSV,ACTD CTRL VALVE 210UV411 | AA01 | 10 | No issue identified | 10260758 | VALVE,REL,NGI G14,700KPAG | 1 | EA | 1 | 6 | 0 | 1 | EA | 22.03 - in Transit to AA53 | Supply for Order 200091250, Item 2 cannot be changed 90004390 item 10 already exists | Material In-Transit on-01-Road | SP12 | Stock at Base | 0 | AA03 | 5300005168 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  | 180010050 | 90004390 | 07 | Execution | 0000129528 | 2 | 0 | EA | 119000000002664 |  | 119000000002670 | 01-Road | 20000585 |  | 1-Not Started |  | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y | 1001 | 2024-01-17 | IDST-0180010050 | 0 | 0 | 0 |  | 2024-03-08 | AA53 | 2024-03-13 |  |  | 2024-03-13 |  |  | 100000000676 | 1190 | 2024-10-10 | 1 | 4900036264_2024_0001 |  | 2024-03-11 | 2024-03-13 |  |  | 0 | 2 | 0 | 0 | 0 | 180010050 | 3 | L | 4900036264 | 2024 |  |  | 0 |  |  | 2024-03-08 |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10260758 | VALVE,REL,NGI G14,700KPAG |  | 0010 | CERTIFY PSV | INT | CERTIFY PSV | 0 |  | 90004390_0010 | [7 empty] | 0070 | Main Work Started (Order) |  | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90004390 |  | 5 |  | 2 |  | 0 |  | 24SDTOT2 | MJ | AU1098 | 1000128899 | S003 | 30 | 30 | 5300005168 | 10 |  |  | 0 | 1 | EA | 2001 | AA03 | 2024-03-08 |  |  |  |  | 1070 |  | 2024-03-13 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 129528 | 0 |  | 3 |  |  | RC00025003 | 2024-05-10 | 2024-05-10 | 2024-05-10 | Partially confirmed/Printed/Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Goods movement posted | AM02 | Proactive Maintenance |  | In Transit Via Road
| 24SDLN1 | Released | 2024-01-01 | 2024-03-31 | 2024-03-17 | 2024-05-03 | 2024-05-03 | INLEC | 100034626 | 0040 | 0010 | 100034626 | OPSD 1K1410 Turb Heat Det Fault 160TZ511 | AA53.160TZ511A | LOOP,HEAT DETECT 1KT1410 TURBINE COMPART | AA01 | 10 | No issue identified | 10034720 | BLOCK,TERM;CER,HIGH TEMP,15A,2W | 20 | EA | 120 | 0 | 0 | 20 | EA | IN GREY TUB | Supply for Order 100034626, Item 2 cannot be changed 90003651 item 10 already exists | Material work-packed @AA02 | SP12 | Stock at Base | 0 | AA02 | 5300006043 | 10 |  | 14 |  | 0 |  |  |  | 0 | 0 | EA |  |  |  |  | 90003651 | 07 | Execution | 0000133118 | 2 | 0 | EA | 102000000003754 |  | 102000000003731 | [5 empty] | WorkPackLink | PACKING | P19 FLInlecs | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y | 1001 | 2024-02-04 | ODST-0090003651_0010 | 0 | 0 | 0 |  | 2024-03-18 | AA53 | 2024-05-03 |  |  | 2024-03-31 |  |  |  |  | 2023-09-24 | 0 |  |  | 2024-03-17 | 2024-03-20 | Buffer |  | 0 | 2 | 0 | 0 | 0 |  | 3 | L |  | 0 |  |  | 0 |  |  | 2024-03-17 | 30POST | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10034720 | BLOCK,TERM;CER,HIGH TEMP,15A,2W |  | 0040 | Fault Find & Repair | INT | Fault Find & Repair |  | Opportune Shutdown | 90003651_0010 | [7 empty] | 0070 | Main Work Started (Order) | ZBPM0001 | 0 |  |  | 106 | AUS Operations | AU00 |  | AA53 | 90003651 |  | 10 |  | 2 |  | 0 |  | 24SDLN1 | MJ | AU1072 | 1000132528 | S002 | 30 | 70 | 5300006043 | 10 |  |  | 0 | 20 | EA | 2001 | AA02 | 2024-03-17 |  | Opportune Shutdown |  |  | 1070 |  | 2024-02-03 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 133118 | 0 |  | 2 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Date set by external system/Object created/Pre-costed/Settlement rule created/Released/Ready For Scheduling Canceled/Part printed/Job In Process/Partially confirmed/Material shortage/Order Approved | AM01 | Reactive Maintenance |  | KSF
1 | 24SDLN1 | Released | 2024-03-11 | 2024-05-03 |  | 2024-05-03 | 2024-05-13 | VALVE | 100073711 | 0020 | 0030 | 100073711 | CV-OH 10" 600# 141FCV01 | AA53.141FCV01 | VALVE,H/W FLOW TO 1E4101 CV | AA01 | 255 | WO item has not been released yet | 10048546 | FLANGE,BLIND;250MM,CL600,RF,LTCS | 2 | EA | 4 | 0 | 0 | 0 |  | 26.03 - PR NEVER |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000224103 | 3 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2026-02-15 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048546 | FLANGE,BLIND;250MM,CL600,RF,LTCS |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | [10 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDLN1 | MJ |  | 1000221711 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-02-26 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-13 | 2024-05-03 | 2024-05-03 | Printed/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Released | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDLN1 | Released | 2024-03-11 | 2024-05-03 |  | 2024-05-03 | 2024-05-13 | VALVE | 100073711 | 0020 | 0020 | 100073711 | CV-OH 10" 600# 141FCV01 | AA53.141FCV01 | VALVE,H/W FLOW TO 1E4101 CV | AA01 | 255 | WO item has not been released yet | 10491127 | STUDBOLT;1.250" X 230MM,L7,BLK | 32 | EA | 0 | 0 | 0 | 0 |  | 26.03 - PR NEVER |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000224103 | 2 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2026-02-15 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491127 | STUDBOLT;1.250" X 230MM,L7,BLK |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | [10 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDLN1 | MJ |  | 1000221711 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-02-26 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-13 | 2024-05-03 | 2024-05-03 | Printed/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed/Released | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDLN1 | Released | 2024-03-11 | 2024-05-03 |  | 2024-05-03 | 2024-05-13 | VALVE | 100073711 | 0020 | 0010 | 100073711 | CV-OH 10" 600# 141FCV01 | AA53.141FCV01 | VALVE,H/W FLOW TO 1E4101 CV | AA01 | 255 | WO item has not been released yet | 10060935 | GASKET;SWCI,250MM,CL600,316L/GR/316 | 2 | EA | 78 | 0 | 0 | 0 |  | 26.03 - PR NEVER |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000224103 | 1 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2026-02-15 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060935 | GASKET;SWCI,250MM,CL600,316L/GR/316 |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | [10 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDLN1 | MJ |  | 1000221711 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-02-26 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-13 | 2024-05-03 | 2024-05-03 | Released/Printed/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDLN1 | Released | 2024-03-05 | 2024-05-03 |  | 2024-05-03 | 2024-05-13 | VALVE | 100073710 | 0020 | 0020 | 100073710 | CV-OH 10" 600# 141FCV02 | AA53.141FCV02 | VALVE,H/W FLOW TO 1E4102 CV | AA01 | 255 | WO item has not been released yet | 10491127 | STUDBOLT;1.250" X 230MM,L7,BLK | 32 | EA | 0 | 0 | 0 | 0 |  | 07.03- PR never |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000224102 | 6 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2026-02-15 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491127 | STUDBOLT;1.250" X 230MM,L7,BLK |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | [10 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDLN1 | MJ |  | 1000221710 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-02-26 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-13 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDLN1 | Released | 2024-03-05 | 2024-05-03 |  | 2024-05-03 | 2024-05-13 | VALVE | 100073710 | 0020 | 0010 | 100073710 | CV-OH 10" 600# 141FCV02 | AA53.141FCV02 | VALVE,H/W FLOW TO 1E4102 CV |  | 255 | WO item has not been released yet | 10060935 | GASKET;SWCI,250MM,CL600,316L/GR/316 | 2 | EA | 0 | 0 | 0 | 0 |  | 07.03- PR never | Supply Process could not be determined for item 5, material 10060935 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000224102 | 5 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2026-02-15 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060935 | GASKET;SWCI,250MM,CL600,316L/GR/316 |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | [10 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDLN1 | MJ |  | 1000221710 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-02-26 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-13 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDLN1 | Released | 2024-03-05 | 2024-05-03 |  | 2024-05-03 | 2024-05-13 | VALVE | 100073710 | 0020 | 0030 | 100073710 | CV-OH 10" 600# 141FCV02 | AA53.141FCV02 | VALVE,H/W FLOW TO 1E4102 CV | AA01 | 255 | WO item has not been released yet | 10048546 | FLANGE,BLIND;250MM,CL600,RF,LTCS | 2 | EA | 4 | 0 | 0 | 0 |  | 07.03- PR never |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000224102 | 7 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2026-02-15 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10048546 | FLANGE,BLIND;250MM,CL600,RF,LTCS |  | 0020 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | [10 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDLN1 | MJ |  | 1000221710 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPBIG | 2024-02-26 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-13 | 2024-05-03 | 2024-05-03 | Printed/Material shortage/Order Approved/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDFR2 | Released | 2024-02-13 | 2024-04-22 |  | 2024-04-22 | 2024-04-23 | PROJ | 100041374 | 0090 | 0030 | 100041374 | KLE- Blast and Paint CL1801 | AA53.CL1801 | LOOP,CORR CL1801 | AA01 | 255 | WO item has not been released yet | 10595798 | INS,BLANKET;PIPE,ROCKWOOL,FIBERTEX BEND+ | 1 | EA | 2 | 0 | 0 | 0 |  | 24/01 PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000139858 | 3 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-22 |  |  | 2024-04-22 |  |  |  |  | 2026-02-01 | 0 |  |  |  |  | TALag_B.Vorn |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  | 30POST | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10595798 | INS,BLANKET;PIPE,ROCKWOOL,FIBERTEX BEND+ |  | 0090 | Install Cladding at CL1801 | ENON | Install Cladding at CL1801 | 5 | [9 empty] | 0060 | Ready to Schedule (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000139289 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-04-23 | 2024-04-22 | 2024-04-22 | Released/Settlement rule created/Object created/Date set by external system/Order Approved/Pre-costed/Ready For Scheduling/Material committed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDFR2 | Released | 2024-02-13 | 2024-04-22 |  | 2024-04-22 | 2024-04-23 | PROJ | 100041374 | 0090 | 0020 | 100041374 | KLE- Blast and Paint CL1801 | AA53.CL1801 | LOOP,CORR CL1801 | AA01 | 255 | WO item has not been released yet | 10595798 | INS,BLANKET;PIPE,ROCKWOOL,FIBERTEX BEND+ | 1 | EA | 2 | 0 | 0 | 0 |  | 24/01 PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000139858 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-22 |  |  | 2024-04-22 |  |  |  |  | 2026-02-01 | 0 |  |  |  |  | TALag_B.Vorn |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  | 30POST | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10595798 | INS,BLANKET;PIPE,ROCKWOOL,FIBERTEX BEND+ |  | 0090 | Install Cladding at CL1801 | ENON | Install Cladding at CL1801 | 5 | [9 empty] | 0060 | Ready to Schedule (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000139289 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-04-23 | 2024-04-22 | 2024-04-22 | Released/Settlement rule created/Object created/Date set by external system/Order Approved/Pre-costed/Ready For Scheduling/Material committed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDFR2 | Released | 2024-02-13 | 2024-04-22 |  | 2024-04-22 | 2024-04-23 | PROJ | 100041374 | 0090 | 0010 | 100041374 | KLE- Blast and Paint CL1801 | AA53.CL1801 | LOOP,CORR CL1801 | AA01 | 255 | WO item has not been released yet | 10258236 | INS,BLANKET;PIPE,ROCKWOOL,FIBERTEX SPI | 2 | EA | 0 | 0 | 0 | 0 |  | 24/01 PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000139858 | 1 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-22 |  |  | 2024-04-22 |  |  |  |  | 2026-02-01 | 0 |  |  |  |  | TALag_B.Vorn |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  | 30POST | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258236 | INS,BLANKET;PIPE,ROCKWOOL,FIBERTEX SPI |  | 0090 | Install Cladding at CL1801 | ENON | Install Cladding at CL1801 | 5 | [9 empty] | 0060 | Ready to Schedule (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000139289 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-04-23 | 2024-04-22 | 2024-04-22 | Released/Settlement rule created/Object created/Date set by external system/Order Approved/Pre-costed/Ready For Scheduling/Material committed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SD4403 | Released | 2024-02-13 | 2024-05-07 |  | 2024-05-07 | 2024-05-07 | MECH | 100044208 | 0022 | 0030 | 100044208 | Fin Fan Plugs Leaking - K4403 E1 | AA53.K4403E1 | EXCH,K4403 LUBE OIL AIR COOLER | AA01 | 20 | WO item has not been released yet | 10416852 | GASKET;GEA BATIG 1643261101RARBRC1 | 25 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP97 | Direct Multi-base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000142722 | 5 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 25 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-07 | [7 empty] | 2018-12-13 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10416852 | GASKET;GEA BATIG 1643261101RARBRC1 |  | 0022 | RE-INSTATE PLUGS | INT | RE-INSTATE PLUGS | [10 empty] | 0060 | Ready to Schedule (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SD4403 | MJ |  | 1000142104 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-07 | 2024-05-07 | 2024-05-07 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Ready For Scheduling | AM01 | Reactive Maintenance |  | PR Never
1 | 24SD4403 | Released | 2024-02-13 | 2024-05-07 |  | 2024-05-07 | 2024-05-07 | MECH | 100044208 | 0022 | 0040 | 100044208 | Fin Fan Plugs Leaking - K4403 E1 | AA53.K4403E1 | EXCH,K4403 LUBE OIL AIR COOLER | AA01 | 20 | WO item has not been released yet | 10247726 | PLUG,HEX,1.125" X 12UNF,ASTM A182,SS304 | 5 | EA | 5 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000142722 | 6 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 5 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-07 |  |  | 2024-05-07 |  |  |  |  | 2018-12-13 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10247726 | PLUG,HEX,1.125" X 12UNF,ASTM A182,SS304 |  | 0022 | RE-INSTATE PLUGS | INT | RE-INSTATE PLUGS | [10 empty] | 0060 | Ready to Schedule (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SD4403 | MJ |  | 1000142104 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-07 | 2024-05-07 | 2024-05-07 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Ready For Scheduling | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT8 | Released | 2024-02-12 | 2024-05-15 |  | 2024-05-15 | 2024-05-15 | ROTAT | 200079115 | 0080 | 0070 | 200079115 | 12Y P01 INT INSP PRESS VESSEL GT4008S5A | AA53.GT4008S5A | FILT,GT FUEL GAS GT4008 FILTERS | AA01 | 10 | WO item has not been released yet | 10058307 | STUDBOLT;1.375" X 250MM,A193 B8M CL2 | 20 | EA | 0 | 0 | 0 | 0 |  | 23.02 - PR Never |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000113450 | 9 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-06-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058307 | STUDBOLT;1.375" X 250MM,A193 B8M CL2 |  | 0080 | Install Filters, Top Lid / N-11 | INT | Install Filters, Top Lid / N-11 | [10 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT8 | MJ |  | 1000112814 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Released | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT8 | Released | 2024-02-12 | 2024-05-15 |  | 2024-05-15 | 2024-05-15 | ROTAT | 200079115 | 0080 | 0010 | 200079115 | 12Y P01 INT INSP PRESS VESSEL GT4008S5A | AA53.GT4008S5A | FILT,GT FUEL GAS GT4008 FILTERS | AA01 | 10 | WO item has not been released yet | 10060937 | GASKET;SWCI,350MM,CL600,316L/GR/316 | 2 | EA | 24 | 0 | 0 | 0 |  | 13.02 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000113450 | 1 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-06-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060937 | GASKET;SWCI,350MM,CL600,316L/GR/316 |  | 0080 | Install Filters, Top Lid / N-11 | INT | Install Filters, Top Lid / N-11 | [10 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT8 | MJ |  | 1000112814 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Released | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT8 | Released | 2024-02-12 | 2024-05-15 |  | 2024-05-15 | 2024-05-15 | ROTAT | 200079115 | 0080 | 0060 | 200079115 | 12Y P01 INT INSP PRESS VESSEL GT4008S5A | AA53.GT4008S5A | FILT,GT FUEL GAS GT4008 FILTERS | AA01 | 10 | WO item has not been released yet | 10220454 | STUDBOLT;0.875" X 150MM,A193 B8M CL2 | 8 | EA | 0 | 0 | 0 | 0 |  | 23.02 - PR Never |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000113450 | 7 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-06-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10220454 | STUDBOLT;0.875" X 150MM,A193 B8M CL2 |  | 0080 | Install Filters, Top Lid / N-11 | INT | Install Filters, Top Lid / N-11 | [10 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT8 | MJ |  | 1000112814 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Released | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT8 | Released | 2024-02-12 | 2024-05-15 |  | 2024-05-15 | 2024-05-15 | ROTAT | 200079115 | 0080 | 0020 | 200079115 | 12Y P01 INT INSP PRESS VESSEL GT4008S5A | AA53.GT4008S5A | FILT,GT FUEL GAS GT4008 FILTERS | AA01 | 10 | WO item has not been released yet | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 2 | EA | 68 | 0 | 0 | 0 |  | 13.02 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000113450 | 2 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-06-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 |  | 0080 | Install Filters, Top Lid / N-11 | INT | Install Filters, Top Lid / N-11 | [10 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT8 | MJ |  | 1000112814 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Released | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT8 | Released | 2024-02-12 | 2024-05-15 |  | 2024-05-15 | 2024-05-15 | ROTAT | 200079118 | 0080 | 0020 | 200079118 | 12Y P01 INT INSP PRESS VESSEL GT4008S5B | AA53.GT4008S5B | FILT,GT FUEL GAS GT4008 FILTERS | AA01 | 10 | WO item has not been released yet | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 2 | EA | 68 | 0 | 0 | 0 |  | 13.02 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000113453 | 2 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-06-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 |  | 0080 | Install Filters, Top Lid / N-11 | INT | Install Filters, Top Lid / N-11 | [10 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT8 | MJ |  | 1000112817 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Released | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT8 | Released | 2024-02-12 | 2024-05-15 |  | 2024-05-15 | 2024-05-15 | ROTAT | 200079118 | 0080 | 0050 | 200079118 | 12Y P01 INT INSP PRESS VESSEL GT4008S5B | AA53.GT4008S5B | FILT,GT FUEL GAS GT4008 FILTERS | AA01 | 10 | WO item has not been released yet | 10058307 | STUDBOLT;1.375" X 250MM,A193 B8M CL2 | 20 | EA | 0 | 0 | 0 | 0 |  | 23.02 - PR Never |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000113453 | 13 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 20 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-06-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058307 | STUDBOLT;1.375" X 250MM,A193 B8M CL2 |  | 0080 | Install Filters, Top Lid / N-11 | INT | Install Filters, Top Lid / N-11 | [10 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT8 | MJ |  | 1000112817 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Released | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT8 | Released | 2024-02-12 | 2024-05-15 |  | 2024-05-15 | 2024-05-15 | ROTAT | 200079118 | 0080 | 0040 | 200079118 | 12Y P01 INT INSP PRESS VESSEL GT4008S5B | AA53.GT4008S5B | FILT,GT FUEL GAS GT4008 FILTERS | AA01 | 10 | WO item has not been released yet | 10220454 | STUDBOLT;0.875" X 150MM,A193 B8M CL2 | 8 | EA | 0 | 0 | 0 | 0 |  | 23.02 - PR Never |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000113453 | 4 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-06-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10220454 | STUDBOLT;0.875" X 150MM,A193 B8M CL2 |  | 0080 | Install Filters, Top Lid / N-11 | INT | Install Filters, Top Lid / N-11 | [10 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT8 | MJ |  | 1000112817 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Released | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT8 | Released | 2024-02-12 | 2024-05-15 |  | 2024-05-15 | 2024-05-15 | ROTAT | 200079118 | 0080 | 0010 | 200079118 | 12Y P01 INT INSP PRESS VESSEL GT4008S5B | AA53.GT4008S5B | FILT,GT FUEL GAS GT4008 FILTERS | AA01 | 10 | WO item has not been released yet | 10060937 | GASKET;SWCI,350MM,CL600,316L/GR/316 | 2 | EA | 24 | 0 | 0 | 0 |  | 13.02 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000113453 | 1 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-06-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060937 | GASKET;SWCI,350MM,CL600,316L/GR/316 |  | 0080 | Install Filters, Top Lid / N-11 | INT | Install Filters, Top Lid / N-11 | [10 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT8 | MJ |  | 1000112817 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Released | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDLN1 | Released | 2024-02-08 | 2024-05-09 |  | 2024-02-08 | 2024-05-09 | VALVE | 100072823 | 0030 | 0010 | 100072823 | Replace HYD Actuator - 114URCA68 | AA53.114URCA68 | VALVE,K1430 RECYCLE CTRL TO V1431 | AA01 | 10 | WO item has not been released yet | 10420385 | ACTUATOR,URCA 08-0835DJB/14010,ASY | 1 | ASY | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | ASY | [5 empty] | 07 | Execution | 0000219479 | 1 | 0 | [9 empty] | WorkPackLink |  | P08 OPSD | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-09 |  |  | 2024-05-09 |  |  |  |  | 2024-06-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10420385 | ACTUATOR,URCA 08-0835DJB/14010,ASY |  | 0030 | Pressure Dynamics - Labour & Materials | ESRV | Pressure Dynamics - Labour & Materials |  | Opportune Shutdown/Order Requires Replanning | [8 empty] | 0070 | Main Work Started (Order) | ZBPM0001 | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDLN1 | MJ |  | 1000217323 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Opportune Shutdown/Order Requires Replanning |  |  | 1070 |  | 2024-02-08 | 1001 | Woodside Energy Ltd | W001 | WOPFN4 | 2024-02-08 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-09 | 2024-02-08 | 2024-02-08 | Pre-costed/Ready For Scheduling Canceled/Date set by external system/Job In Process/Goods movement posted/Partially confirmed/Material committed/Order Approved/Object created/Settlement rule created/Released | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT9 | Released | 2024-02-08 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | ROTAT | 200079166 | 0080 | 0010 | 200079166 | 12Y P01 INT INSP PRESS VESSEL GT4009S5B | AA53.GT4009S5B | FILT,GT4009 FUEL GAS | AA01 | 10 | WO item has not been released yet | 10060937 | GASKET;SWCI,350MM,CL600,316L/GR/316 | 2 | EA | 24 | 0 | 0 | 0 |  | 09.02 - PR Never Line item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000113522 | 1 | 0 | [9 empty] | WorkPackLink |  | NEVER | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-07-15 | 0 |  |  |  |  | NEVER |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060937 | GASKET;SWCI,350MM,CL600,316L/GR/316 |  | 0080 | Install Filters, Top Lid / N-11 | INT | Install Filters, Top Lid / N-11 |  | Ready for Release | [8 empty] | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000112885 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Released | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT9 | Released | 2024-02-08 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | ROTAT | 200079166 | 0080 | 0020 | 200079166 | 12Y P01 INT INSP PRESS VESSEL GT4009S5B | AA53.GT4009S5B | FILT,GT4009 FUEL GAS | AA01 | 10 | WO item has not been released yet | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 2 | EA | 68 | 0 | 0 | 0 |  | 09.02 - PR Never Line item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000113522 | 2 | 0 | [9 empty] | WorkPackLink |  | NEVER | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-07-15 | 0 |  |  |  |  | NEVER |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 |  | 0080 | Install Filters, Top Lid / N-11 | INT | Install Filters, Top Lid / N-11 |  | Ready for Release | [8 empty] | 0055 | In Preparation (Order) | ZBPM0002 | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000112885 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Ready for Release |  |  | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Released | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT9 | Released | 2024-02-08 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | ROTAT | 200079169 | 0080 | 0030 | 200079169 | 12Y P01 INT INSP PRESS VESSEL GT4009S5A | AA53.GT4009S5A | FILT,GT4009 FUEL GAS | AA01 | 10 | WO item has not been released yet | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 2 | EA | 68 | 0 | 0 | 0 |  | 13.02 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000113524 | 3 | 0 | [9 empty] | WorkPackLink |  | NEVER | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-07-15 | 0 |  |  |  |  | NEVER |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 |  | 0080 | Install Filters, Top Lid / N-11 | INT | Install Filters, Top Lid / N-11 | [10 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000112888 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT9 | Released | 2024-02-08 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | ROTAT | 200079169 | 0080 | 0020 | 200079169 | 12Y P01 INT INSP PRESS VESSEL GT4009S5A | AA53.GT4009S5A | FILT,GT4009 FUEL GAS | AA01 | 10 | WO item has not been released yet | 10060937 | GASKET;SWCI,350MM,CL600,316L/GR/316 | 2 | EA | 24 | 0 | 0 | 0 |  | 13.02 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000113524 | 2 | 0 | [9 empty] | WorkPackLink |  | NEVER | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-07-15 | 0 |  |  |  |  | NEVER |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060937 | GASKET;SWCI,350MM,CL600,316L/GR/316 |  | 0080 | Install Filters, Top Lid / N-11 | INT | Install Filters, Top Lid / N-11 | [10 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000112888 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT7 | Released | 2024-02-08 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | ROTAT | 200079172 | 0040 | 0010 | 200079172 | 12Y P01 INT INSP PRESS VESSEL GT4007S5B | AA53.GT4007S5B | FILT,GT FUEL GAS GT4007 FILTERS | AA01 | 10 | WO item has not been released yet | 10060937 | GASKET;SWCI,350MM,CL600,316L/GR/316 | 2 | EA | 24 | 0 | 0 | 0 |  | 13.02 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000113528 | 1 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-07-15 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060937 | GASKET;SWCI,350MM,CL600,316L/GR/316 |  | 0040 | Open Top Lid / N-11, Remove Filters | INT | Open Top Lid / N-11, Remove Filters | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000112891 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Material committed/Printed/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT7 | Released | 2024-02-08 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | ROTAT | 200079172 | 0040 | 0020 | 200079172 | 12Y P01 INT INSP PRESS VESSEL GT4007S5B | AA53.GT4007S5B | FILT,GT FUEL GAS GT4007 FILTERS | AA01 | 10 | WO item has not been released yet | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 2 | EA | 68 | 0 | 0 | 0 |  | 13.02 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000113528 | 2 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-07-15 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 |  | 0040 | Open Top Lid / N-11, Remove Filters | INT | Open Top Lid / N-11, Remove Filters | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000112891 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Material committed/Printed/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT7 | Released | 2024-02-08 | 2024-05-03 |  | 2024-05-03 | 2024-05-06 | ROTAT | 200079174 | 0040 | 0010 | 200079174 | 12Y P01 INT INSP PRESS VESSEL GT4007S5A | AA53.GT4007S5A | FILT,GT FUEL GAS GT4007 FILTERS | AA01 | 10 | WO item has not been released yet | 10060937 | GASKET;SWCI,350MM,CL600,316L/GR/316 | 1 | EA | 24 | 0 | 0 | 0 |  | 13.02 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000113530 | 1 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-07-15 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060937 | GASKET;SWCI,350MM,CL600,316L/GR/316 |  | 0040 | Open Top Lid / N-11 For Insp | INT | Open Top Lid / N-11 For Insp | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000112893 |  |  | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-06 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT7 | Released | 2024-02-08 | 2024-05-03 |  | 2024-05-03 | 2024-05-06 | ROTAT | 200079174 | 0040 | 0020 | 200079174 | 12Y P01 INT INSP PRESS VESSEL GT4007S5A | AA53.GT4007S5A | FILT,GT FUEL GAS GT4007 FILTERS | AA01 | 10 | WO item has not been released yet | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 | 1 | EA | 68 | 0 | 0 | 0 |  | 13.02 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000113530 | 2 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-07-15 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060932 | GASKET;SWCI,100MM,CL600,316L/GR/316 |  | 0040 | Open Top Lid / N-11 For Insp | INT | Open Top Lid / N-11 For Insp | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000112893 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-06 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed/Material committed | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDLN1 | Released | 2024-02-07 | 2024-05-02 |  | 2024-04-26 | 2024-05-04 | VALVE | 100072016 | 0040 | 0060 | 100072016 | CV-OH 8" 600# 114PCV13 | AA53.114PCV13 | VALVE,PRESS CTRL 1E1405 | AA01 | 20 | WO item has not been released yet | 10223375 | STUDBOLT;1.125" X 200MM,A193 B8M CL2 | 24 | EA | 0 | 0 | 0 | 0 |  | PR NEVER |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000216559 | 6 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-02 |  |  | 2024-05-02 |  |  |  |  | 2024-07-22 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10223375 | STUDBOLT;1.125" X 200MM,A193 B8M CL2 |  | 0040 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | [10 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDLN1 | MJ |  | 1000214974 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPDGT | 2024-01-24 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-04-26 | 2024-04-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance | M0-000001-99-01 | PR Never
1 | 24SDLN1 | Released | 2024-02-07 | 2024-05-02 |  | 2024-04-26 | 2024-05-04 | VALVE | 100072016 | 0040 | 0070 | 100072016 | CV-OH 8" 600# 114PCV13 | AA53.114PCV13 | VALVE,PRESS CTRL 1E1405 |  | 20 | WO item has not been released yet | 10060934 | GASKET;SWCI,200MM,CL600,316L/GR/316 | 4 | EA | 0 | 0 | 0 | 0 |  | PR NEVER | Supply Process could not be determined for item 7, material 10060934 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000216559 | 7 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-02 | [7 empty] | 2024-07-22 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060934 | GASKET;SWCI,200MM,CL600,316L/GR/316 |  | 0040 | Remove Valve & Install Blind | INT | Remove Valve & Install Blind | [10 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDLN1 | MJ |  | 1000214974 |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | WOPDGT | 2024-01-24 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-04-26 | 2024-04-26 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance | M0-000001-99-01 | PR Never
1 | 24SDFR2 | Released | 2024-02-02 | 2024-04-23 |  | 2024-04-23 | 2024-09-09 | INLEC | 200089937 | 0020 | 0010 | 200089937 | 8Y LV ABB MNS2/3 FEEDER INSP S20D2A2R05 | AA53.S20D2A2R05 | START,2K1820E2 DEGAS TANK HEATER | AA01 | 20 | WO item has not been released yet | 10313057 | GREASE;ISOFLEX TOPAS,KLUBER A004179N | 1 | CQ | 12 | 0 | 0 | 0 |  | 24/01 PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | CQ | [5 empty] | 05 | Preparation | 0000128231 | 1 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2023-06-14 | 0 |  |  |  |  | S20D2A2R05 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10313057 | GREASE;ISOFLEX TOPAS,KLUBER A004179N |  | 0020 | Complete PRT | INT | Complete PRT | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000127620 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-09-09 | 2024-04-23 | 2024-04-23 | Object created/Date set by external system/Material committed/Printed/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDFR2 | Released | 2024-02-02 | 2024-04-23 |  | 2024-04-23 | 2024-09-09 | INLEC | 200089937 | 0020 | 0020 | 200089937 | 8Y LV ABB MNS2/3 FEEDER INSP S20D2A2R05 | AA53.S20D2A2R05 | START,2K1820E2 DEGAS TANK HEATER | AA01 | 20 | WO item has not been released yet | 10417500 | LUBRICANT;WTR,LIQ,LIGHT AMB,400ML | 1 | CAN | 2 | 0 | 0 | 0 |  | 24/01 PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | CAN | [5 empty] | 05 | Preparation | 0000128231 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2023-06-14 | 0 |  |  |  |  | S20D2A2R05 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10417500 | LUBRICANT;WTR,LIQ,LIGHT AMB,400ML |  | 0020 | Complete PRT | INT | Complete PRT | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000127620 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-09-09 | 2024-04-23 | 2024-04-23 | Object created/Date set by external system/Material committed/Printed/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT10 | Released | 2024-01-02 | 2024-05-02 |  | 2024-05-02 | 2024-05-03 | ROTAT | 100039132 | 0030 | 0040 | 100039132 | DE Sump Drain Line Update CM GT4010 | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 20 | WO item has not been released yet | 10060884 | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR | 1 | EA | 40 | 0 | 0 | 0 |  | 01.02 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000137666 | 4 | 0 | [9 empty] | WorkPackLink |  | NEVER | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-02 |  |  | 2024-05-02 |  |  |  |  | 2023-06-30 | 0 |  |  |  |  | NEVER |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060884 | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR |  | 0030 | Fab/Install Section 2 Drain Line(1 Bend) | INT | Fab/Install Section 2 Drain Line(1 Bend) | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000137048 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-03 | 2024-05-02 | 2024-05-02 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT10 | Released | 2024-01-02 | 2024-05-02 |  | 2024-05-02 | 2024-05-03 | ROTAT | 100039132 | 0030 | 0030 | 100039132 | DE Sump Drain Line Update CM GT4010 | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 20 | WO item has not been released yet | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 4 | EA | 0 | 0 | 0 | 0 |  | 01.02 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000137666 | 3 | 0 | [9 empty] | WorkPackLink |  | NEVER | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-02 |  |  | 2024-05-02 |  |  |  |  | 2023-06-30 | 0 |  |  |  |  | NEVER |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 |  | 0030 | Fab/Install Section 2 Drain Line(1 Bend) | INT | Fab/Install Section 2 Drain Line(1 Bend) | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000137048 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-03 | 2024-05-02 | 2024-05-02 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT9 | Released | 2024-01-02 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | ROTAT | 100040102 | 0030 | 0050 | 100040102 | DE Sump Drain Line Update CM GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | WO item has not been released yet | 10060884 | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR | 1 | EA | 40 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000138574 | 4 | 0 | [9 empty] | WorkPackLink |  | NEVER | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2023-06-30 | 0 |  |  |  |  | NEVER |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060884 | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR |  | 0030 | Fab/Install Section 2 Drain Line(1 Bend) | INT | Fab/Install Section 2 Drain Line(1 Bend) | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000137964 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT9 | Released | 2024-01-02 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | ROTAT | 100040102 | 0030 | 0040 | 100040102 | DE Sump Drain Line Update CM GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 20 | WO item has not been released yet | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 4 | EA | 0 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000138574 | 3 | 0 | [9 empty] | WorkPackLink |  | NEVER | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2023-06-30 | 0 |  |  |  |  | NEVER |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 |  | 0030 | Fab/Install Section 2 Drain Line(1 Bend) | INT | Fab/Install Section 2 Drain Line(1 Bend) | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000137964 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT9 | Released | 2024-01-02 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | ROTAT | 100040408 | 0025 | 0040 | 100040408 | MV-RE 40NB 300# 409BAV0034 GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 255 | WO item has not been released yet | 10602157 | CONTAINER,SPILL,BUND,1900X1500X750MM | 1 | EA | 0 | 0 | 0 | 0 |  | 19.01 - PR Never Line item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000138900 | 1 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-06-08 | 0 |  |  |  |  | GT4009 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10602157 | CONTAINER,SPILL,BUND,1900X1500X750MM |  | 0025 | Set Up Site & Drain Oil From Tank | INT | Set Up Site & Drain Oil From Tank | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000138310 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT9 | Released | 2024-01-02 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | ROTAT | 100040408 | 0025 | 0050 | 100040408 | MV-RE 40NB 300# 409BAV0034 GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 255 | WO item has not been released yet | 10567763 | CONTAINER;IBC,1000L,1000X1200MM | 1 | EA | 9 | 0 | 0 | 0 |  | 19.01 - PR Never Line item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000138900 | 2 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-06-08 | 0 |  |  |  |  | GT4009 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10567763 | CONTAINER;IBC,1000L,1000X1200MM |  | 0025 | Set Up Site & Drain Oil From Tank | INT | Set Up Site & Drain Oil From Tank | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000138310 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT9 | Released | 2024-01-02 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | ROTAT | 100040408 | 0030 | 0020 | 100040408 | MV-RE 40NB 300# 409BAV0034 GT4009 | AA53.GT4009 | TURB,GAS FOR G4009 | AA01 | 255 | WO item has not been released yet | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 2 | EA | 83 | 0 | 0 | 0 |  | 19.01 - PR Never Line item | Supply Process could not be determined for item 4, material 10060918 Plant AA53, check config. |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000138900 | 4 | 0 | [9 empty] | WorkPackLink |  | NEVER | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2024-06-08 | 0 |  |  |  |  | NEVER |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 |  | 0030 | Remove & Replace Valve | INT | Remove & Replace Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000138310 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT10 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | ROTAT | 100040409 | 0101 | 0040 | 100040409 | MV-RE 40NB 300# 410BAV0034 GT4010 | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 255 | WO item has not been released yet | 10567763 | CONTAINER;IBC,1000L,1000X1200MM | 1 | EA | 9 | 0 | 0 | 0 |  | 19.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000138961 | 4 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-06-09 | 0 |  |  |  |  | 100040409 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10567763 | CONTAINER;IBC,1000L,1000X1200MM |  | 0101 | Punchlist & Closeout WP100040409IET001 | ENON | Punchlist & Closeout WP100040409IET001 | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000138311 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT10 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | ROTAT | 100040409 | 0031 | 0020 | 100040409 | MV-RE 40NB 300# 410BAV0034 GT4010 | AA53.GT4010 | TURB,GAS FOR G4010 |  | 255 | WO item has not been released yet | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 2 | EA | 0 | 0 | 0 | 0 |  | 19.01 - PR Never Line Item | Supply Process could not be determined for item 2, material 10060918 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000138961 | 2 | 0 | [9 empty] | WorkPackLink |  | NEVER | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2024-06-09 | 0 |  |  |  |  | NEVER |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 |  | 0031 | Remove & Replace Valve | INT | Remove & Replace Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000138311 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT10 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | ROTAT | 100040409 | 0101 | 0030 | 100040409 | MV-RE 40NB 300# 410BAV0034 GT4010 | AA53.GT4010 | TURB,GAS FOR G4010 | AA01 | 255 | WO item has not been released yet | 10602157 | CONTAINER,SPILL,BUND,1900X1500X750MM | 1 | EA | 0 | 0 | 0 | 0 |  | 19.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000138961 | 3 | 0 | [9 empty] | WorkPackLink |  | T24-W1-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-06-09 | 0 |  |  |  |  | 100040409 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10602157 | CONTAINER,SPILL,BUND,1900X1500X750MM |  | 0101 | Punchlist & Closeout WP100040409IET001 | ENON | Punchlist & Closeout WP100040409IET001 | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000138311 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT7 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | ROTAT | 100040411 | 0025 | 0030 | 100040411 | MV-RE 40NB 300# 407BAV0027 GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 255 | WO item has not been released yet | 10602157 | CONTAINER,SPILL,BUND,1900X1500X750MM | 1 | EA | 0 | 0 | 0 | 0 |  | 23.01 - PR Never line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000138963 | 1 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-06-09 | 0 |  |  |  |  | GT-4007 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10602157 | CONTAINER,SPILL,BUND,1900X1500X750MM |  | 0025 | Set Up Site & Drain Oil From Tank | INT | Set Up Site & Drain Oil From Tank | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000138313 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT7 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | ROTAT | 100040411 | 0030 | 0020 | 100040411 | MV-RE 40NB 300# 407BAV0027 GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 |  | 255 | WO item has not been released yet | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 | 2 | EA | 0 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item | Supply Process could not be determined for item 4, material 10060918 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000138963 | 4 | 0 | [9 empty] | WorkPackLink |  | NEVER | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2024-06-09 | 0 |  |  |  |  | NEVER |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060918 | GASKET;SWCI,40MM,CL300/600,316L/GR/316 |  | 0030 | Remove & Replace Valve | INT | Remove & Replace Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000138313 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT7 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | ROTAT | 100040411 | 0025 | 0040 | 100040411 | MV-RE 40NB 300# 407BAV0027 GT4007 | AA53.GT4007 | TURB,GAS FOR G4007 | AA01 | 255 | WO item has not been released yet | 10567763 | CONTAINER;IBC,1000L,1000X1200MM | 1 | EA | 9 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000138963 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-06-09 | 0 |  |  |  |  | GT-4007 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10567763 | CONTAINER;IBC,1000L,1000X1200MM |  | 0025 | Set Up Site & Drain Oil From Tank | INT | Set Up Site & Drain Oil From Tank | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000138313 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Printed/Material shortage | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDFR2 | Released | 2024-01-02 | 2024-04-23 |  | 2024-04-23 | 2024-09-14 | VALVE | 100040576 | 0010 | 0100 | 100040576 | CV-OH 2" 300# 218PCV507 | AA53.218PCV507 | VALVE,2K1820E1 L/O PRESS CTRL | AA01 | 20 | WO item has not been released yet | 10491108 | STUDBOLT;0.625" X 90MM,L7,BLK | 8 | EA | 16 | 0 | 0 | 0 |  | 24/01 PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139148 | 5 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-31 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | STUDBOLT;0.625" X 90MM,L7,BLK |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000138478 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Released/Pre-costed/Order Approved/Date set by external system/Settlement rule created/Object created/Printed/Material shortage | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDFR2 | Released | 2024-01-02 | 2024-04-23 |  | 2024-04-23 | 2024-09-14 | VALVE | 100040576 | 0010 | 0110 | 100040576 | CV-OH 2" 300# 218PCV507 | AA53.218PCV507 | VALVE,2K1820E1 L/O PRESS CTRL | AA01 | 20 | WO item has not been released yet | 10060919 | GASKET;SWCI,50MM,CL300/600,316L/GR/316 | 2 | EA | 347 | 0 | 0 | 0 |  | 24/01 PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139148 | 6 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-31 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET;SWCI,50MM,CL300/600,316L/GR/316 |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000138478 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Released/Pre-costed/Order Approved/Date set by external system/Settlement rule created/Object created/Printed/Material shortage | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDFR2 | Released | 2024-01-02 | 2024-04-23 |  | 2024-04-23 | 2024-09-14 | VALVE | 100040577 | 0010 | 0120 | 100040577 | CV-OH 1" 300# 218PDCV506 | AA53.218PDCV506 | VALVE,2K1820E1 S/OIL PRESS CTRL | AA01 | 20 | WO item has not been released yet | 10491108 | STUDBOLT;0.625" X 90MM,L7,BLK | 8 | EA | 16 | 0 | 0 | 0 |  | 24/01 PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139149 | 9 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-31 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | STUDBOLT;0.625" X 90MM,L7,BLK |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000138479 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Order Approved/Printed/Object created/Date set by external system/Pre-costed/Released/Settlement rule created/Material shortage | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDFR2 | Released | 2024-01-02 | 2024-04-23 |  | 2024-04-23 | 2024-09-14 | VALVE | 100040577 | 0010 | 0110 | 100040577 | CV-OH 1" 300# 218PDCV506 | AA53.218PDCV506 | VALVE,2K1820E1 S/OIL PRESS CTRL | AA01 | 20 | WO item has not been released yet | 10060917 | GASKET;SWCI,25MM,CL300/600,316L/GR/316 | 2 | EA | 388 | 0 | 0 | 0 |  | 24/01 PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139149 | 8 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-12-31 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060917 | GASKET;SWCI,25MM,CL300/600,316L/GR/316 |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000138479 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-09-14 | 2024-04-23 | 2024-04-23 | Order Approved/Printed/Object created/Date set by external system/Pre-costed/Released/Settlement rule created/Material shortage | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDFR3 | Released | 2024-01-02 | 2024-05-06 |  | 2024-05-06 | 2024-05-08 | MECH | 100040754 | 0020 | 0030 | 100040754 | Repair Fin Fan Plug Header weep-3K1820E1 | AA53.3K1820E1 | EXCH,LUBE OIL COOLER | AA01 | 30 | WO item has not been released yet | 10060884 | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR | 4 | EA | 40 | 0 | 0 | 0 |  | 24/01 PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000139255 | 3 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-06 |  |  | 2024-05-06 |  |  |  |  | 2023-06-19 | 0 |  |  |  |  | 2100347950 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060884 | GASKET,SW;40MM,CL150,4.5MM,SS316L,GR |  | 0020 | Inspect and Tighten the plugs | INT | Inspect and Tighten the plugs | 5 | [9 empty] | 0060 | Ready to Schedule (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SDFR3 | MJ |  | 1000138664 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-08 | 2024-05-06 | 2024-05-06 | Ready For Scheduling/Pre-costed/Settlement rule created/Released/Order Approved/Object created/Printed/Date set by external system/Material committed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDFR3 | Released | 2024-01-02 | 2024-05-06 |  | 2024-05-06 | 2024-05-08 | MECH | 100040754 | 0020 | 0040 | 100040754 | Repair Fin Fan Plug Header weep-3K1820E1 | AA53.3K1820E1 | EXCH,LUBE OIL COOLER | AA01 | 30 | WO item has not been released yet | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 16 | EA | 0 | 0 | 0 | 0 |  | 24/01 PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000139255 | 4 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-06 |  |  | 2024-05-06 |  |  |  |  | 2023-06-19 | 0 |  |  |  |  | 2100347950 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 |  | 0020 | Inspect and Tighten the plugs | INT | Inspect and Tighten the plugs | 5 | [9 empty] | 0060 | Ready to Schedule (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SDFR3 | MJ |  | 1000138664 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-08 | 2024-05-06 | 2024-05-06 | Ready For Scheduling/Pre-costed/Settlement rule created/Released/Order Approved/Object created/Printed/Date set by external system/Material committed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDFR3 | Released | 2024-01-02 | 2024-05-06 |  | 2024-05-06 | 2024-05-08 | MECH | 100040754 | 0020 | 0050 | 100040754 | Repair Fin Fan Plug Header weep-3K1820E1 | AA53.3K1820E1 | EXCH,LUBE OIL COOLER | AA01 | 30 | WO item has not been released yet | 10416852 | GASKET;GEA BATIG 1643261101RARBRC1 | 40 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP97 | Direct Multi-base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000139255 | 5 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 40 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-06 | [7 empty] | 2023-06-19 | 0 |  |  |  |  | 2100347950 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10416852 | GASKET;GEA BATIG 1643261101RARBRC1 |  | 0020 | Inspect and Tighten the plugs | INT | Inspect and Tighten the plugs | 5 | [9 empty] | 0060 | Ready to Schedule (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SDFR3 | MJ |  | 1000138664 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-08 | 2024-05-06 | 2024-05-06 | Ready For Scheduling/Pre-costed/Settlement rule created/Released/Order Approved/Object created/Printed/Date set by external system/Material committed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDFR3 | Released | 2024-01-02 | 2024-05-06 |  | 2024-05-06 | 2024-05-08 | MECH | 100040754 | 0020 | 0060 | 100040754 | Repair Fin Fan Plug Header weep-3K1820E1 | AA53.3K1820E1 | EXCH,LUBE OIL COOLER |  | 30 | WO item has not been released yet | 10418741 | PLUG,HEX,1.125" X 26MM LG,12UNF,F316L | 10 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink | Supply Process could not be determined for item 6, material 10418741 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000139255 | 6 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 10 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-06 | [7 empty] | 2023-06-19 | 0 |  |  |  |  | 2100347950 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS |  | 10418741 | PLUG,HEX,1.125" X 26MM LG,12UNF,F316L |  | 0020 | Inspect and Tighten the plugs | INT | Inspect and Tighten the plugs | 5 | [9 empty] | 0060 | Ready to Schedule (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SDFR3 | MJ |  | 1000138664 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-08 | 2024-05-06 | 2024-05-06 | Ready For Scheduling/Pre-costed/Settlement rule created/Released/Order Approved/Object created/Printed/Date set by external system/Material committed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SD4403 | Released | 2024-01-02 | 2024-05-07 |  | 2024-05-07 | 2024-05-07 | VALVE | 100041467 | 0010 | 0060 | 100041467 | CV-OH 2" 300# 44PCV523 | AA53.44PCV523 | VALVE,PRESS K4403 LUBEOIL TNK RECYC |  | 30 | WO item has not been released yet | 10060919 | GASKET;SWCI,50MM,CL300/600,316L/GR/316 | 2 | EA | 0 | 0 | 0 | 0 |  | 24/01 PR Never Line Item | Supply Process could not be determined for item 2, material 10060919 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139988 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-07 | [7 empty] | 2019-09-13 | 0 |  |  |  |  | 2100338885 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET;SWCI,50MM,CL300/600,316L/GR/316 |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SD4403 | MJ |  | 1000139337 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-07 | 2024-05-07 | 2024-05-07 | Printed/Material shortage/Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved | AM01 | Reactive Maintenance |  | PR Never
1 | 24SD4403 | Released | 2024-01-02 | 2024-05-07 |  | 2024-05-07 | 2024-05-07 | VALVE | 100041467 | 0010 | 0070 | 100041467 | CV-OH 2" 300# 44PCV523 | AA53.44PCV523 | VALVE,PRESS K4403 LUBEOIL TNK RECYC |  | 30 | WO item has not been released yet | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 | 16 | EA | 0 | 0 | 0 | 0 |  | 24/01 PR Never Line Item | Supply Process could not be determined for item 3, material 10058199 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139988 | 3 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-07 | [7 empty] | 2019-09-13 | 0 |  |  |  |  | 2100338885 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SD4403 | MJ |  | 1000139337 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-07 | 2024-05-07 | 2024-05-07 | Printed/Material shortage/Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved | AM01 | Reactive Maintenance |  | PR Never
1 | 24SD4403 | Released | 2024-01-02 | 2024-05-07 |  | 2024-05-07 | 2024-05-07 | VALVE | 100041467 | 0010 | 0080 | 100041467 | CV-OH 2" 300# 44PCV523 | AA53.44PCV523 | VALVE,PRESS K4403 LUBEOIL TNK RECYC | AA01 | 30 | WO item has not been released yet | 10049289 | FLANGE,BLIND;50MM,CL300,RF,SS316 | 2 | EA | 0 | 0 | 0 | 0 |  | PR NEVER |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000139988 | 4 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-07 |  |  | 2024-05-07 |  |  |  |  | 2019-09-13 | 0 |  |  |  |  | 2100338885 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10049289 | FLANGE,BLIND;50MM,CL300,RF,SS316 |  | 0010 | Isolate & Disconnect Valve | INT | Isolate & Disconnect Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SD4403 | MJ |  | 1000139337 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-07 | 2024-05-07 | 2024-05-07 | Printed/Material shortage/Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved | AM01 | Reactive Maintenance |  | PR Never
1 | 24SD3410 | Released | 2024-01-02 | 2024-05-06 |  | 2024-05-06 | 2024-05-18 | MECH | 100042777 | 0040 | 0040 | 100042777 | Replace Reservoir Sight Glass - K3410BV3 | AA53.K3410BV3 | TANK,RESERVOIR LUBE OIL |  | 255 | WO item has not been released yet | 10434236 | OIL,LUB;TURBO,SHELL T46,1000L | 2 | CON | 0 | 0 | 0 | 0 |  | 24/01 PR Never Line Item | Supply Process could not be determined for item 2, material 10434236 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | CON | [5 empty] | 06 | Scheduling | 0000141321 | 2 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-06 | [7 empty] | 2023-03-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10434236 | OIL,LUB;TURBO,SHELL T46,1000L |  | 0040 | Rem/Replace sight glass & gaskets | INT | Rem/Replace sight glass & gaskets | 5 | [9 empty] | 0060 | Ready to Schedule (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SD3410 | MJ |  | 1000140692 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-18 | 2024-05-06 | 2024-05-06 | Object created/Material shortage/Pre-costed/Order Approved/Date set by external system/Released/Settlement rule created/Printed/Ready For Scheduling | AM01 | Reactive Maintenance |  | PR Never
1 | 24SD3410 | Released | 2024-01-02 | 2024-05-06 |  | 2024-05-06 | 2024-05-18 | MECH | 100042777 | 0040 | 0050 | 100042777 | Replace Reservoir Sight Glass - K3410BV3 | AA53.K3410BV3 | TANK,RESERVOIR LUBE OIL |  | 255 | WO item has not been released yet | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 | 4 | EA | 0 | 0 | 0 | 0 |  | 24/01 PR Never Line Item | Supply Process could not be determined for item 3, material 10058199 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000141321 | 3 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-06 | [7 empty] | 2023-03-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 |  | 0040 | Rem/Replace sight glass & gaskets | INT | Rem/Replace sight glass & gaskets | 5 | [9 empty] | 0060 | Ready to Schedule (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SD3410 | MJ |  | 1000140692 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-18 | 2024-05-06 | 2024-05-06 | Object created/Material shortage/Pre-costed/Order Approved/Date set by external system/Released/Settlement rule created/Printed/Ready For Scheduling | AM01 | Reactive Maintenance |  | PR Never
1 | 24SD3410 | Released | 2024-01-02 | 2024-05-06 |  | 2024-05-06 | 2024-05-18 | MECH | 100042777 | 0040 | 0060 | 100042777 | Replace Reservoir Sight Glass - K3410BV3 | AA53.K3410BV3 | TANK,RESERVOIR LUBE OIL | AA01 | 255 | WO item has not been released yet | 10060885 | GASKET;SWCI,50MM,CL150,316L/GR/316 | 2 | EA | 2 | 0 | 0 | 0 |  | 22.03 - qty 312 SOH at AA01 |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000141321 | 4 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-06 |  |  | 2024-05-06 |  |  |  |  | 2023-03-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060885 | GASKET;SWCI,50MM,CL150,316L/GR/316 |  | 0040 | Rem/Replace sight glass & gaskets | INT | Rem/Replace sight glass & gaskets | 5 | [9 empty] | 0060 | Ready to Schedule (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SD3410 | MJ |  | 1000140692 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-18 | 2024-05-06 | 2024-05-06 | Object created/Material shortage/Pre-costed/Order Approved/Date set by external system/Released/Settlement rule created/Printed/Ready For Scheduling | AM01 | Reactive Maintenance |  | PR Never
1 | 24SD3410 | Released | 2024-01-02 | 2024-05-06 |  | 2024-05-06 | 2024-05-18 | MECH | 100042777 | 0040 | 0070 | 100042777 | Replace Reservoir Sight Glass - K3410BV3 | AA53.K3410BV3 | TANK,RESERVOIR LUBE OIL |  | 255 | WO item has not been released yet | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 | 4 | EA | 0 | 0 | 0 | 0 |  | UserCommentLink | Supply Process could not be determined for item 5, material 10058199 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000141321 | 5 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-06 | [7 empty] | 2023-03-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 |  | 0040 | Rem/Replace sight glass & gaskets | INT | Rem/Replace sight glass & gaskets | 5 | [9 empty] | 0060 | Ready to Schedule (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SD3410 | MJ |  | 1000140692 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-18 | 2024-05-06 | 2024-05-06 | Object created/Material shortage/Pre-costed/Order Approved/Date set by external system/Released/Settlement rule created/Printed/Ready For Scheduling | AM01 | Reactive Maintenance |  | PR Never
1 | 24SD3410 | Released | 2024-01-02 | 2024-05-06 |  | 2024-05-06 | 2024-05-18 | MECH | 100042777 | 0040 | 0080 | 100042777 | Replace Reservoir Sight Glass - K3410BV3 | AA53.K3410BV3 | TANK,RESERVOIR LUBE OIL | AA01 | 255 | WO item has not been released yet | 10060887 | GASKET;SWCI,100MM,CL150,316L/GR/316 | 2 | EA | 21 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000141321 | 6 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-06 |  |  | 2024-05-06 |  |  |  |  | 2023-03-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060887 | GASKET;SWCI,100MM,CL150,316L/GR/316 |  | 0040 | Rem/Replace sight glass & gaskets | INT | Rem/Replace sight glass & gaskets | 5 | [9 empty] | 0060 | Ready to Schedule (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SD3410 | MJ |  | 1000140692 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-18 | 2024-05-06 | 2024-05-06 | Object created/Material shortage/Pre-costed/Order Approved/Date set by external system/Released/Settlement rule created/Printed/Ready For Scheduling | AM01 | Reactive Maintenance |  | PR Never
1 | 24SD4401 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-02 | 2024-05-03 | VALVE | 100043677 | 0010 | 0030 | 100043677 | MV-RE 12" 300# 44GAV0277 | AA53.K4401C | COMPR,FUEL GAS BOOSTER | AA01 | 30 | WO item has not been released yet | 10491125 | STUDBOLT;1.125" X 170MM,L7,BLK | 32 | EA | 0 | 0 | 0 | 0 |  | 24/01 PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142209 | 3 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 32 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2020-11-02 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491125 | STUDBOLT;1.125" X 170MM,L7,BLK |  | 0010 | Remove Valve | INT | Remove Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SD4401 | MJ |  | 1000141579 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-03 | 2024-05-02 | 2024-05-02 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | PR Never
1 | 24SD4401 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-02 | 2024-05-03 | VALVE | 100043677 | 0010 | 0020 | 100043677 | MV-RE 12" 300# 44GAV0277 | AA53.K4401C | COMPR,FUEL GAS BOOSTER | AA01 | 30 | WO item has not been released yet | 10060905 | GASKET;SWCI,300MM,CL300,316L/GR/316 | 2 | EA | 8 | 0 | 0 | 0 |  | 24/01 PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142209 | 2 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2020-11-02 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060905 | GASKET;SWCI,300MM,CL300,316L/GR/316 |  | 0010 | Remove Valve | INT | Remove Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SD4401 | MJ |  | 1000141579 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-03 | 2024-05-02 | 2024-05-02 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT10 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-05 | ROTAT | 100043858 | 0020 | 0010 | 100043858 | GT4010A3 Starter Package Hose Replacemen | AA53.GT4010A3 | PKG EQ,GT4010A3 HYDRAULIC STARTING SKID | AA01 | 30 | WO item has not been released yet | 10561030 | HOSE ASY,HYD;1.25"X1.1M,25000KPAG | 1 | EA | 0 | 0 | 0 | 0 |  | 19.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142379 | 1 | 0 | [9 empty] | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2020-12-31 | 0 |  |  |  |  | GT4010HSHY01 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10561030 | HOSE ASY,HYD;1.25"X1.1M,25000KPAG |  | 0020 | old info for hoses, set to never- verify | INT | old info for hoses, set to never- verify | 3 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000141788 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-05 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material shortage | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT10 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-05 | ROTAT | 100043858 | 0020 | 0040 | 100043858 | GT4010A3 Starter Package Hose Replacemen | AA53.GT4010A3 | PKG EQ,GT4010A3 HYDRAULIC STARTING SKID | AA01 | 30 | WO item has not been released yet | 10561033 | HOSE ASY,HYD;1"X1.3M,16500KPAG | 1 | EA | 0 | 0 | 0 | 0 |  | 19.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142379 | 4 | 0 | [9 empty] | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2020-12-31 | 0 |  |  |  |  | GT4010HSHY04 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10561033 | HOSE ASY,HYD;1"X1.3M,16500KPAG |  | 0020 | old info for hoses, set to never- verify | INT | old info for hoses, set to never- verify | 3 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000141788 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-05 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material shortage | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT10 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-05 | ROTAT | 100043858 | 0020 | 0060 | 100043858 | GT4010A3 Starter Package Hose Replacemen | AA53.GT4010A3 | PKG EQ,GT4010A3 HYDRAULIC STARTING SKID | AA01 | 30 | WO item has not been released yet | 10561035 | HOSE ASY,HYD;1"X1.5M,16500KPAG | 1 | EA | 0 | 0 | 0 | 0 |  | 19.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142379 | 6 | 0 | [9 empty] | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2020-12-31 | 0 |  |  |  |  | GT4010HSHY06 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10561035 | HOSE ASY,HYD;1"X1.5M,16500KPAG |  | 0020 | old info for hoses, set to never- verify | INT | old info for hoses, set to never- verify | 3 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000141788 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-05 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material shortage | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT10 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-05 | ROTAT | 100043858 | 0020 | 0050 | 100043858 | GT4010A3 Starter Package Hose Replacemen | AA53.GT4010A3 | PKG EQ,GT4010A3 HYDRAULIC STARTING SKID | AA01 | 30 | WO item has not been released yet | 10561034 | HOSE ASY,HYD;1"X1.12M,16500KPAG | 1 | EA | 0 | 0 | 0 | 0 |  | 19.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142379 | 5 | 0 | [9 empty] | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2020-12-31 | 0 |  |  |  |  | GT4010HSHY05 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10561034 | HOSE ASY,HYD;1"X1.12M,16500KPAG |  | 0020 | old info for hoses, set to never- verify | INT | old info for hoses, set to never- verify | 3 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000141788 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-05 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material shortage | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT10 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-05 | ROTAT | 100043858 | 0020 | 0020 | 100043858 | GT4010A3 Starter Package Hose Replacemen | AA53.GT4010A3 | PKG EQ,GT4010A3 HYDRAULIC STARTING SKID | AA01 | 30 | WO item has not been released yet | 10561031 | HOSE ASY,HYD;1.25"X1.75M,42000KPAG | 1 | EA | 0 | 0 | 0 | 0 |  | 19.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142379 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2020-12-31 | 0 |  |  |  |  | GT4010HSHY02 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10561031 | HOSE ASY,HYD;1.25"X1.75M,42000KPAG |  | 0020 | old info for hoses, set to never- verify | INT | old info for hoses, set to never- verify | 3 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000141788 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-05 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material shortage | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT10 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-05 | ROTAT | 100043858 | 0020 | 0070 | 100043858 | GT4010A3 Starter Package Hose Replacemen | AA53.GT4010A3 | PKG EQ,GT4010A3 HYDRAULIC STARTING SKID | AA01 | 30 | WO item has not been released yet | 10561036 | HOSE ASY,HYD;1"X1.5M,16500KPAG | 1 | EA | 0 | 0 | 0 | 0 |  | At PR Never |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142379 | 7 | 0 | [9 empty] | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2020-12-31 | 0 |  |  |  |  | GT4010HSHY07 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10561036 | HOSE ASY,HYD;1"X1.5M,16500KPAG |  | 0020 | old info for hoses, set to never- verify | INT | old info for hoses, set to never- verify | 3 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000141788 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-05 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material shortage | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT10 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-05 | ROTAT | 100043858 | 0020 | 0030 | 100043858 | GT4010A3 Starter Package Hose Replacemen | AA53.GT4010A3 | PKG EQ,GT4010A3 HYDRAULIC STARTING SKID |  | 30 | WO item has not been released yet | 10561032 | HOSE ASY,HYD;1"X0.69M,16500KPAG | 1 | EA | 0 | 0 | 0 | 0 |  | 19.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000142379 | 3 | 0 | [9 empty] | WorkPackLink |  | AU01P08-UT | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2020-12-31 | 0 |  |  |  |  | GT4010HSHY03 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10561032 | HOSE ASY,HYD;1"X0.69M,16500KPAG |  | 0020 | old info for hoses, set to never- verify | INT | old info for hoses, set to never- verify | 3 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000141788 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-05 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Estimated costs/Material shortage | AM01 | Reactive Maintenance |  | PR Never
1 | 24SD3410 | Released | 2024-01-02 | 2024-05-06 |  | 2024-05-06 | 2024-05-18 | VALVE | 100046014 | 0020 | 0100 | 100046014 | MV-RE 2" 300# 134GAV1111 | AA53.K3410AS3B | FILT,BUFFER GAS | AA01 | 20 | WO item has not been released yet | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 | 16 | EA | 212 | 0 | 0 | 0 |  | 24/01 PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000144515 | 2 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 16 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-06 |  |  | 2024-05-06 |  |  |  |  | 2018-12-07 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058199 | STUDBOLT;0.625" X 90MM,A193 B8M CL2 |  | 0020 | Remove/Replace Valve | INT | Remove/Replace Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SD3410 | MJ |  | 1000143964 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-18 | 2024-05-06 | 2024-05-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SD3410 | Released | 2024-01-02 | 2024-05-06 |  | 2024-05-06 | 2024-05-18 | VALVE | 100046014 | 0020 | 0110 | 100046014 | MV-RE 2" 300# 134GAV1111 | AA53.K3410AS3B | FILT,BUFFER GAS | AA01 | 20 | WO item has not been released yet | 10060919 | GASKET;SWCI,50MM,CL300/600,316L/GR/316 | 2 | EA | 347 | 0 | 0 | 0 |  | 24/01 PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000144515 | 3 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-06 |  |  | 2024-05-06 |  |  |  |  | 2018-12-07 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060919 | GASKET;SWCI,50MM,CL300/600,316L/GR/316 |  | 0020 | Remove/Replace Valve | INT | Remove/Replace Valve | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SD3410 | MJ |  | 1000143964 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-18 | 2024-05-06 | 2024-05-06 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material shortage/Printed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT9 | Released | 2024-01-02 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | ROTAT | 100046883 | 0020 | 0062 | 100046883 | 409LG504 Clean Oil Sampling Valve | AA53.409LG504 | GAUGE,LEVEL GT4009V3 STARTING OIL TANK | AA01 | 255 | WO item has not been released yet | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 | 8 | EA | 0 | 0 | 0 | 0 |  | PR NEVER |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000145404 | 5 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2018-09-14 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058193 | STUDBOLT;0.500" X 75MM,A193 B8M CL2 |  | 0020 | REMOVE / REPLACE UPPER & LOWER GAUGE | INT | REMOVE / REPLACE UPPER & LOWER GAUGE | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000144753 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT9 | Released | 2024-01-02 | 2024-05-19 |  | 2024-05-19 | 2024-05-19 | ROTAT | 100046883 | 0020 | 0052 | 100046883 | 409LG504 Clean Oil Sampling Valve | AA53.409LG504 | GAUGE,LEVEL GT4009V3 STARTING OIL TANK | AA01 | 255 | WO item has not been released yet | 10060882 | GASKET;SWCI,20MM,CL150,316L/GR/316 | 2 | EA | 41 | 0 | 0 | 0 |  | PR NEVER |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000145404 | 4 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 2 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-19 |  |  | 2024-05-19 |  |  |  |  | 2018-09-14 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060882 | GASKET;SWCI,20MM,CL150,316L/GR/316 |  | 0020 | REMOVE / REPLACE UPPER & LOWER GAUGE | INT | REMOVE / REPLACE UPPER & LOWER GAUGE | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT9 | MJ |  | 1000144753 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-19 | 2024-05-19 | 2024-05-19 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Order Approved/Material committed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT7 | Released | 2024-01-02 | 2024-05-04 |  | 2024-05-04 | 2024-05-08 | ROTAT | 100067619 | 0231 | 0090 | 100067619 | MOC-111548 G4007S2M1 Louvre and Motor fa | AA53.G4007S2M1 | MOTOR,GEN AIR FILTER OUTLET LOUVRE G4007 | AA01 | 255 | WO item has not been released yet | 10518803 | WASHER,FLAT;M8,316SS | 200 | EA | 0 | 0 | 0 | 0 |  | 29.01 - PR Never Line item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000212678 | 8 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 200 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-04 |  |  | 2024-05-04 |  |  |  |  | 2024-10-10 | 0 |  |  |  |  | 2100353335 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10518803 | WASHER,FLAT;M8,316SS |  | 0231 | Remediation works On Louver | INT | Remediation works On Louver | 3 | Management of Change | [8 empty] | 0060 | Ready to Schedule (Order) | ZBPM0001 | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000211796 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Management of Change |  |  | 1070 |  | 2024-03-25 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-31 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-08 | 2024-05-04 | 2024-05-04 | Released/Settlement rule created/Partially confirmed/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT7 | Released | 2024-01-02 | 2024-05-04 |  | 2024-05-04 | 2024-05-08 | ROTAT | 100067619 | 0231 | 0070 | 100067619 | MOC-111548 G4007S2M1 Louvre and Motor fa | AA53.G4007S2M1 | MOTOR,GEN AIR FILTER OUTLET LOUVRE G4007 | AA01 | 255 | WO item has not been released yet | 10058022 | BOLT;HEX HD,M8X35MM,ISO 3506-1/2,W/NUT | 100 | EA | 0 | 0 | 0 | 0 |  | 29.01 - PR Never Line item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000212678 | 6 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 100 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-04 |  |  | 2024-05-04 |  |  |  |  | 2024-10-10 | 0 |  |  |  |  | 2100353335 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058022 | BOLT;HEX HD,M8X35MM,ISO 3506-1/2,W/NUT |  | 0231 | Remediation works On Louver | INT | Remediation works On Louver | 3 | Management of Change | [8 empty] | 0060 | Ready to Schedule (Order) | ZBPM0001 | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000211796 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Management of Change |  |  | 1070 |  | 2024-03-25 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-31 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-08 | 2024-05-04 | 2024-05-04 | Released/Settlement rule created/Partially confirmed/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT7 | Released | 2024-01-02 | 2024-05-04 |  | 2024-05-04 | 2024-05-08 | ROTAT | 100067619 | 0231 | 0060 | 100067619 | MOC-111548 G4007S2M1 Louvre and Motor fa | AA53.G4007S2M1 | MOTOR,GEN AIR FILTER OUTLET LOUVRE G4007 | AA01 | 255 | WO item has not been released yet | 10442912 | SCREW,SET;HEX HD,M8 X 35MM,SS316L A4/80 | 100 | EA | 0 | 0 | 0 | 0 |  | 29.01 - PR Never Line item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000212678 | 5 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 100 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-04 |  |  | 2024-05-04 |  |  |  |  | 2024-10-10 | 0 |  |  |  |  | 2100353335 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10442912 | SCREW,SET;HEX HD,M8 X 35MM,SS316L A4/80 |  | 0231 | Remediation works On Louver | INT | Remediation works On Louver | 3 | Management of Change | [8 empty] | 0060 | Ready to Schedule (Order) | ZBPM0001 | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000211796 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Management of Change |  |  | 1070 |  | 2024-03-25 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-31 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-08 | 2024-05-04 | 2024-05-04 | Released/Settlement rule created/Partially confirmed/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDGT7 | Released | 2024-01-02 | 2024-05-04 |  | 2024-05-04 | 2024-05-08 | ROTAT | 100067619 | 0231 | 0080 | 100067619 | MOC-111548 G4007S2M1 Louvre and Motor fa | AA53.G4007S2M1 | MOTOR,GEN AIR FILTER OUTLET LOUVRE G4007 | AA01 | 255 | WO item has not been released yet | 10480299 | WASHER,SPRG;M8,316SS | 100 | EA | 0 | 0 | 0 | 0 |  | 29.01 - PR Never Line item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000212678 | 7 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 100 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-04 |  |  | 2024-05-04 |  |  |  |  | 2024-10-10 | 0 |  |  |  |  | 2100353335 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10480299 | WASHER,SPRG;M8,316SS |  | 0231 | Remediation works On Louver | INT | Remediation works On Louver | 3 | Management of Change | [8 empty] | 0060 | Ready to Schedule (Order) | ZBPM0001 | 0 | [9 empty] | 99 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000211796 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 |  |  | Management of Change |  |  | 1070 |  | 2024-03-25 | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-31 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-08 | 2024-05-04 | 2024-05-04 | Released/Settlement rule created/Partially confirmed/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Order Approved/Material committed/Part printed | AM01 | Reactive Maintenance |  | PR Never
1 | 24SDFR2 | Released | 2024-01-02 | 2024-04-23 |  | 2024-04-23 | 2024-09-10 | WORK | 200064070 | 0020 | 0050 | 200064070 | 9Y F21 RECERTIFY SC PSV ROTABLE | AA53.218RV13 | PSV,2V1805 ON 2" LINE 2W41534 | AA01 | 10 | WO item has not been released yet | 10491108 | STUDBOLT;0.625" X 90MM,L7,BLK | 4 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000098352 | 9 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-07-03 | 0 |  |  |  |  | 218RV13 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | STUDBOLT;0.625" X 90MM,L7,BLK |  | 0020 | REMOVE / INSTALL PSV | INT | REMOVE / INSTALL PSV | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000097789 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-09-10 | 2024-04-23 | 2024-04-23 | Material shortage/Date set by external system/Object created/Pre-costed/Released/Settlement rule created | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDFR2 | Released | 2024-01-02 | 2024-04-23 |  | 2024-04-23 | 2024-09-10 | WORK | 200064070 | 0020 | 0040 | 200064070 | 9Y F21 RECERTIFY SC PSV ROTABLE | AA53.218RV13 | PSV,2V1805 ON 2" LINE 2W41534 | AA01 | 10 | WO item has not been released yet | 10491108 | STUDBOLT;0.625" X 90MM,L7,BLK | 4 | EA | 16 | 0 | 0 | 0 |  | UserCommentLink |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000098352 | 8 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-23 |  |  | 2024-04-23 |  |  |  |  | 2024-07-03 | 0 |  |  |  |  | 218RV13 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491108 | STUDBOLT;0.625" X 90MM,L7,BLK |  | 0020 | REMOVE / INSTALL PSV | INT | REMOVE / INSTALL PSV | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000097789 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-09-10 | 2024-04-23 | 2024-04-23 | Material shortage/Date set by external system/Object created/Pre-costed/Released/Settlement rule created | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT8 | Released | 2024-01-02 | 2024-05-15 |  | 2024-05-15 | 2024-05-15 | ROTAT | 200065053 | 0010 | 0050 | 200065053 | 3Y GT4008 STARTER PKG FILTER REPLACEMENT | AA53.GT4008S7 | FILT,HYDRAULIC STARTER OIL GT4008 | AA01 | 20 | WO item has not been released yet | 10613434 | FILTER,HYD STARTER;NP ISM990645306 | 1 | EA | 0 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000099402 | 2 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-09-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10613434 | FILTER,HYD STARTER;NP ISM990645306 |  | 0010 | Remove & Replace Filters | INT | Remove & Replace Filters | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDGT8 | MJ |  | 1000098772 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT8 | Released | 2024-01-02 | 2024-05-15 |  | 2024-05-15 | 2024-05-15 | ROTAT | 200065053 | 0010 | 0060 | 200065053 | 3Y GT4008 STARTER PKG FILTER REPLACEMENT | AA53.GT4008S7 | FILT,HYDRAULIC STARTER OIL GT4008 | AA01 | 20 | WO item has not been released yet | 10412550 | FILTER,PIGNONE ISM990645338,RTN | 1 | EA | 0 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000099402 | 3 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-09-30 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10412550 | FILTER,PIGNONE ISM990645338,RTN |  | 0010 | Remove & Replace Filters | INT | Remove & Replace Filters | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDGT8 | MJ |  | 1000098772 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material shortage | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT7 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-03 | INLEC | 200066318 | 0010 | 0010 | 200066318 | 2Y F/Gas Valves Function Test (3) GT4007 | AA53.407UV501 | VALVE,CTRL FUEL GAS SHUTOFF GT4007 | AA01 | 10 | WO item has not been released yet | 10543991 | BOX,JCT;EX,XFB6639088759KTB453815 | 1 | EA | 0 | 0 | 0 | 0 |  | 20.02 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000100666 | 1 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-07-25 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10543991 | BOX,JCT;EX,XFB6639088759KTB453815 |  | 0010 | Function Test & Complete PRT / MITR's | INT | Function Test & Complete PRT / MITR's | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000100020 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Printed | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT10 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-03 | ROTAT | 200072140 | 0010 | 0010 | 200072140 | 1Y GT4010 AUXILIARIES GREASING | AA53.GT4010PM2 | MOTOR,GT4010 HYDRAULIC STARTER PUMP | AA01 | 20 | WO item has not been released yet | 10462794 | GREASE,GP;SHELL,GADUS S3 T100 2,450G | 1 | CQ | 19 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | CQ | [5 empty] | 05 | Preparation | 0000106442 | 1 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-06-02 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10462794 | GREASE,GP;SHELL,GADUS S3 T100 2,450G |  | 0010 | REGREASE BEARINGS IN ELECT STARTER MOTOR | INT | REGREASE BEARINGS IN ELECT STARTER MOTOR | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 20 |  | 0 |  | 0 |  | 24SDGT10 | MJ |  | 1000105819 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDLN3 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | INLEC | 200073275 | 0010 | 0020 | 200073275 | 2Y F06 FLAME EYES TEST/REPL (4) 3KT1410 | AA53.314XE306A | DET,U/V 3KT1410 TURB COMBUSTION CHBR #2 | AA01 | 10 | WO item has not been released yet | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 4 | EA | 155 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000107611 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-30 | 0 |  |  |  |  | 314XE306 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDLN3 | MJ |  | 1000107014 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDLN3 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | INLEC | 200073275 | 0010 | 0010 | 200073275 | 2Y F06 FLAME EYES TEST/REPL (4) 3KT1410 | AA53.314XE306A | DET,U/V 3KT1410 TURB COMBUSTION CHBR #2 |  | 10 | WO item has not been released yet | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 4 | EA | 0 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item | Supply Process could not be determined for item 1, material 10026470 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000107611 | 1 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2024-10-30 | 0 |  |  |  |  | 314XE306 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDLN3 | MJ |  | 1000107014 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDLN3 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | INLEC | 200073277 | 0010 | 0010 | 200073277 | 2Y F06 FLAME EYES TEST/REPL (4) 3KT1420 | AA53.314XE406A | DET,U/V 3KT1420 TURB COMBUSTION CHBR #2 |  | 10 | WO item has not been released yet | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 4 | EA | 0 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item | Supply Process could not be determined for item 1, material 10026470 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000107613 | 1 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2024-10-30 | 0 |  |  |  |  | 314XE406 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDLN3 | MJ |  | 1000107016 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Printed/Material committed/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDLN3 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | INLEC | 200073277 | 0010 | 0020 | 200073277 | 2Y F06 FLAME EYES TEST/REPL (4) 3KT1420 | AA53.314XE406A | DET,U/V 3KT1420 TURB COMBUSTION CHBR #2 | AA01 | 10 | WO item has not been released yet | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 4 | EA | 155 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000107613 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-30 | 0 |  |  |  |  | 314XE406 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDLN3 | MJ |  | 1000107016 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Printed/Material committed/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDLN3 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | INLEC | 200073278 | 0010 | 0010 | 200073278 | 2Y F06 FLAME EYES TEST/REPL (4) 3KT1430 | AA53.314XE506A | DET,U/V 3KT1430 TURB COMBUSTION CHBR #2 |  | 10 | WO item has not been released yet | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 4 | EA | 0 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item | Supply Process could not be determined for item 1, material 10026470 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000107614 | 1 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2024-10-30 | 0 |  |  |  |  | 314XE506A |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDLN3 | MJ |  | 1000107017 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed/Released | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDLN3 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | INLEC | 200073278 | 0010 | 0020 | 200073278 | 2Y F06 FLAME EYES TEST/REPL (4) 3KT1430 | AA53.314XE506A | DET,U/V 3KT1430 TURB COMBUSTION CHBR #2 | AA01 | 10 | WO item has not been released yet | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 4 | EA | 155 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000107614 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-10-30 | 0 |  |  |  |  | 314XE506A |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDLN3 | MJ |  | 1000107017 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed/Released | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDLN3 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | INLEC | 200073400 | 0010 | 0010 | 200073400 | 2Y F06 FLAME EYES TEST/REPL (4) 3KT1440 | AA53.314XE606A | DET,U/V 3KT1440 TURB COMBUSTION CHBR #2 |  | 10 | WO item has not been released yet | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 4 | EA | 0 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item | Supply Process could not be determined for item 1, material 10026470 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000107616 | 1 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2024-10-30 | 0 |  |  |  |  | 314XE606A |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDLN3 | MJ |  | 1000107019 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDLN3 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | INLEC | 200073400 | 0010 | 0020 | 200073400 | 2Y F06 FLAME EYES TEST/REPL (4) 3KT1440 | AA53.314XE606A | DET,U/V 3KT1440 TURB COMBUSTION CHBR #2 |  | 10 | WO item has not been released yet | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 4 | EA | 0 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item | Supply Process could not be determined for item 2, material 10258196 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000107616 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2024-10-30 | 0 |  |  |  |  | 314XE606A |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDLN3 | MJ |  | 1000107019 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDLN3 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | INLEC | 200073402 | 0010 | 0010 | 200073402 | 2Y F06 FLAME EYES TEST/REPL (4) 3KT1450 | AA53.314XE706A | DET,U/V 3KT1450 TURB COMBUSTION CHBR #2 |  | 10 | WO item has not been released yet | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 | 4 | EA | 0 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item | Supply Process could not be determined for item 1, material 10026470 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000107618 | 1 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2024-10-30 | 0 |  |  |  |  | 314XE706A |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10026470 | DETECTOR,FLAME;H/WELL LG1093AA24 |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDLN3 | MJ |  | 1000107121 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDLN3 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-04 | INLEC | 200073402 | 0010 | 0020 | 200073402 | 2Y F06 FLAME EYES TEST/REPL (4) 3KT1450 | AA53.314XE706A | DET,U/V 3KT1450 TURB COMBUSTION CHBR #2 |  | 10 | WO item has not been released yet | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 | 4 | EA | 0 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item | Supply Process could not be determined for item 2, material 10258196 Plant AA53, check config. |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000107618 | 2 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 | [7 empty] | 2024-10-30 | 0 |  |  |  |  | 314XE706A |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10258196 | GASKET;96MM,130MM,FF,KLINGER 000007620 |  | 0010 | Isolate & Disconnect | INT | Isolate & Disconnect | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDLN3 | MJ |  | 1000107121 |  | 30 |  |  | 0 |  |  | 0 | 0 | [8 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-04 | 2024-05-03 | 2024-05-03 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT8 | Released | 2024-01-02 | 2024-05-15 |  | 2024-05-15 | 2024-05-15 | ROTAT | 200082347 | 0010 | 0010 | 200082347 | GREASE G4008 MTR BRGS | AA53.G4008 | GEN,GAS TURBINE,G4008 | AA01 | 30 | WO item has not been released yet | 10462794 | GREASE,GP;SHELL,GADUS S3 T100 2,450G | 1 | CQ | 19 | 0 | 0 | 0 |  | 29.01 - PR Never Line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | CQ | [5 empty] | 05 | Preparation | 0000118246 | 1 | 0 | [9 empty] | WorkPackLink |  |  | 0 |  | 0 | 0 |  | 0 | 1 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-15 |  |  | 2024-05-15 |  |  |  |  | 2024-05-23 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10462794 | GREASE,GP;SHELL,GADUS S3 T100 2,450G |  | 0010 | GREASE G4008 MTR BRGS | INT | GREASE G4008 MTR BRGS | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 30 |  | 0 |  | 0 |  | 24SDGT8 | MJ |  | 1000117599 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-15 | 2024-05-15 | 2024-05-15 | Released/Settlement rule created/Pre-costed/Object created/Date set by external system/Material committed/Printed | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT7 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-03 | WORK | 200089392 | 0020 | 0040 | 200089392 | 10Y RECERTIFY PSV ROTABLE | AA53.407RV521 | PSV,CO2 DISCH LINE GT4007A CO2 | AA01 | 10 | WO item has not been released yet | 10058672 | STUDBOLT;0.500" X 90MM,L7,BLK | 4 | EA | 0 | 0 | 0 | 0 |  | 23.01 - PR Never Line item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000127702 | 4 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-07-18 | 0 |  |  |  |  | 2200628652 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058672 | STUDBOLT;0.500" X 90MM,L7,BLK |  | 0020 | Remove / Install PSV | INT | Remove / Install PSV | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000127064 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDGT7 | Released | 2024-01-02 | 2024-05-03 |  | 2024-05-03 | 2024-05-03 | WORK | 200089392 | 0020 | 0050 | 200089392 | 10Y RECERTIFY PSV ROTABLE | AA53.407RV521 | PSV,CO2 DISCH LINE GT4007A CO2 | AA01 | 10 | WO item has not been released yet | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK | 4 | EA | 0 | 0 | 0 | 0 |  | 23.01 - PR Never line Item |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 05 | Preparation | 0000127702 | 5 | 0 | [9 empty] | WorkPackLink |  | AU01-TA-P07 | 0 |  | 0 | 0 |  | 0 | 4 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-03 |  |  | 2024-05-03 |  |  |  |  | 2024-07-18 | 0 |  |  |  |  | 2200628652 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK |  | 0020 | Remove / Install PSV | INT | Remove / Install PSV | 5 | [9 empty] | 0055 | In Preparation (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDGT7 | MJ |  | 1000127064 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00025003 | 2024-05-03 | 2024-05-03 | 2024-05-03 | Material shortage/Date set by external system/Object created/Pre-costed/Settlement rule created/Released | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDTOT2 | Released | 2024-01-02 | 2024-05-10 |  | 2024-05-10 | 2024-05-10 | INLEC | 200089995 | 0010 | 0060 | 200089995 | 4Y Beach Valve Function Test 210HYD001 | AA53.210HYD001 | VALVE,BALL 2TL BEACH VALVE | AA01 | 10 | WO item has not been released yet | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK | 12 | EA | 0 | 0 | 0 | 0 |  | 22.02 - PR Never |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000128269 | 5 | 0 | [9 empty] | WorkPackLink |  | NEVER | 0 |  | 0 | 0 |  | 0 | 12 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-10 |  |  | 2024-05-10 |  |  |  |  | 2024-09-09 | 0 |  |  |  |  | NEVER |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10058984 | STUDBOLT;0.500" X 75MM,L7,BLK |  | 0010 | Operations Assistance | INT | Operations Assistance | 5 | [9 empty] | 0060 | Ready to Schedule (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDTOT2 | MJ |  | 1000127638 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 1 |  |  | RC00025003 | 2024-05-10 | 2024-05-10 | 2024-05-10 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDTOT2 | Released | 2024-01-02 | 2024-05-10 |  | 2024-05-10 | 2024-05-10 | INLEC | 200089995 | 0010 | 0050 | 200089995 | 4Y Beach Valve Function Test 210HYD001 | AA53.210HYD001 | VALVE,BALL 2TL BEACH VALVE | AA01 | 10 | WO item has not been released yet | 10060883 | GASKET,SW;25MM,CL150,4.5MM,SS316L,GR | 3 | EA | 5 | 0 | 0 | 0 |  | 22.02 - PR Never |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000128269 | 4 | 0 | [9 empty] | WorkPackLink |  | NEVER | 0 |  | 0 | 0 |  | 0 | 3 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-05-10 |  |  | 2024-05-10 |  |  |  |  | 2024-09-09 | 0 |  |  |  |  | NEVER |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060883 | GASKET,SW;25MM,CL150,4.5MM,SS316L,GR |  | 0010 | Operations Assistance | INT | Operations Assistance | 5 | [9 empty] | 0060 | Ready to Schedule (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDTOT2 | MJ |  | 1000127638 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 1 |  |  | RC00025003 | 2024-05-10 | 2024-05-10 | 2024-05-10 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Material shortage/Printed | AM02 | Proactive Maintenance |  | PR Never
1 | 24SDFR2 | Released | 2024-01-02 | 2024-04-22 |  | 2024-04-16 | 2024-04-23 | MECH | 600001793 | 0070 |  | 600001793 | MOC-89056 Fab/Weld Install 218UCV112 | AA53.2E1801 | EXCH,HEAT DE-ETH REBOIL FRACT2 | AA01 | 10 | WO item has not been released yet | 10060902 | GASKET;SWCI,150MM,CL300,316L/GR/316 | 8 | EA | 17 | 0 | 0 | 0 |  | 25.01 - PR NEVER LINE ITEM |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000084711 | 2 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 8 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-22 |  |  | 2024-04-22 |  |  |  |  | 2024-12-15 | 0 |  |  |  |  | 218UCV112 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10060902 | GASKET;SWCI,150MM,CL300,316L/GR/316 |  | 0070 | Cut Spool In-Situ | INT | Cut Spool In-Situ | 5 | [9 empty] | 0060 | Ready to Schedule (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000084095 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00018003 | 2024-04-23 | 2024-04-16 | 2024-04-16 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Material shortage/Printed | AM06 | Capital |  | PR Never
1 | 24SDFR2 | Released | 2024-01-02 | 2024-04-22 |  | 2024-04-16 | 2024-04-23 | MECH | 600001793 | 0070 |  | 600001793 | MOC-89056 Fab/Weld Install 218UCV112 | AA53.2E1801 | EXCH,HEAT DE-ETH REBOIL FRACT2 | AA01 | 10 | WO item has not been released yet | 10491146 | STUDBOLT;0.750" X 130MM,L7,BLK | 24 | EA | 0 | 0 | 0 | 0 |  | 25.01 - PR NEVER LINE ITEM |  |  | SP12 | Stock at Base | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | EA | [5 empty] | 06 | Scheduling | 0000084711 | 3 | 0 | [9 empty] | WorkPackLink |  | Never | 0 |  | 0 | 0 |  | 0 | 24 |  |  | Y |  |  |  | 0 | 0 | 0 |  |  | AA53 | 2024-04-22 |  |  | 2024-04-22 |  |  |  |  | 2024-12-15 | 0 |  |  |  |  | 218UCV112 |  | 0 | 0 | 0 | 0 | 0 |  | 2 | L |  | 0 |  |  | 0 |  |  |  |  | AA53 | KGP Karratha Gas Plant-NWS GAS | AA53 | KGP Karratha Gas Plant-NWS GAS | 5001 | 10491146 | STUDBOLT;0.750" X 130MM,L7,BLK |  | 0070 | Cut Spool In-Situ | INT | Cut Spool In-Situ | 5 | [9 empty] | 0060 | Ready to Schedule (Order) |  | 0 | [9 empty] | 5 |  | 0 |  | 0 |  | 24SDFR2 | MJ |  | 1000084095 |  | 30 | 30 |  | 0 |  |  | 0 | 0 |  |  | AA02 | [5 empty] | 1070 |  |  | 1001 | Woodside Energy Ltd | W001 | W74336 | 2023-12-30 | 0 | 0 |  | 2 |  |  | RC00018003 | 2024-04-23 | 2024-04-16 | 2024-04-16 | Released/Settlement rule created/Pre-costed/Object created/Ready For Scheduling/Date set by external system/Material shortage/Printed | AM06 | Capital |  | PR Never
Formulas:
Expected Delivery into PDC = IFS(ISBLANK([INCOTERMS]),"",[INCOTERMS]="FCA",[Delivery date (PO)]+15,[INCOTERMS]="EXW",[Delivery date (PO)]+15,[INCOTERMS]="CPT",[Delivery date (PO)])

## Reservation List
| Reservation | Item number of reservation | Record type | Requirements date | Movement type | Debit/Credit ind | Material | Requirement Quantity | Difference Quantity | Base Unit of Measure | Requirement Urgency | Requirement Priority | Account assignment of reservation | Account assignment | Movement allowed
849774539610034254000600002061 | 84977 | 56 |  | 2024-04-14 | 261 | H | 10034254 | 1 | 1 | PAC | 5 | 10 | F | 000600002061 | X
870914559710060883000200052863 | 87091 | 2 |  | 2024-11-01 | 261 | H | 10060883 | 1 | 1 | EA | 5 | 10 | F | 000200052863 | X
917914541510565960000200057503 | 91791 | 3 |  | 2024-05-03 | 261 | H | 10565960 | 200 | 200 | EA | 20 | 20 | F | 000200057503 | X
923064542710565960000200057958 | 92306 | 2 |  | 2024-05-15 | 261 | H | 10565960 | 200 | 200 | EA | 20 | 20 | F | 000200057958 | X
923074543110565960000200057959 | 92307 | 2 |  | 2024-05-19 | 261 | H | 10565960 | 200 | 200 | EA | 20 | 20 | F | 000200057959 | X
925224550610062910000200058187 | 92522 | 5 |  | 2024-08-02 | 261 | H | 10062910 | 12 | 12 | CQ | 5 | 10 | F | 000200058187 | X
925234550210062910000200058188 | 92523 | 5 |  | 2024-07-29 | 261 | H | 10062910 | 12 | 12 | CQ | 5 | 10 | F | 000200058188 | X
932794545910062910000200058990 | 93279 | 4 |  | 2024-06-16 | 261 | H | 10062910 | 6 | 6 | CQ | 5 | 10 | F | 000200058990 | X
933984541210034649000200059076 | 93398 | 2 |  | 2024-04-30 | 261 | H | 10034649 | 3 | 3 | PKT | 30 | 30 | F | 000200059076 | X
942034550510060883000200059908 | 94203 | 2 |  | 2024-08-01 | 261 | H | 10060883 | 1 | 1 | EA | 5 | 10 | F | 000200059908 | X
947224545310062910000200060387 | 94722 | 4 |  | 2024-06-10 | 261 | H | 10062910 | 6 | 6 | CQ | 5 | 10 | F | 000200060387 | X
992084541610589680000200064906 | 99208 | 9 |  | 2024-05-04 | 261 | H | 10589680 | 1 | 1 | EA | 5 | 10 | F | 000200064906 | X
992084541810537210000200064906 | 99208 | 16 |  | 2024-05-06 | 261 | H | 10537210 | 6 | 6 | EA | 5 | 10 | F | 000200064906 | X
994104541510565960000200065121 | 99410 | 2 |  | 2024-05-03 | 261 | H | 10565960 | 200 | 200 | EA | 20 | 20 | F | 000200065121 | X
1011964572110062910000200066927 | 101196 | 2 |  | 2025-03-05 | 261 | H | 10062910 | 1 | 1 | CQ | 30 | 30 | F | 000200066927 | X
1020314548810060883000200067742 | 102031 | 1 |  | 2024-07-15 | 261 | H | 10060883 | 2 | 2 | EA | 30 | 30 | F | 000200067742 | X
1020324569810060883000200067743 | 102032 | 1 |  | 2025-02-10 | 261 | H | 10060883 | 2 | 2 | EA | 30 | 30 | F | 000200067743 | X
1044594543110435942000200070157 | 104459 | 2 |  | 2024-05-19 | 261 | H | 10435942 | 32 | 32 | EA | 20 | 20 | F | 000200070157 | X
1046464542710435942000200070297 | 104646 | 2 |  | 2024-05-15 | 261 | H | 10435942 | 32 | 32 | EA | 20 | 20 | F | 000200070297 | X
1047444536610062910000200070395 | 104744 | 4 |  | 2024-03-15 | 261 | H | 10062910 | 24 | 24 | CQ | 5 | 10 | F | 000200070395 | X
1051014541910060883000200070754 | 105101 | 2 |  | 2024-05-07 | 261 | H | 10060883 | 1 | 1 | EA | 5 | 10 | F | 000200070754 | X
1054574543110589680000200071136 | 105457 | 9 |  | 2024-05-19 | 261 | H | 10589680 | 1 | 1 | EA | 5 | 10 | F | 000200071136 | X
1054574543110537210000200071136 | 105457 | 16 |  | 2024-05-19 | 261 | H | 10537210 | 6 | 6 | EA | 5 | 10 | F | 000200071136 | X
1088044536510060883000200074415 | 108804 | 2 |  | 2024-03-14 | 261 | H | 10060883 | 1 | 1 | EA | 5 | 10 | F | 000200074415 | X
1133724551710062910000200079018 | 113372 | 5 |  | 2024-08-13 | 261 | H | 10062910 | 12 | 12 | CQ | 5 | 10 | F | 000200079018 | X
1134484537810062910000200079112 | 113448 | 5 |  | 2024-03-27 | 261 | H | 10062910 | 24 | 24 | CQ | 5 | 10 | F | 000200079112 | X
1134554535110062910000200079160 | 113455 | 3 |  | 2024-02-29 | 261 | H | 10062910 | 4 | 4 | CQ | 5 | 10 | F | 000200079160 | X
1135334537610062910000200079179 | 113533 | 3 |  | 2024-03-25 | 261 | H | 10062910 | 4 | 4 | CQ | 5 | 10 | F | 000200079179 | X
1137814540810062910000200079446 | 113781 | 5 |  | 2024-04-26 | 261 | H | 10062910 | 24 | 24 | CQ | 5 | 10 | F | 000200079446 | X
1137914535410062910000200079456 | 113791 | 4 |  | 2024-03-03 | 261 | H | 10062910 | 4 | 4 | CQ | 5 | 10 | F | 000200079456 | X
1138614537810062910000200079506 | 113861 | 5 |  | 2024-03-27 | 261 | H | 10062910 | 4 | 4 | CQ | 5 | 10 | F | 000200079506 | X
1139864551610062910000200079638 | 113986 | 5 |  | 2024-08-12 | 261 | H | 10062910 | 12 | 12 | CQ | 5 | 10 | F | 000200079638 | X
1163794530810034649000200081515 | 116379 | 2 |  | 2024-01-17 | 261 | H | 10034649 | 3 | 3 | PKT | 30 | 30 | F | 000200081515 | X
1179454541510589680000200082196 | 117945 | 15 |  | 2024-05-03 | 261 | H | 10589680 | 1 | 1 | EA | 5 | 10 | F | 000200082196 | X
1181844526010062910000200082323 | 118184 | 2 |  | 2023-11-30 | 261 | H | 10062910 | 6 | 6 | CQ | 5 | 10 | F | 000200082323 | X
1188074554610062910000200082585 | 118807 | 4 |  | 2024-09-11 | 261 | H | 10062910 | 12 | 12 | CQ | 5 | 10 | F | 000200082585 | X
1200134541510060883000200083164 | 120013 | 2 |  | 2024-05-03 | 261 | H | 10060883 | 20 | 20 | EA | 20 | 20 | F | 000200083164 | X
1200144542710060883000200083165 | 120014 | 2 |  | 2024-05-15 | 261 | H | 10060883 | 20 | 20 | EA | 20 | 20 | F | 000200083165 | X
1200154578710060883000200083166 | 120015 | 2 |  | 2025-05-10 | 261 | H | 10060883 | 20 | 20 | EA | 20 | 20 | F | 000200083166 | X
1208854541510435942000200083436 | 120885 | 2 |  | 2024-05-03 | 261 | H | 10435942 | 32 | 32 | EA | 20 | 20 | F | 000200083436 | X
1210374542710537210000200083506 | 121037 | 21 |  | 2024-05-15 | 261 | H | 10537210 | 6 | 6 | EA | 5 | 10 | F | 000200083506 | X
1220644537310060883000200083989 | 122064 | 2 |  | 2024-03-22 | 261 | H | 10060883 | 1 | 1 | EA | 5 | 10 | F | 000200083989 | X
1227194537310060883000200084505 | 122719 | 2 |  | 2024-03-22 | 261 | H | 10060883 | 1 | 1 | EA | 5 | 10 | F | 000200084505 | X
1241914541510060883000200085913 | 124191 | 6 |  | 2024-05-03 | 261 | H | 10060883 | 12 | 12 | EA | 20 | 20 | F | 000200085913 | X
1241934542710060883000200085915 | 124193 | 6 |  | 2024-05-15 | 261 | H | 10060883 | 12 | 12 | EA | 20 | 20 | F | 000200085915 | X
1241954543110060883000200085917 | 124195 | 6 |  | 2024-05-19 | 261 | H | 10060883 | 12 | 12 | EA | 20 | 20 | F | 000200085917 | X
1241974541510060883000200085919 | 124197 | 6 |  | 2024-05-03 | 261 | H | 10060883 | 12 | 12 | EA | 20 | 20 | F | 000200085919 | X
1245784557210060883000200086360 | 124578 | 2 |  | 2024-10-07 | 261 | H | 10060883 | 2 | 2 | EA | 5 | 10 | F | 000200086360 | X
1245794557210060883000200086361 | 124579 | 2 |  | 2024-10-07 | 261 | H | 10060883 | 1 | 1 | EA | 5 | 10 | F | 000200086361 | X
1261394537610060883000200087905 | 126139 | 6 |  | 2024-03-25 | 261 | H | 10060883 | 4 | 4 | EA | 5 | 10 | F | 000200087905 | X
1268274545410062910000200088518 | 126827 | 9 |  | 2024-06-11 | 261 | H | 10062910 | 4 | 4 | CQ | 5 | 10 | F | 000200088518 | X
1275934577510060883000200089335 | 127593 | 2 |  | 2025-04-28 | 261 | H | 10060883 | 1 | 1 | EA | 5 | 10 | F | 000200089335 | X
1277024541510060883000200089392 | 127702 | 2 |  | 2024-05-03 | 261 | H | 10060883 | 1 | 1 | EA | 5 | 10 | F | 000200089392 | X
1277354545410062910000200089477 | 127735 | 2 |  | 2024-06-11 | 261 | H | 10062910 | 2 | 2 | CQ | 5 | 10 | F | 000200089477 | X
1281334542710257883000200089855 | 128133 | 2 |  | 2024-05-15 | 261 | H | 10257883 | 1 | 1 | KIT | 5 | 10 | F | 000200089855 | X
1281334542710255659000200089855 | 128133 | 3 |  | 2024-05-15 | 262 | S | 10255659 | 1 | 1 | EA | 5 | 10 | F | 000200089855 | X
1281334542710255659000200089855 | 128133 | 4 |  | 2024-05-15 | 261 | H | 10255659 | 1 | 1 | EA | 5 | 10 | F | 000200089855 | X
1283394541510257883000200090101 | 128339 | 2 |  | 2024-05-03 | 261 | H | 10257883 | 1 | 1 | KIT | 5 | 10 | F | 000200090101 | X
1283394541510255659000200090101 | 128339 | 3 |  | 2024-05-03 | 262 | S | 10255659 | 1 | 1 | EA | 5 | 10 | F | 000200090101 | X
1283394541510255659000200090101 | 128339 | 4 |  | 2024-05-03 | 261 | H | 10255659 | 1 | 1 | EA | 5 | 10 | F | 000200090101 | X
1286874602210060883000200090449 | 128687 | 2 |  | 2025-12-31 | 261 | H | 10060883 | 2 | 2 | EA | 10 | 10 | F | 000200090449 | X
1286924602310060883000200090454 | 128692 | 2 |  | 2026-01-01 | 261 | H | 10060883 | 2 | 2 | EA | 10 | 10 | F | 000200090454 | X
1286934602310060883000200090455 | 128693 | 2 |  | 2026-01-01 | 261 | H | 10060883 | 2 | 2 | EA | 10 | 10 | F | 000200090455 | X
1286944602310060883000200090456 | 128694 | 1 |  | 2026-01-01 | 261 | H | 10060883 | 2 | 2 | EA | 10 | 10 | F | 000200090456 | X
1288174541510257883000200090588 | 128817 | 2 |  | 2024-05-03 | 261 | H | 10257883 | 1 | 1 | KIT | 5 | 10 | F | 000200090588 | X
1288174541510255659000200090588 | 128817 | 3 |  | 2024-05-03 | 262 | S | 10255659 | 1 | 1 | EA | 5 | 10 | F | 000200090588 | X
1288174541510255659000200090588 | 128817 | 4 |  | 2024-05-03 | 261 | H | 10255659 | 1 | 1 | EA | 5 | 10 | F | 000200090588 | X
1291064590110060883000200090812 | 129106 | 136 |  | 2025-09-01 | 261 | H | 10060883 | 8 | 8 | EA | 20 | 20 | F | 000200090812 | X
1293374546910062910000200091088 | 129337 | 5 |  | 2024-06-26 | 261 | H | 10062910 | 24 | 24 | CQ | 20 | 20 | F | 000200091088 | X
1296974602110060883000200091467 | 129697 | 2 |  | 2025-12-30 | 261 | H | 10060883 | 2 | 2 | EA | 10 | 10 | F | 000200091467 | X
1296984602110060883000200091468 | 129698 | 2 |  | 2025-12-30 | 261 | H | 10060883 | 2 | 2 | EA | 10 | 10 | F | 000200091468 | X
1300234549310058984000200091745 | 130023 | 5 |  | 2024-07-20 | 261 | H | 10058984 | 24 | 24 | EA | 10 | 10 | F | 000200091745 | X
1301304557310062910000200091872 | 130130 | 4 |  | 2024-10-08 | 261 | H | 10062910 | 8 | 8 | CQ | 20 | 20 | F | 000200091872 | X
1306194546110431318000100031735 | 130619 | 25 |  | 2024-06-18 | 261 | H | 10431318 | 4 | 4 | ROL | 5 | 10 | F | 000100031735 | X
1322814543110613434000100033767 | 132281 | 3 |  | 2024-05-19 | 261 | H | 10613434 | 1 | 1 | EA | 20 | 20 | F | 000100033767 | X
1322814543110412550000100033767 | 132281 | 4 |  | 2024-05-19 | 261 | H | 10412550 | 1 | 1 | EA | 20 | 20 | F | 000100033767 | X
1323814535710034649000100033847 | 132381 | 9 |  | 2024-03-06 | 261 | H | 10034649 | 20 | 20 | PKT | 99 | 255 | F | 000100033847 | X
1323814535710569805000100033847 | 132381 | 14 |  | 2024-03-06 | 261 | H | 10569805 | 5 | 5 | EA | 99 | 255 | F | 000100033847 | X
1323814535710461586000100033847 | 132381 | 19 |  | 2024-03-06 | 261 | H | 10461586 | 600 | 600 | EA | 99 | 255 | F | 000100033847 | X
1323814535710062910000100033847 | 132381 | 36 |  | 2024-03-06 | 261 | H | 10062910 | 60 | 60 | CQ | 99 | 255 | F | 000100033847 | X
1323814538510059589000100033847 | 132381 | 37 |  | 2024-04-03 | 261 | H | 10059589 | 10 | 10 | EA | 99 | 255 | F | 000100033847 | X
1327504548810034254000100034266 | 132750 | 7 |  | 2024-07-15 | 261 | H | 10034254 | 2 | 2 | PAC | 20 | 20 | F | 000100034266 | X
1340554541510034254000100035583 | 134055 | 2 |  | 2024-05-03 | 261 | H | 10034254 | 5 | 5 | PAC | 30 | 30 | F | 000100035583 | X
1342224544710060883000100035630 | 134222 | 1 |  | 2024-06-04 | 261 | H | 10060883 | 2 | 2 | EA | 20 | 20 | F | 000100035630 | X
1354424532110062910000100036910 | 135442 | 46 |  | 2024-01-30 | 261 | H | 10062910 | 8 | 8 | CQ | 20 | 20 | F | 000100036910 | X
1361974541510581204000100037745 | 136197 | 2 |  | 2024-05-03 | 261 | H | 10581204 | 1 | 1 | EA | 20 | 20 | F | 000100037745 | X
1361984535310412550000100037746 | 136198 | 2 |  | 2024-03-02 | 261 | H | 10412550 | 4 | 4 | EA | 99 | 255 | F | 000100037746 | X
1361984535310613434000100037746 | 136198 | 3 |  | 2024-03-02 | 261 | H | 10613434 | 4 | 4 | EA | 99 | 255 | F | 000100037746 | X
1367724541510048158000100038248 | 136772 | 7 |  | 2024-05-03 | 261 | H | 10048158 | 10 | 10 | EA | 30 | 30 | F | 000100038248 | X
1374404578310062910000100038916 | 137440 | 5 |  | 2025-05-06 | 261 | H | 10062910 | 2 | 2 | CQ | 30 | 30 | F | 000100038916 | X
1374824590110062910000100038918 | 137482 | 3 |  | 2025-09-01 | 261 | H | 10062910 | 1 | 1 | CQ | 30 | 30 | F | 000100038918 | X
1375624580310062910000100038998 | 137562 | 1 |  | 2025-05-26 | 261 | H | 10062910 | 1 | 1 | CQ | 20 | 20 | F | 000100038998 | X
1376914543110059951000100039179 | 137691 | 2 |  | 2024-05-19 | 261 | H | 10059951 | 1 | 1 | SHT | 30 | 30 | F | 000100039179 | X
1380954551610034254000100039611 | 138095 | 4 |  | 2024-08-12 | 261 | H | 10034254 | 1 | 1 | PAC | 5 | 10 | F | 000100039611 | X
1381564539810062910000100039682 | 138156 | 1 |  | 2024-04-16 | 261 | H | 10062910 | 2 | 2 | CQ | 10 | 10 | F | 000100039682 | X
1383184543110048158000100039826 | 138318 | 3 |  | 2024-05-19 | 261 | H | 10048158 | 10 | 10 | EA | 99 | 255 | F | 000100039826 | X
1384524530610062910000100039940 | 138452 | 4 |  | 2024-01-15 | 261 | H | 10062910 | 4 | 4 | CQ | 20 | 20 | F | 000100039940 | X
1384544590110062910000100039942 | 138454 | 1 |  | 2025-09-01 | 261 | H | 10062910 | 1 | 1 | CQ | 30 | 30 | F | 000100039942 | X
1384544590110461586000100039942 | 138454 | 6 |  | 2025-09-01 | 261 | H | 10461586 | 250 | 250 | EA | 30 | 30 | F | 000100039942 | X
1385004548810060883000100040028 | 138500 | 3 |  | 2024-07-15 | 261 | H | 10060883 | 4 | 4 | EA | 30 | 30 | F | 000100040028 | X
1385914541511401662000100040070 | 138591 | 3 |  | 2024-05-03 | 261 | H | 11401662 | 1 | 1 | EA | 20 | 20 | F | 000100040070 | X
1385914541511401663000100040070 | 138591 | 4 |  | 2024-05-03 | 261 | H | 11401663 | 1 | 1 | EA | 20 | 20 | F | 000100040070 | X
1385914541511401664000100040070 | 138591 | 5 |  | 2024-05-03 | 261 | H | 11401664 | 1 | 1 | EA | 20 | 20 | F | 000100040070 | X
1385914541511401665000100040070 | 138591 | 6 |  | 2024-05-03 | 261 | H | 11401665 | 1 | 1 | EA | 20 | 20 | F | 000100040070 | X
1386414544810062910000100040057 | 138641 | 5 |  | 2024-06-05 | 261 | H | 10062910 | 2 | 2 | CQ | 99 | 255 | F | 000100040057 | X
1389004543110473763000100040408 | 138900 | 5 |  | 2024-05-19 | 261 | H | 10473763 | 1 | 1 | DR | 99 | 255 | F | 000100040408 | X
1389614541510473763000100040409 | 138961 | 5 |  | 2024-05-03 | 261 | H | 10473763 | 1 | 1 | DR | 99 | 255 | F | 000100040409 | X
1389634541510473763000100040411 | 138963 | 5 |  | 2024-05-03 | 261 | H | 10473763 | 1 | 1 | DR | 99 | 255 | F | 000100040411 | X
1390044541510297503000100040480 | 139004 | 5 |  | 2024-05-03 | 261 | H | 10297503 | 12 | 12 | EA | 99 | 255 | F | 000100040480 | X
1391954543210062910000100040723 | 139195 | 5 |  | 2024-05-20 | 261 | H | 10062910 | 12 | 12 | CQ | 30 | 30 | F | 000100040723 | X
1394264594310431318000100040872 | 139426 | 1 |  | 2025-10-13 | 261 | H | 10431318 | 1 | 1 | ROL | 99 | 255 | F | 000100040872 | X
1395444549510062910000100041043 | 139544 | 4 |  | 2024-07-22 | 261 | H | 10062910 | 6 | 6 | CQ | 5 | 10 | F | 000100041043 | X
1397584557210062910000100041257 | 139758 | 3 |  | 2024-10-07 | 261 | H | 10062910 | 1 | 1 | CQ | 20 | 20 | F | 000100041257 | X
1399994550910062910000100041478 | 139999 | 8 |  | 2024-08-05 | 261 | H | 10062910 | 6 | 6 | CQ | 10 | 10 | F | 000100041478 | X
1405184538610060883000100042034 | 140518 | 26 |  | 2024-04-04 | 261 | H | 10060883 | 4 | 4 | EA | 30 | 30 | F | 000100042034 | X
1406604598110062910000100042156 | 140660 | 2 |  | 2025-11-20 | 261 | H | 10062910 | 1 | 1 | CQ | 20 | 20 | F | 000100042156 | X
1413354539710062910000100042851 | 141335 | 1 |  | 2024-04-15 | 261 | H | 10062910 | 1 | 1 | CQ | 30 | 30 | F | 000100042851 | X
1419274541510545015000100043426 | 141927 | 7 |  | 2024-05-03 | 261 | H | 10545015 | 1 | 1 | EA | 30 | 30 | F | 000100043426 | X
1420094561210062910000100043505 | 142009 | 8 |  | 2024-11-16 | 261 | H | 10062910 | 2 | 2 | CQ | 10 | 10 | F | 000100043505 | X
1420404572210062910000100043539 | 142040 | 5 |  | 2025-03-06 | 261 | H | 10062910 | 3 | 3 | CQ | 30 | 30 | F | 000100043539 | X
1420404572010062910000100043539 | 142040 | 10 |  | 2025-03-04 | 261 | H | 10062910 | 2 | 2 | CQ | 30 | 30 | F | 000100043539 | X
1422304548810062910000100043729 | 142230 | 5 |  | 2024-07-15 | 261 | H | 10062910 | 2 | 2 | CQ | 30 | 30 | F | 000100043729 | X
1425724551910060883000100044060 | 142572 | 3 |  | 2024-08-15 | 261 | H | 10060883 | 4 | 4 | EA | 20 | 20 | F | 000100044060 | X
1427224541910058984000100044208 | 142722 | 2 |  | 2024-05-07 | 261 | H | 10058984 | 8 | 8 | EA | 20 | 20 | F | 000100044208 | X
1427594602310062910000100044255 | 142759 | 3 |  | 2026-01-01 | 261 | H | 10062910 | 2 | 2 | CQ | 5 | 10 | F | 000100044255 | X
1428104549110062910000100044326 | 142810 | 24 |  | 2024-07-18 | 261 | H | 10062910 | 6 | 6 | CQ | 30 | 30 | F | 000100044326 | X
1432284553410062910000100044716 | 143228 | 4 |  | 2024-08-30 | 261 | H | 10062910 | 6 | 6 | CQ | 30 | 30 | F | 000100044716 | X
1437314539010062910000100045230 | 143731 | 5 |  | 2024-04-08 | 261 | H | 10062910 | 2 | 2 | CQ | 20 | 20 | F | 000100045230 | X
1438474560710062910000100045293 | 143847 | 1 |  | 2024-11-11 | 261 | H | 10062910 | 1 | 1 | CQ | 30 | 30 | F | 000100045293 | X
1440024572610034649000100045450 | 144002 | 2 |  | 2025-03-10 | 261 | H | 10034649 | 1 | 1 | PKT | 20 | 20 | F | 000100045450 | X
1440364580310062910000100045515 | 144036 | 4 |  | 2025-05-26 | 261 | H | 10062910 | 2 | 2 | CQ | 30 | 30 | F | 000100045515 | X
1440384557210062910000100045517 | 144038 | 6 |  | 2024-10-07 | 261 | H | 10062910 | 4 | 4 | CQ | 30 | 30 | F | 000100045517 | X
1441304593610062910000100045616 | 144130 | 10 |  | 2025-10-06 | 261 | H | 10062910 | 1 | 1 | CQ | 30 | 30 | F | 000100045616 | X
1442104581210034254000100045706 | 144210 | 13 |  | 2025-06-04 | 261 | H | 10034254 | 1 | 1 | PAC | 30 | 30 | F | 000100045706 | X
1443954551610060883000100045894 | 144395 | 4 |  | 2024-08-12 | 261 | H | 10060883 | 1 | 1 | EA | 30 | 30 | F | 000100045894 | X
1444204544110062910000100045916 | 144420 | 3 |  | 2024-05-29 | 261 | H | 10062910 | 3 | 3 | CQ | 20 | 20 | F | 000100045916 | X
1445744575010062910000100046100 | 144574 | 3 |  | 2025-04-03 | 261 | H | 10062910 | 2 | 2 | CQ | 30 | 30 | F | 000100046100 | X
1446844580310062910000100046152 | 144684 | 5 |  | 2025-05-26 | 261 | H | 10062910 | 2 | 2 | CQ | 20 | 20 | F | 000100046152 | X
1451224541510034254000100046610 | 145122 | 2 |  | 2024-05-03 | 261 | H | 10034254 | 1 | 1 | PAC | 30 | 30 | F | 000100046610 | X
1454044543110601394000100046883 | 145404 | 1 |  | 2024-05-19 | 261 | H | 10601394 | 1 | 1 | EA | 99 | 255 | F | 000100046883 | X
1454434538510060883000100046911 | 145443 | 1 |  | 2024-04-03 | 261 | H | 10060883 | 2 | 2 | EA | 30 | 30 | F | 000100046911 | X
1456914549110062910000100047227 | 145691 | 5 |  | 2024-07-18 | 261 | H | 10062910 | 4 | 4 | CQ | 20 | 20 | F | 000100047227 | X
1461834638710034649000100047631 | 146183 | 30 |  | 2026-12-31 | 261 | H | 10034649 | 1 | 1 | PKT | 10 | 10 | F | 000100047631 | X
1466624617410060883000100048150 | 146662 | 21 |  | 2026-06-01 | 261 | H | 10060883 | 2 | 2 | EA | 20 | 20 | F | 000100048150 | X
2134674539010473763000500003780 | 213467 | 30 |  | 2024-04-08 | 261 | H | 10473763 | 4 | 4 | DR | 20 | 20 | F | 000500003780 | X
2135454531510473763000500003761 | 213545 | 1 |  | 2024-01-24 | 261 | H | 10473763 | 1 | 1 | DR | 20 | 20 | F | 000500003761 | X
2135454531510473763000500003761 | 213545 | 9 |  | 2024-01-24 | 261 | H | 10473763 | 4 | 4 | DR | 20 | 20 | F | 000500003761 | X
2139884535610060883000100071832 | 213988 | 3 |  | 2024-03-05 | 261 | H | 10060883 | 12 | 12 | EA | 20 | 20 | F | 000100071832 | X
2143154533110062910000100071929 | 214315 | 5 |  | 2024-02-09 | 261 | H | 10062910 | 6 | 6 | CQ | 5 | 10 | F | 000100071929 | X
2165454538310060883000500003860 | 216545 | 57 |  | 2024-04-01 | 261 | H | 10060883 | 2 | 2 | EA | 30 | 30 | F | 000500003860 | X
2165594541410473950000100072016 | 216559 | 5 |  | 2024-05-02 | 261 | H | 10473950 | 1 | 1 | KIT | 20 | 20 | F | 000100072016 | X
2181944561010062910000100072464 | 218194 | 3 |  | 2024-11-14 | 261 | H | 10062910 | 4 | 4 | CQ | 20 | 20 | F | 000100072464 | X
2226494569910060883000200139381 | 222649 | 2 |  | 2025-02-11 | 261 | H | 10060883 | 1 | 1 | EA | 5 | 10 | F | 000200139381 | X
2226504569910060883000200139382 | 222650 | 2 |  | 2025-02-11 | 261 | H | 10060883 | 1 | 1 | EA | 5 | 10 | F | 000200139382 | X
2226514569810060883000200139383 | 222651 | 2 |  | 2025-02-10 | 261 | H | 10060883 | 1 | 1 | EA | 5 | 10 | F | 000200139383 | X
2236534570410060883000200140008 | 223653 | 2 |  | 2025-02-16 | 261 | H | 10060883 | 1 | 1 | EA | 5 | 10 | F | 000200140008 | X
2236554570610060883000200140010 | 223655 | 2 |  | 2025-02-18 | 261 | H | 10060883 | 1 | 1 | EA | 5 | 10 | F | 000200140010 | X
2241964550110062910000100073767 | 224196 | 7 |  | 2024-07-28 | 261 | H | 10062910 | 6 | 6 | CQ | 5 | 10 | F | 000100073767 | X
2251604537510062910000100074076 | 225160 | 15 |  | 2024-03-24 | 261 | H | 10062910 | 1 | 1 | CQ | 10 | 10 | F | 000100074076 | X
2260774566310062910000200141291 | 226077 | 4 |  | 2025-01-06 | 261 | H | 10062910 | 4 | 4 | CQ | 5 | 10 | F | 000200141291 | X
2286904537610062910000100075226 | 228690 | 4 |  | 2024-03-25 | 261 | H | 10062910 | 4 | 4 | CQ | 30 | 30 | F | 000100075226 | X
1391484537410021107000100040576 | 139148 | 7 |  | 2024-03-23 | 261 | H | 10021107 | 1 | 1 | EA | 20 | 20 | F | 000100040576 | X
1391474537110021107000100040576 | 139147 | 7 |  | 2024-03-20 | 261 | H | 10021107 | 1 | 1 | EA | 20 | 20 | F | 000100040576 | X

## MM17
Material | Plant | Storage location | DF stor. loc. level | Base Unit of Measure | Unrestricted | Currency | Value Unrestricted | Transit and Transfer | Val. in Trans./Tfr | Quality Inspection | Value in QualInsp. | Restricted-Use Stock | Value Restricted | Blocked | Value BlockedStock | Returns | Value Rets Blocked
10008156 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10008156 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10008156 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10008156 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10008156 | AA02 | 1001 |  | EA | 2 | AUD | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10008156 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10008156 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10008156 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021107 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021107 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021107 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021107 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021107 | AA02 | 1001 |  | EA | 1 | AUD | 10.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021107 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021107 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021107 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021149 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021149 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021149 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021149 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021149 | AA02 | 1001 |  | EA | 1 | AUD | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021149 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021149 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021149 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021156 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021156 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021156 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021156 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021156 | AA02 | 1001 |  | EA | 1 | AUD | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021156 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021156 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021156 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021292 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021292 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021292 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021292 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021292 | AA02 | 1001 |  | EA | 1 | AUD | 23.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021292 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021292 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021292 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021426 | AA01 | 1001 |  | KIT | 3 | AUD | 812.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021426 | AA01 | 3001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021426 | AA01 | 4001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021426 | AA01 | 5001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021426 | AA02 |  |  | KIT | 0 | AUD | 0 | 1 | 217.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021426 | AA02 | 1001 |  | KIT | 1 | AUD | 217.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021426 | AA02 | 3001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021426 | AA02 | 4001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021426 | AA02 | 5001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021547 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021547 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021547 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021547 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021547 | AA02 | 1001 |  | EA | 1 | AUD | 32.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021547 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021547 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021547 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021722 | AA01 | 1001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021722 | AA01 | 3001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021722 | AA01 | 4001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021722 | AA01 | 5001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021722 | AA02 | 1001 |  | KIT | 1 | AUD | 227.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021722 | AA02 | 3001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021722 | AA02 | 4001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021722 | AA02 | 5001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021813 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021813 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021813 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021813 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021813 | AA02 | 1001 |  | EA | 1 | AUD | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021813 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021813 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021813 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022983 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022983 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022983 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022983 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022983 | AA02 | 1001 |  | EA | 1 | AUD | 740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022983 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022983 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022983 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022984 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022984 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022984 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022984 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022984 | AA02 | 1001 |  | EA | 1 | AUD | 312.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022984 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022984 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022984 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022985 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022985 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022985 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022985 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022985 | AA02 | 1001 |  | EA | 1 | AUD | 187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022985 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022985 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022985 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034254 | AA01 | 1001 |  | PAC | 3 | AUD | 22.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034254 | AA01 | 3001 |  | PAC | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034254 | AA01 | 4001 |  | PAC | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034254 | AA01 | 5001 |  | PAC | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034254 | AA02 |  |  | PAC | 0 | AUD | 0 | 6 | 44.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034254 | AA02 | 1001 |  | PAC | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034254 | AA02 | 1002 |  | PAC | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034254 | AA02 | 3001 |  | PAC | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034254 | AA02 | 4001 |  | PAC | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034254 | AA02 | 5001 |  | PAC | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034649 | AA01 | 1001 |  | PKT | 40 | AUD | 828.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034649 | AA01 | 3001 |  | PKT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034649 | AA01 | 4001 |  | PKT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034649 | AA01 | 5001 |  | PKT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034649 | AA02 |  |  | PKT | 0 | AUD | 0 | 21 | 431.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034649 | AA02 | 1001 |  | PKT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034649 | AA02 | 3001 |  | PKT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034649 | AA02 | 4001 |  | PKT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034649 | AA02 | 5001 |  | PKT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034650 | AA01 | 1001 |  | PKT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034650 | AA01 | 3001 |  | PKT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034650 | AA01 | 4001 |  | PKT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034650 | AA01 | 5001 |  | PKT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034650 | AA02 |  |  | PKT | 0 | AUD | 0 | 29 | 286.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034650 | AA02 | 1001 |  | PKT | 10 | AUD | 98.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034650 | AA02 | 3001 |  | PKT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034650 | AA02 | 4001 |  | PKT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034650 | AA02 | 5001 |  | PKT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10038178 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10038178 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10038178 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10038178 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10038178 | AA02 | 1001 |  | EA | 30 | AUD | 2195.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10038178 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10038178 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10038178 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10038826 | AA01 | 1001 |  | EA | 5 | AUD | 2177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10038826 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10038826 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10038826 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10038826 | AA02 | 1001 |  | EA | 5 | AUD | 927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10038826 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10038826 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10038826 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10047842 | AA01 | 1001 |  | EA | 10 | AUD | 584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10047842 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10047842 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10047842 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10047842 | AA02 | 1001 |  | EA | 1 | AUD | 58.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10047842 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10047842 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10047842 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10047898 | AA01 | 1001 |  | EA | 82 | AUD | 1020.9 | 0 | 0 | 86 | 1070.7 | 0 | 0 | 0 | 0 | 0 | 0
10047898 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10047898 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10047898 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10047898 | AA02 | 1001 |  | EA | 118 | AUD | 1464.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10047898 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10047898 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10047898 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10048155 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 40 | 824 | 0 | 0 | 0 | 0 | 0 | 0
10048155 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10048155 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10048155 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10048155 | AA02 | 1001 |  | EA | 31 | AUD | 622.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10048155 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10048155 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10048155 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10048158 | AA01 | 1001 |  | EA | 22 | AUD | 1850.42 | 0 | 0 | 2 | 168.22 | 0 | 0 | 0 | 0 | 0 | 0
10048158 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10048158 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10048158 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10048158 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10054896 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10054896 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10054896 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10054896 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10054896 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10057799 | AA01 | 1001 |  | SHT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10057799 | AA01 | 3001 |  | SHT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10057799 | AA01 | 4001 |  | SHT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10057799 | AA01 | 5001 |  | SHT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10057799 | AA02 | 1001 |  | SHT | 2 | AUD | 51.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10057799 | AA02 | 3001 |  | SHT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10057799 | AA02 | 4001 |  | SHT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10057799 | AA02 | 5001 |  | SHT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10058984 | AA01 | 1001 |  | EA | 168 | AUD | 105.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10058984 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10058984 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10058984 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10058984 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059514 | AA01 | 1001 |  | EA | 7 | AUD | 20.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059514 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059514 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059514 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059514 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059514 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059514 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059514 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059550 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059550 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059550 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059550 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059550 | AA02 | 1001 |  | EA | 88 | AUD | 976.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059550 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059550 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059550 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059589 | AA01 | 1001 |  | EA | 10 | AUD | 123.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059589 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059589 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059589 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059589 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059951 | AA01 | 1001 |  | SHT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059951 | AA01 | 3001 |  | SHT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | aa01 remote
10059951 | AA01 | 4001 |  | SHT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059951 | AA01 | 5001 |  | SHT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059951 | AA02 |  |  | SHT | 0 | AUD | 0 | 1 | 183.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059951 | AA02 | 1001 |  | SHT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060883 | AA01 | 1001 |  | EA | 68 | AUD | 144.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060883 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060883 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060883 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060883 | AA02 |  |  | EA | 0 | AUD | 0 | 53 | 112.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060883 | AA02 | 1001 |  | EA | 5 | AUD | 10.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060883 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060883 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060883 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060884 | AA01 | 1001 |  | EA | 140 | AUD | 466.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060884 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060884 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060884 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060884 | AA02 | 1001 |  | EA | 40 | AUD | 130.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060884 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060884 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060884 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060885 | AA01 | 1001 |  | EA | 318 | AUD | 1516.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060885 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060885 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060885 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060885 | AA02 | 1001 |  | EA | 2 | AUD | 9.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060885 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060885 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060885 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060887 | AA01 | 1001 |  | EA | 198 | AUD | 2029.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060887 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060887 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060887 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060887 | AA02 |  |  | EA | 0 | AUD | 0 | 4 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060887 | AA02 | 1001 |  | EA | 21 | AUD | 215.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060887 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060887 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060887 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060917 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060917 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060917 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060917 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060917 | AA02 | 1001 |  | EA | 388 | AUD | 1257.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060917 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060917 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060917 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10062555 | AA02 | 1001 |  | CYL | 4 | AUD | 121.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10062555 | AA02 | 3001 |  | CYL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10062555 | AA02 | 4001 |  | CYL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10062555 | AA02 | 5001 |  | CYL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10062910 | AA01 | 1001 |  | CQ | 256 | AUD | 2621.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10062910 | AA01 | 3001 |  | CQ | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10062910 | AA01 | 4001 |  | CQ | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10062910 | AA01 | 5001 |  | CQ | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10062910 | AA02 | 1001 |  | CQ | 18 | AUD | 179.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10062910 | AA02 | 3001 |  | CQ | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10062910 | AA02 | 4001 |  | CQ | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10062910 | AA02 | 5001 |  | CQ | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10202346 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10202346 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10202346 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10202346 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10202346 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10202346 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10202346 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10202346 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10204140 | AA01 | 1001 |  | EA | 50 | AUD | 133.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10204140 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10204140 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10204140 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10204140 | AA02 | 1001 |  | EA | 815 | AUD | 2290.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10204140 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10204140 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10204140 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10210152 | AA01 |  |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10210152 | AA01 | 1001 |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10210152 | AA01 | 3001 |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10210152 | AA01 | 4001 |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10210152 | AA01 | 5001 |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10210152 | AA02 | 1001 |  | DR | 1 | AUD | 150.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10210152 | AA02 | 3001 |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10210152 | AA02 | 4001 |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10210152 | AA02 | 5001 |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242467 | AA01 | 1001 |  | KG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242467 | AA01 | 3001 |  | KG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242467 | AA01 | 4001 |  | KG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242467 | AA01 | 5001 |  | KG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242467 | AA02 | 1001 |  | KG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242467 | AA02 | 3001 |  | KG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242467 | AA02 | 4001 |  | KG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242467 | AA02 | 5001 |  | KG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242468 | AA01 | 1001 |  | KG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242468 | AA01 | 3001 |  | KG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242468 | AA01 | 4001 |  | KG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242468 | AA01 | 5001 |  | KG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242468 | AA02 | 1001 |  | KG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242468 | AA02 | 3001 |  | KG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242468 | AA02 | 4001 |  | KG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242468 | AA02 | 5001 |  | KG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242497 | AA01 | 1001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242497 | AA01 | 3001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242497 | AA01 | 4001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242497 | AA01 | 5001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242497 | AA02 | 1001 |  | ROL | 74 | AUD | 1695.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242497 | AA02 | 3001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242497 | AA02 | 4001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242497 | AA02 | 5001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245543 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245543 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245543 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245543 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245543 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245543 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245543 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245543 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245570 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245570 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245570 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245570 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245570 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245570 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245570 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245570 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245837 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245837 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245837 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245837 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245837 | AA02 | 1001 |  | EA | 36 | AUD | 82.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245837 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245837 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245837 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10248914 | AA01 | 1001 |  | ROL | 30 | AUD | 505.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10248914 | AA01 | 3001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10248914 | AA01 | 4001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10248914 | AA01 | 5001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10248914 | AA02 | 1001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10248914 | AA02 | 3001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10248914 | AA02 | 4001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10248914 | AA02 | 5001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10255241 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10255241 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10255241 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10255241 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10255241 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10255659 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10255659 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10255659 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10255659 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10255659 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10255659 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10255659 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10255659 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10257642 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10257642 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10257642 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10257642 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10257642 | AA02 | 1001 |  | EA | 33 | AUD | 138.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10257642 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10257642 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10257642 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10257883 | AA01 | 1001 |  | KIT | 8 | AUD | 4917.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10257883 | AA01 | 3001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10257883 | AA01 | 4001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10257883 | AA01 | 5001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10257883 | AA02 | 1001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10257883 | AA02 | 3001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10257883 | AA02 | 4001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10257883 | AA02 | 5001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10258211 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10258211 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10258211 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10258211 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10258211 | AA02 | 1001 |  | EA | 8230 | AUD | 1075.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10258211 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10258211 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10258211 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10260114 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10260114 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10260114 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10260114 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10260114 | AA02 | 1001 |  | EA | 1 | AUD | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10260114 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10260114 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10260114 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10264996 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10264996 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10264996 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10264996 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10264996 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10264996 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10264996 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10264996 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10266469 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10266469 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10266469 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10266469 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10266469 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10266469 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10266469 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10266469 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10290467 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10290467 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10290467 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10290467 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10290467 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10290467 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10290467 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10290467 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10294388 | AA01 | 1001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10294388 | AA01 | 3001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10294388 | AA01 | 4001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10294388 | AA01 | 5001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10294388 | AA02 | 1001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10294794 | AA01 | 1001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10294794 | AA02 | 1001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297383 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297383 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297383 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297383 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297383 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297383 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297383 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297383 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297385 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297385 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297385 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297385 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297385 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297385 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297385 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297385 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297503 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297503 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297503 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297503 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297503 | AA02 | 1001 |  | EA | 9 | AUD | 23319.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297503 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297503 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297503 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10305744 | AA01 | 1001 |  | EA | 27 | AUD | 250.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10305744 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10305744 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10305744 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10305744 | AA02 | 1001 |  | EA | 26 | AUD | 240.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10305744 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10305744 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10305744 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10306122 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10306122 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10306122 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10306122 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10306122 | AA02 | 1001 |  | EA | 1 | AUD | 28.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10306122 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10306122 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10306122 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10313669 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10313669 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10313669 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10313669 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10313669 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10349278 | AA01 | 1001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10349278 | AA01 | 3001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10349278 | AA01 | 4001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10349278 | AA01 | 5001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10349278 | AA02 | 1001 |  | KIT | 2 | AUD | 32.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10349278 | AA02 | 3001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10349278 | AA02 | 4001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10349278 | AA02 | 5001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10353457 | AA01 | 1001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10353457 | AA01 | 3001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10353457 | AA01 | 4001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10353457 | AA01 | 5001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10353457 | AA02 | 1001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10353457 | AA02 | 3001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10353457 | AA02 | 4001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10353457 | AA02 | 5001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10412550 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10412550 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10412550 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10412550 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10412550 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10412550 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10412550 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10412550 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10423729 | AA01 | 1001 | X | SET | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10423729 | AA01 | 3001 | X | SET | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10423729 | AA01 | 4001 | X | SET | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10423729 | AA01 | 5001 | X | SET | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10423729 | AA02 | 1001 |  | SET | 1 | AUD | 530.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10423729 | AA02 | 3001 |  | SET | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10423729 | AA02 | 4001 |  | SET | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10423729 | AA02 | 5001 |  | SET | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10428762 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10428762 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10428762 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10428762 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10428762 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10430134 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10430134 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10430134 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10430134 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10430134 | AA02 | 1001 |  | EA | 1 | AUD | 28.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10430134 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10430134 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10430134 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431311 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431311 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431311 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431311 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431311 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431318 | AA01 | 1001 |  | ROL | 12 | AUD | 222.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431318 | AA01 | 3001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431318 | AA01 | 4001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431318 | AA01 | 5001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431318 | AA02 |  |  | ROL | 0 | AUD | 0 | 3 | 53.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431318 | AA02 | 1001 |  | ROL | 1 | AUD | 17.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431318 | AA02 | 3001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431318 | AA02 | 4001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431318 | AA02 | 5001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431950 | AA01 | 1001 |  | ROL | 10 | AUD | 1564.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431950 | AA01 | 3001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431950 | AA01 | 4001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431950 | AA01 | 5001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431950 | AA02 |  |  | ROL | 0 | AUD | 0 | 3 | 442.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431950 | AA02 | 1001 |  | ROL | 2 | AUD | 294.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431950 | AA02 | 3001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431950 | AA02 | 4001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431950 | AA02 | 5001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10434976 | AA01 | 1001 |  | EA | 357 | AUD | 50879.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10434976 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10434976 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10434976 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10434976 | AA02 | 1001 |  | EA | 230 | AUD | 32781.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10434976 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10434976 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10434976 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10435942 | AA01 | 1001 |  | EA | 742 | AUD | 144690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10435942 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10435942 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10435942 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10435942 | AA02 |  |  | EA | 0 | AUD | 0 | 32 | 6240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10435942 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10435942 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10435942 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10435942 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10441222 | AA01 | 1001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10441222 | AA01 | 3001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10441222 | AA01 | 4001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10441222 | AA01 | 5001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10441222 | AA02 |  |  | ROL | 0 | AUD | 0 | 32 | 1128.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10441222 | AA02 | 1001 |  | ROL | 2 | AUD | 70.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10441222 | AA02 | 3001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10441222 | AA02 | 4001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10441222 | AA02 | 5001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10443375 | AA01 | 1001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10443375 | AA01 | 3001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10443375 | AA01 | 4001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10443375 | AA01 | 5001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10443375 | AA02 | 1001 |  | KIT | 1 | AUD | 1703.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10443375 | AA02 | 3001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10443375 | AA02 | 4001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10443375 | AA02 | 5001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10452627 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10452627 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10452627 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10452627 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10452627 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10452627 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10452627 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10452627 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10453021 | AA01 | 1001 |  | CON | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10453021 | AA01 | 3001 |  | CON | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10453021 | AA01 | 4001 |  | CON | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10453021 | AA01 | 5001 |  | CON | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10453021 | AA02 | 1001 |  | CON | 34 | AUD | 3741.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10453021 | AA02 | 3001 |  | CON | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10453021 | AA02 | 4001 |  | CON | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10453021 | AA02 | 5001 |  | CON | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10453861 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10453861 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10453861 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10453861 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10453861 | AA02 |  |  | EA | 0 | AUD | 0 | 10 | 87.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10453861 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10453861 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10453861 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10453861 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10458031 | AA01 | 1001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10458031 | AA01 | 1051 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10458031 | AA01 | 3001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10458031 | AA01 | 4001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10458031 | AA01 | 5001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10458031 | AA02 | 1001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10458031 | AA02 | 1002 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10458031 | AA02 | 1051 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10458031 | AA02 | 3001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10458031 | AA02 | 4001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10458031 | AA02 | 5001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10461586 | AA01 | 1001 |  | EA | 350 | AUD | 371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10461586 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10461586 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10461586 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10461586 | AA02 | 1001 |  | EA | 250 | AUD | 122.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10461586 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10461586 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10461586 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10473763 | AA01 | 1001 |  | DR | 5 | AUD | 29554.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10473763 | AA01 | 3001 |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10473763 | AA01 | 4001 |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10473763 | AA01 | 5001 |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10473763 | AA02 | 1001 |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10473763 | AA02 | 3001 |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10473763 | AA02 | 4001 |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10473763 | AA02 | 5001 |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10473950 | AA01 | 1001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10473950 | AA01 | 3001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10473950 | AA01 | 4001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10473950 | AA01 | 5001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10473950 | AA02 | 1001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10473950 | AA02 | 3001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10473950 | AA02 | 4001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10473950 | AA02 | 5001 |  | KIT | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10499155 | AA01 | 1001 |  | EA | 20 | AUD | 1612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10499155 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10499155 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10499155 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10499155 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10507164 | AA01 | 1001 |  | EA | 50 | AUD | 397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10507164 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10507164 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10507164 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10507164 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10507164 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10507164 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10507164 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10507597 | AA01 | 1001 |  | EA | 5 | AUD | 1175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10507597 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10507597 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10507597 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10507597 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10517811 | AA01 | 1001 |  | EA | 10 | AUD | 213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10517811 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10517811 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10517811 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10517811 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10529603 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10529603 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10529603 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10529603 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10529603 | AA02 | 1001 |  | EA | 50 | AUD | 2293.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10529603 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10529603 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10529603 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10530791 | AA01 | 1001 |  | DR | 1 | AUD | 1241.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10530791 | AA01 | 3001 |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10530791 | AA01 | 4001 |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10530791 | AA01 | 5001 |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10530791 | AA02 | 1001 |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10530791 | AA02 | 3001 |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10530791 | AA02 | 4001 |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10530791 | AA02 | 5001 |  | DR | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10536165 | AA01 | 1001 |  | BAG | 64 | AUD | 2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10536165 | AA01 | 3001 |  | BAG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10536165 | AA01 | 4001 |  | BAG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10536165 | AA01 | 5001 |  | BAG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10536165 | AA02 |  |  | BAG | 0 | AUD | 0 | 16 | 450.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10536165 | AA02 | 1001 |  | BAG | 43 | AUD | 1209.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10536165 | AA02 | 3001 |  | BAG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10536165 | AA02 | 4001 |  | BAG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10536165 | AA02 | 5001 |  | BAG | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10536673 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10536673 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10536673 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10536673 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10536673 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10537210 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 48 | 1665.12 | 0 | 0 | 0 | 0 | 0 | 0
10537210 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10537210 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10537210 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10537210 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10537210 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10537210 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10537210 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10539834 | AA01 |  |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10539834 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10539834 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10539834 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10539834 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10539834 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10542035 | AA01 |  |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10542035 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10542035 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10542035 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10542035 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10542035 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10543991 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10543991 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10543991 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10543991 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10543991 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10545015 | AA01 | 1001 |  | EA | 1 | AUD | 1909.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10545015 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10545015 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10545015 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10545015 | AA02 |  |  | EA | 0 | AUD | 0 | 1 | 1909.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10545015 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10547418 | AA01 | 1001 |  | M | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10547418 | AA01 | 3001 |  | M | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10547418 | AA01 | 4001 |  | M | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10547418 | AA01 | 5001 |  | M | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10547418 | AA02 | 1001 |  | M | 10 | AUD | 356.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10547852 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10547852 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10547852 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10547852 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10547852 | AA02 | 1001 |  | EA | 5 | AUD | 81.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10562513 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10562513 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10562513 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10562513 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10562513 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10564940 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10564940 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10564940 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10564940 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10564940 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10565746 | AA01 | 1001 |  | EA | 3 | AUD | 332.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10565746 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10565746 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10565746 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10565746 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10565960 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10565960 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10565960 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10565960 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10565960 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10569805 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10569805 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10569805 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10569805 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10569805 | AA02 |  |  | EA | 0 | AUD | 0 | 5 | 3552.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10569805 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10572733 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10572733 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10572733 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10572733 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10572733 | AA02 | 1001 |  | EA | 6 | AUD | 45.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10573194 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10573194 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10577117 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10577117 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10577117 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10577117 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10577117 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10577778 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10577778 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10577778 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10577778 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10577778 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10581204 | AA01 | 1001 |  | EA | 1 | AUD | 664.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10581204 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10581204 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10581204 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10581204 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10586057 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10586057 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10586057 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10586057 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10586057 | AA02 | 1001 |  | EA | 8 | AUD | 15.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10589680 | AA01 |  |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10589680 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10589680 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10589680 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10589680 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10589680 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10589680 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10589680 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10589680 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10589833 | AA01 |  |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10589833 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10589833 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10589833 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10589833 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10589833 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10591716 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10591716 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10591716 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10591716 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10591716 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10591966 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10591966 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10591966 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10591966 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10591966 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10599947 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10599947 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10600397 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10600397 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10600397 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10600397 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10600397 | AA02 |  |  | EA | 0 | AUD | 0 | 10 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10600397 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10600399 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10600399 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10600399 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10600399 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10600399 | AA02 |  |  | EA | 0 | AUD | 0 | 2 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10600399 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10600755 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10600755 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10600755 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10600755 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10600755 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10601288 | AA01 | 1001 |  | ROL | 1 | AUD | 882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10601288 | AA01 | 3001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10601288 | AA01 | 4001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10601288 | AA01 | 5001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10601288 | AA02 | 1001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10601288 | AA02 | 3001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10601288 | AA02 | 4001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10601288 | AA02 | 5001 |  | ROL | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10601394 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10601394 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10601394 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10601394 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10601394 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10601394 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10601394 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10601394 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10603662 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10603662 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10603662 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10603662 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10603662 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605598 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605598 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605598 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605598 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605598 | AA02 | 1001 |  | EA | 1 | AUD | 7220.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605598 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605598 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605598 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605918 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605918 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605918 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605918 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605918 | AA02 | 1001 |  | EA | 1 | AUD | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605918 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605918 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605918 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605927 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605927 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605927 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605927 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605927 | AA02 | 1001 |  | EA | 1 | AUD | 77.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605927 | AA02 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605927 | AA02 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605927 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10607812 | AA01 |  |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10607812 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10607812 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10607812 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10607812 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10607812 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10607812 | AA02 | 1002 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10607812 | AA02 | 5002 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10607813 | AA01 |  |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10607813 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10607813 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10607813 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10607813 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10607813 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10607813 | AA02 | 1002 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10607813 | AA02 | 5002 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10613434 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10613434 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10613434 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10613434 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10613434 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400261 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400261 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400262 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400262 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400263 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400263 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400383 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400383 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400383 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400526 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400526 | AA01 | 1051 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400526 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400530 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400530 | AA01 | 1051 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400530 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400538 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400538 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400538 | AA02 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400557 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400557 | AA01 | 1051 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400557 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400560 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400560 | AA01 | 1051 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400560 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400583 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400583 | AA01 | 1051 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400583 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400631 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400631 | AA01 | 1051 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400631 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400704 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400704 | AA01 | 1051 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400704 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400705 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400705 | AA01 | 1051 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400705 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400706 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400706 | AA01 | 1051 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400706 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400707 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400707 | AA01 | 1051 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400707 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400708 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400708 | AA01 | 1051 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400708 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400709 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400709 | AA01 | 1051 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400709 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400710 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400710 | AA01 | 1051 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400710 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400722 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400722 | AA01 | 1051 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400722 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400723 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400723 | AA01 | 1051 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400723 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400724 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400724 | AA01 | 1051 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400724 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11401662 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11401662 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11401663 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11401663 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11401664 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11401664 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11401665 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11401665 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30003261 | AA01 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30003261 | AA01 | 3001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30003261 | AA01 | 4001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30003261 | AA01 | 5001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30003261 | AA02 | 1001 |  | EA | 0 | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0